## MetaShare
Part 1
|  | Hourly Rate(CAD) | Weekly Rate(CAD) | Unit | Weekly Cost(CAD)
| System Analyst & Tester & PM | 30 | 1200 | 0.5 | 600
| Architect | 30 | 1200 | 0.5 | 600
| Developer | 30 | 1200 | 2 | 2400
|  |  | Weekly Total Cost(CAD) |  | 3600
| Duration(Weeks) | 2 | Total Cost(CAD) |  | 7200 | 240
Part 2
|  | Hourly Rate(CAD) | Weekly Rate(CAD) | Unit | Weekly Cost(CAD)
| System Analyst & Tester & PM | 30 | 1200 | 0.5 | 600
| Architect | 30 | 1200 | 0.2 | 240
| Developer | 30 | 1200 | 3.5 | 4200
|  |  | Weekly Total Cost(CAD) |  | 5040
| Duration(Weeks) | 2 | Total Cost(CAD) |  | 10080 | 336
Part 3
|  | Hourly Rate(CAD) | Weekly Rate(CAD) | Unit | Weekly Cost(CAD)
| System Analyst & Tester & PM | 30 | 1200 | 1 | 1200 | 80
| Architect | 30 | 1200 | 0.3 | 360 | 24
| Developer | 30 | 1200 | 3 | 3600 | 240
|  |  | Weekly Total Cost(CAD) |  | 5160
| Duration(Weeks) | 2 | Total Cost(CAD) |  | 10320 | 344
Part 4
|  | Hourly Rate(CAD) | Weekly Rate(CAD) | Unit | Weekly Cost(CAD)
| System Analyst & Tester & PM | 30 | 1200 | 1 | 1200 | 80
| Architect | 30 | 1200 | 1 | 1200 | 80
| Developer | 30 | 1200 | 3 | 3600 | 240
|  |  | Weekly Total Cost(CAD) |  | 6000
| Duration(Weeks) | 2 | Total Cost(CAD) |  | 12000 | 400
Part 5
|  | Hourly Rate(CAD) | Weekly Rate(CAD) | Unit | Weekly Cost(CAD)
| System Analyst & Tester & PM | 30 | 1200 | 1 | 1200 | 180
| Architect | 30 | 1200 | 0.5 | 600 | 90
| Developer | 30 | 1200 | 4 | 4800 | 720
|  |  | Weekly Total Cost(CAD) |  | 6600
| Duration(Weeks) | 4.5 | Total Cost(CAD) |  | 29700 | 990

## Details
Part 2
Workflow | Hour |  |  |  | Part | Hours | Rate | Cost
Requirements | 20 |  |  |  | Total | 10056.5 |  | 1568814
Project Management | 20 |  |  |  | Part 2 | 336 | 153.6 | 51609.6
Implementation | 296 |  |  |  | Part 3 | 343 | 153.6 | 52684.8
Total | 336 |  |  |  | Part 4 | 396 | 153.6 | 60825.6
[5 empty] | Part 5 From20170710 to 20170818 | 990 | 153.6 | 152064
[5 empty] | Part 6 From20171012 | 1079 | 153.6 | 165734.4
[5 empty] | Part 7-1 From20171203 | 290 | 153.6 | 44544
Part 3 |  |  |  |  | Part 7-2 From20180103 to 20180126 | 261 | 153.6 | 40089.6
Workflow | Hour |  |  |  | Part 8 Cost for Feb. 2018(From20180129 to 20180228) | 320 | 153.6 | 49152
Requirements | 35 |  |  |  | Part 8 Cost for Mar. 2018(From20180301 to 20180330) | 556 | 153.6 | 85401.6
Project Management | 60 |  |  |  | Part 9 Cost for Apr. 2018(From 20180402 to 20180428) | 387 | 153.6 | 59443.2
Implementation | 178 |  |  |  | Part 10 Cost for May. 2018(From 20180501 to 20180531) | 260 | 153.6 | 39936
Test | 70 |  |  |  | Part 10 Cost for Jun. 2018(From 20180601 to 20180630) | 466 | 153.6 | 71577.6
Total | 343 |  |  |  | Part 10 Cost for Jul. 2018(From 20180701 to 20180731) | 476 | 153.6 | 73113.6
[5 empty] | Part 11 Cost for Aug. 2018(From 20180801 to 20180831) | 144 | 153.6 | 22118.4
[5 empty] | Part 11 Cost for Sep. 2018(From 20180901 to 20180930) | 363.5 | 153.6 | 55833.6
Part 4 |  |  |  |  | Part 11 Cost for Oct. 2018(From 20181001 to 20181031) | 297.5 | 153.6 | 45696
Workflow | Hour |  |  |  | Part 11 Cost for Nov. 2018(From 20181101 to 20181130) | 470 | 153.6 | 72192
Requirements | 50 |  |  |  | Part 12 Cost for Dec. 2018(From 20181201 to 20181231) | 470 | 153.6 | 72192
Project Management | 40 |  |  |  | Part 12 Cost for Jan. 2019(From 20190101 to 20190131) | 457 | 153.6 | 70195.2
Architecture design | 40 |  |  |  | Part 12 Cost for Feb. 2019(From 20190201 to 20190228) | 207 | 153.6 | 31795.2
Implementation | 196 |  |  |  | Part 12 Cost for Mar. 2019(From 20190301 to 20190331) | 298.5 | 153.6 | 45849.6
Test | 70 |  |  |  | Part 12 Cost for Apr. 2019(From 20190401 to 20190430) | 362 | 153.6 | 55603.2
Total | 396 |  |  |  | Part 12 Cost for May. 2019(From 20190501 to 20190531) | 352 | 153.6 | 54067.2
[5 empty] | Part 12 Cost for July 2019(From 20190701 to 20190731) | 475 | 153.6 | 72960
Part 5 From20170710 to 20170818
Workflow | Hour
Requirements | 80
Project Management | 50
Implementation | 790
Test | 70
Total | 990
Part 6 From20171012
Workflow | Total Hours
Requirements | 130
Project Management | 135
Implementation | 754
Test | 60
Total | 1079
Part 7-1 From20171203
Workflow | Total Hours
Requirements | 10
Project Management | 30
Implementation | 227
Test | 23
Total | 290
Part 7-2 From20180103 to 20180126
Workflow | Total Hours
Requirements | 20
Project Management | 16
Implementation | 205
Test | 20
Total | 261
Part 8 Cost for Feb. 2018(From20180129 to 20180228)
Workflow | Total Hours
Requirements | 24
Project Management | 20
Implementation | 256
Test | 20
Total | 320
Part 8 Cost for Mar. 2018(From20180301 to 20180330)
Workflow | Total Hours
Requirements | 18
Project Management | 32
Implementation | 476
Test | 30
Total | 556
Part 9 Cost for Apr. 2018(From 20180402 to 20180428)
Workflow | Total Hours
Requirements | 56
Project Management | 58
Implementation | 233
Test | 40
Total | 387
Part 10 Cost for May. 2018(From 20180501 to 20180531)
Workflow | Total Hours
Requirements | 50
Project Management | 60
Implementation | 412
Test | 80
Total | 602
Sanjel Need to Pay | 260
Part 10 Cost for Jun. 2018(From 20180601 to 20180630)
Workflow | Total Hours
Requirements | 50
Project Management | 60
Implementation | 404
Test | 80
Total | 594
Sanjel Need to Pay | 466
Part 10 Cost for Jul. 2018(From 20180701 to 20180731)
Workflow | Total Hours
Requirements | 38
Project Management | 53
Implementation | 375
Test | 10
Transfer for eService | 101.5
Total | 577.5
Sanjel Need to Pay | 476
Part 11 Cost for Aug. 2018(From 20180801 to 20180831)
Workflow | Total Hours
Project Management | 14
Requirements | 0
Design | 55
Implementation | 75
CodeReview | 69
Thinking training | 14.5
Total | 227.5
Sanjel Need to Pay | 144
Part 11 Cost for Sep. 2018(From 20180901 to 20180930)
Workflow | Total Hours
Eservice Express
Project Management | 14
Requirements | 7
Implementation | 161.5
Eservice Refactoring with new Blend Master Data database
Project Management | 4
Design | 15
Implementation | 27
Sanjel Blend Master Data Database | 135
Total | 363.5
Sanjel Need to Pay | 363.5
Part 11 Cost for Oct. 2018(From 20181001 to 20181031)
Workflow | Total Hours
Eservice Express
Project Management | 6
Implementation | 31
Eservice Online
Implementation | 16
Eservice Refactoring with new Blend Master Data database
Implementation | 174.5
Sanjel Blend Master Data Database | 70
Total | 297.5
Sanjel Need to Pay | 297.5
Part 11 Cost for Nov. 2018(From 20181101 to 20181130)
Workflow | Total Hours | Actual cost | Prepaid
Eservice Express
Project Management | 12 | 12
Implementation | 70 | 70
Eservice Online
Implementation | 183 | 111 | 72
Eservice Refactoring with new Blend Master Data database
Implementation | 70 | 70
Sanjel Blend Master Data Database | 135 | 135
Total | 470 | 398 | 72
Sanjel Need to Pay | 470
Part 12 Cost for Dec. 2018(From 20181201 to 20181231)
Workflow | Total Hours | Actual cost | Prepaid
Database Conversion | 40 | 16 | 24
Eservice Express | 160 | 119 | 41
Eservice Online | 160 | 83 | 77
eService Refactoring with Cost Analysis | 110 | 52 | 58
Total | 470 | 270 | 200
Sanjel Need to Pay | 470
Part 12 Cost for Jan. 2019(From 20190101 to 20190131)
Workflow | Total Hours | Actual cost | Prepaid
Eservice Online | 457 | 457 | 0
Total | 457 | 457 | 0
Sanjel Need to Pay | 457
Part 12 Cost for Feb. 2019(From 20190201 to 20190228)
Workflow | Total Hours | Actual cost | Prepaid
Eservice Online | 184 | 184 | 0
Eservice Express | 23 | 23 | 0
Total | 207 | 207 | 0
Sanjel Need to Pay | 207
Part 12 Cost for Mar. 2019(From 20190301 to 20190331)
Workflow | Total Hours | Actual cost | Prepaid
Eservice Online | 298.5 | 298.5 | 0
0
Total | 298.5 | 298.5 | 0
Sanjel Need to Pay | 298.5
Part 12 Cost for Apr. 2019(From 20190401 to 20190430)
Workflow | Total Hours | Actual cost | Prepaid
Eservice Online | 350.5 | 350.5 | 0
Eservice Application | 11.5 | 11.5 | 0
Total | 362 | 362 | 0
Sanjel Need to Pay | 362
Part 12 Cost for May. 2019(From 20190501 to 20190531)
Workflow | Total Hours | Actual cost | Prepaid
Eservice Online | 239.5 | 239.5 | 0
Sanjel Master Data Database | 224.5 | 224.5
0
Total | 464 | 464 | 0
Sanjel Need to Pay | 352 | 352
Part 12 Cost for July 2019(From 20190701 to 20190731)
Workflow | Total Hours | Actual cost | Prepaid
Eservice Online | 75 | 150 | -75
Eservice Express | 400 | 400
Total | 550 | 550
Sanjel Need to Pay | 475 | 550 | -75 | 197
Part 13 Cost for Aug. 2019(From 20190801 to 20190831)
Workflow | Total Hours | Actual cost | Prepaid
Eservice Online | 106 | 106
Eservice Express | 65.5 | 65.5
Total | 171.5 | 171.5
Sanjel Need to Pay | 171.5 | 171.5 | 0
Part 14 Cost for Oct. 2019(From 20191001 to 20191031)
Workflow | Total Hours | Actual cost | Prepaid
Eservice Online | 21 | 21
Total | 21 | 21
Sanjel Need to Pay | 21 | 21 | 0
Part 15 Cost for Nov. 2019(From 20191101 to 20191130)
Workflow | Total Hours | Actual cost | Prepaid
Eservice Online | 11 | 11
Total | 11 | 11
Sanjel Need to Pay | 11 | 11 | 0
Part 16 Cost for Dec. 2019(From 20191201 to 20191231)
Workflow | Total Hours | Actual cost | Prepaid
Eservice | 127.5 | 127.5
Total | 127.5 | 127.5
Sanjel Need to Pay | 127.5 | 127.5 | 0
Part 17 Cost for Jen. 2020(From 20200101 to 20200131)
Workflow | Total Hours | Actual cost | Prepaid
Eservice | 130 | 130
Total | 130 | 130
Sanjel Need to Pay | 130 | 130 | 0
Part 18 Cost for Feb. 2020(From 20200201 to 20200229)
Workflow | Total Hours | Actual cost | Prepaid
Eservice | 152 | 152
Total | 152 | 152
Sanjel Need to Pay | 152 | 152 | 0
Part 19 Cost for Mar. 2020(From 20200301 to 20200331)
Workflow | Total Hours | Actual cost | Prepaid
Eservice | 330.5 | 330.5
Total | 330.5 | 330.5
Sanjel Need to Pay | 330.5 | 330.5 | 0
Note on C163: Bella Bi: 此列数据为实际工时
Note on D163: Bella Bi: 此列数据为预付工时
Note on C168: Bella Bi: 72小时为预付，用于支付19年1月份开发工时
Note on C177: Bella Bi: 此列数据为实际工时
Note on D177: Bella Bi: 此列数据为预付工时
Note on C187: Bella Bi: 此列数据为实际工时
Note on D187: Bella Bi: 此列数据为预付工时
Note on C194: Bella Bi: 此列数据为实际工时
Note on D194: Bella Bi: 此列数据为预付工时
Note on C202: Bella Bi: 此列数据为实际工时
Note on D202: Bella Bi: 此列数据为预付工时
Note on C210: Bella Bi: 此列数据为实际工时
Note on D210: Bella Bi: 此列数据为预付工时
Note on C218: Bella Bi: 此列数据为实际工时
Note on D218: Bella Bi: 此列数据为预付工时
Note on C220: Bella Bi: Sanjel需要支付50%-112人时
Note on C228: Bella Bi: 此列数据为实际工时
Note on D228: Bella Bi: 此列数据为预付工时
Note on B231: Bella Bi:本月共花费550人时 Sanjel支付475，预付支付75人时
Note on E232: Bella Bi: 总共预付工时272，本次使用75人时，余197人时
Note on C236: Bella Bi: 此列数据为实际工时
Note on D236: Bella Bi: 此列数据为预付工时
Note on C244: Bella Bi: 此列数据为实际工时
Note on D244: Bella Bi: 此列数据为预付工时
Note on C251: Bella Bi: 此列数据为实际工时
Note on D251: Bella Bi: 此列数据为预付工时
Note on C258: Bella Bi: 此列数据为实际工时
Note on D258: Bella Bi: 此列数据为预付工时
Note on C265: Bella Bi: 此列数据为实际工时
Note on D265: Bella Bi: 此列数据为预付工时
Note on C272: Bella Bi: 此列数据为实际工时
Note on D272: Bella Bi: 此列数据为预付工时
Note on C279: Bella Bi: 此列数据为实际工时
Note on D279: Bella Bi: 此列数据为预付工时