## Daily Records
ID | Name | Prioritize | Est(Hour) | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31 | Total Hours
|  |  |  | 43221 | 43222 | 43223 | 43224 | 43227 | 43228 | 43229 | 43230 | 43231 | 43234 | 43235 | 43236 | 43237 | 43238 | 43241 | 43242 | 43243 | 43244 | 43245 | 43248 | 43249 | 43250 | 43251
| Ideal Burndown |  | 505 | 505 | 488 | 471 | 454 | 434 | 396 | 354 | 320 | 286 | 258 | 231 | 214 | 197 | 180 | 164 | 140 | 116 | 88 | 60 | 36 | 24 | 12 | 0 | 602
| Actual |  | 657 | 505 | 491 | 473 | 458 | 435.5 | 401.5 | 360.5 | 324.5 | 287.5 | 242.5 | 223 | 207 | 185 | 160 | 128 | 96 | 72 | 54 | 24 | -11 | -45 | -69 | -97
|  |  |  | 0 | 14 | 18 | 15 | 22.5 | 34 | 41 | 36 | 37 | 45 | 19.5 | 16 | 22 | 25 | 32 | 32 | 24 | 18 | 30 | 35 | 34 | 24 | 28 |  | Assign to | Completion Status
Phase10.P001 | Meeting-Phase 9 | 900 | 80 |  |  | 6 | 3 | 10 | 4 | 4 | 10 | 4 | 16 | 2.5 | 2 | 3 | 2 | 2 | 2 | 4 | 2 | 2 | 2 | 2 | 2 | 5 | 89.5 | All | 0
Phase10.P002 | Project management | 900 | 15 | 2018-05-07: 2; 2018-05-08: 3; 2018-05-09: 2; 2018-05-10: 2; 2018-05-11: 1; 2018-05-15: 1; 2018-05-28: 1 | 12 | Bella.bi | 0
Phase10.S001 | Analysis requirements | 900 | 12 | 2018-05-07: 2; 2018-05-28: 4 | 6 | Bella.bi | 0
Phase10.P003 | Task documentation_Bright | 900 | 10 | [23 empty] | 1 | Bright.liu | 0 | bar: 2018-05-04
Ticket118 | Reschedule a Product Haul | 900 | 8 | 2018-05-02: 7 | 7 | Bright.liu | 1
Ticket124 | Reschedule a Product load | 900 | 6 | 2018-05-03: 5 | 5 | Bright.liu | 1
Ticket93 | Add a "Create Job Alert" page | 900 | 24 | 2018-05-02: 7; 2018-05-03: 7; 2018-05-04: 11; 2018-05-07: 4 | 29 | Linsee.lin | 1
Ticket121 | Update job alert | 900 | 3 | 2018-05-07: 2.5 | 2.5 | Linsee.lin | 1
Ticket129 | Display rigjob list | 900 | 2 | 2018-05-07: 2 | 2 | Bright.liu | 1
Prototype_1.1 | Design for CommonCore | 850 | 8 | 2018-05-08: 7 | 7 | Bela.zhao | 0
Prototype_1.2 | Create CommonCore solution with .net standard and resolve compatibility issues | 850 | 8 | 2018-05-09: 7; 2018-05-10: 6; 2018-05-11: 7 | 20 | Bela.zhao | 0
Prototype_1.7 | Refactor CommonLibrary to .net standard | 850 | 80 | 2018-05-14: 3; 2018-05-15: 7; 2018-05-16: 7; 2018-05-17: 8; 2018-05-18: 8; 2018-05-21: 8; 2018-05-22: 8; 2018-05-23: 6.5; 2018-05-24: 8; 2018-05-25: 7; 2018-05-28: 7; 2018-05-29: 2; 2018-05-31: 2 | 81.5 | Bela.zhao | 0
Prototype_1.6 | TestSQLite Database Prepare | 850 | 8 | 2018-05-08: 6 | 6 | Stone.zhao | 1
Prototype_2.1 | Display X/Y axis - step size is dynamic | 850 | 16 | 2018-05-09: 7; 2018-05-10: 6; 2018-05-14: 4 | 17 | Stone.zhao&Bright.liu | 0
Prototype_2.2 | Display line chart with data feeding @ 1Hz | 850 | 4 | 2018-05-08: 3 | 3 | Linsee.lin | 0
Prototype_2.3 | Display multiple lines in same chart @ same Y axis | 850 | 4 | 2018-05-08: 4 | 4 | Linsee.lin | 0
Prototype_2.6 | Create FDAC project and consistent with the structure of online | 850 | 16 | 2018-05-11: 7 | 7 | Bright.liu | 0
Prototype_2.7 | Implement ChartLibrary prototype | 850 | 16 | 2018-05-11: 7; 2018-05-14: 14 | 21 | Linsee.lin&Bright.liu | 0
Prototype_3.1 | Design for Chart Printing in PDF format | 850 | 16 | 2018-05-09: 7; 2018-05-10: 6 | 13 | Olivia.ge | 0
Prototype_4.0 | Email Sending | 850 | 16 | 2018-05-08: 7; 2018-05-09: 7; 2018-05-10: 6; 2018-05-11: 7; 2018-05-14: 4; 2018-05-15: 2 | 33 | Bessie.Yin | 1
Prototype_1.3 | Test CommonCore in Windows and Linux | 850 | 24 | 2018-05-17: 4; 2018-05-18: 7; 2018-05-30: 4; 2018-05-31: 7 | 22 | Bright.liu | 0
Prototype_1.4 | Modify MetaShare CommonCore to support Sqlite | 850 | 64 | 2018-05-25: 7 | 7 | Bela.zhao | 0
Prototype_2.8 | Implement dynamic pass parameters to Chart | 800 | 16 | 2018-05-28: 7; 2018-05-30: 7; 2018-05-31: 7 | 21 | Linsee.lin
Prototype_3.2 | 3.2 Implement Chart Printing in PDF format prototype | 800 | 80 | [8 empty] | 4 | 4 | 7 | 7 | 7 | 8 | 8 | 8 | 6.5 | 8 | 7 | 7 | 7 | 7 | 7 | 102.5 | Olivia.ge | 0
Prototype_2.4 | 2.4 Display multiple lines in same chart @ two different Y axis | 800 | 8 | 2018-05-09: 7 | 7 | Linsee.lin | 0
Prototype_2.5 | 2.5 Dynamically adjust X axis for displaying more data | 800 | 16 | 2018-05-29: 5 | 5 | Linsee.lin | 0
Ticket116 | Add attachment from Rig Board to call sheet | 650 | 8 | [23 empty] | 0 |  | 0
Ticket123 | Update Reference data is not loaded for use | 650 | 8 | [23 empty] | 0 |  | 0
Ticket135 | Print LoadSheet | 450 | 4 | [23 empty] | 0 |  | 0
Phase10.T001 | Test for Product Haul | 700 | 16 | 2018-05-21: 7; 2018-05-22: 7; 2018-05-23: 7 | 21 | Bright.liu
Phase10.T002 | Test for Job Alert | 700 | 16 | 2018-05-21: 7; 2018-05-22: 7; 2018-05-25: 7 | 21 | Linsee.lin
Ticket118 | Reschedule a Product Haul | 700 | 6 | 2018-05-28: 2; 2018-05-29: 2; 2018-05-30: 1 | 5 | Bright.liu
Ticket111 | Schedule a new product haul | 700 | 4 | 2018-05-28: 2; 2018-05-29: 1; 2018-05-30: 1 | 4 | Bright.liu
Ticket133 | Product Haul On Location | 700 | 4 | 2018-05-29: 2; 2018-05-30: 1 | 3 | Bright.liu
Ticket141 | Product Haul Load on location | 700 | 4 | 2018-05-28: 1; 2018-05-29: 2; 2018-05-30: 1 | 4 | Bright.liu
Ticket130 | Cancel product haul | 700 | 4 | 2018-05-28: 2; 2018-05-29: 1 | 3 | Bright.liu
BUG | Fix bug_Linsee | 700 | 7 | 2018-05-29: 4 | 4 | Linsee.lin
Phase10.E001 | Express migrate to .net core 2.0 and deploy | 700 | 16 | 2018-05-29: 6 | 6 | Bela.zhao
0
Note on B6: Bella Bi: 红色背景：与Product Haul相关的； 蓝色背景：与Job Alert相关的； 绿色背景：其他任务 黄色背景：FDAC任务
Note on L6: Bella Bi: 跟Adam一起讨论架构问题
Note on N6: Bella Bi: Luke指导大家做架构设计 3h*5 跟Adam语音通话1h
Note on Q6: Bella Bi: Luke对目前重构CommonCore的指导
Note on H12: bin liu: 修改需求 Bright 4h Linsee 7h
Note on I14: Bella Bi: 将Company为空的Job Alert显示在页面最后面
Note on N19: Bella Bi: Stone
Note on Y31: Bella Bi: Bela 1h Linsee 4h
Note on B32: Bella Bi: 灰色字体的任务暂时不在本迭代实现，如果有时间再做

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-28 | 2018-05-29
|  |  |  | 43221 | 43222 | 43223 | 43224 | 43227 | 43228 | 43229 | 43230 | 43231 | 43234 | 43235 | 43236 | 43237 | 43238 | 43241 | 43242 | 43243 | 43244 | 43245 | 43248 | 43249
| Ideal Burndown |  | 505 | 505 | 488 | 471 | 454 | 434 | 396 | 354 | 320 | 286 | 258 | 231 | 214 | 197 | 180 | 164 | 140 | 116 | 88 | 60 | 36 | 24
| Actual burndown |  | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Phase10.P001 | Meeting-Phase 9 | 900 | 80 | 80 | 28 | 26 | 25 | 24 | 22 | 20 | 18 | 16 | 14 | 12 | 9 | 9 | 9 | 8 | 7 | 6 | 4 | 3 | 1 | 0
Phase10.P002 | Project management | 900 | 15 | 15 | 15 | 14 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 4.5 | 4.5 | 4 | 4 | 4 | 3 | 2 | 1 | 1 | 0
Phase10.S001 | Analysis requirements | 900 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 17 | 14 | 10 | 5 | 10 | 5 | 5 | 5 | 4 | 2 | 1 | 1 | 1 | 0 | 0
Phase10.P003 | Task documentation_Bright | 900 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 17 | 10 | 5 | 5 | 5 | 4 | 2 | 1 | 1 | 1 | 0 | 0
Ticket118 | Reschedule a Product Haul | 900 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 17 | 10 | 5 | 5 | 5 | 4 | 2 | 1 | 1 | 1 | 0 | 0
Ticket124 | Reschedule a Product load | 900 | 6 | 6 | 2 | 1 | 1 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 5 | 5 | 3 | 3 | 2 | 2 | 1 | 1 | 0
Ticket93 | Add a "Create Job Alert" page | 900 | 24 | 24 | 24 | 24 | 24 | 24 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
Ticket116 | Add attachment from Rig Board to call sheet | 650 | 8 | 8 | 8 | 20 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket123 | Update Reference data is not loaded for use | 650 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket135 | Print LoadSheet | 450 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase10.T001 | Test for Product Haul | 700 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase10.T002 | Test for Job Alert | 700 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket118 | Reschedule a Product Haul | 700 | 6 | 6 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket111 | Schedule a new product haul | 700 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 6 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket133 | Product Haul On Location | 700 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket141 | Product Haul Load on location | 700 | 4 | 4 | 4 | 4 | 4 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket130 | Cancel product haul | 700 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BUG | Fix bug_Linsee | 700 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase10.E001 | Express migrate to .net core 2.0 and deploy | 700 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 4 | 3 | 3 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 2 | 2 | 1 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0
0 | 0 | 0 | 0 | 2018-05-24: 0; 2018-05-25: 0; 2018-05-28: 0; 2018-05-29: 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 1 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成第10期FDAS的需求
StartDate | 2018-05-02
EndDate | 2018-05-31
Est Time
Name | Role | Total Hours | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31
|  |  | 43222 | 43223 | 43224 | 43227 | 43228 | 43229 | 43230 | 43231 | 43234 | 43235 | 43236 | 43237 | 43238 | 43241 | 43242 | 43243 | 43244 | 43245 | 43248 | 43249 | 43250 | 43251
Ideal Burndown |  | 505 | 488 | 471 | 454 | 434 | 396 | 354 | 320 | 286 | 258 | 231 | 214 | 197 | 180 | 164 | 140 | 116 | 88 | 60 | 36 | 24 | 12 | 0
Hours consumed |  | 505 | 17 | 17 | 17 | 20 | 38 | 42 | 34 | 34 | 28 | 27 | 17 | 17 | 17 | 16 | 24 | 24 | 28 | 28 | 24 | 12 | 12 | 12
Bella.Bi |  | 32 | 1 | 1 | 1 | 4 | 6 | 6 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Linsee.Lin |  | 68 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
Olivia.Ge |  | 118 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2
Bright.Liu |  | 119 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 5 | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 8 | 8 | 8 | 8 | 8 | 8
Stone.Zhao |  | 14 | 0 | 0 | 0 | 2 | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bela.Zhao |  | 128 | 0 | 0 | 0 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2
Bessie.Yin |  | 26 | 0 | 0 | 0 | 2 | 8 | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Time
Name | Role | Total Hours | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31
|  |  | 43222 | 43223 | 43224 | 43227 | 43228 | 43229 | 43230 | 43231 | 43234 | 43235 | 43236 | 43237 | 43238 | 43241 | 43242 | 43243 | 43244 | 43245 | 43248 | 43249 | 43250 | 43251
Ideal Burndown |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours consumed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bella.Bi |  | 0
Linsee.Lin |  | 0
Olivia.Ge |  | 0
Bright.Liu |  | 0
0
0
0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase10.P001 | Meeting-Phase 9 | 900 | 80 | 0 | All | 89.5
Phase10.P002 | Project management | 900 | 15 | 0 | Bella.bi | 12
Phase10.S001 | Analysis requirements | 900 | 12 | 0 | Bella.bi | 6
Phase10.P003 | Task documentation_Bright | 900 | 10 | 0 | Bright.liu | 1
Ticket118 | Reschedule a Product Haul | 900 | 8 | 1 | Bright.liu | 7
Ticket124 | Reschedule a Product load | 900 | 6 | 1 | Bright.liu | 5
Ticket93 | Add a "Create Job Alert" page | 900 | 24 | 1 | Linsee.lin | 29
Ticket121 | Update job alert | 900 | 3 | 1 | Linsee.lin | 2.5
Ticket129 | Display rigjob list | 900 | 2 | 1 | Bright.liu | 2
Prototype_1.1 | Design for CommonCore | 850 | 8 | 0 | Bela.zhao | 7
Prototype_1.2 | Create CommonCore solution with .net standard and resolve compatibility issues | 850 | 8 | 0 | Bela.zhao | 20
Prototype_1.7 | Refactor CommonLibrary to .net standard | 850 | 80 | 0 | Bela.zhao | 81.5
Prototype_1.6 | TestSQLite Database Prepare | 850 | 8 | 1 | Stone.zhao | 6
Prototype_2.1 | Display X/Y axis - step size is dynamic | 850 | 16 | 0 | Stone.zhao&Bright.liu | 17
Prototype_2.2 | Display line chart with data feeding @ 1Hz | 850 | 4 | 0 | Linsee.lin | 3
Prototype_2.3 | Display multiple lines in same chart @ same Y axis | 850 | 4 | 0 | Linsee.lin | 4
Prototype_2.6 | Create FDAC project and consistent with the structure of online | 850 | 16 | 0 | Bright.liu | 7
Prototype_2.7 | Implement ChartLibrary prototype | 850 | 16 | 0 | Linsee.lin&Bright.liu | 21
Prototype_3.1 | Design for Chart Printing in PDF format | 850 | 16 | 0 | Olivia.ge | 13
Prototype_4.0 | Email Sending | 850 | 16 | 1 | Bessie.Yin | 33
Prototype_1.3 | Test CommonCore in Windows and Linux | 850 | 24 | 0 | Bright.liu | 22
Prototype_1.4 | Modify MetaShare CommonCore to support Sqlite | 850 | 64 | 0 | Bela.zhao | 7
Prototype_2.8 | Implement dynamic pass parameters to Chart | 800 | 16 | 0 | Linsee.lin | 21
Prototype_3.2 | 3.2 Implement Chart Printing in PDF format prototype | 800 | 80 | 0 | Olivia.ge | 102.5
Prototype_2.4 | 2.4 Display multiple lines in same chart @ two different Y axis | 800 | 8 | 0 | Linsee.lin | 7
Prototype_2.5 | 2.5 Dynamically adjust X axis for displaying more data | 800 | 16 | 0 | Linsee.lin | 5
Ticket116 | Add attachment from Rig Board to call sheet | 650 | 8 | 0 | 0 | 0
Ticket123 | Update Reference data is not loaded for use | 650 | 8 | 0 | 0 | 0
Ticket135 | Print LoadSheet | 450 | 4 | 0 | 0 | 0
Phase10.T001 | Test for Product Haul | 700 | 16 | 0 | Bright.liu | 21
Phase10.T002 | Test for Job Alert | 700 | 16 | 0 | Linsee.lin | 21
Ticket118 | Reschedule a Product Haul | 700 | 6 | 0 | Bright.liu | 5
Ticket111 | Schedule a new product haul | 700 | 4 | 0 | Bright.liu | 4
Ticket133 | Product Haul On Location | 700 | 4 | 0 | Bright.liu | 3
Ticket141 | Product Haul Load on location | 700 | 4 | 0 | Bright.liu | 4
Ticket130 | Cancel product haul | 700 | 4 | 0 | Bright.liu | 3
BUG | Fix bug_Linsee | 700 | 7 | 0 | Linsee.lin | 4
Phase10.E001 | Express migrate to .net core 2.0 and deploy | 700 | 16 | 0 | Bela.zhao | 6
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
Phase10.E001 | Express migrate to .net core 2.0 and deploy | 700 | 16 |  | Bela.zhao | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间