## Daily Records
ID | Name | Prioritize | Est(Hour) | 2018-05-31 | 2018-06-01 | 2018-06-04 | 2018-06-05 | 2018-06-06 | 2018-06-11 | 2018-06-12 | 2018-06-13 | 2018-06-14 | 2018-06-15 | 2018-06-19 | 2018-06-20 | 2018-06-21 | 2018-06-22 | 2018-06-23 | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29 | Total Hours
|  |  |  | 43251 | 43252 | 43255 | 43256 | 43257 | 43262 | 43263 | 43264 | 43265 | 43266 | 43270 | 43271 | 43272 | 43273 | 43274 | 43276 | 43277 | 43278 | 43279 | 43280
| Ideal Burndown |  | 644 | 644 | 629 | 603 | 581 | 555 | 525 | 495 | 465 | 437 | 409 | 381 | 353 | 319 | 285 | 233 | 183 | 133 | 83 | 44 | 0 | 593.5
| Actual |  | 605 | 644 | 628 | 596.5 | 565.5 | 529.5 | 491.5 | 460 | 431.5 | 404.5 | 380.5 | 359.5 | 332.5 | 313.5 | 282 | 246.5 | 251 | 217.5 | 177.5 | 139.5 | 86
|  |  |  | 0 | 16 | 31.5 | 31 | 36 | 38 | 31.5 | 28.5 | 27 | 24 | 21 | 27 | 19 | 31.5 | 35.5 | 31 | 33.5 | 40 | 38 | 53.5 |  | Assign to | Completion Status | Pay by
Phase10.P001 | Meeting-Phase 9 | 900 | 40 |  | 2 | 9 | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 2 | 4 | 2 | 10.5 | 2 | 2 | 2 | 2 | 2 | 2 | 59.5 | All | 1 | Sanjel
Phase10.P002 | Project management | 900 | 15 | 2018-06-04: 2; 2018-06-05: 4; 2018-06-11: 1; 2018-06-12: 1; 2018-06-13: 1; 2018-06-23: 1; 2018-06-25: 2; 2018-06-26: 1; 2018-06-27: 1; 2018-06-28: 1; 2018-06-29: 1 | 16 | Bella.bi | 1 | Sanjel
Phase10.S001 | Analysis requirements | 900 | 45 |  |  |  |  | 4 | 5 | 2 | 3 | 5 | 4 | 5 | 9 | 3 | 2 |  | 1 | 2 | 2 | 1 | 6 | 54 | Bella.bi | 1 | Sanjel
Phase10.P003 | Task documentation | 900 | 10 | 2018-06-05: 0.5; 2018-06-20: 2; 2018-06-22: 1; 2018-06-23: 2; 2018-06-26: 0.5; 2018-06-28: 0.5; 2018-06-29: 0.5 | 7 | Bella.bi | 1 | Sanjel
Prototype_2.7.1 | Implement ChartLibrary prototype_Bright | 850 | 40 | 2018-06-01: 4; 2018-06-04: 5.5; 2018-06-05: 7.5; 2018-06-06: 7.5; 2018-06-11: 7.5; 2018-06-12: 4.5; 2018-06-13: 7; 2018-06-14: 14; 2018-06-15: 7 | 64.5 | Bright.liu | 1 | MetaShare
Prototype_2.7.2 | Implement ChartLibrary prototype_Stone | 850 | 16 | 2018-06-04: 4; 2018-06-05: 4 | 8 | Bright.liu | 1 | MetaShare
Prototype_2.7.3 | Implement ChartLibrary prototype_Kevin | 850 | 12 | 2018-06-04: 4; 2018-06-06: 5; 2018-06-12: 1; 2018-06-13: 1 | 11 | Kevin.Wu | 1 | MetaShare
Prototype_1.4 | Modify MetaShare CommonCore to support Sqlite | 850 | 64 |  | 1 | 4 | 4 | 6 | 7.5 | 7 | 7 | 3 | 8 | 9 | 9 | 7 | [7 empty] | 72.5 | Bela.zhao | 1 | Sanjel | 建议Sanjel和MetaShare一起承担
Prototype_1.3 | Test CommonCore in Windows and Linux | 850 | 16 | 2018-06-01: 9; 2018-06-05: 4; 2018-06-06: 7.5; 2018-06-11: 4 | 24.5 | Linsee.lin&Bright.liu | 1 | MetaShare
Prototype_3.2 | Implement Chart Printing in PDF format prototype | 830 | 8 | 2018-06-04: 3; 2018-06-05: 5 | 8 | Olivia.ge | 1 | Sanjel
Phase10.E001 | Publish Online | 830 | 8 | 2018-06-06: 4; 2018-06-11: 7; 2018-06-12: 7; 2018-06-13: 1.5 | 19.5 | Stone.Zhao | 1 | MetaShare
Phase10.S002 | Add TestCase_Linsee | 830 | 8 | 2018-06-11: 4; 2018-06-12: 3 | 7 | Linsee.Lin | 1 | Sanjel
Phase10.S003 | Analysis for TestCase_Bright | 830 | 8 | 2018-06-19: 5; 2018-06-20: 3 | 8 | Bright.Liu | 1 | Sanjel
Prototype_1.7 | Research for SQLite implementation mechanism | 830 | 16 | 2018-06-13: 6; 2018-06-14: 3; 2018-06-15: 3 | 12 | Stone.Zhao | 1 | Sanjel
Phase10.D002 | Design for FDAS | 830 | 16 | 2018-06-21: 7 | 7 | Bright.Liu | 1 | Sanjel
#178 | Merge Common Library to trunk | 830 | 40 | 2018-06-22: 5.5; 2018-06-23: 8; 2018-06-25: 13; 2018-06-26: 8 | 34.5 | Bela.Zhao | 1 | Sanjel
Phase10.T001 | Test for Oracle to sql migration | 830 | 16 | 2018-06-22: 3; 2018-06-23: 8 | 11 | Stone.Zhao | 0 | Sanjel
#200 | Modify namespace and dependence for all projects | 830 | 16 | 2018-06-27: 7.5; 2018-06-28: 6; 2018-06-29: 5 | 18.5 | Bela.Zhao | 1 | Sanjel
#201 | Test Dao and mofidy dao if necessary | 830 | 16 | 2018-06-29: 20 | 20 | Bela.Zhao&Bright.Liu | 0 | Sanjel
#202 | System Testing for all projects | 830 | 32 | 2018-06-28: 7 | 7 | Bela.Zhao&Bright.Liu | 0 | Sanjel
#189 | Design for Express front-end architecture | 830 | 15 | 2018-06-23: 3.5; 2018-06-25: 5; 2018-06-26: 7; 2018-06-27: 3 | 18.5 | Olivia.Ge&Bright.Liu | 1 | Sanjel
#172 | Add Menu to eService Express | 800 | 2 | [20 empty] | 0 | Linsee.Lin | 0 | Sanjel
#173 | Add Local Jobs function to eService Express | 800 | 6 | 2018-06-22: 4 | 4 | Linsee.Lin | 1 | Sanjel
#176 | Set current job _express front-end architecture Implementation | 800 | 4 | 2018-06-22: 3; 2018-06-27: 5 | 8 | Bright.Liu | 1 | Sanjel
#177 | Set current job _FrontEnd | 800 | 6 | 2018-06-23: 5; 2018-06-29: 8 | 13 | Linsee.Lin | 0 | Sanjel
#182 | Upgrade .net framework for all projects | 800 | 8 | 2018-06-22: 2.5 | 2.5 | Bright.Liu | 1 | Sanjel
#192 | Design eService Express UI Layout | 760 | 3 | 2018-06-26: 1.5; 2018-06-27: 5 | 6.5 | Niki.Wang | 1 | Sanjel
#175 | Database access architecture | 790 | 32 | 2018-06-27: 3; 2018-06-28: 7; 2018-06-29: 7 | 17 | Olivia.Ge | 0 | Sanjel
#193 | Implement eService Express New Layout | 790 | 8 | 2018-06-29: 3 | 3 | Linsee.Lin | 0 | Sanjel
#183 | Display Job Monitor _Get Job Monitor Setting_backend | 780 | 6 | [20 empty] | 0 | Bright.Liu | 0 | Sanjel
#184 | Display Chart _display X axis label as time format | 780 | 8 | 2018-06-26: 3 | 3 | Linsee.Lin | 0 | Sanjel
#197 | Display Chart _display privious data | 780 | 8 | 2018-06-28: 6.5 | 6.5 | Linsee.Lin | 0 | Sanjel
#198 | Display Chart _display real-time data | 780 | 8 | [20 empty] | 0 |  | 0 | Sanjel
#187 | Print chart architecture | 750 | 8 | 2018-06-23: 6 | 6 | Olivia.Ge&Kevin.wu | 1 | Sanjel
#194 | Print chart_Modify X axis label as time format | 750 | 14 | 2018-06-25: 8; 2018-06-26: 6 | 14 | Kevin.Wu | 1 | Sanjel
#195 | Print coordinate point and grid | 750 | 11 | 2018-06-26: 2.5; 2018-06-27: 8.5; 2018-06-28: 2; 2018-06-29: 1 | 14 | Olivia.Ge&Kevin.wu | 0 | Sanjel
#199 | Enrich printing interface | 750 | 16 | 2018-06-27: 3; 2018-06-28: 5 | 8 | Olivia.Ge | 0 | Sanjel
#185 | Display Job Monitor _Calculate default start time | 760
Ticket #162 | Cancel a product load —only one load in a haul | 200 | 4 | [22 empty] | 0
Ticket #133 | Product Haul On Location | 200 | 4 | [22 empty] | 0
Ticket #163 | Schedule a load to an existing haul-Update Unit Section/Third Party | 200 | 6 | [22 empty] | 0
Ticket #164 | Reschedule a Product Haul-Update unit section/Third party section | 200 | 6 | [22 empty] | 0
Ticket #165 | Re-schedule product haul Load - Modify page | 200 | 6 | [22 empty] | 0
Ticket #166 | Re-schedule product haul Load - Use original haul or not | 200 | 10 | [22 empty] | 0
Note on B6: Bella Bi: 红色背景：与Product Haul相关的； 蓝色背景：与Job Alert相关的； 绿色背景：其他任务 黄色背景：FDAC任务
Note on G6: Bella Bi: 讨论目前实时制图原型存在的问题，重新整理思路
Note on K6: Bella Bi: 与Adam开会讨论目前原型存在的问题及思路
Note on P6: Bella Bi: 需求分析讨论 1h*3 早会1h
Note on R6: Bella Bi: 开会讨论code merge的问题 5*1.5 早会：0.5*6
Note on I8: Bella Bi: 分析ProductHaul的需求并补充TestCase
Note on M10: Bella Bi: Bright 7h Bela 4h Olivia 3h
Note on F14: Bella Bi: Bela 5h Bright 4h
Note on H14: Bella Bi: Linsee 5h
Note on I14: Bella Bi: 解决XML读取问题 Stone 2.5h Linsee 3h Bela 2h
Note on H15: Bella Bi: 分析目前存在的问题
Note on I16: Bella Bi: 升级VS到core 2.0之后本地部署报500.19问题
Note on S21: Bella Bi: Bela 6h Kevin 2h 测试
Note on T21: Bella Bi: Bela 6h Bright 7h Merge之后修改其他项目的引用关系
Note on U21: Bella Bi: Bela 5.5h Bright 2.5h
Note on V23: Bella Bi: Bela 7h Linsee 0.5h
Note on X24: Bella Bi: Bela 8h Bright 12h 测试Dao，修改问题
Note on W25: Bella Bi: Bright 3h Bela 3h Linsee 1h
Note on U26: Bella Bi: Olivia 3h Bright 4h
Note on V26: Bella Bi: Bright 2h Olivia 1.5h
Note on X30: Bella Bi: 前后台串起来
Note on W33: Bella Bi: Olivia 1.5h Bright 5.5h 实现存操作
Note on S39: Bella Bi: 熟悉PrintingService代码 Kevin 6h Olivia 1h
Note on V41: Bella Bi: Kevin 7.5h Olivia 1h
Note on W41: Bella Bi: Olivia 2h 实现主标尺
Note on X41: Bella Bi: 完善标尺线 Olivia 1h

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2018-05-31 | 2018-06-01 | 2018-06-04 | 2018-06-05 | 2018-06-06 | 2018-06-11 | 2018-06-12 | 2018-06-13 | 2018-06-14 | 2018-06-15 | 2018-06-19 | 2018-06-20 | 2018-06-21 | 2018-06-22 | 2018-06-23 | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29
|  |  |  | 43251 | 43252 | 43255 | 43256 | 43257 | 43262 | 43263 | 43264 | 43265 | 43266 | 43270 | 43271 | 43272 | 43273 | 43274 | 43276 | 43277 | 43278 | 43279 | 43280
| Ideal Burndown |  | 644 | 644 | 629 | 603 | 581 | 555 | 525 | 495 | 465 | 437 | 409 | 381 | 353 | 319 | 285 | 233 | 183 | 133 | 83 | 44 | 0
| Actual burndown |  | 605 | 306 | 294 | 291 | 255 | 249 | 179 | 156 | 113 | 102 | 58.5 | 61.5 | 62 | 234 | 217 | 185 | 174 | 195 | 133 | 117 | 87
Phase10.P001 | Meeting-Phase 9 | 900 | 40 | 40 | 28 | 26 | 25 | 24 | 18 | 16 | 14 | 12 | 9 | 9 | 20 | 8 | 7 | 7 | 6 | 4 | 3 | 4 | 0
Phase10.P002 | Project management | 900 | 15 | 15 | 15 | 14 | 12 | 12 | 12 | 12 | 12 | 12 | 4.5 | 4.5 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 2 | 0
Phase10.S001 | Analysis requirements | 900 | 45 | 45 | 45 | 45 | 45 | 45 | 14 | 10 | 5 | 10 | 5 | 20 | 24 | 24 | 24 | 16 | 10 | 6 | 6 | 12 | 0
Phase10.P003 | Task documentation | 900 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 6 | 4 | 2 | 2 | 1 | 1 | 1 | 1 | 0
Prototype_2.7.1 | Implement ChartLibrary prototype_Bright | 850 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 24 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prototype_2.7.2 | Implement ChartLibrary prototype_Stone | 850 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prototype_2.7.3 | Implement ChartLibrary prototype_Kevin | 850 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prototype_1.4 | Modify MetaShare CommonCore to support Sqlite | 850 | 64 | 64 | 64 | 64 | 55 | 50 | 45 | 40 | 32 | 26 | 18 | 12 | 8 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Prototype_1.3 | Test CommonCore in Windows and Linux | 850 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prototype_3.2 | Implement Chart Printing in PDF format prototype | 830 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase10.E001 | Publish Online | 830 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase10.S002 | Add TestCase_Linsee | 830 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase10.S003 | Analysis for TestCase_Bright | 830 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prototype_1.7 | Research for SQLite implementation mechanism | 830 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase10.D002 | Design for FDAS | 830 | 16 | 2018-06-21: 16; 2018-06-22: 8; 2018-06-23: 6; 2018-06-25: 4; 2018-06-26: 4; 2018-06-27: 4; 2018-06-28: 0; 2018-06-29: 0
#178 | Merge Common Library to trunk | 830 | 40 | 2018-06-21: 40; 2018-06-22: 35; 2018-06-23: 35; 2018-06-25: 24; 2018-06-26: 1; 2018-06-27: 1; 2018-06-28: 0; 2018-06-29: 0
Phase10.T001 | Test for Oracle to sql migration | 830 | 16 | 2018-06-21: 16; 2018-06-22: 5; 2018-06-23: 5; 2018-06-25: 5; 2018-06-26: 5; 2018-06-27: 5; 2018-06-28: 5; 2018-06-29: 5
#200 | Modify namespace and dependence for all projects | 830 | 16 | 2018-06-26: 16; 2018-06-27: 8; 2018-06-28: 6; 2018-06-29: 0
#201 | Test Dao and mofidy dao if necessary | 830 | 16 | 2018-06-26: 16; 2018-06-27: 16; 2018-06-28: 16; 2018-06-29: 16
#202 | System Testing for all projects | 830 | 32 | 2018-06-26: 32; 2018-06-27: 32; 2018-06-28: 24; 2018-06-29: 24
#189 | Design for Express front-end architecture | 830 | 15 | 2018-06-22: 15; 2018-06-23: 8; 2018-06-25: 8; 2018-06-26: 8; 2018-06-27: 0; 2018-06-28: 0; 2018-06-29: 0
#172 | Add Menu to eService Express | 800 | 2 | 2018-06-21: 2; 2018-06-22: 2; 2018-06-23: 2; 2018-06-25: 2; 2018-06-26: 2; 2018-06-27: 2; 2018-06-28: 2; 2018-06-29: 2
#173 | Add Local Jobs function to eService Express | 800 | 6 | 2018-06-21: 6; 2018-06-22: 3; 2018-06-23: 3; 2018-06-25: 3; 2018-06-26: 3; 2018-06-27: 3; 2018-06-28: 3; 2018-06-29: 0
#176 | Set current job _express front-end architecture Implementation | 800 | 4 | 2018-06-21: 4; 2018-06-22: 4; 2018-06-23: 4; 2018-06-25: 4; 2018-06-26: 4; 2018-06-27: 0; 2018-06-28: 0; 2018-06-29: 0
#177 | Set current job _FrontEnd | 800 | 6 | 2018-06-21: 6; 2018-06-22: 6; 2018-06-23: 1; 2018-06-25: 1; 2018-06-26: 1; 2018-06-27: 1; 2018-06-28: 2; 2018-06-29: 0
#182 | Upgrade .net framework for all projects | 800 | 8 | 2018-06-21: 8; 2018-06-22: 6; 2018-06-23: 0; 2018-06-25: 0; 2018-06-26: 0; 2018-06-27: 0; 2018-06-28: 0; 2018-06-29: 0
#192 | Design eService Express UI Layout | 760 | 3 | 2018-06-25: 3; 2018-06-26: 0; 2018-06-27: 0; 2018-06-28: 0; 2018-06-29: 0
#175 | Database access architecture | 790 | 32 | 2018-06-21: 32; 2018-06-22: 32; 2018-06-23: 32; 2018-06-25: 32; 2018-06-26: 32; 2018-06-27: 8; 2018-06-28: 12; 2018-06-29: 12
#193 | Implement eService Express New Layout | 790 | 8 | 2018-06-28: 8; 2018-06-29: 8
#183 | Display Job Monitor _Get Job Monitor Setting_backend | 780 | 6 | 2018-06-21: 6; 2018-06-22: 6; 2018-06-23: 6; 2018-06-25: 6; 2018-06-26: 6; 2018-06-27: 6; 2018-06-28: 6; 2018-06-29: 6
#184 | Display Chart _display X axis label as time format | 780 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0
#197 | Display Chart _display privious data | 780 | 8 | 2018-06-25: 8; 2018-06-26: 8; 2018-06-27: 8; 2018-06-28: 2; 2018-06-29: 2
#198 | Display Chart _display real-time data | 780 | 8 | 2018-06-25: 8; 2018-06-26: 8; 2018-06-27: 8; 2018-06-28: 8; 2018-06-29: 8
#187 | Print chart architecture | 750 | 8 | 2018-06-21: 8; 2018-06-22: 8; 2018-06-23: 4; 2018-06-25: 4; 2018-06-26: 4; 2018-06-27: 0; 2018-06-28: 0; 2018-06-29: 0
#194 | Print chart_Modify X axis label as time format | 750 | 14 | 2018-06-21: 14; 2018-06-22: 14; 2018-06-23: 14; 2018-06-25: 6; 2018-06-26: 0; 2018-06-27: 0; 2018-06-28: 0; 2018-06-29: 0
#195 | Print coordinate point and grid | 750 | 11 | 2018-06-21: 11; 2018-06-22: 11; 2018-06-23: 11; 2018-06-25: 11; 2018-06-26: 8; 2018-06-27: 8; 2018-06-28: 4; 2018-06-29: 4
#199 | Enrich printing interface | 750 | 16 | 2018-06-21: 16; 2018-06-22: 16; 2018-06-23: 16; 2018-06-25: 16; 2018-06-26: 16; 2018-06-27: 12; 2018-06-28: 0; 2018-06-29: 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成第10期FDAS的需求
StartDate | 2018-06-01
EndDate | 2018-06-30
Est Time
Name | Role | Total Hours | 2018-06-01 | 2018-06-04 | 2018-06-05 | 2018-06-06 | 2018-06-11 | 2018-06-12 | 2018-06-13 | 2018-06-14 | 2018-06-15 | 2018-06-19 | 2018-06-20 | 2018-06-21 | 2018-06-22 | 2018-06-23 | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29
|  |  | 43252 | 43255 | 43256 | 43257 | 43262 | 43263 | 43264 | 43265 | 43266 | 43270 | 43271 | 43272 | 43273 | 43274 | 43276 | 43277 | 43278 | 43279 | 43280
Ideal Burndown |  | 644 | 629 | 603 | 581 | 555 | 525 | 495 | 465 | 437 | 409 | 381 | 353 | 319 | 285 | 233 | 183 | 133 | 83 | 44 | 0
Hours consumed |  | 644 | 15 | 26 | 22 | 26 | 30 | 30 | 30 | 28 | 28 | 28 | 28 | 34 | 34 | 52 | 50 | 50 | 50 | 39 | 44
Bella.Bi |  | 70 | 1 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Linsee.Lin |  | 79 | 1 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Olivia.Ge |  | 66 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8
Bright.Liu |  | 152 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Stone.Zhao |  | 50 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 6 | 6 | 2 | 6
Bela.Zhao |  | 148 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Kevin.Wu |  | 79 | 0 | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 8 | 8 | 8 | 8 | 1 | 2
Actual Time
Name | Role | Total Hours | 2018-06-01 |  | 2018-06-05 | 2018-06-06 | 2018-06-11 | 2018-06-12 | 2018-06-13 | 2018-06-14 | 2018-06-15 | 2018-06-19 | 2018-06-20 | 2018-06-21 | 2018-06-22 |  | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29
|  |  | 43252 |  | 43256 | 43257 | 43262 | 43263 | 43264 | 43265 | 43266 | 43270 | 43271 | 43272 | 43273 |  | 43276 | 43277 | 43278 | 43279 | 43280
Ideal Burndown |  | 0 | 0 |  | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
Hours consumed |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Bella.Bi |  | 0
Linsee.Lin |  | 0
Olivia.Ge |  | 0
Bright.Liu |  | 0
0
0
0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase10.P001 | Meeting-Phase 9 | 900 | 40 | 1 | All | 59.5
Phase10.P002 | Project management | 900 | 15 | 1 | Bella.bi | 16
Phase10.S001 | Analysis requirements | 900 | 45 | 1 | Bella.bi | 54
Phase10.P003 | Task documentation | 900 | 10 | 1 | Bella.bi | 7
Prototype_2.7.1 | Implement ChartLibrary prototype_Bright | 850 | 40 | 1 | Bright.liu | 64.5
Prototype_2.7.2 | Implement ChartLibrary prototype_Stone | 850 | 16 | 1 | Bright.liu | 8
Prototype_2.7.3 | Implement ChartLibrary prototype_Kevin | 850 | 12 | 1 | Kevin.Wu | 11
Prototype_1.4 | Modify MetaShare CommonCore to support Sqlite | 850 | 64 | 1 | Bela.zhao | 72.5
Prototype_1.3 | Test CommonCore in Windows and Linux | 850 | 16 | 1 | Linsee.lin&Bright.liu | 24.5
Prototype_3.2 | Implement Chart Printing in PDF format prototype | 830 | 8 | 1 | Olivia.ge | 8
Phase10.E001 | Publish Online | 830 | 8 | 1 | Stone.Zhao | 19.5
Phase10.S002 | Add TestCase_Linsee | 830 | 8 | 1 | Linsee.Lin | 7
Phase10.S003 | Analysis for TestCase_Bright | 830 | 8 | 1 | Bright.Liu | 8
Prototype_1.7 | Research for SQLite implementation mechanism | 830 | 16 | 1 | Stone.Zhao | 12
Phase10.D002 | Design for FDAS | 830 | 16 | 1 | Bright.Liu | 7
#178 | Merge Common Library to trunk | 830 | 40 | 1 | Bela.Zhao | 34.5
Phase10.T001 | Test for Oracle to sql migration | 830 | 16 | 0 | Stone.Zhao | 11
#200 | Modify namespace and dependence for all projects | 830 | 16 | 1 | Bela.Zhao | 18.5
#201 | Test Dao and mofidy dao if necessary | 830 | 16 | 0 | Bela.Zhao&Bright.Liu | 20
#202 | System Testing for all projects | 830 | 32 | 0 | Bela.Zhao&Bright.Liu | 7
#189 | Design for Express front-end architecture | 830 | 15 | 1 | Olivia.Ge&Bright.Liu | 18.5
#172 | Add Menu to eService Express | 800 | 2 | 0 | Linsee.Lin | 0
#173 | Add Local Jobs function to eService Express | 800 | 6 | 1 | Linsee.Lin | 4
#176 | Set current job _express front-end architecture Implementation | 800 | 4 | 1 | Bright.Liu | 8
#177 | Set current job _FrontEnd | 800 | 6 | 0 | Linsee.Lin | 13
#182 | Upgrade .net framework for all projects | 800 | 8 | 1 | Bright.Liu | 2.5
#192 | Design eService Express UI Layout | 760 | 3 | 1 | Niki.Wang | 6.5
#175 | Database access architecture | 790 | 32 | 0 | Olivia.Ge | 17
#193 | Implement eService Express New Layout | 790 | 8 | 0 | Linsee.Lin | 3
#183 | Display Job Monitor _Get Job Monitor Setting_backend | 780 | 6 | 0 | Bright.Liu | 0
#184 | Display Chart _display X axis label as time format | 780 | 8 | 0 | Linsee.Lin | 3
#197 | Display Chart _display privious data | 780 | 8 | 0 | Linsee.Lin | 6.5
#198 | Display Chart _display real-time data | 780 | 8 | 0 | 0 | 0
#187 | Print chart architecture | 750 | 8 | 1 | Olivia.Ge&Kevin.wu | 6
#194 | Print chart_Modify X axis label as time format | 750 | 14 | 1 | Kevin.Wu | 14
#195 | Print coordinate point and grid | 750 | 11 | 0 | Olivia.Ge&Kevin.wu | 14
#199 | Enrich printing interface | 750 | 16 | 0 | Olivia.Ge | 8
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
#185 | Display Job Monitor _Calculate default start time | 760 | 0 | 0 | 0 | 0
Ticket #162 | Cancel a product load —only one load in a haul | 200 | 4 | 0 | 0 | 0
Ticket #133 | Product Haul On Location | 200 | 4 | 0 | 0 | 0
Ticket #163 | Schedule a load to an existing haul-Update Unit Section/Third Party | 200 | 6 | 0 | 0 | 0
Ticket #164 | Reschedule a Product Haul-Update unit section/Third party section | 200 | 6 | 0 | 0 | 0
Ticket #165 | Re-schedule product haul Load - Modify page | 200 | 6 | 0 | 0 | 0
Ticket #166 | Re-schedule product haul Load - Use original haul or not | 200 | 10 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
Prototype_1.4 | Modify MetaShare CommonCore to support Sqlite | 850 | 64 |  | Bela.zhao | 0
Prototype_1.3 | Test CommonCore in Windows and Linux | 850 | 16 |  | Linsee.lin&Bright.liu | 0
Prototype_3.2 | Implement Chart Printing in PDF format prototype | 830 | 8 |  | Olivia.ge | 0
Phase10.E001 | Publish Online | 830 | 8 |  | Stone.Zhao | 0
Phase10.S002 | Add TestCase_Linsee | 830 | 8 |  | Linsee.Lin | 0
Prototype_1.7 | Research for SQLite implementation mechanism | 830 | 16 |  | Stone.Zhao | 0
Ticket #162 | Cancel a product load —only one load in a haul | 200 | 4 |  | 0 | 0
Ticket #133 | Product Haul On Location | 200 | 4 |  | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间