## Daily Records
ID | Name | Prioritize | Est(Hour) | 2018-07-01 | 2018-07-02 | 2018-07-03 | 2018-07-04 | 2018-07-05 | 2018-07-06 | 2018-07-09 | 2018-07-10 | 2018-07-11 | 2018-07-12 | 2018-07-13 | 2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-26 | 2018-07-27 | 2018-07-30 | 2018-07-31 | Total Hours
|  |  |  | 43282 | 43283 | 43284 | 43285 | 43286 | 43287 | 43290 | 43291 | 43292 | 43293 | 43294 | 43297 | 43298 | 43299 | 43300 | 43301 | 43304 | 43305 | 43306 | 43307 | 43308 | 43311 | 43312
| Ideal Burndown |  | 723 | 723 | 689 | 651 | 613 | 575 | 543 | 516 | 491 | 466 | 441 | 416 | 384 | 344 | 304 | 264 | 224 | 192 | 160 | 128 | 96 | 64 | 32 | 0 | 577.5
| Actual |  | 592.5 | 723 | 689.5 | 654.5 | 621 | 591 | 567.5 | 539.5 | 496 | 457 | 423.5 | 388.5 | 350.5 | 312 | 276 | 257 | 267 | 253.5 | 242 | 230.5 | 210.5 | 196.5 | 182 | 164.5
|  |  |  | 0 | 33.5 | 35 | 33.5 | 30 | 23.5 | 28 | 43.5 | 39 | 33.5 | 35 | 38 | 38.5 | 36 | 19 | 9 | 13.5 | 11.5 | 11.5 | 20 | 14 | 14.5 | 17.5 | 577.5 | Assign to | Completion Status | Pay by
Phase10.P001 | Meeting-Phase 9 | 900 | 60 |  | 2 | 2 | 2 | 2 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 38 | All | 0 | Sanjel
Phase10.P002 | Project management | 900 | 15 | 2018-07-03: 1; 2018-07-04: 1; 2018-07-05: 1; 2018-07-06: 1; 2018-07-09: 1; 2018-07-10: 2; 2018-07-11: 1; 2018-07-12: 1; 2018-07-13: 1; 2018-07-16: 1; 2018-07-17: 1 | 12 | Bella.bi | 0 | Sanjel
Phase10.S001 | Analysis requirements | 900 | 45 | 2018-07-02: 4; 2018-07-03: 1; 2018-07-05: 1; 2018-07-11: 0.5; 2018-07-13: 1; 2018-07-16: 1; 2018-07-17: 2; 2018-07-19: 2 | 12.5 | Bella.bi | 0 | Sanjel
Phase10.S002 | Analysis requirements_Serena | 900 | 40 | 2018-07-16: 4; 2018-07-17: 7.5; 2018-07-20: 1; 2018-07-23: 3; 2018-07-24: 4; 2018-07-25: 6 | 25.5 | Serena.Li | 0 | MetaShare
Phase10.P003 | Task documentation | 900 | 10 | 2018-07-02: 0.5; 2018-07-04: 0.5; 2018-07-05: 0.5; 2018-07-09: 0.5; 2018-07-10: 0.5; 2018-07-11: 0.5 | 3 | Bella.bi | 0 | Sanjel
Phase10.T001 | Test for Oracle to sql migration | 830 | 12 | 2018-07-02: 3; 2018-07-03: 1 | 4 | Linsee.Lin | 1 | Sanjel
Phase10.T002 | Update development guideline | 830 | 12 | 2018-07-05: 6 | 6 | Bela.Zhao&Linsee.Lin | 1 | Sanjel
#201 | Test Dao and mofidy dao if necessary | 830 | 16 | 2018-07-02: 9; 2018-07-03: 8 | 17 | Bela.Zhao&Bright.Liu | 1 | Sanjel
#202 | System Testing for all projects | 830 | 32 | 2018-07-03: 7; 2018-07-04: 14.5 | 21.5 | Bela.Zhao&Bright.Liu | 1 | Sanjel
#176 | Set current job _express front-end architecture Implementation | 800 | 24 | 2018-07-02: 3.5; 2018-07-05: 2 | 5.5 | Bright.Liu | 1 | Sanjel
#175 | Database access architecture | 790 | 24 | 2018-07-02: 7.5; 2018-07-03: 7.5; 2018-07-04: 7.5; 2018-07-05: 5 | 27.5 | Olivia.Ge | 1 | Sanjel
#193 | Implement eService Express New Layout | 790 | 20 | 2018-07-02: 4; 2018-07-03: 7.5; 2018-07-04: 8; 2018-07-05: 1.5 | 21 | Linsee.Lin | 1 | Sanjel
#172 | Add "Billing" page to host current pricing update page | 790 | 8 | 2018-07-05: 6.5 | 6.5 | Linsee.Lin | 1 | Sanjel
#183 | Display Job Monitor _Get Job Monitor Setting_backend | 780 | 2 | 2018-07-09: 2 | 2 | Linsee.Lin | 1 | Sanjel
#197 | Display Chart _display privious data | 780 | 8 | [23 empty] | 0 | Linsee.Lin | 1 | Sanjel
#198 | Display Chart _display real-time data | 780 | 8 | 2018-07-11: 7; 2018-07-12: 6; 2018-07-13: 6.5; 2018-07-16: 2 | 21.5 | Bright.Liu | 1 | Sanjel
#195 | Print coordinate point and grid | 750 | 11 | 2018-07-09: 3; 2018-07-17: 8; 2018-07-19: 1 | 12 | Olivia.Ge&Kevin.wu | 1 | Sanjel
#217 | Display chart - Get data from SCM_PLC database_backend | 750 | 5 | 2018-07-05: 4.5 | 4.5 | Bright.Liu | 1 | Sanjel
#218 | Display chart - Get data from SCM_PLC database_Deserialization JSON | 750 | 16 | 2018-07-06: 7; 2018-07-09: 7; 2018-07-10: 7.5 | 21.5 | Bright.Liu | 1 | Sanjel
#219 | Display monitor - Adjust monitor page style | 740 | 8 | 2018-07-06: 7.5 | 7.5 | Linsee.Lin | 1 | Sanjel
#220 | Automatically create a local database | 740 | 16 | 2018-07-06: 4; 2018-07-10: 8; 2018-07-11: 7; 2018-07-12: 4; 2018-07-13: 5; 2018-07-16: 1 | 29 | Bela.Zhao | 1 | Sanjel
#222 | Chart Display Setting in Monitor page | 740 | 16 | 2018-07-09: 5.5; 2018-07-10: 6.5; 2018-07-11: 2; 2018-07-16: 1.5 | 15.5 | Linsee.Lin | 1 | Sanjel
#224 | Print chart_backend | 740 | 12 | 2018-07-09: 7; 2018-07-10: 3.5; 2018-07-12: 10; 2018-07-13: 3 | 23.5 | Olivia.Ge | 1 | Sanjel
#223 | Exchange data to print chart | 740 | 8 | 2018-07-10: 7.5; 2018-07-11: 3 | 10.5 | Kevin.Wu | 1 | Sanjel
#225 | Print title of Chart | 730 | 12 | 2018-07-10: 4; 2018-07-11: 7 | 11 | Olivia.Ge | 1 | Sanjel
#226 | Print Job header information | 730 | 16 | 2018-07-11: 4; 2018-07-12: 3 | 7 | Kevin.Wu | 1 | Sanjel
#227 | Job unit set up | 730 | 8 | 2018-07-11: 3; 2018-07-12: 7.5; 2018-07-13: 3 | 13.5 | Linsee.Lin | 1 | Sanjel
#187 | Print chart architecture | 720 | 12 | 2018-07-13: 8; 2018-07-16: 4 | 12 | Olivia.Ge | 1 | Sanjel
#236 | Print legend | 720 | 20 | 2018-07-16: 4; 2018-07-17: 3; 2018-07-18: 8 | 15 | Olivia.Ge | 1 | Sanjel
#231 | WITS Configuration Setup_update job tag | 720 | 12 | 2018-07-13: 5.5; 2018-07-16: 7 | 12.5 | Linsee.lin | 1 | Sanjel
#232 | WITS Configuration Setup_update WITSSetting table | 720 | 7 | 2018-07-18: 6 | 6 | Linsee.lin | 1 | Sanjel
Phase10.T003 | Transfer rigboard function to new member | 700 | 16 | 2018-07-16: 7.5; 2018-07-17: 3.5; 2018-07-18: 4; 2018-07-19: 7; 2018-07-20: 4; 2018-07-23: 6; 2018-07-24: 1.5; 2018-07-26: 11.5; 2018-07-27: 7; 2018-07-30: 7; 2018-07-31: 17 | 76 | Bright.liu&Kevin.wu&Colin.ji | 0 | MetaShare
Ticket #162 | Cancel a product load —only one load in a haul | 700 | 4 | 2018-07-16: 3 | 3 | Bright.liu | 1 | Sanjel
Ticket #133 | Product Haul On Location | 700 | 4 | 2018-07-17: 4 | 4 | Bright.liu | 1 | Sanjel
Ticket #163 | Schedule a load to an existing haul-Update Unit Section/Third Party | 700 | 6 | 2018-07-17: 7.5 | 7.5 | Colin.Ji | 1 | Sanjel
Ticket #164 | Reschedule a Product Haul-Update unit section/Third party section | 650 | 6 | 2018-07-18: 4 | 4 | Bright.liu | 1 | Sanjel
Ticket #165 | Re-schedule product haul Load - Modify page | 650 | 6 | 2018-07-18: 6; 2018-07-19: 3 | 9 | Kevin.Wu | 1 | Sanjel
Ticket #166 | Re-schedule product haul Load - Use original haul or not | 650 | 10 | 2018-07-18: 6; 2018-07-23: 1.5; 2018-07-24: 3; 2018-07-25: 5; 2018-07-26: 3; 2018-07-30: 4 | 22.5 | Colin.Ji | 0 | Sanjel
Ticket #248 | Update Short Name for a client from Rig Board | 630 | 5 | 2018-07-19: 4; 2018-07-20: 3.5 | 7.5 | Kevin.Wu | 1 | Sanjel
Ticket #251 | Update Dispatched/In-Progress Rig Job Date Time | 630 | 4 | 2018-07-23: 2.5; 2018-07-24: 2.5 | 5 | Kevin.Wu | 0 | Sanjel
Ticket #254 | Fix Amount display in Product Haul functions | 630 | 0.5 | [23 empty] | 0 |  | 0 | Sanjel
Ticket #255 | Fix Product Haul Page Display Issue | 630 | 16 | 2018-07-26: 5; 2018-07-27: 6.5; 2018-07-30: 3 | 14.5 |  | 0 | Sanjel
Note on B6: Bella Bi: 红色背景：与Product Haul相关的； 蓝色背景：与Job Alert相关的； 绿色背景：其他任务 黄色背景：FDAC任务
Note on S8: Bella Bi: 整理新的Rig Board任务
Note on I12: Bella Bi: 更新开发规范 更新底层重构记录及问题
Note on F13: Bella Bi: Bright 1.5h Bela 7.5h
Note on G13: Bella Bi: Bela 4h Bright 4h
Note on G14: Bella Bi: Bright 3.5h Bela 3.5h
Note on H14: Bella Bi: Bright 7.5 Bella 7
Note on I16: Bella Bi: 多进程访问数据库测试
Note on H17: Bella Bi: Linsee 7.5 Bela 0.5 实现前台Layout
Note on I17: Bella Bi: Bela 0.5协助
Note on I18: Bella Bi: Bela 1h协助Linsee
Note on O21: Bella Bi: 处理Duration自动加倍后的存储
Note on N28: Bella Bi: Kevin 2h
Note on L30: Bella Bi: 打印出Title
Note on Q34: Bella Bi: Olivia 3h 修改图例的定义和接口
Note on P35: Bella Bi: Linsee 6h Bela 1h协助
Note on Q37: Bella Bi: Bright 3.5指导Colin和Bright
Note on S37: Bella Bi: Bright协助Kevin实现#165 2.5 Bella协助Kevin写TestCase 1h Kevin学习TestCase 3h
Note on A44: Bella Bi: Bright带着Colin、Kevin一起分析设计
Note on A46: Bella Bi: Adam已经修改，需要测试
Note on A47: Bella Bi: 需要分析Bug,新增Task Ticket

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2018-07-01 | 2018-07-02 | 2018-07-03 | 2018-07-04 | 2018-07-05 | 2018-07-06 | 2018-07-09 | 2018-07-10 | 2018-07-11 | 2018-07-12 | 2018-07-13 | 2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-26 | 2018-07-27 | 2018-07-30 | 2018-07-31
|  |  |  | 43282 | 43283 | 43284 | 43285 | 43286 | 43287 | 43290 | 43291 | 43292 | 43293 | 43294 | 43297 | 43298 | 43299 | 43300 | 43301 | 43304 | 43305 | 43306 | 43307 | 43308 | 43311 | 43312
| Ideal Burndown |  | 723 | 723 | 689 | 651 | 613 | 575 | 543 | 516 | 491 | 466 | 441 | 416 | 384 | 344 | 304 | 264 | 224 | 192 | 160 | 128 | 96 | 64 | 32 | 0
| Actual burndown |  | 593.5 | 328 | 300 | 252 | 220.5 | 194 | 194.5 | 175 | 178.5 | 147 | 151 | 154 | 159 | 129 | 87 | 94.5 | 94.5 | 79.5 | 60 | 59.5 | 54.5 | 29.5 | 12.5 | 0
Phase10.P001 | Meeting-Phase 9 | 900 | 60 | 60 | 58 | 56 | 54 | 52 | 50 | 48 | 46 | 44 | 42 | 40 | 20 | 18 | 16 | 14 | 14 | 13 | 6 | 5 | 4 | 3 | 2 | 0
Phase10.P002 | Project management | 900 | 15 | 15 | 15 | 14 | 13 | 13 | 12 | 11 | 10 | 9 | 8 | 8 | 7 | 6 | 6 | 5 | 5 | 5 | 3 | 2 | 2 | 2 | 0 | 0
Phase10.S001 | Analysis requirements | 900 | 45 | 45 | 43 | 42 | 42 | 40 | 35 | 35 | 34 | 33 | 31 | 29 | 16 | 14 | 12 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase10.S002 | Analysis requirements_Serena | 900 | 40 | 2018-07-16: 40; 2018-07-17: 36; 2018-07-18: 30; 2018-07-19: 28; 2018-07-20: 28; 2018-07-23: 28; 2018-07-24: 20; 2018-07-25: 20; 2018-07-26: 20; 2018-07-27: 2; 2018-07-30: 0; 2018-07-31: 0
Phase10.P003 | Task documentation | 900 | 10 | 10 | 10 | 9 | 8.5 | 8 | 7.5 | 7 | 6.5 | 6 | 6 | 6 | 5 | 5 | 5 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase10.T001 | Test for Oracle to sql migration | 830 | 12 | 12 | 12 | 10 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase10.T002 | Update development guideline | 830 | 12 | 12 | 12 | 12 | 12 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#201 | Test Dao and mofidy dao if necessary | 830 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#202 | System Testing for all projects | 830 | 32 | 32 | 32 | 24 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#176 | Set current job _express front-end architecture Implementation | 800 | 24 | 24 | 24 | 11 | 11 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#175 | Database access architecture | 790 | 24 | 24 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#193 | Implement eService Express New Layout | 790 | 20 | 20 | 4 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#172 | Add "Billing" page to host current pricing update page | 790 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#183 | Display Job Monitor _Get Job Monitor Setting_backend | 780 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#197 | Display Chart _display privious data | 780 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#198 | Display Chart _display real-time data | 780 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 6 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#195 | Print coordinate point and grid | 750 | 11 | 11 | 11 | 11 | 11 | 11 | 8 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#217 | Display chart - Get data from SCM_PLC database_backend | 750 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#218 | Display chart - Get data from SCM_PLC database_Deserialization JSON | 750 | 16 | 16 | 16 | 16 | 16 | 16 | 12 | 8 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#219 | Display monitor - Adjust monitor page style | 740 | 8 |  |  |  |  | 8 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#220 | Automatically create a local database | 740 | 16 |  |  |  |  | 16 | 12 | 12 | 8 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#222 | Chart Display Setting in Monitor page | 740 | 16 | [5 empty] | 16 | 8 | 6 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#224 | Print chart_backend | 740 | 12 | [5 empty] | 12 | 5 | 8 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#223 | Exchange data to print chart | 740 | 8 | [6 empty] | 8 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#225 | Print title of Chart | 730 | 12 | [6 empty] | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#226 | Print Job header information | 730 | 16 | [7 empty] | 16 | 12 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#227 | Job unit set up | 730 | 8 | [7 empty] | 8 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#187 | Print chart architecture | 720 | 12 | [9 empty] | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#236 | Print legend | 720 | 20 | 2018-07-13: 20; 2018-07-16: 16; 2018-07-17: 16; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 0; 2018-07-27: 0; 2018-07-30: 0; 2018-07-31: 0
#231 | WITS Configuration Setup_update job tag | 720 | 12 | [9 empty] | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#232 | WITS Configuration Setup_update WITSSetting table | 720 | 8 | 2018-07-16: 8; 2018-07-17: 2; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 0; 2018-07-27: 0; 2018-07-30: 0; 2018-07-31: 0
Phase10.T003 | Transfer rigboard function to new member | 700 | 16 | 2018-07-13: 16; 2018-07-16: 10; 2018-07-17: 8; 2018-07-18: 8; 2018-07-19: 8; 2018-07-20: 8; 2018-07-23: 8; 2018-07-24: 8; 2018-07-25: 8; 2018-07-26: 8; 2018-07-27: 8; 2018-07-30: 4; 2018-07-31: 0
Ticket #162 | Cancel a product load —only one load in a haul | 700 | 4 | 2018-07-13: 4; 2018-07-16: 0; 2018-07-17: 0; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 0; 2018-07-27: 0; 2018-07-30: 0; 2018-07-31: 0
Ticket #133 | Product Haul On Location | 700 | 4 | 2018-07-16: 4; 2018-07-17: 0; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 0; 2018-07-27: 0; 2018-07-30: 0; 2018-07-31: 0
Ticket #163 | Schedule a load to an existing haul-Update Unit Section/Third Party | 700 | 6 | 2018-07-16: 6; 2018-07-17: 0; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 0; 2018-07-27: 0; 2018-07-30: 0; 2018-07-31: 0
Ticket #164 | Reschedule a Product Haul-Update unit section/Third party section | 650 | 6 | 2018-07-16: 6; 2018-07-17: 6; 2018-07-18: 0; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 0; 2018-07-27: 0; 2018-07-30: 0; 2018-07-31: 0
Ticket #165 | Re-schedule product haul Load - Modify page | 650 | 6 | 2018-07-16: 6; 2018-07-17: 6; 2018-07-18: 3; 2018-07-19: 0; 2018-07-20: 0; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 0; 2018-07-27: 0; 2018-07-30: 0; 2018-07-31: 0
Ticket #166 | Re-schedule product haul Load - Use original haul or not | 650 | 10 | 2018-07-16: 10; 2018-07-17: 10; 2018-07-18: 5; 2018-07-19: 5; 2018-07-20: 5; 2018-07-23: 5; 2018-07-24: 5; 2018-07-25: 8; 2018-07-26: 4; 2018-07-27: 4; 2018-07-30: 4; 2018-07-31: 0
Ticket #248 | Update Short Name for a client from Rig Board | 630 | 5 | 2018-07-19: 2; 2018-07-20: 2; 2018-07-23: 0; 2018-07-24: 0; 2018-07-25: 0; 2018-07-26: 0; 2018-07-27: 0; 2018-07-30: 0; 2018-07-31: 0
Ticket #251 | Update Dispatched/In-Progress Rig Job Date Time | 630 | 4 | 2018-07-19: 4; 2018-07-20: 4; 2018-07-23: 4; 2018-07-24: 1.5; 2018-07-25: 0; 2018-07-26: 0; 2018-07-27: 0; 2018-07-30: 0; 2018-07-31: 0
Ticket #254 | Fix Amount display in Product Haul functions | 630 | 0.5 | 2018-07-19: 0.5; 2018-07-20: 0.5; 2018-07-23: 0.5; 2018-07-24: 0.5; 2018-07-25: 0.5; 2018-07-26: 0.5; 2018-07-27: 0.5; 2018-07-30: 0.5; 2018-07-31: 0
Ticket #255 | Fix Product Haul Page Display Issue | 630 | 16 | 2018-07-19: 16; 2018-07-20: 16; 2018-07-23: 16; 2018-07-24: 16; 2018-07-25: 16; 2018-07-26: 16; 2018-07-27: 10; 2018-07-30: 2; 2018-07-31: 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成第10期FDAS的需求
StartDate | 2018-07-02
EndDate | 2018-07-31
Est Time
Name | Role | Total Hours | 2018-07-02 | 2018-07-03 | 2018-07-04 | 2018-07-05 | 2018-07-06 | 2018-07-09 | 2018-07-10 | 2018-07-11 | 2018-07-12 | 2018-07-13 | 2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-07-26 | 2018-07-27 | 2018-07-30 | 2018-07-31
|  |  | 43283 | 43284 | 43285 | 43286 | 43287 | 43290 | 43291 | 43292 | 43293 | 43294 | 43297 | 43298 | 43299 | 43300 | 43301 | 43304 | 43305 | 43306 | 43307 | 43308 | 43311 | 43312
Ideal Burndown |  | 723 | 689 | 651 | 613 | 575 | 543 | 516 | 491 | 466 | 441 | 416 | 384 | 344 | 304 | 264 | 224 | 192 | 160 | 128 | 96 | 64 | 32 | 0
Hours consumed |  | 723 | 34 | 38 | 38 | 38 | 32 | 27 | 25 | 25 | 25 | 25 | 32 | 40 | 40 | 40 | 40 | 32 | 32 | 32 | 32 | 32 | 32 | 32
Bella.Bi |  | 56 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Linsee.Lin |  | 176 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Olivia.Ge |  | 51 | 8 | 8 | 8 | 8 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Bright.Liu |  | 176 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Stone.Zhao |  | 10 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bela.Zhao |  | 53 | 4 | 8 | 8 | 8 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Kevin.Wu |  | 73 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Serena.Li |  | 64 | 2018-07-16: 4; 2018-07-17: 8; 2018-07-18: 8; 2018-07-19: 8; 2018-07-20: 8; 2018-07-23: 4; 2018-07-24: 4; 2018-07-25: 4; 2018-07-26: 4; 2018-07-27: 4; 2018-07-30: 4; 2018-07-31: 4
Colin.Ji |  | 64 | 2018-07-16: 4; 2018-07-17: 8; 2018-07-18: 8; 2018-07-19: 8; 2018-07-20: 8; 2018-07-23: 4; 2018-07-24: 4; 2018-07-25: 4; 2018-07-26: 4; 2018-07-27: 4; 2018-07-30: 4; 2018-07-31: 4

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase10.P001 | Meeting-Phase 9 | 900 | 60 | 0 | All | 38
Phase10.P002 | Project management | 900 | 15 | 0 | Bella.bi | 12
Phase10.S001 | Analysis requirements | 900 | 45 | 0 | Bella.bi | 12.5
Phase10.S002 | Analysis requirements_Serena | 900 | 40 | 0 | Serena.Li | 25.5
Phase10.P003 | Task documentation | 900 | 10 | 0 | Bella.bi | 3
Phase10.T001 | Test for Oracle to sql migration | 830 | 12 | 1 | Linsee.Lin | 4
Phase10.T002 | Update development guideline | 830 | 12 | 1 | Bela.Zhao&Linsee.Lin | 6
#201 | Test Dao and mofidy dao if necessary | 830 | 16 | 1 | Bela.Zhao&Bright.Liu | 17
#202 | System Testing for all projects | 830 | 32 | 1 | Bela.Zhao&Bright.Liu | 21.5
#176 | Set current job _express front-end architecture Implementation | 800 | 24 | 1 | Bright.Liu | 5.5
#175 | Database access architecture | 790 | 24 | 1 | Olivia.Ge | 27.5
#193 | Implement eService Express New Layout | 790 | 20 | 1 | Linsee.Lin | 21
#172 | Add "Billing" page to host current pricing update page | 790 | 8 | 1 | Linsee.Lin | 6.5
#183 | Display Job Monitor _Get Job Monitor Setting_backend | 780 | 2 | 1 | Linsee.Lin | 2
#197 | Display Chart _display privious data | 780 | 8 | 1 | Linsee.Lin | 0
#198 | Display Chart _display real-time data | 780 | 8 | 1 | Bright.Liu | 21.5
#195 | Print coordinate point and grid | 750 | 11 | 1 | Olivia.Ge&Kevin.wu | 12
#217 | Display chart - Get data from SCM_PLC database_backend | 750 | 5 | 1 | Bright.Liu | 4.5
#218 | Display chart - Get data from SCM_PLC database_Deserialization JSON | 750 | 16 | 1 | Bright.Liu | 21.5
#219 | Display monitor - Adjust monitor page style | 740 | 8 | 1 | Linsee.Lin | 7.5
#220 | Automatically create a local database | 740 | 16 | 1 | Bela.Zhao | 29
#222 | Chart Display Setting in Monitor page | 740 | 16 | 1 | Linsee.Lin | 15.5
#224 | Print chart_backend | 740 | 12 | 1 | Olivia.Ge | 23.5
#223 | Exchange data to print chart | 740 | 8 | 1 | Kevin.Wu | 10.5
#225 | Print title of Chart | 730 | 12 | 1 | Olivia.Ge | 11
#226 | Print Job header information | 730 | 16 | 1 | Kevin.Wu | 7
#227 | Job unit set up | 730 | 8 | 1 | Linsee.Lin | 13.5
#187 | Print chart architecture | 720 | 12 | 1 | Olivia.Ge | 12
#236 | Print legend | 720 | 20 | 1 | Olivia.Ge | 15
#231 | WITS Configuration Setup_update job tag | 720 | 12 | 1 | Linsee.lin | 12.5
#232 | WITS Configuration Setup_update WITSSetting table | 720 | 7 | 1 | Linsee.lin | 6
Phase10.T003 | Transfer rigboard function to new member | 700 | 16 | 0 | Bright.liu&Kevin.wu&Colin.ji | 76
Ticket #162 | Cancel a product load —only one load in a haul | 700 | 4 | 1 | Bright.liu | 3
Ticket #133 | Product Haul On Location | 700 | 4 | 1 | Bright.liu | 4
Ticket #163 | Schedule a load to an existing haul-Update Unit Section/Third Party | 700 | 6 | 1 | Colin.Ji | 7.5
Ticket #164 | Reschedule a Product Haul-Update unit section/Third party section | 650 | 6 | 1 | Bright.liu | 4
Ticket #165 | Re-schedule product haul Load - Modify page | 650 | 6 | 1 | Kevin.Wu | 9
Ticket #166 | Re-schedule product haul Load - Use original haul or not | 650 | 10 | 0 | Colin.Ji | 22.5
Ticket #248 | Update Short Name for a client from Rig Board | 630 | 5 | 1 | Kevin.Wu | 7.5
Ticket #251 | Update Dispatched/In-Progress Rig Job Date Time | 630 | 4 | 0 | Kevin.Wu | 5
Ticket #254 | Fix Amount display in Product Haul functions | 630 | 0.5 | 0 | 0 | 0
Ticket #255 | Fix Product Haul Page Display Issue | 630 | 16 | 0 | 0 | 14.5
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间