## Daily Records
ID | Name | Prioritize | Est(Hour) | 2018-07-31 | 2018-08-01 | 2018-08-02 | 2018-08-03 | 2018-08-06 | 2018-08-07 | 2018-08-08 | 2018-08-09 | 2018-08-10 | 2018-08-13 | 2018-08-14 | 2018-08-15 | 2018-08-16 | 2018-08-17 | 2018-08-20 | 2018-08-21 | 2018-08-22 | 2018-08-23 | 2018-08-24 | 2018-08-27 | 2018-08-28 | 2018-08-29 | 2018-08-30 | 2018-08-31 | Total Hours
|  |  |  | 43312 | 43313 | 43314 | 43315 | 43318 | 43319 | 43320 | 43321 | 43322 | 43325 | 43326 | 43327 | 43328 | 43329 | 43332 | 43333 | 43334 | 43335 | 43336 | 43339 | 43340 | 43341 | 43342 | 43343
| Ideal Burndown |  | 231 | 231 | 221 | 211 | 201 | 191 | 181 | 171 | 161 | 151 | 141 | 131 | 121 | 111 | 101 | 91 | 81 | 71 | 61 | 51 | 41 | 31 | 21 | 11 | 0 | 227.5
| Actual |  | 273 | 231 | 216.5 | 200 | 188 | 175 | 159 | 155 | 150 | 146 | 129.5 | 119.5 | 109.5 | 109.5 | 104.5 | 98.5 | 98.5 | 82.5 | 65.5 | 45 | 32.5 | 25 | 13.5 | 13.5 | 9.5
|  |  |  | 0 | 14.5 | 16.5 | 12 | 13 | 16 | 4 | 5 | 4 | 16.5 | 10 | 10 | 0 | 5 | 6 | 6 | 16 | 17 | 20.5 | 12.5 | 7.5 | 11.5 | 0 | 4 |  | Assign to | Completion Status | Pay by
Phase10.P001 | Planning | 900 | 20 | 2018-08-01: 0.5; 2018-08-02: 0.5; 2018-08-20: 6 | 7 | All | 0 | Sanjel
Phase10.P002 | Scrum Meeting | 900 | 30 | [24 empty] | 0 | All | 0
Phase10.P003 | Retrospective | 900 | 20 | 2018-08-17: 5 | 5 | All | 0
Phase10.P004 | Project management | 900 | 10 | [24 empty] | 2 | Serena.Li | 0 | Sanjel | bar: 2018-08-01; 2018-08-09
Phase10.P005 | Analysis requirements | 900 | 20 | [24 empty] | 0 | Serena.Li | 0 | Sanjel
Phase10.P008 | Transfer rigboard function to new member | 890 | 12 | [24 empty] | 0 | Bright.liu&Kevin.wu&Colin.ji | 1 | MetaShare
Phase10.P009 | CodeReview | 880 | 40 | 2018-08-01: 8; 2018-08-02: 10; 2018-08-03: 12; 2018-08-06: 13; 2018-08-07: 16; 2018-08-08: 4; 2018-08-09: 0; 2018-08-10: 4; 2018-08-13: 1.5 | 68.5 | Bright.liu&Kevin.wu&Colin.ji | 1 | MetaShare
Phase10.P010 | Unit Test | 870 | 40 | [24 empty] | 0 | Bright.liu&Kevin.wu&Colin.ji |  | MetaShare
Phase10.P011 | Thinking training | 860 | 15 | 2018-08-01: 4.5; 2018-08-02: 6; 2018-08-09: 4 | 14.5 | Bright.liu&Kevin.wu&Colin.ji |  | MetaShare
Phase10.P012 | Review Documents |  |  | 2018-08-01: 0.5 | 0.5 | Mike.Zhao |  | MetaShare
Ticket #166 | Re-schedule product haul Load - Use original haul or not | 850 | 2 | [24 empty] | 0 | Colin.Ji |  | Sanjel
Ticket #255 | Fix Product Haul Page Display Issue | 840 | 2 | [24 empty] | 0 | Kevin.Wu | 1 | Sanjel
Ticket #265 | Update Y Axis label printing/display format | 830 | 13 | 2018-08-13: 4; 2018-08-14: 8 | 12 | Kevin.Wu | 1 | Sanjel
Ticket #266 | Printing Chart Header - Label width is not right | 820 | 4 | 2018-08-13: 4 | 4 | Kevin.Wu | 1 | Sanjel
Ticket #275 | Second Y Axis Display | 800 | 6 | 2018-08-13: 6; 2018-08-14: 2 | 8 | Colin.Ji | 1 | Sanjel
Ticket #276 | Update Pricing Page is not working | 790 | 6 | [24 empty] | 1 | Linsee.Lin | 1 | Sanjel | bar: 2018-08-13
Ticket #260 | Print Setting needs to be redefined -- waiting for detail requirement | 810 | 0 | [24 empty] | 0 | Kevin.Wu | 1 | Sanjel
| MessageExecutor send message failed | 770 | 10 | 2018-08-15: 10 | 10 | Olivia.Ge&Bright.liu | 1 | Sanjel
Ticket #281 | 修改Job Monitor页面Job Start Time 和 Job End Time两个空间的日期和时间控件展示样式 | 760 | 7 | 2018-08-23: 1; 2018-08-24: 6; 2018-08-29: 0.5 | 7.5 | Linsee.Lin | 1 | Sanjel
Ticket #282 | 打印路径固定为数据路径下的Output子目录 | 750 | 7 | 2018-08-22: 5; 2018-08-23: 1; 2018-08-24: 3 | 9 | Kevin.Wu | 1 | Sanjel
Ticket #283 | 打印chart 文件名称格式化 | 740 | 6 | 2018-08-23: 2; 2018-08-24: 2; 2018-08-28: 1.5 | 5.5 | Kevin.Wu | 1 | Sanjel
Ticket #284 | 格式化WITS Setting 表数据 | 730 |  | 2018-08-24: 2; 2018-08-27: 6; 2018-08-29: 7 | 15 | Colin.Ji | 1 | Sanjel
Ticket #285 | Job Set Up 页面Units Section 的按钮显示不正确 | 720 | 3 | 2018-08-23: 3 | 3 | Colin.Ji | 1 | Sanjel
Ticket #286 | JobMonitorSetting扩展-一条线是多个数据项计算后的结果 | 710 |  | 2018-08-21: 6; 2018-08-22: 11; 2018-08-23: 10; 2018-08-24: 7.5; 2018-08-27: 6.5; 2018-08-28: 6; 2018-08-29: 4; 2018-08-31: 4 | 55 | Bright.Liu | 1 | Sanjel
Ticket #287 | JobMonitorSetting扩展-一条线是两个Unit的数据项计算后的结果 | 700 | [25 empty] | 0 | Bright.Liu | 1 | Sanjel
|  | 690 | [25 empty] | 0 |  | 1 | Sanjel
|  | 690 | [25 empty] | 0 |  | 1 | Sanjel
|  | 680 | [25 empty] | 0 |  | 1 | Sanjel
|  | 670 | [25 empty] | 0 |  | 1 | Sanjel
|  | 660 | [25 empty] | 0 |  | 1 | Sanjel
|  | 650 | [25 empty] | 0 |  | 1 | Sanjel
|  | 640 | [25 empty] | 0 |  | 1 | Sanjel
|  | 630 | [25 empty] | 0 |  | 1 | Sanjel
|  | 620 | [25 empty] | 0 |  | 1 | Sanjel
|  | 610 | [25 empty] | 0 |  | 0 | MetaShare
|  | 600 | [25 empty] | 0
|  | 590 | [25 empty] | 0
|  | 580 | [25 empty] | 0
|  | 570 | [25 empty] | 0
|  | 560 | [25 empty] | 0
|  | 550 | [25 empty] | 0 |  | 0 | Sanjel
|  | 540 | [25 empty] | 0
|  | 530 | [25 empty] | 0 |  | 0 | Sanjel
|  | 520 | [25 empty] | 0
|  | 510 | [25 empty] | 0 |  | 0 | Sanjel
Note on B6: Bella Bi: 红色背景：与Product Haul相关的； 蓝色背景：与Job Alert相关的； 绿色背景：其他任务 黄色背景：FDAC任务
Note on I12: Bella Bi: 更新开发规范 更新底层重构记录及问题
Note on A17: Bella Bi: 需要分析Bug,新增Task Ticket
Note on P23: Colin Ji: Olivia.Ge:4h Bright.liu:6h
Note on V25: Colin Ji: Olivia.Ge:1h
Note on U29: Colin Ji: Bright.Liu:8h Olivia.Ge:3h
Note on V29: Colin Ji: Bright:Liu:8h Olivia.Ge:2h
Note on A50: Bella Bi: 需要分析Bug,新增Task Ticket

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2018-07-31 | 2018-08-01 | 2018-08-02 | 2018-08-03 | 2018-08-06 | 2018-08-07 | 2018-08-08 | 2018-08-09 | 2018-08-10 | 2018-08-13 | 2018-08-14 | 2018-08-15 | 2018-08-16 | 2018-08-17 | 2018-08-20 | 2018-08-21 | 2018-08-22 | 2018-08-23 | 2018-08-24 | 2018-08-27 | 2018-08-28 | 2018-08-29 | 2018-08-30 | 2018-08-31
|  |  |  | 43312 | 43313 | 43314 | 43315 | 43318 | 43319 | 43320 | 43321 | 43322 | 43325 | 43326 | 43327 | 43328 | 43329 | 43332 | 43333 | 43334 | 43335 | 43336 | 43339 | 43340 | 43341 | 43342 | 43343
| Ideal Burndown |  | 231 | 231 | 221 | 211 | 201 | 191 | 181 | 171 | 161 | 151 | 141 | 131 | 121 | 111 | 101 | 91 | 81 | 71 | 61 | 51 | 41 | 31 | 21 | 11 | 0
| Actual burndown |  | 273 | 252 | 246 | 262 | 256 | 245 | 239 | 243 | 242 | 241 | 226 | 224 | 192 | 181 | 180 | 169 | 169 | 169 | 169 | 158 | 150 | 148 | 148 | 149 | 148
Phase10.P001 | Planning | 900 | 20 | 20 | 20 | 20 | 20 | 15 | 15 | 15 | 15 | 15 | 10 | 15 | 15 | 15 | 15 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Phase10.P002 | Scrum Meeting | 900 | 30 | 9 | 8 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
Phase10.P003 | Retrospective | 900 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Phase10.P004 | Project management | 900 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Phase10.P005 | Analysis requirements | 900 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Phase10.P008 | Transfer rigboard function to new member | 890 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Phase10.P009 | CodeReview | 880 | 40 | 40 | 35 | 30 | 25 | 20 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Phase10.P010 | Unit Test | 870 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Phase10.P011 | Thinking training | 860 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 13 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Phase10.P012 | Review Documents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #166 | Re-schedule product haul Load - Use original haul or not | 850 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Ticket #255 | Fix Product Haul Page Display Issue | 840 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #265 | Update Y Axis label printing/display format | 830 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #266 | Printing Chart Header - Label width is not right | 820 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #275 | Second Y Axis Display | 800 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #276 | Update Pricing Page is not working | 790 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #260 | Print Setting needs to be redefined -- waiting for detail requirement | 810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | MessageExecutor send message failed | 770 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #281 | 修改Job Monitor页面Job Start Time 和 Job End Time两个空间的日期和时间控件展示样式 | 760 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 0 | 0 | 0 | 0 | 0
Ticket #282 | 打印路径固定为数据路径下的Output子目录 | 710 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 2 | 2 | 2 | 2 | 2 | 2
Ticket #283 | 打印chart 文件名称格式化 | 700 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0
Ticket #284 | 格式化WITS Setting 表数据 | 690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #285 | Job Set Up 页面Units Section 的按钮显示不正确 | 690 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #286 | JobMonitorSetting扩展-一条线是多个数据项计算后的结果 | 680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #287 | JobMonitorSetting扩展-一条线是两个Unit的数据项计算后的结果 | 670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成第11期FDAS的反馈需求
StartDate | 2018-08-01
EndDate | 2018-08-31
Est Time
Name | Role | Total Hours | 2018-08-01 | 2018-08-02 | 2018-08-03 | 2018-08-06 | 2018-08-07 | 2018-08-08 | 2018-08-09 | 2018-08-10 | 2018-08-13 | 2018-08-14 | 2018-08-15 | 2018-08-16 | 2018-08-17 | 2018-08-20 | 2018-08-21 | 2018-08-22 | 2018-08-23 | 2018-08-24 | 2018-08-27 | 2018-08-28 | 2018-08-29 | 2018-08-30 | 2018-08-31
|  |  | 43313 | 43314 | 43315 | 43318 | 43319 | 43320 | 43321 | 43322 | 43325 | 43326 | 43327 | 43328 | 43329 | 43332 | 43333 | 43334 | 43335 | 43336 | 43339 | 43340 | 43341 | 43342 | 43343
Ideal Burndown |  | 231 | 221 | 211 | 201 | 191 | 181 | 171 | 161 | 151 | 141 | 131 | 121 | 111 | 101 | 91 | 81 | 71 | 61 | 51 | 41 | 31 | 21 | 11 | 0
Hours consumed |  | 231 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11
Olivia.Ge |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bright.Liu |  | 23 | bar: 2018-08-01 to 2018-08-31
Linsee.Lin |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mike.Zhao |  | 11.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Kevin.Wu |  | 92 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Serena.Li |  | 11.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Colin.Ji |  | 93 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase10.P001 | Planning | 900 | 20 | 0 | All | 7
Phase10.P004 | Project management | 900 | 10 | 0 | Serena.Li | 2
Phase10.P005 | Analysis requirements | 900 | 20 | 0 | Serena.Li | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Phase10.P008 | Transfer rigboard function to new member | 890 | 12 | 1 | Bright.liu&Kevin.wu&Colin.ji | 0
Phase10.P009 | CodeReview | 880 | 40 | 1 | Bright.liu&Kevin.wu&Colin.ji | 68.5
Ticket #255 | Fix Product Haul Page Display Issue | 840 | 2 | 1 | Kevin.Wu | 0
Ticket #265 | Update Y Axis label printing/display format | 830 | 13 | 1 | Kevin.Wu | 12
Ticket #266 | Printing Chart Header - Label width is not right | 820 | 4 | 1 | Kevin.Wu | 4
Ticket #260 | Print Setting needs to be redefined -- waiting for detail requirement | 810 | 0 | 1 | Kevin.Wu | 0
Ticket #275 | Second Y Axis Display | 800 | 6 | 1 | Colin.Ji | 8
Ticket #276 | Update Pricing Page is not working | 790 | 6 | 1 | Linsee.Lin | 1
0 | MessageExecutor send message failed | 770 | 10 | 1 | Olivia.Ge&Bright.liu | 10
Ticket #281 | 修改Job Monitor页面Job Start Time 和 Job End Time两个空间的日期和时间控件展示样式 | 760 | 7 | 1 | Linsee.Lin | 7.5
Ticket #282 | 打印路径固定为数据路径下的Output子目录 | 750 | 7 | 1 | Kevin.Wu | 9
Ticket #283 | 打印chart 文件名称格式化 | 740 | 6 | 1 | Kevin.Wu | 5.5
Ticket #284 | 格式化WITS Setting 表数据 | 730 | 0 | 1 | Colin.Ji | 15
Ticket #285 | Job Set Up 页面Units Section 的按钮显示不正确 | 720 | 3 | 1 | Colin.Ji | 3
Ticket #286 | JobMonitorSetting扩展-一条线是多个数据项计算后的结果 | 710 | 0 | 1 | Bright.Liu | 55
Ticket #287 | JobMonitorSetting扩展-一条线是两个Unit的数据项计算后的结果 | 700 | 0 | 1 | Bright.Liu | 0
0 | 0 | 690 | 0 | 1 | 0 | 0
0 | 0 | 690 | 0 | 1 | 0 | 0
0 | 0 | 680 | 0 | 1 | 0 | 0
0 | 0 | 670 | 0 | 1 | 0 | 0
0 | 0 | 660 | 0 | 1 | 0 | 0
0 | 0 | 650 | 0 | 1 | 0 | 0
0 | 0 | 640 | 0 | 1 | 0 | 0
0 | 0 | 630 | 0 | 1 | 0 | 0
0 | 0 | 620 | 0 | 1 | 0 | 0
0 | 0 | 610 | 0 | 0 | 0 | 0
0 | 0 | 600 | 0 | 0 | 0 | 0
0 | 0 | 590 | 0 | 0 | 0 | 0
0 | 0 | 580 | 0 | 0 | 0 | 0
0 | 0 | 570 | 0 | 0 | 0 | 0
0 | 0 | 560 | 0 | 0 | 0 | 0
0 | 0 | 550 | 0 | 0 | 0 | 0
0 | 0 | 540 | 0 | 0 | 0 | 0
0 | 0 | 530 | 0 | 0 | 0 | 0
0 | 0 | 520 | 0 | 0 | 0 | 0
0 | 0 | 510 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间