## Daily Records
ID | Name | Prioritize | Est(Hour) | 2018-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30 | Total Hours
|  |  |  | 43404 | 43405 | 43406 | 43409 | 43410 | 43411 | 43412 | 43413 | 43416 | 43417 | 43418 | 43419 | 43420 | 43423 | 43424 | 43425 | 43426 | 43427 | 43430 | 43431 | 43432 | 43433 | 43434
| Ideal Burndown |  | 288 | 288 | 272 | 256 | 240 | 224 | 208 | 192 | 176 | 160 | 144 | 128 | 112 | 96 | 80 | 64 | 48 | 32 | 32 | 16 | 0 | -16 | -32 | -48 | 263
| Actual |  | 87 | 288 | 276 | 272 | 264 | 253 | 237 | 234 | 226 | 214 | 201 | 185 | 169 | 161 | 149 | 137 | 123 | 107 | 101 | 83 | 71 | 57 | 41 | 25
|  |  |  | 0 | 12 | 4 | 8 | 11 | 16 | 3 | 8 | 12 | 13 | 16 | 16 | 8 | 12 | 12 | 14 | 16 | 6 | 18 | 12 | 14 | 16 | 16 |  | Assign to | Completion Status | Pay by | Module
Phase11.P001 | Planning | 900 | 15 | [23 empty] | 0 | All | 0 | Sanjel | Express
Phase11.P002 | Retrospective | 890 | 0 | [23 empty] | 0 | All | 1 | Sanjel | Express
Phase11.R001 | Analysis requirements | 870 | 8 | [23 empty] | 0 | Serena.Li | 1 | Sanjel | Express
Phase11.T001 | Unit Test | 860 | 0 | [23 empty] | 0 | Colin.Ji | 1 | MetaShare | Express
| MDM系统生成功能完善 |  | 8 | [23 empty] | 0 | Kevin.Wu | 1 | Sanjel | MDM
| MDM 测试数据整理排查所有测试数据并找出对应数控表确定数据正确性 |  | 8 | 2018-11-01: 4; 2018-11-02: 4 | 8 | Kevin.Wu | 1 | Sanjel | MDM
| MDM 测试数据同步 |  | 0 | [23 empty] | 0 | Kevin.Wu | 1 | Sanjel | MDM
| MDM生成系统添加扩展层用于修改扩展 |  | 24 | 2018-11-13: 5; 2018-11-14: 8; 2018-11-15: 8 | 21 | Kevin.Wu | 0 | Sanjel | MDM
| 根据MeasureUnit实体结构确认MDD如何支持 | [25 empty] | 0 | Kevin.Wu | 1 | Sanjel | MDM
| CompletedJobs功能 |  | 12 | 2018-11-01: 8; 2018-11-05: 8; 2018-11-06: 8 | 24 | Colin.Ji | 1 | Sanjel | Online
| 在过滤条件区，加Service Point过滤器 |  | 12 | [23 empty] | 0 | Colin.Ji | 1 | Sanjel | Online
| online架构熟悉了解 |  |  | 2018-11-06: 3; 2018-11-19: 4; 2018-11-22: 6 | 13 | Kevin.Wu | 1 | Sanjel | Online
| PDF自动打开的功能 |  |  | 2018-11-08: 1; 2018-11-09: 8 | 9 | Colin.Ji | 1 | Sanjel | Express
| EService Express 中的打印有bug修改-图例显示位置不正确 |  |  | 2018-11-07: 4 | 4 | Kevin.Wu | 1 | Sanjel | Express
| EService Express 中的打印有bug修改-X轴刻度打印不正确 | [25 empty] | 1 | Kevin.Wu | 1 | Sanjel | Express | bar: 2018-11-07
| EService Express 中的打印有bug修改-打印时副Y轴显示为主轴 |  |  | 2018-11-07: 3 | 3 | Kevin.Wu | 1 | Sanjel | Express
| 在EService Express中Monitor页面中，Chart Selection的右侧，有一个”-“(减号) |  |  | 2018-11-08: 2 | 2 | Colin.Ji | 1 | Sanjel | Express
| Eservice Online架构图 |  |  | 2018-11-07: 6 | 6 | Colin.Ji | 1 | Sanjel | Online
| 研习Calendar Control |  |  | 2018-11-07: 2; 2018-11-12: 12; 2018-11-13: 8; 2018-11-14: 8; 2018-11-15: 8; 2018-11-16: 8; 2018-11-19: 8 | 54 | Colin.Ji | 1 | Sanjel | Online
| MDM界面集成和统一 |  |  | 2018-11-20: 4; 2018-11-22: 2 | 6 | Kevin.Wu | 1 | Sanjel | MDM
| MDM与Online集成 |  |  | 2018-11-21: 6 | 6 | Colin.Ji | 1 | Sanjel | Online
Ticket374 | Duration和Interval自动增加后需要回填到上面的设置框中 |  |  | 2018-11-20: 2 | 2 | Colin.Ji | 1 | Sanjel | Express
| 根据MDM最新版本替换SanjelClientSolutionTool, eServiceOnline、Commonlibrary的相关引用 |  |  | 2018-11-21: 8; 2018-11-22: 8; 2018-11-23: 3; 2018-11-28: 4; 2018-11-29: 4; 2018-11-30: 4 | 31 | Colin.Ji | 1 | Sanjel | MDM
| 用Microsoft Office Form 创建一个调查表,嵌入到eServiceExpress |  |  | 2018-11-23: 3 | 3 | Kevin.Wu | 1 | Sanjel | Express
Ticket376 | 打印job信息部分，由于内容过长打印不下的时候，产生换行导致移位错误 |  |  | 2018-11-26: 7; 2018-11-27: 8; 2018-11-28: 6; 2018-11-29: 8; 2018-11-30: 5 | 34 | Kevin.Wu | 1 | Sanjel | Express
Ticket379 | 在Local Jobs 界面，“Set Current Job" 按钮后面加一个按钮，"Pressure Test"。 |  |  | 2018-11-26: 3 | 3 | Colin.Ji | 1 | Sanjel | Express
Ticket380 | 点击”Pressure Test" 按钮，系统自动产生一个job tag |  |  | 2018-11-26: 4 | 4 | Colin.Ji | 1 | Sanjel | Express
Ticket382 | Pressure Test 可以被选中为Current Job。选中时，实时读取SCM_PLC数据中最后5秒钟的数据，提取其中的Unit Number，实例化Job Monitor Setting和WITS Setting |  |  | 2018-11-26: 3 | 3 | Colin.Ji | 1 | Sanjel | Express
Ticket384 | Monitor可以根据Pressure Test Job tag中的设置进行实时绘图 |  |  | 2018-11-27: 2 | 2 | Colin.Ji | 1 | Sanjel | Express
Ticket386 | Pressure Test Job，可以对其数据进行打印。表头数据项的数据值待打印出来的 |  |  | 2018-11-27: 2 | 2 | Colin.Ji | 1 | Sanjel | Express
| TestData数据整理 |  |  | 2018-11-28: 4; 2018-11-29: 4 | 8 | Colin.Ji | 2 | Sanjel | Express
| 编译说明文档 |  |  | 2018-11-30: 4 | 4 | Colin.Ji | 3 | Sanjel | MDM
| 打印控件文档整理、UML图更新 |  |  | 2018-11-30: 3 | 3 | Olivia.Ge | 3 | Sanjel | Express
| Review code | [25 empty] | 1 | Olivia.Ge | 1 | Sanjel | Express | bar: 2018-11-26
| online scheduler 控件添加Context Menu |  |  | 2018-11-20: 6 | 6 | Colin.Ji | 1 | Sanjel | Online
Note on A14: Bella Bi: 需要分析Bug,新增Task Ticket
Note on A24: Bella Bi: 需要分析Bug,新增Task Ticket
Note on M24: Serena Li: colin 8 kevin 4
Note on B26: Bella Bi: 后来没有继续做，任务中断
Note on Y30: Serena Li: kevin 3h olivia 3h
Note on Z30: Serena Li: olivia 8h
Note on W31: Serena Li: olivia.ge：1h colin.ji:6h

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2018-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-30
|  |  |  | 43404 | 43405 | 43406 | 43409 | 43410 | 43411 | 43412 | 43413 | 43416 | 43417 | 43418 | 43419 | 43420 | 43423 | 43424 | 43425 | 43426 | 43427 | 43434
| Ideal Burndown |  | 288 | 288 | 272 | 256 | 240 | 224 | 208 | 192 | 176 | 160 | 144 | 128 | 112 | 96 | 80 | 64 | 48 | 32 | 16 | #REF!
| Actual burndown |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Phase11.P001 | Planning | 900 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Phase11.P002 | Retrospective | 890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase11.R001 | Analysis requirements | 870 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Phase11.T001 | Unit Test | 860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | MDM系统生成功能完善 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
0 | MDM 测试数据整理排查所有测试数据并找出对应数控表确定数据正确性 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
0 | MDM 测试数据同步 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | MDM生成系统添加扩展层用于修改扩展 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
0 | 根据MeasureUnit实体结构确认MDD如何支持 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | CompletedJobs功能 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
0 | 在过滤条件区，加Service Point过滤器 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
0 | online架构熟悉了解 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 研习Calendar Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 研习Calendar Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT | 25 | 迭代目标 | 本次迭代主要完成第11期FDAS的反馈需求
StartDate | 2018-11-01
EndDate | 2018-11-30
Est Time
Name | Role | Total Hours | 2018-11-01 | 2018-11-02 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30
|  |  | 43405 | 43406 | 43409 | 43410 | 43411 | 43412 | 43413 | 43416 | 43417 | 43418 | 43419 | 43420 | 43423 | 43424 | 43425 | 43426 | 43427 | 43430 | 43431 | 43432 | 43433 | 43434
Ideal Burndown |  | 288 | 272 | 256 | 240 | 224 | 208 | 192 | 176 | 160 | 144 | 128 | 112 | 96 | 80 | 64 | 48 | 32 | 32 | 16 | 0 | -16 | -32 | -48
Hours consumed |  | 288 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
Olivia.Ge |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bright.Liu |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Linsee.Lin |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kevin.Wu |  | 126 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
Serena.Li |  | 18 | bar: 2018-11-01 to 2018-11-30
Colin.Ji |  | 144 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase11.P001 | Planning | 900 | 15 | 0 | All | 0
Phase11.P002 | Retrospective | 890 | 0 | 1 | All | 0
Phase11.R001 | Analysis requirements | 870 | 8 | 1 | Serena.Li | 0
Phase11.T001 | Unit Test | 860 | 0 | 1 | Colin.Ji | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | MDM系统生成功能完善 | 0 | 8 | 1 | Kevin.Wu | 0
0 | MDM 测试数据整理排查所有测试数据并找出对应数控表确定数据正确性 | 0 | 8 | 1 | Kevin.Wu | 8
0 | MDM 测试数据同步 | 0 | 0 | 1 | Kevin.Wu | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | 研习Calendar Control | 0 | 0 | 1 | Colin.Ji | 54
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间