## Daily Records
ID | Name | Prioritize | Est(Hour) | 2018-12-02 | 2018-12-03 | 2018-12-04 | 2018-12-05 | 2018-12-06 | 2018-12-07 | 2018-12-10 | 2018-12-11 | 2018-12-12 | 2018-12-13 | 2018-12-14 | 2018-12-16 | 2018-12-17 | 2018-12-18 | 2018-12-19 | 2018-12-20 | 2018-12-21 | 2018-12-24 | 2018-12-25 | 2018-12-26 | 2018-12-27 | 2018-12-28 | 2018-12-29 | Total Hours
|  |  |  | 43436 | 43437 | 43438 | 43439 | 43440 | 43441 | 43444 | 43445 | 43446 | 43447 | 43448 | 43450 | 43451 | 43452 | 43453 | 43454 | 43455 | 43458 | 43459 | 43460 | 43461 | 43462 | 43463
| Ideal Burndown |  | 436 | 436 | 416 | 396 | 376 | 356 | 336 | 316 | 296 | 276 | 256 | 236 | 220 | 200 | 180 | 160 | 140 | 120 | 100 | 80 | 60 | 40 | 20 | 0 | 300
| Actual |  | 429 | 436 | 414.5 | 385.5 | 347.5 | 324.5 | 308.5 | 299 | 277.5 | 264.5 | 259.5 | 257.5 | 241.5 | 245.5 | 242.5 | 239.5 | 236.5 | 235.5 | 233.5 | 220.5 | 198.5 | 176.5 | 160 | 155
|  |  |  | 0 | 21.5 | 29 | 38 | 23 | 16 | 9.5 | 21.5 | 13 | 5 | 2 | 16 | 12 | 3 | 3 | 3 | 4 | 2 | 13 | 22 | 22 | 16.5 | 5 | 300 | Assign to | Completion Status | Pay by | Module
Phase12.P001 | Meeting-Phase 12 | 1000 | 60 | 2018-12-03: 5; 2018-12-04: 5; 2018-12-05: 2.5; 2018-12-06: 2; 2018-12-07: 2; 2018-12-10: 2; 2018-12-11: 7.5; 2018-12-12: 2; 2018-12-25: 8; 2018-12-26: 2; 2018-12-27: 3; 2018-12-28: 2; 2018-12-29: 1 | 44 | All | 0 | Sanjel | Express
Phase12.P002 | Project management | 1000 | 15 | 2018-12-03: 3; 2018-12-04: 3; 2018-12-05: 3; 2018-12-06: 3; 2018-12-07: 1; 2018-12-10: 1; 2018-12-11: 1; 2018-12-26: 2; 2018-12-27: 2 | 19 | Bella.bi | 0 | Sanjel | Express
Phase12.S001 | Analysis requirements | 1000 | 40 | 2018-12-04: 3; 2018-12-07: 1; 2018-12-11: 1; 2018-12-17: 4; 2018-12-18: 3; 2018-12-19: 3; 2018-12-20: 3; 2018-12-21: 2; 2018-12-25: 2; 2018-12-26: 1 | 23 | Bella.bi | 0 | Sanjel | Online
Phase12.P003 | Task documentation | 1000 | 10 | 2018-12-05: 0.5; 2018-12-21: 2; 2018-12-24: 2 | 4.5 | Bella.bi | 0 | Sanjel | Online
Phase12.P004 | Document summary | 1000 | 24 | 2018-12-03: 13.5 | 13.5 | All | 1 | Sanjel | Express
Phase12.D001 | Architecture extension | 950 | 16 | 2018-12-05: 6.5 | 6.5 | Olivia.Ge | 1 | Sanjel | Express
Phase12.P005 | Discussion forum | 950 | 16 | 2018-12-13: 5 | 5 | All | 0 | MetaShare | Express
Phase12.I003 | Entry CIM model in MDD | 950 | 8 | 2018-12-26: 2; 2018-12-27: 2; 2018-12-29: 1 | 5 | Bella.Bi | 0 | Sanjel | Online
Phase12.I004 | UI Design for CrewBoard and Calendar | 950 | 4 | 2018-12-25: 2 | 2 | Niki.Wang | 0 | Sanjel | Online
Ticket #402 | Refactor packing function in Express_Modify database and check for updates | 950 | 6 | 2018-12-04: 2; 2018-12-05: 2 | 4 | Colin.Ji | 1 | Sanjel | Express
Ticket #403 | Refactor packing function in Express_Modify the packaging mode | 950 | 10 | 2018-12-04: 3; 2018-12-05: 4; 2018-12-06: 2 | 9 | Colin.Ji | 1 | Sanjel | Express
Ticket #404 | Refactor packing function in Express_Limit the size of the package file | 950 | 10 | 2018-12-04: 4; 2018-12-05: 3; 2018-12-06: 3 | 10 | Colin.Ji | 1 | Sanjel | Express
Ticket #405 | Update invoke method for packing in eService | 950 | 8 | 2018-12-04: 5; 2018-12-05: 3 | 8 | Bright.Liu | 1 | Sanjel | eService
Ticket #406 | Add exception handling for invoke packing method | 950 | 16 | 2018-12-04: 4; 2018-12-05: 5.5; 2018-12-06: 7 | 16.5 | Kevin.Wu | 1 | Sanjel | eService
Phase12.E001 | Fix problem which caused by Nuget package upgrade | 940 | 4 | 2018-12-05: 4 | 4 | Bright.Liu | 1 | Sanjel | eService
Ticket #410 | Fix bug about file name for UploadDocumentSection when two job use same Job Number | 940 | 16 | 2018-12-07: 5 | 5 | Colin.Ji | 1 | Sanjel | eService
Ticket #409 | Integration Testing for packing between eService and express | 940 | 16 | 2018-12-05: 4; 2018-12-06: 6 | 10 | Colin.Ji | 1 | Sanjel | Express
Ticket #412 | Handling exceptions to access the web API | 930 | 16 | 2018-12-10: 4; 2018-12-11: 6 | 10 | Colin.Ji | 1 | Sanjel | eService
Ticket #416 | Fix Costing Errors about integration of MDM and Program Tool | 930 | 8 | 2018-12-12: 8.5 | 8.5 | Colin.Ji | 1 | Sanjel | Program
Ticket #418 | Fix bug about the Job Set Up page cannot save state after unchecked in Pressure Test page | 930 | 3 | 2018-12-12: 2.5 | 2.5 | Colin.Ji | 0 | Sanjel | Express
Phase12.I001 | New team member familiar with business processes | 930 | 16 | 2018-12-07: 7; 2018-12-10: 2.5; 2018-12-11: 6 | 15.5 | Bright.Liu | 0 | MetaShare | Express
Ticket #425 | Conversion from Oracle to Sql server | 920 | 40 | 2018-12-16: 8; 2018-12-17: 8 | 16 | Stone.Zhao | 0 | Sanjel | Database
Phase12.I002 | Assist in the completion of ticket #425 | 920 | 8 | 2018-12-14: 2; 2018-12-16: 8 | 10 | Bright.Liu | 0 | MetaShare | Database
Ticket #448 | View crew list in crew board | 900 | 8 | 2018-12-25: 1; 2018-12-26: 7.5; 2018-12-29: 3 | 11.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #450 | View calendar | 900 | 6 | 2018-12-26: 4.5; 2018-12-27: 6; 2018-12-28: 4 | 14.5 | Colin.Ji | 0 | Sanjel | Online
Ticket #440 | View Crew Schedule | 900 | 8 | 2018-12-26: 1; 2018-12-27: 0.5; 2018-12-28: 1 | 2.5 | Colin.Ji | 0 | Sanjel | Online
Ticket #441 | View worker schedule | 900 | 4 | 2018-12-26: 1; 2018-12-27: 0.5; 2018-12-28: 1 | 2.5 | Colin.Ji | 0 | Sanjel | Online
Ticket #442 | View unit schedule | 900 | 4 | 2018-12-26: 1; 2018-12-27: 0.5; 2018-12-28: 1 | 2.5 | Colin.Ji | 0 | Sanjel | Online
Ticket #443 | Search by name in Calendar | 900 | 6 | [23 empty] | 0 | Colin.Ji | 0 | Sanjel | Online
Ticket #451 | Add a crew | 850 | 5 | 2018-12-27: 3; 2018-12-28: 1.5 | 4.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #454 | Assign a crew to a job | 850 | 3 | 2018-12-28: 0.5 | 0.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #457 | Call crew for a job | 850 | 3 | 2018-12-28: 0.5 | 0.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #460 | Remove crew for a job | 850 | 2 | [23 empty] | 1 | Bright.Liu | 1 | Sanjel | Online | bar: 2018-12-02 to 2018-12-29
Ticket #463 | Add unit to a crew | 800 | 3 | 2018-12-27: 1.5; 2018-12-28: 1 | 2.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #465 | Add worker to a crew | 800 | 3 | [23 empty] | 2 | Bright.Liu | 1 | Sanjel | Online | bar: 2018-12-02 to 2018-12-29
Ticket #468 | Remove a unit from a crew | 800 | 2 | [23 empty] | 2 | Bright.Liu | 1 | Sanjel | Online | bar: 2018-12-02 to 2018-12-29
Ticket #469 | Remove a worker from a crew | 800 | 2 | [23 empty] | 2 | Bright.Liu | 1 | Sanjel | Online | bar: 2018-12-02 to 2018-12-29
[27 empty] | 0 |  | 0
[27 empty] | 0 |  | 0
[27 empty] | 0 |  | 0
[27 empty] | 0 |  | 0
[27 empty] | 0 |  | 0
Note on F6: Bella Bi: 对前一期工作的总结及开发过程及规范的统一
Note on G6: Bella Bi: 讨论邮件中的任务，并跟Adam沟通需求及实现
Note on L6: Bella Bi: 早会 跟Adam讨论问题
Note on W6: Bella Bi: 开会讲解需求，以及大致估算
Note on F7: Bella Bi: 整理文档目录结构
Note on Q8: Bella Bi: 分析Phase12新需求
Note on F10: Bella Bi: Colin 5h Kevin 4h 整理问题汇总及上一期工作总结 Bright 1.5 整理MDM API文档 Olivia 3h 整理打印部分的文档
Note on C12: Bella Bi: 讨论会，主要讨论如何提高我们的开发质量问题，以及开发过程
Note on N12: Bella Bi: 讨论会-如何提高我们的开发质量。
Note on J21: Bella Bi: Colin 5h
Note on K23: Bella Bi: Colin 4h
Note on L23: Bella Bi: Colin 6h 实现逻辑修改：先判断Version
Note on J26: Bella Bi: Bright协助Colin完成 #410
Note on K26: Bella Bi: Bright协助Colin完成 #412
Note on L26: Bella Bi: Bright协助Colin完成 #412
Note on A29: Bella Bi: 以下预估时间为实现原型的时间。
Note on AA29: Bella Bi: 在Branch上改为引用EJ2的库

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2018-12-02 | 2018-12-03 | 2018-12-04 | 2018-12-05 | 2018-12-06 | 2018-12-07 | 2018-12-10 | 2018-12-11 | 2018-12-12 | 2018-12-13 | 2018-12-14 | 2018-12-17 | 2018-12-18 | 2018-12-19 | 2018-12-20 | 2018-12-21 | 2018-12-24 | 2018-12-25 | 2018-12-26 | 2018-12-27 | 2018-12-28 | 2018-12-29
|  |  |  | 43436 | 43437 | 43438 | 43439 | 43440 | 43441 | 43444 | 43445 | 43446 | 43447 | 43448 | 43451 | 43452 | 43453 | 43454 | 43455 | 43458 | 43459 | 43460 | 43461 | 43462 | 43463
| Ideal Burndown |  | 436 | 436 | 416 | 396 | 376 | 356 | 336 | 316 | 296 | 276 | 256 | 236 | 200 | 180 | 160 | 140 | 120 | 100 | 80 | 60 | 40 | 20 | 0
| Actual burndown |  | 353 | 302 | 282 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Phase12.P001 | Meeting-Phase 12 | 1000 | 60 | 60 | 60 | 56 | 54 | 52 | 50 | 48 | 46 | 44 | 42 | 40 | 20 | 18 | 16 | 14 | 14 | 13 | 6 | 5 | 4 | 3 | 2
Phase12.P002 | Project management | 1000 | 15 | 15 | 15 | 14 | 13 | 13 | 12 | 11 | 10 | 9 | 8 | 8 | 7 | 6 | 6 | 5 | 5 | 5 | 3 | 2 | 2 | 2 | 0
Phase12.S001 | Analysis requirements | 1000 | 40 | 40 | 40 | 42 | 42 | 40 | 35 | 35 | 34 | 33 | 31 | 29 | 16 | 14 | 12 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0
Phase12.P003 | Task documentation | 1000 | 10 | 10 | 10 | 9 | 8.5 | 8 | 7.5 | 7 | 6.5 | 6 | 6 | 6 | 5 | 5 | 5 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Phase12.P004 | Document summary | 1000 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #404 | Refactor packing function in Express_Limit the size of the package file | 950 | 10 | 10 | 10 | 24 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #406 | Add exception handling for invoke packing method | 950 | 16 | 16 | 16 | 11 | 11 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase12.E001 | Fix problem which caused by Nuget package upgrade | 940 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #410 | Fix bug about file name for UploadDocumentSection when two job use same Job Number | 940 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #409 | Integration Testing for packing between eService and express | 940 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #412 | Handling exceptions to access the web API | 930 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #418 | Fix bug about the Job Set Up page cannot save state after unchecked in Pressure Test page | 930 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase12.I001 | New team member familiar with business processes | 930 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #425 | Conversion from Oracle to Sql server | 920 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase12.I002 | Assist in the completion of ticket #425 | 920 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #448 | View crew list in crew board | 900 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #440 | View Crew Schedule | 900 | 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #441 | View worker schedule | 900 | 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #442 | View unit schedule | 900 | 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #443 | Search by name in Calendar | 900 | 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #451 | Add a crew | 850 | 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #454 | Assign a crew to a job | 850 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #457 | Call crew for a job | 850 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #460 | Remove crew for a job | 850 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #463 | Add unit to a crew | 800 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #465 | Add worker to a crew | 800 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #468 | Remove a unit from a crew | 800 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #469 | Remove a worker from a crew | 800 | 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成第12期工作——Rig Board第三期
StartDate | 2018-12-03
EndDate | 2019-01-01
Est Time
Name | Role | Total Hours | 2018-12-03 | 2018-12-04 | 2018-12-05 | 2018-12-06 | 2018-12-07 | 2018-12-10 | 2018-12-11 | 2018-12-12 | 2018-12-13 | 2018-12-14 | 2018-12-16 | 2018-12-17 | 2018-12-18 | 2018-12-19 | 2018-12-20 | 2018-12-21 | 2018-12-24 | 2018-12-25 | 2018-12-26 | 2018-12-27 | 2018-12-28 | 2018-12-29
|  |  | 43437 | 43438 | 43439 | 43440 | 43441 | 43444 | 43445 | 43446 | 43447 | 43448 | 43450 | 43451 | 43452 | 43453 | 43454 | 43455 | 43458 | 43459 | 43460 | 43461 | 43462 | 43463
Ideal Burndown |  | 436 | 416 | 396 | 376 | 356 | 336 | 316 | 296 | 276 | 256 | 236 | 220 | 200 | 180 | 160 | 140 | 120 | 100 | 80 | 60 | 40 | 20 | 0
Hours consumed |  | 436 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 16 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Bella.Bi |  | 84 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Olivia.Ge |  | 84 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Bright.Liu |  | 92 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Colin.Ji |  | 84 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Kevin.Wu |  | 84 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Stone.Zhao |  | 8 | 2018-12-16: 8
Niki.Wang

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase12.P001 | Meeting-Phase 12 | 1000 | 60 | 0 | All | 44
Phase12.P002 | Project management | 1000 | 15 | 0 | Bella.bi | 19
Phase12.S001 | Analysis requirements | 1000 | 40 | 0 | Bella.bi | 23
Phase12.P003 | Task documentation | 1000 | 10 | 0 | Bella.bi | 4.5
Phase12.P004 | Document summary | 1000 | 24 | 1 | All | 13.5
Ticket #404 | Refactor packing function in Express_Limit the size of the package file | 950 | 10 | 1 | Colin.Ji | 10
Ticket #406 | Add exception handling for invoke packing method | 950 | 16 | 1 | Kevin.Wu | 16.5
Phase12.E001 | Fix problem which caused by Nuget package upgrade | 940 | 4 | 1 | Bright.Liu | 4
Ticket #410 | Fix bug about file name for UploadDocumentSection when two job use same Job Number | 940 | 16 | 1 | Colin.Ji | 5
Ticket #409 | Integration Testing for packing between eService and express | 940 | 16 | 1 | Colin.Ji | 10
Ticket #412 | Handling exceptions to access the web API | 930 | 16 | 1 | Colin.Ji | 10
Ticket #418 | Fix bug about the Job Set Up page cannot save state after unchecked in Pressure Test page | 930 | 3 | 0 | Colin.Ji | 2.5
Phase12.I001 | New team member familiar with business processes | 930 | 16 | 0 | Bright.Liu | 15.5
Ticket #425 | Conversion from Oracle to Sql server | 920 | 40 | 0 | Stone.Zhao | 16
Phase12.I002 | Assist in the completion of ticket #425 | 920 | 8 | 0 | Bright.Liu | 10
Ticket #448 | View crew list in crew board | 900 | 8 | 1 | Bright.Liu | 11.5
Ticket #440 | View Crew Schedule | 900 | 8 | 0 | Colin.Ji | 2.5
Ticket #441 | View worker schedule | 900 | 4 | 0 | Colin.Ji | 2.5
Ticket #442 | View unit schedule | 900 | 4 | 0 | Colin.Ji | 2.5
Ticket #443 | Search by name in Calendar | 900 | 6 | 0 | Colin.Ji | 0
Ticket #451 | Add a crew | 850 | 5 | 1 | Bright.Liu | 4.5
Ticket #454 | Assign a crew to a job | 850 | 3 | 1 | Bright.Liu | 0.5
Ticket #457 | Call crew for a job | 850 | 3 | 1 | Bright.Liu | 0.5
Ticket #460 | Remove crew for a job | 850 | 2 | 1 | Bright.Liu | 1
Ticket #463 | Add unit to a crew | 800 | 3 | 1 | Bright.Liu | 2.5
Ticket #465 | Add worker to a crew | 800 | 3 | 1 | Bright.Liu | 2
Ticket #468 | Remove a unit from a crew | 800 | 2 | 1 | Bright.Liu | 2
Ticket #469 | Remove a worker from a crew | 800 | 2 | 1 | Bright.Liu | 2
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间