## Daily Records
ID | Name | Prioritize | Est(Hour) | 2019-01-01 | 2019-01-02 | 2019-01-03 | 2019-01-04 | 2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-14 | 2019-01-15 | 2019-01-16 | 2019-01-17 | 2019-01-18 | 2019-01-19 | 2019-01-21 | 2019-01-22 | 2019-01-23 | 2019-01-24 | 2019-01-25 | 2019-01-26 | 2019-01-28 | 2019-01-29 | 2019-01-30 | 2019-01-31 | Total Hours
|  |  |  | 43466 | 43467 | 43468 | 43469 | 43472 | 43473 | 43474 | 43475 | 43476 | 43479 | 43480 | 43481 | 43482 | 43483 | 43484 | 43486 | 43487 | 43488 | 43489 | 43490 | 43491 | 43493 | 43494 | 43495 | 43496
| Ideal Burndown |  | 494 | 494 | 478 | 462 | 441 | 420 | 399 | 378 | 357 | 336 | 315 | 294 | 273 | 252 | 231 | 210 | 189 | 168 | 147 | 126 | 105 | 84 | 63 | 42 | 21 | 0 | 611.5
| Actual |  | 779 | 494 | 471 | 449.5 | 425.5 | 403 | 382.5 | 363 | 333 | 309.5 | 279 | 254 | 226.5 | 215 | 180 | 165 | 143.5 | 114 | 114.5 | 79 | 56 | 32 | 25.5 | 6 | -5.5 | -21.5
|  |  |  | 0 | 23 | 21.5 | 24 | 22.5 | 20.5 | 19.5 | 30 | 23.5 | 30.5 | 25 | 27.5 | 39 | 35 | 15 | 36.5 | 29.5 | 29 | 35.5 | 23 | 24 | 30.5 | 19.5 | 11.5 | 16 | 611.5 | Assign to | Completion Status | Pay by | Module
Phase12.P001 | Meeting-Phase 12 | 1000 | 60 |  | 2 | 3 | 1.5 |  | 1.5 | 2 | 1.5 | 2 | 2 | 2 | 4 | 2 | 2 | 1 | 3 | 3 | 1.5 | 3 | 1.5 |  | 1.5 | 1.5 |  | 1 | 42.5 | All | 0 | Sanjel | Express
Phase12.P002 | Project management | 1000 | 35 | 2019-01-02: 1; 2019-01-03: 1; 2019-01-09: 1; 2019-01-10: 1; 2019-01-11: 1; 2019-01-16: 3; 2019-01-17: 2; 2019-01-18: 1; 2019-01-21: 2; 2019-01-22: 3; 2019-01-23: 2; 2019-01-24: 1; 2019-01-25: 1 | 20 | Bella.bi | 0 | Sanjel | Express
Phase12.S001 | Analysis requirements | 1000 | 30 | 2019-01-03: 1; 2019-01-21: 3.5; 2019-01-22: 3; 2019-01-23: 2; 2019-01-24: 2 | 11.5 | Bella.bi | 0 | Sanjel | Online
Phase12.P003 | Task documentation | 1000 | 10 | 2019-01-16: 3.5; 2019-01-23: 2 | 5.5 | Bright.Liu | 0 | Sanjel | Online
Phase12.I003 | Entry CIM model in MDD | 950 | 8 | 2019-01-09: 4; 2019-01-10: 3.5; 2019-01-11: 6; 2019-01-15: 1; 2019-01-17: 1.5; 2019-01-18: 1; 2019-01-19: 1; 2019-01-24: 1; 2019-01-25: 1; 2019-01-29: 1.5; 2019-01-30: 2; 2019-01-31: 1 | 24.5 | Bright.Liu | 0 | Sanjel | Online
Phase12.I004 | UI Design for CrewBoard and Calendar | 950 | 4 | [25 empty] | 0 | Niki.Wang | 1 | Sanjel | Online
Phase12.I005 | Summarize the implementation of each branch | 950 | 4 | 2019-01-10: 3 | 3 | Colin.Ji | 1 | Sanjel | eService
Phase12.I006 | Integrate generated projects into Online | 950 | 8 | 2019-01-09: 2; 2019-01-10: 2.5; 2019-01-14: 5; 2019-01-17: 6; 2019-01-18: 1.5 | 17 | Bright.Liu | 0 | Sanjel | Online
Phase12.I007 | Merge Online branch | 950 | 12 | 2019-01-14: 9.5; 2019-01-19: 1.5; 2019-01-22: 1 | 12 | Bright.Liu&Colin.Ji | 1 | Sanjel | Online
Phase12.I008 | Refactor models to differente packages | 950 | 8 | 2019-01-16: 3 | 3 | Bright.Liu | 1 | Sanjel | Online
Phase12.D001 | Modify Online Architecture design | 950 | 4 | [25 empty] | 1 | Bright.Liu | 1 | Sanjel | Online | bar: 2019-01-16
Phase12.I009 | Update reference between several projects | 920 | 4 | [25 empty] | 0 | Colin.Ji | 0 | Sanjel | Online
Ticket #425 | Conversion from Oracle to Sql server | 920 | 4 | 2019-01-15: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
Ticket #472 | Implement crew board prototype with Syncfution EJ2 controls | 900 | 24 | 2019-01-02: 6.5; 2019-01-03: 6.5; 2019-01-04: 9; 2019-01-07: 7.5 | 29.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #450 | View calendar | 900 | 9 | 2019-01-02: 5; 2019-01-03: 4; 2019-01-08: 4; 2019-01-10: 2 | 15 | Colin.Ji | 1 | Sanjel | Online
Ticket #473 | Create new worker schedule in Calendar | 900 | 16 | 2019-01-17: 7.5; 2019-01-18: 7.5; 2019-01-19: 7.5 | 22.5 | Colin.Ji | 1 | Sanjel | Online
Ticket #448 | View crew list in crew board | 900 | 8 | 2019-01-21: 3; 2019-01-23: 1; 2019-01-31: 2 | 6 | Bright.Liu | 1 | Sanjel | Online
Ticket #440 | View Crew Schedule | 900 | 8 | 2019-01-21: 3; 2019-01-24: 1; 2019-01-31: 1 | 5 | Colin.Ji | 1 | Sanjel | Online
Ticket #441 | View worker schedule | 900 | 4 | 2019-01-21: 2; 2019-01-24: 1; 2019-01-31: 1 | 4 | Colin.Ji | 1 | Sanjel | Online
Ticket #442 | View unit schedule | 900 | 4 | 2019-01-21: 2; 2019-01-24: 1; 2019-01-31: 0.5 | 3.5 | Colin.Ji | 1 | Sanjel | Online
Ticket #443 | Search by service point in Calendar | 900 | 6 | 2019-01-09: 4; 2019-01-22: 3.5; 2019-01-23: 2 | 9.5 | Colin.Ji | 1 | Sanjel | Online
Ticket #451 | Add a crew | 850 | 5 | 2019-01-08: 3; 2019-01-15: 1; 2019-01-18: 1; 2019-01-29: 2 | 7 | Bright.Liu | 1 | Sanjel | Online
Ticket #454 | Assign a crew to a job | 850 | 3 | 2019-01-24: 1.5; 2019-01-25: 6.5 | 8 | Bright.Liu | 1 | Sanjel | Online
Ticket #457 | Call crew for a job | 850 | 3 | 2019-01-28: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
Ticket #460 | Withdraw a crew for a job | 850 | 2 | 2019-01-28: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
Ticket #463 | Add unit to a crew | 800 | 3 | 2019-01-08: 1; 2019-01-10: 0.5; 2019-01-15: 1; 2019-01-18: 1; 2019-01-21: 0.5; 2019-01-22: 1; 2019-01-24: 2 | 7 | Bright.Liu | 1 | Sanjel | Online
Ticket #465 | Add worker to a crew | 800 | 3 | 2019-01-08: 1; 2019-01-10: 0.5; 2019-01-15: 1; 2019-01-18: 1; 2019-01-21: 0.5; 2019-01-22: 1; 2019-01-24: 1 | 6 | Bright.Liu | 1 | Sanjel | Online
Ticket #468 | Remove a unit from a crew | 800 | 2 | 2019-01-02: 0.5; 2019-01-08: 1; 2019-01-10: 0.5; 2019-01-15: 1; 2019-01-18: 1; 2019-01-22: 2.5; 2019-01-23: 3; 2019-01-24: 1 | 10.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #469 | Remove a worker from a crew | 800 | 2 | 2019-01-02: 0.5; 2019-01-08: 1; 2019-01-15: 1; 2019-01-18: 1; 2019-01-22: 1; 2019-01-23: 3; 2019-01-24: 1 | 8.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #477 | Mark a crew as Log On Duty | 780 | 3 | 2019-01-19: 2; 2019-01-21: 1; 2019-01-29: 1.5 | 4.5 | Bright.Liu | 0 | Sanjel | Online
Ticket #478 | Mark a crew as Log Off Duty | 780 | 3 | 2019-01-19: 2; 2019-01-21: 1; 2019-01-29: 1.5 | 4.5 | Bright.Liu | 0 | Sanjel | Online
Ticket #502 | Cancel unit schedule in Calendar | 760 | 1 | 2019-01-22: 0.5; 2019-01-23: 1 | 1.5 | Colin.Ji | 0 | Sanjel | Online
Ticket #505 | Cancel worker schedule in Calendar | 760 | 1 | 2019-01-22: 0.5; 2019-01-23: 1 | 1.5 | Colin.Ji | 1 | Sanjel | Online
Ticket #508 | Update unit schedule in Calendar | 760 | 2 | 2019-01-22: 0.5; 2019-01-23: 1; 2019-01-24: 1.5 | 3 | Colin.Ji | 1 | Sanjel | Online
Ticket #511 | Update worker schedule in Calendar | 760 | 2 | 2019-01-22: 0.5; 2019-01-23: 1; 2019-01-24: 1.5 | 3 | Colin.Ji | 1 | Sanjel | Online
Ticket #517 | Create new unit schedule in Calendar | 760 | 2 | [25 empty] | 3 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-01-22 to 2019-01-24
Ticket #520 | Send alert | 750 | 20 | 2019-01-25: 7.5; 2019-01-26: 8.5 | 16 | Colin.Ji | 0 | Sanjel | Online
Ticket #521 | Display unit board | 740 | 2 | 2019-01-29: 3.5 | 3.5 | Colin.Ji | 0 | Sanjel | Online
Ticket #522 | Display worker board | 740 | 2 | 2019-01-29: 3 | 3 | Colin.Ji | 0 | Sanjel | Online
Ticket #525 | Display crew information in Rig Board | 730 | 4 | 2019-01-28: 3.5 | 3.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #526 | Add unit section in call sheet when assign a crew to a job | 730 | 8 | 2019-01-28: 7 | 7 | Colin.Ji | 0 | Sanjel | Online
| Update Notes for Crew | 730 | 2 | 2019-01-31: 2 | 2 | Bright.Liu | 0 | Sanjel | Online
| Update references to dependent projects and test | 730 | 8 | 2019-01-31: 5 | 5 | Colin.Ji | 0 | Sanjel | Online
| Update references to dependent projects and test | 730 | 8 | 2019-01-30: 2; 2019-01-31: 2.5 | 4.5 | Bright.Liu | 0 | Sanjel | Online
UC002.T010 | 生成代码升级到.net core 2.0 | 4800 | 40 | 2019-01-02: 7.5; 2019-01-03: 6; 2019-01-04: 7.5; 2019-01-07: 7; 2019-01-08: 5; 2019-01-09: 6.5; 2019-01-10: 6; 2019-01-11: 8; 2019-01-22: 2 | 55.5 | Bela.Zhao | 1 | MetaShare | MDD
UC013.T010 | 实现继承关系 | 4800 | 18 | 2019-01-04: 6; 2019-01-07: 8; 2019-01-08: 3; 2019-01-11: 0.5; 2019-01-17: 0.5 | 18 | Olivia.Ge | 1 | MetaShare | MDD
UC033.T001 | 关联第三方库 | 4800 | 48 | [25 empty] | 0 |  | 0 | MetaShare | MDD
UC002.T012 | MDD生成代码与Syncfusion控件集成 | 4800 | 80 | [25 empty] | 0 |  | 0 | MetaShare | MDD
UC002.T013 | 完成Schedule底层支持 | 4800 | 56 | [25 empty] | 0 |  | 0 | MetaShare | MDD
UC002.T014 | .net core项目自动部署 | 4800 | 24 | 2019-01-14: 2; 2019-01-15: 8; 2019-01-16: 6 | 16 | Bela.Zhao | 0 | MetaShare | MDD
UC028.T001 | Package merge | 4700 | 40 | 2019-01-10: 3; 2019-01-11: 6; 2019-01-14: 3; 2019-01-15: 2; 2019-01-17: 6; 2019-01-18: 6; 2019-01-21: 7.5; 2019-01-24: 7.5; 2019-01-26: 6; 2019-01-28: 1 | 48 | Olivia.Ge | 0 | MetaShare | MDD
MDD.D001 | CIM/PIM/PSM分层设计 | 4700 | 40 | 2019-01-10: 6; 2019-01-14: 9; 2019-01-16: 2; 2019-01-17: 7.5; 2019-01-18: 7; 2019-01-21: 7.5; 2019-01-22: 5.5; 2019-01-23: 7.5; 2019-01-24: 7.5 | 59.5 | Bela.Zhao | 0 | MetaShare | MDD
Bug #101 | CIM有子包时生成的.Net core项目运行报错 | 4600 | 16 | 2019-01-15: 5; 2019-01-16: 5; 2019-01-17: 6; 2019-01-18: 4 | 20 | Bessie.Yin | 0 | MetaShare | MDD
UC002.T011 | 生成新的数据库名 | 4500 | 8 | 2019-01-25: 5.5; 2019-01-26: 1.5 | 7 | Olivia.Ge | 0 | MetaShare | MDD
UC002.T012 | 增加SelectAllByDateTime的API | 4300 | 8 | 2019-01-28: 6 | 6 | Olivia.Ge | 0 | MetaShare | MDD
UC034.T001 | 实现按Name搜索功能 | 4300 | 40 | 2019-01-26: 8; 2019-01-28: 7.5; 2019-01-29: 5; 2019-01-30: 7.5 | 28 | Bela.Zhao | 0 | MetaShare | MDD
Note on P9: Bella Bi: 分析并整理问题
Note on M10: Bella Bi: 分包讨论，录入MDM原有类以及Online中已识别的类。
Note on N14: Bella Bi: Bright 2.5, Colin 7h
Note on U14: Bella Bi: EJ1和EJ2的Layout完善
Note on P15: Bella Bi: 将Online的Model层分包，由于RigBoard页面未调通，此任务暂时往后放。
Note on O18: Bella Bi: 核对数据
Note on H19: Bella Bi: Olivia协助 1.5h
Note on O27: Bella Bi: 连后台
Note on Y42: Bella Bi: Olivia 协助1小时
Note on O55: Bella Bi: Colin 6h
Note on P55: Bella Bi: Colin 4h
Note on N57: Bella Bi: Bela 5h Olivia 4h

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2019-01-01 | 2019-01-02 | 2019-01-03 | 2019-01-04 | 2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-14 | 2019-01-15 | 2019-01-16 | 2019-01-17 | 2019-01-18 | 2019-01-19 | 2019-01-21 | 2019-01-22 | 2019-01-23 | 2019-01-24 | 2019-01-25 | 2019-01-26 | 2019-01-28 | 2019-01-29 | 2019-01-30 | 2019-01-31
|  |  |  | 43466 | 43467 | 43468 | 43469 | 43472 | 43473 | 43474 | 43475 | 43476 | 43479 | 43480 | 43481 | 43482 | 43483 | 43484 | 43486 | 43487 | 43488 | 43489 | 43490 | 43491 | 43493 | 43494 | 43495 | 43496
| Ideal Burndown |  | 494 | 494 | 478 | 462 | 441 | 420 | 399 | 378 | 357 | 336 | 315 | 294 | 273 | 252 | 231 | 210 | 189 | 168 | 147 | 126 | 105 | 84 | 63 | 42 | 21 | 0
| Actual burndown |  | 761 | 228 | 220 | 206 | 204 | 201 | 163.5 | 152 | 146.5 | 163 | 154 | 134 | 120 | 113 | 75 | 74 | 74 | 101 | 81 | 82 | 53 | 53 | 39 | 29 | 20 | 8
Phase12.P001 | Meeting-Phase 12 | 1000 | 60 | 56 | 54 | 52 | 50 | 48 | 48 | 44 | 42 | 40 | 36 | 30 | 24 | 20 | 18 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 5 | 4 | 3 | 0
Phase12.P002 | Project management | 1000 | 35 | 34 | 33 | 33 | 33 | 33 | 12 | 11 | 10 | 9 | 8 | 8 | 15 | 12 | 12 | 12 | 12 | 10 | 10 | 8 | 3 | 3 | 2 | 2 | 2 | 0
Phase12.S001 | Analysis requirements | 1000 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 10 | 10 | 10 | 10 | 20 | 16 | 14 | 10 | 10 | 8 | 6 | 2 | 2 | 0
Phase12.P003 | Task documentation | 1000 | 10 | 10 | 10 | 9 | 9 | 8 | 7.5 | 7 | 6.5 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 0
Phase12.I003 | Entry CIM model in MDD | 950 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 8 | 8 | 10 | 8 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 2 | 0 | 0 | 0
Phase12.I004 | UI Design for CrewBoard and Calendar | 950 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase12.I005 | Summarize the implementation of each branch | 950 | 4 | [6 empty] | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase12.I006 | Integrate generated projects into Online | 950 | 8 | [5 empty] | 8 | 6 | 4 | 4 | 6 | 6 | 4 | 8 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 0 | 0
Phase12.I007 | Merge Online branch | 950 | 12 | [8 empty] | 12 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase12.I008 | Refactor models to differente packages | 950 | 8 | [8 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Phase12.D001 | Modify Online Architecture design | 950 | 4 | 2019-01-15: 4; 2019-01-16: 1; 2019-01-17: 0; 2019-01-18: 0; 2019-01-19: 0; 2019-01-21: 0; 2019-01-22: 0; 2019-01-23: 0; 2019-01-24: 0; 2019-01-25: 0; 2019-01-26: 0; 2019-01-28: 0; 2019-01-29: 0
Phase12.I009 | Update reference between several projects | 920 | 4 | 2019-01-28: 4; 2019-01-29: 2; 2019-01-30: 2; 2019-01-31: 0
Ticket #425 | Conversion from Oracle to Sql server | 920 | 4 | 2019-01-14: 4; 2019-01-15: 0; 2019-01-16: 0; 2019-01-17: 1; 2019-01-18: 0; 2019-01-19: 0; 2019-01-21: 0; 2019-01-22: 0; 2019-01-23: 0; 2019-01-24: 0; 2019-01-28: 0; 2019-01-29: 0
Ticket #472 | Implement crew board prototype with Syncfution EJ2 controls | 900 | 24 | 24 | 24 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Ticket #450 | View calendar | 900 | 9 | 9 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #473 | Create new worker schedule in Calendar | 900 | 16 | 2019-01-16: 16; 2019-01-17: 16; 2019-01-18: 10; 2019-01-19: 2; 2019-01-21: 2; 2019-01-22: 2; 2019-01-23: 1; 2019-01-24: 0; 2019-01-25: 0; 2019-01-26: 0; 2019-01-28: 0
Ticket #448 | View crew list in crew board | 900 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 0 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #440 | View Crew Schedule | 900 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 4 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #441 | View worker schedule | 900 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #442 | View unit schedule | 900 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #443 | Search by service point in Calendar | 900 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #451 | Add a crew | 850 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #454 | Assign a crew to a job | 850 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #457 | Call crew for a job | 850 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #460 | Withdraw a crew for a job | 850 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #463 | Add unit to a crew | 800 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #465 | Add worker to a crew | 800 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #468 | Remove a unit from a crew | 800 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #469 | Remove a worker from a crew | 800 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #477 | Mark a crew as Log On Duty | 780 | 3 | 2019-01-18: 3; 2019-01-19: 2; 2019-01-21: 1; 2019-01-22: 1; 2019-01-23: 1; 2019-01-24: 0; 2019-01-25: 0; 2019-01-26: 0; 2019-01-28: 0
Ticket #478 | Mark a crew as Log Off Duty | 780 | 3 | 2019-01-18: 3; 2019-01-19: 2; 2019-01-21: 1; 2019-01-22: 1; 2019-01-23: 1; 2019-01-24: 0; 2019-01-25: 0; 2019-01-26: 0; 2019-01-28: 0
Ticket #502 | Cancel unit schedule in Calendar | 760 | 1 | 2019-01-22: 1; 2019-01-23: 1; 2019-01-24: 0; 2019-01-25: 0; 2019-01-26: 0; 2019-01-28: 0
Ticket #505 | Cancel worker schedule in Calendar | 760 | 1 | 2019-01-22: 1; 2019-01-23: 1; 2019-01-24: 0; 2019-01-25: 0; 2019-01-26: 0; 2019-01-28: 0
Ticket #508 | Update unit schedule in Calendar | 760 | 2 | 2019-01-22: 2; 2019-01-23: 1; 2019-01-24: 0; 2019-01-25: 0; 2019-01-26: 0; 2019-01-28: 0
Ticket #511 | Update worker schedule in Calendar | 760 | 2 | 2019-01-22: 2; 2019-01-23: 1; 2019-01-24: 0; 2019-01-25: 0; 2019-01-26: 0; 2019-01-28: 0
Ticket #517 | Create new unit schedule in Calendar | 760 | 2 | 2019-01-22: 2; 2019-01-23: 1; 2019-01-24: 0; 2019-01-25: 0; 2019-01-26: 0; 2019-01-28: 0
Ticket #520 | Send alert | 750 | 20 | 2019-01-24: 20; 2019-01-25: 12; 2019-01-26: 4; 2019-01-28: 0; 2019-01-29: 0
Ticket #521 | Display unit board | 740 | 2 | 2019-01-24: 2; 2019-01-25: 2; 2019-01-26: 2; 2019-01-28: 2; 2019-01-29: 2; 2019-01-30: 0; 2019-01-31: 0
Ticket #522 | Display worker board | 740 | 2 | 2019-01-24: 2; 2019-01-25: 2; 2019-01-26: 2; 2019-01-28: 2; 2019-01-29: 2; 2019-01-30: 0
Ticket #525 | Display crew information in Rig Board | 730 | 4 | 2019-01-26: 4; 2019-01-28: 0; 2019-01-29: 0; 2019-01-30: 0
Ticket #526 | Add unit section in call sheet when assign a crew to a job | 730 | 8 | 2019-01-26: 8; 2019-01-28: 2; 2019-01-29: 2; 2019-01-30: 0
UC002.T010 | 生成代码升级到.net core 2.0 | 4800 | 40
UC013.T010 | 实现继承关系 | 4800 | 18
UC033.T001 | 关联第三方库 | 4800 | 48
UC002.T012 | MDD生成代码与Syncfusion控件集成 | 4800 | 80
UC002.T013 | 完成Schedule底层支持 | 4800 | 56
UC002.T014 | .net core项目自动部署 | 4800 | 24
UC028.T001 | Package merge | 4700 | 40
MDD.D001 | CIM/PIM/PSM分层设计 | 4700 | 40
Bug #101 | CIM有子包时生成的.Net core项目运行报错 | 4600 | 16
UC002.T011 | 生成新的数据库名 | 4500 | 8
UC002.T012 | 增加SelectAllByDateTime的API | 4300 | 8
UC034.T001 | 实现按Name搜索功能 | 4300 | 40
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成第12期工作——Rig Board第三期，Crew board和Calendar
StartDate | 2019-01-02
EndDate | 2019-01-31
Est Time
Name | Role | Total Hours | 2019-01-02 | 2019-01-03 | 2019-01-04 | 2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-14 | 2019-01-15 | 2019-01-16 | 2019-01-17 | 2019-01-18 | 2019-01-19 | 2019-01-21 | 2019-01-22 | 2019-01-23 | 2019-01-24 | 2019-01-25 | 2019-01-26 | 2019-01-28 | 2019-01-29 | 2019-01-30 | 2019-01-31
|  |  | 43467 | 43468 | 43469 | 43472 | 43473 | 43474 | 43475 | 43476 | 43479 | 43480 | 43481 | 43482 | 43483 | 43484 | 43486 | 43487 | 43488 | 43489 | 43490 | 43491 | 43493 | 43494 | 43495 | 43496
Ideal Burndown |  | 494 | 478 | 462 | 441 | 420 | 399 | 378 | 357 | 336 | 315 | 294 | 273 | 252 | 231 | 210 | 189 | 168 | 147 | 126 | 105 | 84 | 63 | 42 | 21 | 0
Hours consumed |  | 494 | 16 | 16 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
Bella.Bi |  | 72 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Olivia.Ge |  | 22 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Bright.Liu |  | 192 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Colin.Ji |  | 184 | 4 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Kevin.Wu |  | 24 | bar: 2019-01-02 to 2019-01-31
Niki.Wang
Olivia.Ge
Bela.Zhao
Bessie.Yin

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase12.P001 | Meeting-Phase 12 | 1000 | 60 | 0 | All | 42.5
Phase12.P002 | Project management | 1000 | 35 | 0 | Bella.bi | 20
Phase12.S001 | Analysis requirements | 1000 | 30 | 0 | Bella.bi | 11.5
Phase12.P003 | Task documentation | 1000 | 10 | 0 | Bright.Liu | 5.5
Phase12.I003 | Entry CIM model in MDD | 950 | 8 | 0 | Bright.Liu | 24.5
Phase12.I004 | UI Design for CrewBoard and Calendar | 950 | 4 | 1 | Niki.Wang | 0
Phase12.I005 | Summarize the implementation of each branch | 950 | 4 | 1 | Colin.Ji | 3
Phase12.I006 | Integrate generated projects into Online | 950 | 8 | 0 | Bright.Liu | 17
Phase12.I007 | Merge Online branch | 950 | 12 | 1 | Bright.Liu&Colin.Ji | 12
Phase12.I008 | Refactor models to differente packages | 950 | 8 | 1 | Bright.Liu | 3
Phase12.D001 | Modify Online Architecture design | 950 | 4 | 1 | Bright.Liu | 1
Ticket #425 | Conversion from Oracle to Sql server | 920 | 4 | 1 | Bright.Liu | 2
Ticket #472 | Implement crew board prototype with Syncfution EJ2 controls | 900 | 24 | 1 | Bright.Liu | 29.5
Ticket #450 | View calendar | 900 | 9 | 1 | Colin.Ji | 15
Ticket #473 | Create new worker schedule in Calendar | 900 | 16 | 1 | Colin.Ji | 22.5
Ticket #448 | View crew list in crew board | 900 | 8 | 1 | Bright.Liu | 6
Ticket #440 | View Crew Schedule | 900 | 8 | 1 | Colin.Ji | 5
Ticket #441 | View worker schedule | 900 | 4 | 1 | Colin.Ji | 4
Ticket #442 | View unit schedule | 900 | 4 | 1 | Colin.Ji | 3.5
Ticket #443 | Search by service point in Calendar | 900 | 6 | 1 | Colin.Ji | 9.5
Ticket #451 | Add a crew | 850 | 5 | 1 | Bright.Liu | 7
Ticket #454 | Assign a crew to a job | 850 | 3 | 1 | Bright.Liu | 8
Ticket #457 | Call crew for a job | 850 | 3 | 1 | Bright.Liu | 2
Ticket #460 | Withdraw a crew for a job | 850 | 2 | 1 | Bright.Liu | 2
Ticket #463 | Add unit to a crew | 800 | 3 | 1 | Bright.Liu | 7
Ticket #465 | Add worker to a crew | 800 | 3 | 1 | Bright.Liu | 6
Ticket #468 | Remove a unit from a crew | 800 | 2 | 1 | Bright.Liu | 10.5
Ticket #469 | Remove a worker from a crew | 800 | 2 | 1 | Bright.Liu | 8.5
UC002.T010 | 生成代码升级到.net core 2.0 | 4800 | 40 | 1 | Bela.Zhao | 55.5
UC013.T010 | 实现继承关系 | 4800 | 18 | 1 | Olivia.Ge | 18
UC033.T001 | 关联第三方库 | 4800 | 48 | 0 | 0 | 0
UC002.T012 | MDD生成代码与Syncfusion控件集成 | 4800 | 80 | 0 | 0 | 0
UC002.T013 | 完成Schedule底层支持 | 4800 | 56 | 0 | 0 | 0
UC002.T014 | .net core项目自动部署 | 4800 | 24 | 0 | Bela.Zhao | 16
UC028.T001 | Package merge | 4700 | 40 | 0 | Olivia.Ge | 48
MDD.D001 | CIM/PIM/PSM分层设计 | 4700 | 40 | 0 | Bela.Zhao | 59.5
Bug #101 | CIM有子包时生成的.Net core项目运行报错 | 4600 | 16 | 0 | Bessie.Yin | 20
UC002.T011 | 生成新的数据库名 | 4500 | 8 | 0 | Olivia.Ge | 7
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间