## Daily Records
ID | Name | Prioritize | Est(Hour) | 2019-01-31 | 2019-02-01 | 2019-02-13 | 2019-02-14 | 2019-02-15 | 2019-02-18 | 2019-02-20 | 2019-02-21 | 2019-02-22 | 2019-02-25 | 2019-02-26 | 2019-02-27 | 2019-02-28 | Total Hours
|  |  |  | 43496 | 43497 | 43509 | 43510 | 43511 | 43514 | 43516 | 43517 | 43518 | 43521 | 43522 | 43523 | 43524
| Ideal Burndown |  | 217 | 217 | 198 | 195 | 175 | 155 | 135 | 115 | 95 | 76 | 57 | 38 | 19 | 0 | 207
| Actual |  | 265.5 | 217 | 209 | 207 | 185 | 167 | 149.5 | 132.5 | 112.5 | 82.5 | 62.5 | 43.5 | 26.5 | 27
|  |  |  | 0 | 8 | 2 | 22 | 18 | 17.5 | 17 | 20 | 30 | 20 | 19 | 17 | 16.5 | 207 | Assign to | Completion Status | Pay by | Module
Phase12.P001 | Meeting-Phase 12 | 1000 | 26 |  |  |  | 6 | 1.5 | 1.5 | 1.5 | 6 | 6 | 4 | 6 | 2 | 2 | 36.5 | All | 1 | Sanjel | Express
Phase12.P002 | Project management | 1000 | 15 | 2019-02-14: 2; 2019-02-15: 1; 2019-02-18: 1; 2019-02-20: 0.5; 2019-02-21: 1; 2019-02-22: 1; 2019-02-25: 1 | 7.5 | Bella.bi | 1 | Sanjel | Express
Phase12.S001 | Analysis requirements | 1000 | 15 | 2019-02-13: 2; 2019-02-14: 2; 2019-02-15: 2; 2019-02-22: 2 | 8 | Bella.bi | 1 | Sanjel | Online
Phase12.I003 | Entry CIM model in MDD | 950 | 8 | 2019-02-14: 2; 2019-02-15: 0.5 | 2.5 | Bright.Liu | 1 | Sanjel | Online
Phase12.I006 | Integrate generated projects into Online | 950 | 12 | 2019-02-01: 8; 2019-02-20: 1.5 | 9.5 | Bright.Liu | 1 | Sanjel | Online
Phase12.I008 | Refactor models to differente packages | 950 | 8 | 2019-02-28: 3 | 3 | Bright.Liu | 1 | Sanjel | Online
Phase12.I009 | Update reference between several projects | 920 | 10 | 2019-02-14: 1.5; 2019-02-15: 1.5 | 3 | Bright.Liu | 1 | Sanjel | Online
Phase12.I010 | Update database upgrade script | 920 | 6 | 2019-02-20: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
Ticket #465 | Add worker to a crew | 900 | 4 | 2019-02-15: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
Ticket #522 | Display worker board | 900 | 4 | 2019-02-14: 1.5; 2019-02-15: 2.5; 2019-02-18: 0.5 | 4.5 | Colin.Ji | 1 | Sanjel | Online
Ticket #521 | Display unit board | 900 | 4 | 2019-02-14: 1.5; 2019-02-15: 1 | 2.5 | Colin.Ji | 1 | Sanjel | Online
Ticket #527 | Remove the number column in all board | 900 | 2 | [13 empty] | 1 | Bright.Liu | 1 | Sanjel | Online | bar: 2019-02-14
Ticket #451 | Add a crew | 850 | 4 | 2019-02-15: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
Ticket #463 | Add unit to a crew | 850 | 4 | [13 empty] | 0 | Bright.Liu | 1 | Sanjel | Online | bar: 2019-02-15
Ticket #529 | Assign a crew to another district | 850 | 8 | 2019-02-14: 1.5; 2019-02-20: 4 | 5.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #448 | View crew list in crew board | 900 | 2 | 2019-02-14: 0.5 | 0.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #454 | Assign a crew to a job | 850 | 5 | 2019-02-14: 2.5; 2019-02-18: 4; 2019-02-21: 1.5 | 8 | Bright.Liu | 1 | Sanjel | Online
Ticket #547 | Filter by service point in Crew Board | 850 | 2 | [13 empty] | 1 | Bright.Liu | 1 | Sanjel | Online | bar: 2019-02-18
Ticket #536 | Update Worker Profile | 850 | 4.5 | 2019-02-15: 4; 2019-02-18: 1 | 5 | Colin.Ji | 1 | Sanjel | Online
Ticket #541 | Remove the crew | 820 | 4 | 2019-02-18: 2.5 | 2.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #543 | Release Crew | 700 | 7 | 2019-02-20: 5 | 5 | Colin.Ji | 1 | Sanjel | Online
Ticket #545 | Adjust Job Duration | 700 | 6 | 2019-02-18: 6 | 6 | Colin.Ji | 1 | Sanjel | Online
Ticket #537 | View third party bulker crew | 700 | 12 | 2019-02-27: 6 | 6 | Bright.Liu | 1 | Sanjel | Online
Phase12.I011 | JS file refactor | 700 | 8 | 2019-02-20: 2.5; 2019-02-21: 1.5; 2019-02-22: 5.5 | 9.5 | Colin.Ji | 1 | Sanjel | Online
Phase12.I012 | Refactor for context menu | 700 | 6 | 2019-02-21: 6 | 6 | Colin.Ji | 1 | Sanjel | Online
Phase12.D001 | Update design model | 700 | 8 | 2019-02-21: 4 | 4 | Bright.Liu | 1 | Sanjel | Online
Ticket #556 | Deselect Total Rate if only one truck is selected | 600 | 1 | [13 empty] | 1 | Colin.Ji | 1 | Sanjel | Express | bar: 2019-02-22
Ticket #558 | Hide Duration and interval | 600 | 1 | 2019-02-22: 0.5 | 0.5 | Colin.Ji | 1 | Sanjel | Express
Ticket #560 | Add Supervisor on Job Setup Page | 600 | 6 | 2019-02-22: 5.5 | 5.5 | Bright.Liu | 1 | Sanjel | Express
Ticket #562 | Modify printing service | 600 | 12 | 2019-02-22: 8.5; 2019-02-25: 1 | 9.5 | Olivia.Ge | 1 | Sanjel | Express
Phase12.I013 | Refactor crew function | 600 | 16 | 2019-02-25: 7; 2019-02-26: 6.5 | 13.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #569 | Schedule product haul_choose crew | 580 | 8 | 2019-02-25: 4; 2019-02-27: 4.5 | 8.5 | Colin.Ji | 1 | Sanjel | Online
Ticket #571 | ReSchedule product haul_choose crew | 580 | 6 | 2019-02-25: 3; 2019-02-27: 3 | 6 | Colin.Ji | 1 | Sanjel | Online
Phase12.I014 | Get ProcessedScmPlcLog | 560 | 8 | 2019-02-26: 6.5 | 6.5 | Colin.Ji | 1 | Sanjel | Express
Ticket #572 | Schedule product haul_choose third party crew | 560 | 5 | 2019-02-28: 4.5 | 4.5 | Colin.Ji | 1 | Sanjel | Online
Ticket #573 | ReSchedule product haul_choose third party crew | 560 | 3 | 2019-02-28: 3 | 3 | Colin.Ji | 1 | Sanjel | Online
Ticket #576 | Create third party bulk crew | 560 | 5 | 2019-02-27: 1.5; 2019-02-28: 4 | 5.5 | Bright.Liu | 1 | Sanjel | Online
| Handing schedule conflicts | 560 | [14 empty] | 0 |  | 0 | Sanjel | Online
Ticket #534 | Edit a crew | 600 | [14 empty] | 0
Note on H6: Bella Bi: 讲解需求和讨论
Note on L6: Bella Bi: 早会及跟Adam讨论设计
Note on M6: Bella Bi: 讨论express的新需求
Note on B14: Bella Bi: Woker下拉框中数据按Bonus Position不为空过滤（意味着只有Field Worker），然后按所选Service Point进行过滤，按姓名字符串字母顺序排序
Note on B15: Bella Bi: 展示Worker的姓名、职位和状态等信息。 按Bonus Position不为空过滤（意味着只有Field Worker），然后按所选Service Point进行过滤，按姓名字符串字母顺序排序
Note on B16: Bella Bi: 按照Service Point过滤，然后按unit type过滤，然后按unit number排序。 4 过滤掉过期数据
Note on B18: Bella Bi: `Home District`下拉框：默认显示当前页面已选择的Service Point，如果选择了多个Service Point则默认显示第一个。
Note on H20: Bella Bi: Colin 写TestCase
Note on B21: Bella Bi: Job info列应该显示client和rig，而不是Call Sheet Number，而且应该根据状态进行颜色区分：“assigned (scheduled), called out, active on job, on way home, etc.” 在Crew number的Tooltips新增Crew home District
Note on M35: Bella Bi: Bright 准备测试数据
Note on B36: Bella Bi: 修改设计模型后对代码进行重构、数据库升级脚本、mdd重新生成代码

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2019-01-31 | 2019-02-01 | 2019-02-13 | 2019-02-14 | 2019-02-15 | 2019-02-18 | 2019-02-20 | 2019-02-21 | 2019-02-22 | 2019-02-25 | 2019-02-26 | 2019-02-27 | 2019-02-28
|  |  |  | 43496 | 43497 | 43509 | 43510 | 43511 | 43514 | 43516 | 43517 | 43518 | 43521 | 43522 | 43523 | 43524
| Ideal Burndown |  | 217 | 217 | 198 | 195 | 175 | 155 | 135 | 115 | 95 | 76 | 57 | 38 | 19 | 0
| Actual burndown |  | 265.5 | 166.5 | 158.5 | 156.5 | 141.5 | 118 | 91 | 91 | 79 | 61 | 59 | 43 | 17 | 0
Phase12.P001 | Meeting-Phase 12 | 1000 | 26 | 26 | 26 | 26 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0
Phase12.P002 | Project management | 1000 | 15 | 15 | 15 | 15 | 13 | 12 | 10 | 8 | 6 | 5 | 5 | 4 | 1 | 0
Phase12.S001 | Analysis requirements | 1000 | 15 | 15 | 15 | 13 | 11 | 10 | 8 | 8 | 6 | 4 | 4 | 3 | 1 | 0
Phase12.I003 | Entry CIM model in MDD | 950 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 2 | 1 | 0
Phase12.I006 | Integrate generated projects into Online | 950 | 12 | 12 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0
Phase12.I008 | Refactor models to differente packages | 950 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
Phase12.I009 | Update reference between several projects | 920 | 10 | 10 | 10 | 10 | 9 | 8 | 8 | 8 | 6 | 6 | 4 | 2 | 1 | 0
Phase12.I010 | Update database upgrade script | 920 | 6 | [5 empty] | 6 | 4 | 4 | 4 | 4 | 4 | 1 | 0
Ticket #465 | Add worker to a crew | 900 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #522 | Display worker board | 900 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #521 | Display unit board | 900 | 4 | 4 | 4 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #527 | Remove the number column in all board | 900 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #451 | Add a crew | 850 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #463 | Add unit to a crew | 850 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #529 | Assign a crew to another district | 850 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #448 | View crew list in crew board | 900 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #454 | Assign a crew to a job | 850 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #547 | Filter by service point in Crew Board | 850 | 2 | 2 | 2 | 2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #536 | Update Worker Profile | 850 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #541 | Remove the crew | 820 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #543 | Release Crew | 700 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #545 | Adjust Job Duration | 700 | 6 | 6 | 6 | 6 | 6 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #537 | View third party bulker crew | 700 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 0 | 0
Phase12.I011 | JS file refactor | 700 | 8 | 2019-02-20: 8; 2019-02-21: 6; 2019-02-22: 0; 2019-02-25: 0; 2019-02-26: 0; 2019-02-27: 0; 2019-02-28: 0
Phase12.I012 | Refactor for context menu | 700 | 6 | 2019-02-20: 6; 2019-02-21: 0; 2019-02-22: 0; 2019-02-25: 0; 2019-02-26: 0; 2019-02-27: 0; 2019-02-28: 0
Phase12.D001 | Update design model | 700 | 8 | 2019-02-20: 8; 2019-02-21: 4; 2019-02-22: 4; 2019-02-25: 4; 2019-02-26: 4; 2019-02-27: 1; 2019-02-28: 0
Ticket #556 | Deselect Total Rate if only one truck is selected | 600 | 1 | 2019-02-21: 1; 2019-02-22: 0; 2019-02-25: 0; 2019-02-26: 0; 2019-02-27: 0; 2019-02-28: 0
Ticket #558 | Hide Duration and interval | 600 | 1 | 2019-02-21: 1; 2019-02-22: 0; 2019-02-25: 0; 2019-02-26: 0; 2019-02-27: 0; 2019-02-28: 0
Ticket #560 | Add Supervisor on Job Setup Page | 600 | 6 | 2019-02-21: 6; 2019-02-22: 0; 2019-02-25: 0; 2019-02-26: 0; 2019-02-27: 0; 2019-02-28: 0
Ticket #562 | Modify printing service | 600 | 12 | 2019-02-21: 12; 2019-02-22: 0; 2019-02-25: 0; 2019-02-26: 0; 2019-02-27: 0; 2019-02-28: 0
Phase12.I013 | Refactor crew function | 600 | 16 | 2019-02-22: 16; 2019-02-25: 10; 2019-02-26: 3; 2019-02-27: 1; 2019-02-28: 0
Ticket #569 | Schedule product haul_choose crew | 580 | 8 | 2019-02-22: 8; 2019-02-25: 8; 2019-02-26: 4; 2019-02-27: 1; 2019-02-28: 0
Ticket #571 | ReSchedule product haul_choose crew | 580 | 6 | 2019-02-22: 6; 2019-02-25: 6; 2019-02-26: 3; 2019-02-27: 1; 2019-02-28: 0
Phase12.I014 | Get ProcessedScmPlcLog | 560 | 8 | 2019-02-22: 8; 2019-02-25: 8; 2019-02-26: 0; 2019-02-27: 0; 2019-02-28: 0
Ticket #572 | Schedule product haul_choose third party crew | 560 | 5 | 2019-02-26: 5; 2019-02-27: 5; 2019-02-28: 0
Ticket #573 | ReSchedule product haul_choose third party crew | 560 | 3 | 2019-02-26: 3; 2019-02-27: 3; 2019-02-28: 0
Ticket #576 | Create third party bulk crew | 560 | 5 | 2019-02-26: 5; 2019-02-27: 5; 2019-02-28: 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成第12期工作——Rig Board第三期，Resource和Calendar
StartDate | 2019-02-01
EndDate | 2019-03-01
Est Time
Name | Role | Total Hours | 2019-02-01 | 2019-02-13 | 2019-02-14 | 2019-02-15 | 2019-02-18 | 2019-02-20 | 2019-02-21 | 2019-02-22 | 2019-02-25 | 2019-02-26 | 2019-02-27 | 2019-02-28
|  |  | 43497 | 43509 | 43510 | 43511 | 43514 | 43516 | 43517 | 43518 | 43521 | 43522 | 43523 | 43524
Ideal Burndown |  | 217 | 198 | 195 | 175 | 155 | 135 | 115 | 95 | 76 | 57 | 38 | 19 | 0
Hours consumed |  | 217 | 19 | 3 | 20 | 20 | 20 | 20 | 20 | 19 | 19 | 19 | 19 | 19
Bella.Bi |  | 36 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Olivia.Ge |  | 5 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Bright.Liu |  | 88 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Colin.Ji |  | 88 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Kevin.Wu |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Niki.Wang

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase12.P001 | Meeting-Phase 12 | 1000 | 26 | 1 | All | 36.5
Phase12.P002 | Project management | 1000 | 15 | 1 | Bella.bi | 7.5
Phase12.S001 | Analysis requirements | 1000 | 15 | 1 | Bella.bi | 8
Phase12.I003 | Entry CIM model in MDD | 950 | 8 | 1 | Bright.Liu | 2.5
Phase12.I006 | Integrate generated projects into Online | 950 | 12 | 1 | Bright.Liu | 9.5
Phase12.I008 | Refactor models to differente packages | 950 | 8 | 1 | Bright.Liu | 3
Phase12.I009 | Update reference between several projects | 920 | 10 | 1 | Bright.Liu | 3
Phase12.I010 | Update database upgrade script | 920 | 6 | 1 | Bright.Liu | 2
Ticket #465 | Add worker to a crew | 900 | 4 | 1 | Bright.Liu | 2
Ticket #522 | Display worker board | 900 | 4 | 1 | Colin.Ji | 4.5
Ticket #521 | Display unit board | 900 | 4 | 1 | Colin.Ji | 2.5
Ticket #527 | Remove the number column in all board | 900 | 2 | 1 | Bright.Liu | 1
Ticket #451 | Add a crew | 850 | 4 | 1 | Bright.Liu | 2
Ticket #463 | Add unit to a crew | 850 | 4 | 1 | Bright.Liu | 0
Ticket #529 | Assign a crew to another district | 850 | 8 | 1 | Bright.Liu | 5.5
Ticket #448 | View crew list in crew board | 900 | 2 | 1 | Bright.Liu | 0.5
Ticket #454 | Assign a crew to a job | 850 | 5 | 1 | Bright.Liu | 8
Ticket #547 | Filter by service point in Crew Board | 850 | 2 | 1 | Bright.Liu | 1
Ticket #536 | Update Worker Profile | 850 | 4.5 | 1 | Colin.Ji | 5
Ticket #541 | Remove the crew | 820 | 4 | 1 | Bright.Liu | 2.5
Ticket #543 | Release Crew | 700 | 7 | 1 | Colin.Ji | 5
Ticket #545 | Adjust Job Duration | 700 | 6 | 1 | Colin.Ji | 6
Ticket #537 | View third party bulker crew | 700 | 12 | 1 | Bright.Liu | 6
Phase12.I011 | JS file refactor | 700 | 8 | 1 | Colin.Ji | 9.5
Ticket #534 | Edit a crew | 600 | 0 | 0 | 0 | 0
Ticket #556 | Deselect Total Rate if only one truck is selected | 600 | 1 | 1 | Colin.Ji | 1
Ticket #558 | Hide Duration and interval | 600 | 1 | 1 | Colin.Ji | 0.5
Ticket #560 | Add Supervisor on Job Setup Page | 600 | 6 | 1 | Bright.Liu | 5.5
Ticket #562 | Modify printing service | 600 | 12 | 1 | Olivia.Ge | 9.5
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间