## Daily Records
ID | Name | Prioritize | Est(Hour) | 2019-02-28 | 2019-03-01 | 2019-03-04 | 2019-03-05 | 2019-03-06 | 2019-03-07 | 2019-03-08 | 2019-03-11 | 2019-03-12 | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29 | Total Hours
|  |  |  | 43524 | 43525 | 43528 | 43529 | 43530 | 43531 | 43532 | 43535 | 43536 | 43537 | 43538 | 43539 | 43542 | 43543 | 43544 | 43545 | 43546 | 43549 | 43550 | 43551 | 43552 | 43553
| Ideal Burndown |  | 380 | 380 | 364 | 361 | 342 | 323 | 304 | 285 | 266 | 247 | 228 | 209 | 190 | 171 | 152 | 133 | 114 | 95 | 76 | 57 | 38 | 19 | 0 | 298.5
| Actual |  | 395 | 380 | 364 | 351 | 333.5 | 315.5 | 315.5 | 298.5 | 276.5 | 266.5 | 250 | 242.5 | 224.5 | 226.5 | 207.5 | 210 | 191 | 201 | 179.5 | 184.5 | 163 | 165.5 | 146
|  |  |  | 0 | 16 | 13 | 17.5 | 18 | 0 | 17 | 22 | 10 | 16.5 | 7.5 | 18 | 16 | 17 | 16.5 | 16.5 | 9 | 11.5 | 16.5 | 16.5 | 19 | 17 | 298.5 | Assign to | Completion Status | Pay by | Module
Phase12.P001 | Meeting-Phase 12 | 1000 | 40 |  | 1 | 1.5 | 4.5 | 1.5 |  | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 4 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 2 | 2 | 37.5 | All | 1 | Sanjel | Express
Phase12.P002 | Project management | 1000 | 20 | 2019-03-04: 2 | 2 | Bella.bi | 1 | Sanjel | Express
Phase12.P003 | Retrospective Meeting | 1000 | 16 | 2019-03-04: 6 | 6 | All | 1 | Sanjel | Express
Phase12.S001 | Analysis requirements | 1000 | 20 | [22 empty] | 0 | Bella.bi | 1 | Sanjel | Online
Phase12.I003 | Entry CIM model in MDD | 950 | 8 | 2019-03-13: 6.5; 2019-03-15: 3; 2019-03-19: 2.5; 2019-03-27: 1 | 13 | Bright.Liu | 1 | Sanjel | Online
Phase12.I006 | Integrate generated projects into Online | 950 | 12 | [22 empty] | 0 | Bright.Liu | 1 | Sanjel | Online
Phase12.I009 | Update reference between several projects | 920 | 10 | [22 empty] | 0 | Bright.Liu | 1 | Sanjel | Online
Phase12.I010 | Update database upgrade script | 920 | 6 | 2019-03-01: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
Phase12.D001 | Update design model | 900 | 8 | [22 empty] | 0 | Bright.Liu | 1 | Sanjel | Online
Phase12.E002 | Online deployment | 900 | 6 | 2019-03-01: 5.5 | 5.5 | Bright.Liu | 1 | MetaShare | Online
Phase12.E003 | Discuss for domain model and design model | 900 | 16 | 2019-03-05: 7; 2019-03-06: 5.5 | 12.5 | All | 1 | Sanjel | Online
Ticket #579 | Refactor product haul load | 900 | 8 | 2019-03-01: 7.5; 2019-03-04: 3.5 | 11 | Colin.Ji | 1 | Sanjel | Online
Ticket #581 | Handling schedule conflicts | 850 | 3 | 2019-03-05: 3 | 3 | Colin.Ji | 1 | Sanjel | Online
Phase12.T001 | Test for schedule product haul | 850 | 10 | 2019-03-05: 3; 2019-03-06: 5.5 | 8.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #569 | Refactor schedule product haul function | 850 | 6 | 2019-03-06: 5.5 | 5.5 | Colin.Ji | 1 | Sanjel | Online
Refactor.T001 | eService Online Test | 800 | 8 | 2019-03-08: 7.5 | 7.5 | Bright.Liu | 1 | Sanjel | Online
Refactor.T002 | eService Online Test | 800 | 8 | 2019-03-08: 7.5 | 7.5 | Colin.Ji | 1 | Sanjel | Online
Refactor.T003 | Resolve chart printing issue | 800 | 3 | 2019-03-11: 3 | 3 | Olivia.Ge | 1 | Sanjel | Online
Refactor.T004 | Update RigJob Domain Model | 800 | 6 | 2019-03-11: 5.5 | 5.5 | Bright.Liu | 1 | Sanjel | Online
Refactor.T007 | Analyzing entity dependencies for RigJob | 800 | 12 | 2019-03-11: 11 | 11 | Colin.Ji | 1 | Sanjel | Online
Refactor.T008 | Update migration entities document | 800 | 3 | [22 empty] | 3 | Bright.Liu | 1 | Sanjel | Online | bar: 2019-03-11; 2019-03-15 to 2019-03-18
Refactor.T009 | Update RigJob Design Model | 750 | 16 | 2019-03-12: 5.5; 2019-03-13: 1; 2019-03-15: 3; 2019-03-18: 6 | 15.5 | Bright.Liu | 1 | Sanjel | Online
Refactor.T010 | Update Entity_Model | 750 | 6 | 2019-03-12: 3; 2019-03-13: 2 | 5 | Colin.Ji | 1 | Sanjel | Online
Refactor.T011 | Update data import scripts | 750 | 32 | 2019-03-13: 5.5; 2019-03-14: 6; 2019-03-15: 5; 2019-03-18: 7; 2019-03-25: 7.5 | 31 | Colin.Ji | 1 | Sanjel | Online
Refactor.T012 | Analyse RigJob related code | 750 | 3 | 2019-03-15: 2 | 2 | Colin.Ji | 1 | Sanjel | Online
Refactor.T013 | Separate derived attributes from CommonLibrary | 750 | 8 | 2019-03-19: 7.5 | 7.5 | Colin.Ji | 1 | Sanjel | Online
Refactor.T014 | Refactor eServiceOnline | 700 | 32 | 2019-03-19: 5; 2019-03-20: 7.5; 2019-03-21: 7.5; 2019-03-22: 7.5 | 27.5 | Bright.Liu | 1 | Sanjel | Online
Refactor.T015 | Refactor eServiceOnline | 700 | 16 | 2019-03-20: 7.5; 2019-03-21: 7.5 | 15 | Colin.Ji | 1 | Sanjel | Online
Refactor.T016 | Update sql script | 700 | 10 | 2019-03-25: 2.5; 2019-03-26: 3; 2019-03-27: 2; 2019-03-28: 1.5 | 9 | Bright.Liu | 1 | Sanjel | Online
Refactor.T017 | View RigJob List | 700 | 20 | 2019-03-26: 12; 2019-03-27: 4.5; 2019-03-28: 4 | 20.5 | Bright.Liu | 1 | Sanjel | Online
Refactor.T019 | Create Job Alert | 700 | 2 | 2019-03-27: 2.5 | 2.5 | Colin.Ji | 1 | Sanjel | Online
Refactor.T020 | Update Job Alert | 700 | 2 | [22 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-03-27
Refactor.T021 | Remove Job Alert | 700 | 1 | [22 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-03-27
Refactor.T022 | Remove COD Cleared | 650 | 1 | [22 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-03-27
Refactor.T023 | Update Company Short Name | 650 | 1 | [22 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-03-27
Refactor.T024 | Update Notes | 650 | 1 | [22 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-03-27
Refactor.T025 | Add New Rig | 650 | 2 | 2019-03-28: 2 | 2 | Colin.Ji | 1 | Sanjel | Online
Refactor.T026 | Update the rig | 650 | 4 | 2019-03-28: 3.5 | 3.5 | Colin.Ji | 1 | Sanjel | Online
Refactor.T027 | Enable the rig | 650 | 1 | [22 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-03-28
Refactor.T028 | Down Rig | 650 | 1 | [22 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-03-28
Refactor.T029 | Deactivate | 650 | 1 | [22 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-03-28
Refactor.T030 | Activate a rig | 650 | 1 | [22 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-03-28
Refactor.T031 | Modify the display of BL Column | 650 | 2 | 2019-03-28: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
Refactor.T032 | Add a consultant | 650 | 2 | 2019-03-29: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
Refactor.T033 | Create new consultant | 650 | 1 | 2019-03-29: 0.5 | 0.5 | Bright.Liu | 1 | Sanjel | Online
Refactor.T034 | Update consultant | 600 | 1 | 2019-03-29: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
Refactor.T035 | Remove consultant | 600 | 3 | 2019-03-29: 2.5 | 2.5 | Bright.Liu | 1 | Sanjel | Online
Refactor.T036 | Assign work shift | 600 | 1 | 2019-03-29: 0.5 | 0.5 | Bright.Liu | 1 | Sanjel | Online
Refactor.T037 | Need Bins | 600 | 1 | [22 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-03-29
Refactor.T038 | Don't need bin | 600 | 1 | [22 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-03-29
Refactor.T039 | Assign a bin | 600 | 2 | 2019-03-29: 1.5 | 1.5 | Colin.Ji | 1 | Sanjel | Online
Refactor.T040 | Remove the bin | 600 | 1 | [22 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-03-29
Refactor.T041 | Fix the operation of Date column | 600 | 3 | 2019-03-29: 3 | 3 | Colin.Ji | 1 | Sanjel | Online
0
0
0
0
0
0
0
0
0
Note on B8: Bella Bi: 针对部署出现错误的情况进行反思并制定改进方案
Note on B15: Bella Bi: 部署Online，重现本地遇到的菜单不显示问题并解决问题
Note on L24: Bella Bi: Colin 2.5h
Note on L25: Bella Bi: Bright 3.5h
Note on W35: Bella Bi: Colin 7.5h

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2019-02-28 | 2019-03-01 | 2019-03-04 | 2019-03-05 | 2019-03-06 | 2019-03-07 | 2019-03-08 | 2019-03-11 | 2019-03-12 | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-18
|  |  |  | 43524 | 43525 | 43528 | 43529 | 43530 | 43531 | 43532 | 43535 | 43536 | 43537 | 43538 | 43539 | 43542
| Ideal Burndown |  | 380 | 380 | 364 | 361 | 342 | 323 | 304 | 285 | 266 | 247 | 228 | 209 | 190 | 171
| Actual burndown |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
Phase12.P001 | Meeting-Phase 12 | 1000 | 40 | 40 | 40 | 40 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0
Phase12.P002 | Project management | 1000 | 20 | 20 | 20 | 20 | 13 | 12 | 10 | 8 | 6 | 5 | 5 | 4 | 1 | 0
Phase12.S001 | Analysis requirements | 1000 | 20 | 20 | 20 | 13 | 11 | 10 | 8 | 8 | 6 | 4 | 4 | 3 | 1 | 0
Phase12.I003 | Entry CIM model in MDD | 950 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 2 | 1 | 0
Phase12.I006 | Integrate generated projects into Online | 950 | 12 | 12 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
Phase12.I009 | Update reference between several projects | 920 | 10 | 10 | 10 | 10 | 9 | 8 | 8 | 8 | 6 | 6 | 4 | 2 | 1 | 0
Phase12.I010 | Update database upgrade script | 920 | 6 | [5 empty] | 6 | 4 | 4 | 4 | 4 | 4 | 1 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 8 | 0 | 0
#REF! | #REF! | #REF! | #REF! | 2019-03-08: 8; 2019-03-11: 6; 2019-03-12: 0; 2019-03-13: 0; 2019-03-14: 0; 2019-03-15: 0; 2019-03-18: 0
#REF! | #REF! | #REF! | #REF! | 2019-03-08: 6; 2019-03-11: 0; 2019-03-12: 0; 2019-03-13: 0; 2019-03-14: 0; 2019-03-15: 0; 2019-03-18: 0
Phase12.D001 | Update design model | 900 | 8 | 2019-03-08: 8; 2019-03-11: 4; 2019-03-12: 4; 2019-03-13: 4; 2019-03-14: 4; 2019-03-15: 1; 2019-03-18: 0
#REF! | #REF! | #REF! | #REF! | 2019-03-11: #REF!; 2019-03-12: 0; 2019-03-13: 0; 2019-03-14: 0; 2019-03-15: 0; 2019-03-18: 0
#REF! | #REF! | #REF! | #REF! | 2019-03-11: #REF!; 2019-03-12: 0; 2019-03-13: 0; 2019-03-14: 0; 2019-03-15: 0; 2019-03-18: 0
#REF! | #REF! | #REF! | #REF! | 2019-03-11: #REF!; 2019-03-12: 0; 2019-03-13: 0; 2019-03-14: 0; 2019-03-15: 0; 2019-03-18: 0
#REF! | #REF! | #REF! | #REF! | 2019-03-11: #REF!; 2019-03-12: 0; 2019-03-13: 0; 2019-03-14: 0; 2019-03-15: 0; 2019-03-18: 0
#REF! | #REF! | #REF! | #REF! | 2019-03-12: #REF!; 2019-03-13: 10; 2019-03-14: 3; 2019-03-15: 1; 2019-03-18: 0
#REF! | #REF! | #REF! | #REF! | 2019-03-12: #REF!; 2019-03-13: 8; 2019-03-14: 4; 2019-03-15: 1; 2019-03-18: 0
#REF! | #REF! | #REF! | #REF! | 2019-03-12: #REF!; 2019-03-13: 6; 2019-03-14: 3; 2019-03-15: 1; 2019-03-18: 0
#REF! | #REF! | #REF! | #REF! | 2019-03-12: #REF!; 2019-03-13: 8; 2019-03-14: 0; 2019-03-15: 0; 2019-03-18: 0
#REF! | #REF! | #REF! | #REF! | 2019-03-14: #REF!; 2019-03-15: 5; 2019-03-18: 0
#REF! | #REF! | #REF! | #REF! | 2019-03-14: #REF!; 2019-03-15: 3; 2019-03-18: 0
#REF! | #REF! | #REF! | #REF! | 2019-03-14: #REF!; 2019-03-15: 5; 2019-03-18: 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成第12期工作——Rig Board第三期，Resource和Calendar
StartDate | 2019-03-01
EndDate | 2019-03-29
Est Time
Name | Role | Total Hours | 2019-03-01 | 2019-03-04 | 2019-03-05 | 2019-03-06 | 2019-03-07 | 2019-03-08 | 2019-03-11 | 2019-03-12 | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29
|  |  | 43525 | 43528 | 43529 | 43530 | 43531 | 43532 | 43535 | 43536 | 43537 | 43538 | 43539 | 43542 | 43543 | 43544 | 43545 | 43546 | 43549 | 43550 | 43551 | 43552 | 43553
Ideal Burndown |  | 380 | 364 | 361 | 342 | 323 | 304 | 285 | 266 | 247 | 228 | 209 | 190 | 171 | 152 | 133 | 114 | 95 | 76 | 57 | 38 | 19 | 0
Hours consumed |  | 380 | 16 | 3 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
Bella.Bi |  | 60 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Olivia.Ge |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bright.Liu |  | 160 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Colin.Ji |  | 160 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Kevin.Wu |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Niki.Wang

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase12.P001 | Meeting-Phase 12 | 1000 | 40 | 1 | All | 37.5
Phase12.P002 | Project management | 1000 | 20 | 1 | Bella.bi | 2
Phase12.S001 | Analysis requirements | 1000 | 20 | 1 | Bella.bi | 0
Phase12.I003 | Entry CIM model in MDD | 950 | 8 | 1 | Bright.Liu | 13
Phase12.I006 | Integrate generated projects into Online | 950 | 12 | 1 | Bright.Liu | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Phase12.I009 | Update reference between several projects | 920 | 10 | 1 | Bright.Liu | 0
Phase12.I010 | Update database upgrade script | 920 | 6 | 1 | Bright.Liu | 2
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Refactor.T001 | eService Online Test | 800 | 8 | 1 | Bright.Liu | 7.5
Refactor.T002 | eService Online Test | 800 | 8 | 1 | Colin.Ji | 7.5
Refactor.T003 | Resolve chart printing issue | 800 | 3 | 1 | Olivia.Ge | 3
Refactor.T004 | Update RigJob Domain Model | 800 | 6 | 1 | Bright.Liu | 5.5
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Refactor.T007 | Analyzing entity dependencies for RigJob | 800 | 12 | 1 | Colin.Ji | 11
Refactor.T008 | Update migration entities document | 800 | 3 | 1 | Bright.Liu | 3
Refactor.T009 | Update RigJob Design Model | 750 | 16 | 1 | Bright.Liu | 15.5
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间