## Daily Records
ID | Name | Prioritize | Est(Hour) | 2019-03-31 | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | 2019-04-26 | 2019-04-28 | 2019-04-29 | 2019-04-30 | Total Hours
|  |  |  | 43555 | 43556 | 43557 | 43558 | 43559 | 43563 | 43564 | 43565 | 43566 | 43567 | 43570 | 43571 | 43572 | 43573 | 43574 | 43577 | 43578 | 43579 | 43580 | 43581 | 43583 | 43584 | 43585
| Ideal Burndown |  | 399 | 399 | 383 | 380 | 361 | 342 | 323 | 304 | 285 | 266 | 247 | 228 | 209 | 190 | 171 | 152 | 133 | 114 | 95 | 76 | 57 | 38 | 19 | 0 | 362
| Actual |  | 353 | 399 | 382 | 366 | 350 | 342 | 321 | 312 | 312 | 300.5 | 292 | 273 | 256.5 | 253.5 | 239 | 235 | 222 | 214 | 203.5 | 196.5 | 184 | 166.5 | 160 | 150
|  |  |  | 0 | 17 | 16 | 16 | 8 | 21 | 9 | 0 | 11.5 | 8.5 | 19 | 16.5 | 19.5 | 17.5 | 18.5 | 17 | 21 | 18.5 | 17.5 | 19.5 | 30 | 24 | 16.5 | 362 | Assign to | Completion Status | Pay by | Module
Phase12.P001 | Meeting-Phase 12 | 1000 | 40 |  | 2 | 1 | 1 | 1 | 1 | 2 |  | 1.5 | 1 | 9 | 1.5 | 1.5 | 1.5 | 7.5 | 3 | 3 | 1.5 | 3 | 4.5 | 1.5 | 4.5 | 1.5 | 54 | All | 0 | Sanjel | Online
Phase12.P002 | Project management | 1000 | 20 | 2019-04-18: 1; 2019-04-23: 2; 2019-04-24: 1; 2019-04-25: 3; 2019-04-26: 2; 2019-04-28: 2; 2019-04-29: 2 | 13 | Bella.bi | 0 | Sanjel | Online
Phase12.S001 | Analysis requirements | 1000 | 20 | 2019-04-17: 3; 2019-04-23: 2; 2019-04-24: 1 | 6 | Bella.bi | 0 | Sanjel | Online
Phase12.I003 | Update CIM model in MDD | 950 | 10 | 2019-04-08: 3; 2019-04-09: 1.5; 2019-04-22: 0.5; 2019-04-23: 1; 2019-04-24: 0.5 | 6.5 | Bright.Liu | 0 | Sanjel | Online
Phase12.I009 | Upgrade SanjelData and eServiceMDM | 920 | 10 | 2019-04-04: 1; 2019-04-11: 4; 2019-04-18: 1.5; 2019-04-30: 1 | 7.5 | Bright.Liu | 0 | Sanjel | Online
Phase12.I010 | Update database upgrade script | 920 | 16 | 2019-04-04: 2; 2019-04-08: 4; 2019-04-09: 2.5; 2019-04-11: 0.5; 2019-04-22: 0.5; 2019-04-23: 1; 2019-04-24: 0.5 | 11 | Bright.Liu | 0 | Sanjel | Online
Phase12.D001 | Update domain model | 900 | 8 | 2019-04-02: 3.5; 2019-04-23: 1 | 4.5 | Bright.Liu | 0 | Sanjel | Online
Refactor.T001 | eService Online Test | 800 | 8 | 2019-04-03: 7.5; 2019-04-17: 7.5; 2019-04-18: 5.5 | 20.5 | Colin.Ji | 1 | Sanjel | Online
Refactor.T002 | eService Online Test | 800 | 8 | 2019-04-03: 7.5; 2019-04-04: 4; 2019-04-17: 7.5; 2019-04-18: 5; 2019-04-30: 6.5 | 30.5 | Bright.Liu | 1 | Sanjel | Online
Refactor.T003 | Update sql script | 750 | 8 | 2019-04-01: 2; 2019-04-02: 2; 2019-04-29: 1 | 5 | Bright.Liu | 1 | Sanjel | Online
Refactor.T005 | Cancel Product Haul | 750 | 3 | 2019-04-01: 2; 2019-04-29: 1 | 3 | Colin.Ji | 1 | Sanjel | Online
Refactor.T006 | On Location Product Haul | 750 | 3 | 2019-04-01: 2 | 2 | Colin.Ji | 1 | Sanjel | Online
Refactor.T007 | View Product haul list | 750 | 4 | 2019-04-01: 3.5 | 3.5 | Bright.Liu | 1 | Sanjel | Online
Refactor.T008 | Print load sheet | 750 | 3 | 2019-04-01: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
Refactor.T010 | Refactoring Re-Schedule ProductHaulLoad | 750 | 12 | 2019-04-23: 4.5; 2019-04-24: 2; 2019-04-29: 2 | 8.5 | Colin.Ji | 1 | Sanjel | Online
Refactor.T011 | Remove a bin | 750 | 3 | 2019-04-02: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
Refactor.T012 | Integrate RigJob in Eservice | 720 | 10 | 2019-04-08: 6; 2019-04-12: 7.5; 2019-04-15: 2 | 15.5 | Colin.Ji | 1 | Sanjel | Online
Refactor.T013 | Get new data from the generated project | 720 | 16 | 2019-04-15: 3; 2019-04-16: 9 | 12 | Colin.Ji | 1 | Sanjel | Online
Refactor.T014 | Refactoring UnitSection/ThirdPartyUnitSection | 720 | 10 | 2019-04-08: 7 | 7 | Colin.Ji | 1 | Sanjel | Online
Refactor.T015 | Display Unit/Crew in Upcoming Jobs | 720 | 5 | 2019-04-09: 3; 2019-04-11: 3 | 6 | Bright.Liu | 1 | Sanjel | Online
Refactor.T016 | Refactoring ObjectUtitlity | 720 | 1 | [23 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-04-11
Refactor.T017 | Refactoring RigBinSection Logic | 720 | 2 | 2019-04-11: 1.5 | 1.5 | Colin.Ji | 1 | Sanjel | Online
Refactor.T018 | Update deployment scripts | 700 | 16 | 2019-04-15: 5; 2019-04-16: 6; 2019-04-18: 1 | 12 | Bright.Liu | 1 | Sanjel | Online
Refactor.T019 | Display Unit and driver on Product Hauls Page | 700 | 2 | 2019-04-18: 2 | 2 | Colin.Ji | 1 | Sanjel | Online
Ticket #603 | Schedule Product Haul | 680 | 4 | 2019-04-01: 3.5; 2019-04-19: 4.5; 2019-04-23: 3; 2019-04-24: 2; 2019-04-26: 2.5; 2019-04-29: 2 | 17.5 | Colin.Ji | 1 | Sanjel | Online
Ticket #605 | Reschedule product haul | 680 | 8 | 2019-04-02: 7.5; 2019-04-23: 2; 2019-04-24: 2; 2019-04-25: 1; 2019-04-26: 3; 2019-04-28: 1; 2019-04-29: 3 | 19.5 | Colin.Ji | 1 | Sanjel | Online
Ticket #600 | Display Crew in Rig board | 680 | 6 | 2019-04-24: 6.5; 2019-04-25: 2.5 | 9 | Bright.Liu | 1 | Sanjel | Online
Ticket #597 | Filter by service point | 650 | 8 | 2019-04-19: 1; 2019-04-22: 5; 2019-04-23: 1.5 | 7.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #596 | Add a worker/unit to crew | 650 | 4 | 2019-04-22: 4 | 4 | Bright.Liu | 1 | Sanjel | Online
Ticket #606 | Assign a crew to a job | 650 | 4 | 2019-04-19: 2.5; 2019-04-26: 1 | 3.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #448 | View crew list in crew board | 650 | 2 | 2019-04-19: 2; 2019-04-25: 1 | 3 | Bright.Liu | 1 | Sanjel | Online
Ticket #607 | Add a remarkable Test sign on the right end of top menu bar for testing versions | 650 | 1 | [23 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-04-19
Ticket #598 | Display job info in crew board | 600 | 7 | 2019-04-22: 4; 2019-04-24: 1.5; 2019-04-25: 6; 2019-04-26: 3.5 | 15 | Colin.Ji | 1 | Sanjel | Online
Ticket #609 | Add ratation column in CrewBoard | 600 | 4 | 2019-04-25: 1; 2019-04-26: 3 | 4 | Bright.Liu | 1 | Sanjel | Online
Ticket #581 | Handling schedule conflicts_functions implementation | 600 | 6 | 2019-04-28: 5 | 5 | Bright.Liu | 1 | Sanjel | Online
Ticket #612 | Handling schedule conflicts_in Rig board | 600 | 16 | 2019-04-28: 11.5; 2019-04-29: 3 | 14.5 | Bright&Colin | 1 | Sanjel | Online
Ticket #613 | Handling schedule conflicts_in Calendar&Resource | 600 | 10 | 2019-04-28: 6.5; 2019-04-29: 1.5 | 8 | Colin.Ji | 1 | Sanjel | Online
Ticket #601 | Integrated from eService to Online | 550 | 16 | 2019-04-29: 4; 2019-04-30: 7.5 | 11.5 | Colin.Ji | 0 | Sanjel | eService
Ticket #611 | Update notes in board | 550 | 16 | [23 empty] | 0 |  | 0 | Sanjel | Online
Phase12.D002 | Design for Note | 550 | 3 | 2019-04-28: 2.5 | 2.5 | Bessie.yin | 1 | Sanjel | Online
Resolve the slow loading problem in rigjob list
Note on O6: bin liu: 讨论、分析新需求
Note on S6: bin liu:讨论、分析需求
Note on Z6: Bella Bi: 跟Adam讨论问题：crew对应的RigJob的获取方式
Note on Z16: Bella Bi: Bright 由于RigJobSanjelCrewSection增加了ProductHaulID，所以查询的逻辑需要修改
Note on U20: bin liu: Colin 3h Bright 1.5h
Note on Z20: Bella Bi: Bright 由于RigJobSanjelCrewSection增加了ProductHaulID，所以查询的逻辑需要修改
Note on N22: bin liu: Bright
Note on P23: bin liu: Colin 7.5h Bright 1.5h
Note on U30: bin liu: Colin 2h Bright 1h
Note on X30: Bella Bi: Bright
Note on Z30: Bella Bi: Bright 由于RigJobSanjelCrewSection增加了ProductHaulID，所以查询的逻辑需要修改
Note on Z31: Bella Bi: Bright 由于RigJobSanjelCrewSection增加了ProductHaulID，所以查询的逻辑需要修改
Note on Y41: Bella Bi: Bright 6.5h Colin 5h
Note on Z41: Bella Bi: Colin
Note on D43: Bella Bi: 需要再分析和细分任务

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2019-03-31 | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | 2019-04-26 | 2019-04-28 | 2019-04-29 | 2019-04-30
|  |  |  | 43555 | 43556 | 43557 | 43558 | 43559 | 43563 | 43564 | 43565 | 43566 | 43567 | 43570 | 43571 | 43572 | 43573 | 43574 | 43577 | 43578 | 43579 | 43580 | 43581 | 43583 | 43584 | 43585
| Ideal Burndown |  | 399 | 399 | 383 | 380 | 361 | 342 | 323 | 304 | 285 | 266 | 247 | 228 | 209 | 190 | 171 | 152 | 133 | 114 | 95 | 76 | 57 | 38 | 19 | 0
| Actual burndown |  | 324 | 173 | 173 | 142 | 113 | 109 | 100 | 98 | 92 | 88 | 88 | 82 | 74 | 69 | 69 | 69 | 69 | 69 | 69 | 28 | 17 | 17 | 17 | 17
Phase12.P001 | Meeting-Phase 12 | 1000 | 40 | 40 | 40 | 40 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Phase12.P002 | Project management | 1000 | 20 | 20 | 20 | 20 | 13 | 12 | 10 | 8 | 6 | 5 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Phase12.S001 | Analysis requirements | 1000 | 20 | 20 | 20 | 13 | 11 | 10 | 8 | 8 | 6 | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase12.I003 | Update CIM model in MDD | 950 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 2 | 2 | 2 | 2 | 2
Phase12.I009 | Upgrade SanjelData and eServiceMDM | 920 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 2 | 2 | 2 | 2 | 2
Phase12.I010 | Update database upgrade script | 920 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 2 | 2 | 2 | 2 | 2
Phase12.D001 | Update domain model | 900 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2
Refactor.T001 | eService Online Test | 800 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0
Refactor.T002 | eService Online Test | 800 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0
Refactor.T003 | Update sql script | 750 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8
Refactor.T005 | Cancel Product Haul | 750 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
Refactor.T006 | On Location Product Haul | 750 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refactor.T007 | View Product haul list | 750 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refactor.T008 | Print load sheet | 750 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refactor.T010 | Refactoring Re-Schedule ProductHaulLoad | 750 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refactor.T011 | Remove a bin | 750 | 3 | 2019-04-25: 0
Refactor.T012 | Integrate RigJob in Eservice | 720 | 10 | 2019-04-25: 0
Refactor.T013 | Get new data from the generated project | 720 | 16 | 2019-04-25: 0
Refactor.T014 | Refactoring UnitSection/ThirdPartyUnitSection | 720 | 10 | 2019-04-25: 0
Refactor.T015 | Display Unit/Crew in Upcoming Jobs | 720 | 5 | 2019-04-25: 0
Refactor.T016 | Refactoring ObjectUtitlity | 720 | 1 | 2019-04-25: 0
Refactor.T017 | Refactoring RigBinSection Logic | 720 | 2 | 2019-04-25: 0
Refactor.T018 | Update deployment scripts | 700 | 16 | 2019-04-25: 0
Refactor.T019 | Display Unit and driver on Product Hauls Page | 700 | 2 | 2019-04-25: 0
Ticket #603 | Schedule Product Haul | 680 | 4 | 2019-04-25: 0
Ticket #605 | Reschedule product haul | 680 | 8 | 2019-04-25: 0
Ticket #600 | Display Crew in Rig board | 680 | 6 | 2019-04-25: 0
Ticket #597 | Filter by service point | 650 | 8 | 2019-04-25: 4
Ticket #596 | Add a worker/unit to crew | 650 | 4
Ticket #606 | Assign a crew to a job | 650 | 4 | bar: 2019-04-25
Ticket #448 | View crew list in crew board | 650 | 2
Ticket #607 | Add a remarkable Test sign on the right end of top menu bar for testing versions | 650 | 1
Ticket #598 | Display job info in crew board | 600 | 7 | 2019-04-25: 4
Ticket #609 | Add ratation column in CrewBoard | 600 | 4 | 2019-04-25: 3
Ticket #581 | Handling schedule conflicts_functions implementation | 600 | 6 | 2019-04-25: 16
Ticket #601 | Integrated from eService to Online | 550 | 16 | 2019-04-25: 16
Ticket #611 | Update notes in board | 550 | 16 | 2019-04-17: 0; 2019-04-18: 0; 2019-04-19: 0; 2019-04-22: 0; 2019-04-23: 0; 2019-04-24: 0; 2019-04-25: 16; 2019-04-26: 0; 2019-04-28: 0; 2019-04-29: 0; 2019-04-30: 0
0 | Resolve the slow loading problem in rigjob list | 0 | 0 | 2019-04-17: 0; 2019-04-18: 0; 2019-04-19: 0; 2019-04-22: 0; 2019-04-23: 0; 2019-04-24: 0; 2019-04-25: 0; 2019-04-26: 0; 2019-04-28: 0; 2019-04-29: 0; 2019-04-30: 0
0 | 0 | 0 | 0 | 2019-04-17: 0; 2019-04-18: 0; 2019-04-19: 0; 2019-04-22: 0; 2019-04-23: 0; 2019-04-24: 0; 2019-04-25: 0; 2019-04-26: 0; 2019-04-28: 0; 2019-04-29: 0; 2019-04-30: 0
0 | 0 | 0 | 0 | 2019-04-17: 0; 2019-04-18: 0; 2019-04-19: 0; 2019-04-22: 0; 2019-04-23: 0; 2019-04-24: 0; 2019-04-25: 0; 2019-04-26: 0; 2019-04-28: 0; 2019-04-29: 0; 2019-04-30: 0
0 | 0 | 0 | 0 | 2019-04-17: 0; 2019-04-18: 0; 2019-04-19: 0; 2019-04-22: 0; 2019-04-23: 0; 2019-04-24: 0; 2019-04-25: 0; 2019-04-26: 0; 2019-04-28: 0; 2019-04-29: 0; 2019-04-30: 0
0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成第12期工作——Rig Board第三期，Resource和Calendar
StartDate | 2019-04-01
EndDate | 2019-04-30
Est Time
Name | Role | Total Hours | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | 2019-04-26 | 2019-04-28 | 2019-04-29 | 2019-04-30
|  |  | 43556 | 43557 | 43558 | 43559 | 43563 | 43564 | 43565 | 43566 | 43567 | 43570 | 43571 | 43572 | 43573 | 43574 | 43577 | 43578 | 43579 | 43580 | 43581 | 43583 | 43584 | 43585
Ideal Burndown |  | 399 | 383 | 380 | 361 | 342 | 323 | 304 | 285 | 266 | 247 | 228 | 209 | 190 | 171 | 152 | 133 | 114 | 95 | 76 | 57 | 38 | 19 | 0
Hours consumed |  | 399 | 16 | 3 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
Bella.Bi |  | 63 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Olivia.Ge |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bright.Liu |  | 168 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Colin.Ji |  | 168 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Kevin.Wu |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Niki.Wang

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase12.P001 | Meeting-Phase 12 | 1000 | 40 | 0 | All | 54
Phase12.P002 | Project management | 1000 | 20 | 0 | Bella.bi | 13
Phase12.S001 | Analysis requirements | 1000 | 20 | 0 | Bella.bi | 6
Phase12.I003 | Update CIM model in MDD | 950 | 10 | 0 | Bright.Liu | 6.5
Phase12.I009 | Upgrade SanjelData and eServiceMDM | 920 | 10 | 0 | Bright.Liu | 7.5
Phase12.I010 | Update database upgrade script | 920 | 16 | 0 | Bright.Liu | 11
Phase12.D001 | Update domain model | 900 | 8 | 0 | Bright.Liu | 4.5
Refactor.T001 | eService Online Test | 800 | 8 | 1 | Colin.Ji | 20.5
Refactor.T002 | eService Online Test | 800 | 8 | 1 | Bright.Liu | 30.5
Refactor.T003 | Update sql script | 750 | 8 | 1 | Bright.Liu | 5
Refactor.T005 | Cancel Product Haul | 750 | 3 | 1 | Colin.Ji | 3
Refactor.T006 | On Location Product Haul | 750 | 3 | 1 | Colin.Ji | 2
Refactor.T007 | View Product haul list | 750 | 4 | 1 | Bright.Liu | 3.5
Refactor.T008 | Print load sheet | 750 | 3 | 1 | Bright.Liu | 2
Refactor.T010 | Refactoring Re-Schedule ProductHaulLoad | 750 | 12 | 1 | Colin.Ji | 8.5
Refactor.T011 | Remove a bin | 750 | 3 | 1 | Bright.Liu | 2
Refactor.T012 | Integrate RigJob in Eservice | 720 | 10 | 1 | Colin.Ji | 15.5
Refactor.T013 | Get new data from the generated project | 720 | 16 | 1 | Colin.Ji | 12
Refactor.T014 | Refactoring UnitSection/ThirdPartyUnitSection | 720 | 10 | 1 | Colin.Ji | 7
Refactor.T015 | Display Unit/Crew in Upcoming Jobs | 720 | 5 | 1 | Bright.Liu | 6
Refactor.T016 | Refactoring ObjectUtitlity | 720 | 1 | 1 | Colin.Ji | 1
Refactor.T017 | Refactoring RigBinSection Logic | 720 | 2 | 1 | Colin.Ji | 1.5
Refactor.T018 | Update deployment scripts | 700 | 16 | 1 | Bright.Liu | 12
Refactor.T019 | Display Unit and driver on Product Hauls Page | 700 | 2 | 1 | Colin.Ji | 2
Ticket #603 | Schedule Product Haul | 680 | 4 | 1 | Colin.Ji | 17.5
Ticket #605 | Reschedule product haul | 680 | 8 | 1 | Colin.Ji | 19.5
Ticket #600 | Display Crew in Rig board | 680 | 6 | 1 | Bright.Liu | 9
Ticket #597 | Filter by service point | 650 | 8 | 1 | Bright.Liu | 7.5
Ticket #596 | Add a worker/unit to crew | 650 | 4 | 1 | Bright.Liu | 4
Ticket #606 | Assign a crew to a job | 650 | 4 | 1 | Bright.Liu | 3.5
Ticket #448 | View crew list in crew board | 650 | 2 | 1 | Bright.Liu | 3
Ticket #607 | Add a remarkable Test sign on the right end of top menu bar for testing versions | 650 | 1 | 1 | Colin.Ji | 1
Ticket #598 | Display job info in crew board | 600 | 7 | 1 | Colin.Ji | 15
Ticket #609 | Add ratation column in CrewBoard | 600 | 4 | 1 | Bright.Liu | 4
Ticket #581 | Handling schedule conflicts_functions implementation | 600 | 6 | 1 | Bright.Liu | 5
Ticket #601 | Integrated from eService to Online | 550 | 16 | 0 | Colin.Ji | 11.5
Ticket #611 | Update notes in board | 550 | 16 | 0 | 0 | 0
0 | Resolve the slow loading problem in rigjob list | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间