## Daily Records
ID | Name | Prioritize | Est(Hour) | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10 | 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | Total Hours
|  |  |  | 43589 | 43590 | 43591 | 43592 | 43593 | 43594 | 43595 | 43598 | 43599 | 43600 | 43601 | 43602 | 43605 | 43606 | 43607 | 43608 | 43609 | 43612 | 43613 | 43614 | 43615 | 43616
| Ideal Burndown |  | 440 | 440 | 420 | 397 | 374 | 351 | 328 | 305 | 282 | 259 | 236 | 213 | 190 | 171 | 152 | 133 | 114 | 95 | 76 | 57 | 38 | 19 | 0 | 416.5
| Actual |  | 395 | 440 | 422.5 | 401 | 379.5 | 356.5 | 333 | 297.5 | 262 | 235 | 204 | 182.5 | 158.5 | 158.5 | 132 | 130 | 116.5 | 128.5 | 107.5 | 108.5 | 101.5 | 108.5 | 101.5
|  |  |  | 0 | 17.5 | 21.5 | 21.5 | 23 | 23.5 | 35.5 | 35.5 | 27 | 31 | 21.5 | 24 | 24 | 26.5 | 28.5 | 15.5 | 1.5 | 9 | 20 | 6 | 0 | 0 | 416.5 | Assign to | Completion Status | Pay by | Module
Phase12.P001 | Meeting-Phase 12 | 1000 | 50 |  | 2 | 1.5 | 1 | 1 | 1.5 | 1.5 | 2.5 | 1.5 | 1.5 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 20 | All | 0 | Sanjel | Online
Phase12.P002 | Project management | 1000 | 16 | 2019-05-05: 2; 2019-05-06: 1 | 3 | Bella.bi | 0 | Sanjel | Online
Phase12.S001 | Analysis requirements | 1000 | 16 | [22 empty] | 0 | Bella.bi | 0 | Sanjel | Online
Phase12.I003 | Update CIM model in MDD | 950 | 8 | [22 empty] | 0 | Bright.Liu | 0 | Sanjel | Online
Phase12.I009 | Upgrade SanjelData and eServiceMDM | 950 | 8 | 2019-05-05: 3; 2019-05-08: 3; 2019-05-13: 1; 2019-05-14: 1; 2019-05-28: 1 | 9 | Bright.Liu | 0 | Sanjel | Online
Phase12.I010 | Update database upgrade script | 950 | 10 | 2019-05-05: 1.5; 2019-05-07: 1; 2019-05-08: 1.5; 2019-05-09: 1.5; 2019-05-14: 1.5 | 7 | Bright.Liu | 0 | Sanjel | Online
Phase12.D001 | Update domain model | 950 | 8 | [22 empty] | 0 | Bright.Liu | 0 | Sanjel | Online
Phase12.D002 | Add OnlineDesignModel | 900 | 1 | 2019-05-24: 1; 2019-05-27: 2.5 | 3.5 | Bright.Liu | 1 | Sanjel | Online
Phase12.S002 | Update Data dictionary | 850 | 3 | 2019-05-27: 1; 2019-05-28: 7.5 | 8.5 | Joe.huang | 0 | Sanjel | Online
| Merge branch code | 900 | 1 | 2019-05-27: 1; 2019-05-28: 6.5 | 1 | Bright.Liu | 1 | Sanjel | Online
Refactor.T001 | eService Online Test | 950 | 8 | 2019-05-07: 4; 2019-05-10: 1; 2019-05-13: 3.5; 2019-05-15: 15; 2019-05-16: 1 | 24.5 | Colin.Ji | 0 | Sanjel | Online
Refactor.T002 | Refactoring Update/Delete Schedule | 950 | 2 | 2019-05-08: 2 | 2 | Bright.Liu | 0 | Sanjel | Online
Refactor.T003 | Re-Schedule Product Haul | 900 | 2 | 2019-05-09: 2 | 2 | Colin.Ji | 1 | Sanjel | Online
Refactor.T004 | Re-Schedule Product Haul Load | 900 | 2 | 2019-05-09: 2 | 2 | Colin.Ji | 1 | Sanjel | Online
Refactor.T005 | Assign a crew to a job | 900 | 2 | 2019-05-09: 2 | 2 | Colin.Ji | 1 | Sanjel | Online
Refactor.T006 | Refactoring eServiceOnlineGateway | 900 | 4 | 2019-05-14: 3.5 | 3.5 | Colin.Ji | 1 | Sanjel | Online
Refactor.T007 | Refactoring Enumeration | 950 | 16 | 2019-05-22: 15 | 15 | Colin&Bright | 1 | Sanjel | Online
Ticket #614 | Update a Crew_on Third party crew board | 930 | 2 | 2019-05-05: 2 | 2 | Colin.Ji | 1 | Sanjel | Online
Ticket #616 | Remove a Crew_on Third party crew board | 930 | 2 | 2019-05-05: 2 | 2 | Colin.Ji | 1 | Sanjel | Online
Ticket #251 | Update Dispatched/In-Progress Rig Job Date Time(Postpone) | 930 | 1 | [22 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-05-05
Ticket #606 | Assign a crew to a job | 930 | 1 | 2019-05-05: 1.5 | 1.5 | Bright.Liu | 1 | Sanjel | Online
Ticket #598 | Display job info in crew board | 930 | 3 | 2019-05-05: 0.5; 2019-05-06: 2 | 2.5 | Colin.Ji | 1 | Sanjel | Online
Ticket #612 | Handling schedule conflicts_in Rig board | 930 | 2 | 2019-05-05: 2 | 2 | Colin.Ji | 1 | Sanjel | Online
Ticket #611 | Update notes in board | 900 | 16 | 2019-05-06: 5.5; 2019-05-08: 4.5; 2019-05-21: 1 | 11 | Colin.Ji | 1 | Sanjel | Online
Ticket #454 | Check productHaul when assgin A crew | 900 | 4 | 2019-05-10: 3 | 3 | Colin.Ji | 1 | Sanjel | Online
Ticket #545 | Check productHaul when Adjust Job Duration | 900 | 4 | 2019-05-10: 2.5 | 2.5 | Colin.Ji | 1 | Sanjel | Online
Ticket #536 | update worker profile | 900 | 3 | 2019-05-10: 1; 2019-05-13: 3 | 4 | Colin.Ji | 1 | Sanjel | Online
Phase12.E001 | Update deployment scripts | 900 | 8 | 2019-05-13: 6; 2019-05-14: 1 | 7 | Bright.Liu | 0 | Sanjel | Online
Ticket #121 | Update Job Alert | 900 | 3 | 2019-05-14: 3 | 3 | Colin.Ji | 1 | Sanjel | Online
Phase12.I011 | Update Rig Board detailed documentation | 900 | 4 | 2019-05-14: 3 | 3 | Colin.Ji | 1 | Sanjel | Online
Ticket #451 | Refactoring add a crew | 900 | 4 | 2019-05-17: 4 | 4 | Colin.Ji | 1 | Sanjel | Online
Ticket #620 | View Rig's Future Job | 900 | 5 | 2019-05-20: 5 | 5 | Bright.Liu | 1 | Sanjel | Online
Ticket #621 | Add BinBoard in Online system | 950 | 5 | 2019-05-21: 5; 2019-05-27: 4 | 5 | Bright.Liu | 1 | Sanjel | Online
Ticket #645 | Display Plug Loading Head Board | 850 | [24 empty] | Bright.Liu | 0 | Sanjel | Online
Ticket #646 | Assign an equipment to a Crew - Plug Loading Head | 850 | [24 empty] | Bright.Liu | 0 | Sanjel | Online
Ticket #647 | Return an Equipment from a crew - Plug Loading Head | 850 | [24 empty] | Bright.Liu | 0 | Sanjel | Online
Ticket #648 | Assign an Equipment to another district - Plug Loading Head | 850 | [24 empty] | Bright.Liu | 0 | Sanjel | Online
| Test for eService Online | 900 | 15 | 2019-05-23: 15; 2019-05-28: 4.5; 2019-05-29: 5.5 | 15 | Bright&Colin | 1 | Sanjel | Online
Bug #001 | Reschedule Rig Job | 900 | 4 | 2019-05-07: 3 | 3 | Colin.Ji | 1 | Sanjel | Online
Bug #002 | Update Well Location | 900 | 1 | [22 empty] | 1 | Colin.Ji | 1 | Sanjel | Online | bar: 2019-05-07
Bug #003 | Update RigStatus and ClientCompany ShortName | 900 | 2 | [22 empty] | 1 | Bright.Liu | 1 | Sanjel | Online | bar: 2019-05-07
Bug #004 | Schedule Product Haul | 900 | 6 | 2019-05-08: 3; 2019-05-09: 1.5 | 4.5 | Colin.Ji | 1 | Sanjel | Online
Bug #005 | Fix for Servie Point not working on Resource Board | 900 | 1 | [22 empty] | 1 | Bright.Liu | 1 | Sanjel | Online | bar: 2019-05-10
Bug #006 | Functional stability of add a crew | 950 | 5 | 2019-05-24: 3 | 3 | Bright.Liu | 1 | Sanjel | Online
Bug #007 | The add a crew updates the problem multiple times | 950 | 2 | 2019-05-24: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
MDD.T001 | Enum template example | 900 | 8 | 2019-05-06: 5 | 5 | Bright.Liu | 1 | MetaShare | MDD
MDD.T002 | Implement for Enum_backend | 900 | 12 | 2019-05-06: 1.5; 2019-05-08: 1; 2019-05-10: 5; 2019-05-13: 1.5; 2019-05-15: 7.5; 2019-05-16: 6 | 22.5 | Bela&Bright | 0 | MetaShare | MDD
MDD.T003 | Implement for Enum_frontend | 900 | 16 | 2019-05-13: 4.5; 2019-05-14: 6 | 10.5 | Bela.Zhao | 0 | MetaShare | MDD
MDD.T004 | CimToPimTransform，PimToPsmTransform，PsmToDatabaseScriptTransform | 900 | 12 | 2019-05-10: 6; 2019-05-13: 3; 2019-05-16: 2; 2019-05-21: 4 | 15 | Bela.Zhao | 1 | MetaShare | MDD
MDD.T005 | Modify MDD Enum template example | 900 | 16 | 2019-05-13: 7.5; 2019-05-14: 4; 2019-05-16: 6.5; 2019-05-17: 7.5; 2019-05-20: 8 | 33.5 | Bessie&Bright | 0 | MetaShare | MDD
MDD.T006 | Modify modified_user_id data type | 900 | 8 | 2019-05-07: 5.5 | 5.5 | Bright.Liu | 1 | MetaShare | MDD
MDD.T007 | Add Name and Description for non-versioned entity | 900 | 16 | 2019-05-09: 6; 2019-05-14: 2 | 8 | Bright.Liu | 1 | MetaShare | MDD
MDD.T008 | Parse column name endwith id or Id | 900 | 3 | 2019-05-10: 3 | 3 | Bela&Bright | 1 | MetaShare | MDD
MDD.T009 | Add multi-properties's id query interface | 900 | 16 | 2019-05-09: 2.5; 2019-05-10: 8 | 10.5 | Bessie.yin | 1 | MetaShare | MDD
MDD.T010 | Extend for Service and Webapi | 850 | 16 | 2019-05-20: 2; 2019-05-21: 1; 2019-05-22: 7.5; 2019-05-23: 8; 2019-05-29: 2 | 20.5 | Bessie.yin | 0 | MetaShare | MDD
MDD.T011 | Test for MDD new function | 850 | 12 | 2019-05-17: 5; 2019-05-20: 2.5; 2019-05-21: 7.5; 2019-05-22: 2; 2019-05-23: 2; 2019-05-24: 3.5 | 22.5 | Bela.Zhao | 0 | MetaShare | MDD
Resolve the slow loading problem in rigjob list
Rests | Familiar with requirement Sanjel |  |  |  |  | 5 | 5 | 7 | 4.5 | 3.5 | 3 | 0.5 | 7 | 5 | 7 | 5.5 | 7.5 | 3.5 | 2 | 2 | [5 empty] | 68 | Joe.huang | 1 | MetaShare
Note on G7: bin liu: bright
Note on B9: Bella Bi: RigJobSanjelCrewSection需要加上版本控制
Note on L10: bin liu: colin
Note on W14: joe.huang: Joe:4.5h Conlin:3h
Note on W15: joe.huang: Bright:5h Conlin:1.5h
Note on N16: bin liu: colin 7.5h bright 7.5h
Note on M21: bin liu: colin 2.5h bright 1h
Note on S22: joe.huang: Bright：7.5h Colin：7.5h
Note on B25: Bella Bi: Postpone时不显示Company信息
Note on B26: Bella Bi: 加验证条件：不能将同一个Crew分给一个Job两次
Note on B27: Bella： 同时显示目前发生冲突的Job info信息
Note on B28: Bella Bi: 提示信息需要将两个Schedule的信息都显示出来
Note on R29: joe.huang: Bright
Note on M35: bin liu: colin 2h bright 1h
Note on T43: joe.huang: Bright:7.5h Conlin:7.5h
Note on W43: joe.huang: Bright:1.5h Conlin:3h
Note on X43: joe.huang: Bright
Note on N52: bin liu: bela
Note on O52: bin liu: bela
Note on O55: bin liu: bright
Note on P55: yu huang: bela：4h Bright：3.5h
Note on Q55: yu huang: Bela
Note on K58: bin liu: Bela 1.5h Bright 1.5h
Note on X60: joe.huang: Bright
Note on R61: joe.huang: Bela：4h Bright：1.5h Olivia：2h

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10 | 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | #REF!
|  |  |  | 43589 | 43590 | 43591 | 43592 | 43593 | 43594 | 43595 | 43598 | 43599 | 43600 | 43601 | 43602 | 43605 | 43606 | 43607 | 43608 | 43609 | 43612 | 43613 | 43614 | 43615 | 43616 | #REF!
| Ideal Burndown |  | 440 | 440 | 420 | 397 | 374 | 351 | 328 | 305 | 282 | 259 | 236 | 213 | 190 | 171 | 152 | 133 | 114 | 95 | 76 | 57 | 38 | 19 | 0 | #REF!
| Actual burndown |  | 319 | 192 | 192 | 192 | 560 | 504 | 364 | 364 | 308 | 280 | 280 | 168 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 0 | 0 | 0 | 0
Phase12.P001 | Meeting-Phase 12 | 1000 | 50 | 50 | 50 | 50 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Phase12.P002 | Project management | 1000 | 16 | 16 | 16 | 16 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Phase12.S001 | Analysis requirements | 1000 | 16 | 16 | 16 | 16 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Phase12.I003 | Update CIM model in MDD | 950 | 8 | 8 | 8 | 8 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Phase12.I009 | Upgrade SanjelData and eServiceMDM | 950 | 8 | 8 | 8 | 8 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Phase12.I010 | Update database upgrade script | 950 | 10 | 10 | 10 | 10 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Phase12.D001 | Update domain model | 950 | 8 | 8 | 8 | 8 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Refactor.T001 | eService Online Test | 950 | 8 | 8 | 8 | 8 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Refactor.T002 | Refactoring Update/Delete Schedule | 950 | 2 | 2 | 2 | 2 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Refactor.T003 | Re-Schedule Product Haul | 900 | 2 | 2 | 2 | 2 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Refactor.T004 | Re-Schedule Product Haul Load | 900 | 2 | 2 | 2 | 2 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Refactor.T005 | Assign a crew to a job | 900 | 2 | 2 | 2 | 2 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Ticket #614 | Update a Crew_on Third party crew board | 930 | 2 | 2 | 2 | 2 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Ticket #616 | Remove a Crew_on Third party crew board | 930 | 2 | 2 | 2 | 2 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Ticket #251 | Update Dispatched/In-Progress Rig Job Date Time(Postpone) | 930 | 1 | 1 | 1 | 1 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Ticket #606 | Assign a crew to a job | 930 | 1 | 1 | 1 | 1 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Ticket #598 | Display job info in crew board | 930 | 3 | 3 | 3 | 3 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Ticket #612 | Handling schedule conflicts_in Rig board | 930 | 2 | 2 | 2 | 2 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Ticket #611 | Update notes in board | 900 | 16 | 16 | 16 | 16 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Ticket #454 | Check productHaul when assgin A crew | 900 | 4 | 4 | 4 | 4 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Ticket #545 | Check productHaul when Adjust Job Duration | 900 | 4 | 4 | 4 | 4 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Ticket #536 | update worker profile | 900 | 3 | 3 | 3 | 3 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Bug #001 | Reschedule Rig Job | 900 | 4 | 4 | 4 | 4 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Bug #002 | Update Well Location | 900 | 1 | 1 | 1 | 1 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Bug #003 | Update RigStatus and ClientCompany ShortName | 900 | 2 | 2 | 2 | 2 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Bug #004 | Schedule Product Haul | 900 | 6 | 6 | 6 | 6 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
Bug #005 | Fix for Servie Point not working on Resource Board | 900 | 1 | 1 | 1 | 1 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
MDD.T001 | Enum template example | 900 | 8 | 8 | 8 | 8 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
MDD.T002 | Implement for Enum_backend | 900 | 12 | 12 | 12 | 12 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
MDD.T003 | Implement for Enum_frontend | 900 | 16 | 16 | 16 | 16 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
MDD.T004 | CimToPimTransform，PimToPsmTransform，PsmToDatabaseScriptTransform | 900 | 12 | 12 | 12 | 12 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
MDD.T005 | Modify MDD Enum template example | 900 | 16 | 16 | 16 | 16 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
MDD.T006 | Modify modified_user_id data type | 900 | 8 | 8 | 8 | 8 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
MDD.T007 | Add Name and Description for non-versioned entity | 900 | 16 | 16 | 16 | 16 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
MDD.T008 | Parse column name endwith id or Id | 900 | 3 | 3 | 3 | 3 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
MDD.T009 | Add multi-properties's id query interface | 900 | 16 | 16 | 16 | 16 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
MDD.T010 | Extend for Service and Webapi | 850 | 16 | 16 | 16 | 16 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
MDD.T011 | Test for MDD new function | 850 | 12 | 12 | 12 | 12 | 20 | 18 | 13 | 13 | 11 | 10 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
0 | Resolve the slow loading problem in rigjob list | 0 | 0 | 0 | 0 | 0 | 20 | 18 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成第12期工作——Rig Board第三期，Resource和Calendar
StartDate | 2019-05-05
EndDate | 2019-05-31
Est Time
Name | Role | Total Hours | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10 | 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31
|  |  | 43590 | 43591 | 43592 | 43593 | 43594 | 43595 | 43598 | 43599 | 43600 | 43601 | 43602 | 43605 | 43606 | 43607 | 43608 | 43609 | 43612 | 43613 | 43614 | 43615 | 43616
Ideal Burndown |  | 440 | 420 | 397 | 374 | 351 | 328 | 305 | 282 | 259 | 236 | 213 | 190 | 171 | 152 | 133 | 114 | 95 | 76 | 57 | 38 | 19 | 0
Hours consumed |  | 440 | 20 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
Bella.Bi |  | 60 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Bela.Zhao |  | 44 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bright.Liu |  | 168 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Colin.Ji |  | 168 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Bessie.yin

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase12.P001 | Meeting-Phase 12 | 1000 | 50 | 0 | All | 20
Phase12.P002 | Project management | 1000 | 16 | 0 | Bella.bi | 3
Phase12.S001 | Analysis requirements | 1000 | 16 | 0 | Bella.bi | 0
Phase12.I003 | Update CIM model in MDD | 950 | 8 | 0 | Bright.Liu | 0
Phase12.I009 | Upgrade SanjelData and eServiceMDM | 950 | 8 | 0 | Bright.Liu | 9
Phase12.I010 | Update database upgrade script | 950 | 10 | 0 | Bright.Liu | 7
Phase12.D001 | Update domain model | 950 | 8 | 0 | Bright.Liu | 0
Refactor.T002 | Refactoring Update/Delete Schedule | 950 | 2 | 0 | Bright.Liu | 2
Ticket #614 | Update a Crew_on Third party crew board | 930 | 2 | 1 | Colin.Ji | 2
Ticket #616 | Remove a Crew_on Third party crew board | 930 | 2 | 1 | Colin.Ji | 2
Ticket #251 | Update Dispatched/In-Progress Rig Job Date Time(Postpone) | 930 | 1 | 1 | Colin.Ji | 1
Ticket #606 | Assign a crew to a job | 930 | 1 | 1 | Bright.Liu | 1.5
Ticket #598 | Display job info in crew board | 930 | 3 | 1 | Colin.Ji | 2.5
Ticket #612 | Handling schedule conflicts_in Rig board | 930 | 2 | 1 | Colin.Ji | 2
Ticket #611 | Update notes in board | 900 | 16 | 1 | Colin.Ji | 11
MDD.T001 | Enum template example | 900 | 8 | 1 | Bright.Liu | 5
MDD.T002 | Implement for Enum_backend | 900 | 12 | 0 | Bela&Bright | 22.5
MDD.T003 | Implement for Enum_frontend | 900 | 16 | 0 | Bela.Zhao | 10.5
MDD.T004 | CimToPimTransform，PimToPsmTransform，PsmToDatabaseScriptTransform | 900 | 12 | 1 | Bela.Zhao | 15
MDD.T006 | Modify modified_user_id data type | 900 | 8 | 1 | Bright.Liu | 5.5
MDD.T007 | Add Name and Description for non-versioned entity | 900 | 16 | 1 | Bright.Liu | 8
MDD.T010 | Extend for Service and Webapi | 850 | 16 | 0 | Bessie.yin | 20.5
MDD.T011 | Test for MDD new function | 850 | 12 | 0 | Bela.Zhao | 22.5
0 | Resolve the slow loading problem in rigjob list | 0 | 0 | 0 | 0 | 0
Bug #001 | Reschedule Rig Job | 900 | 4 | 1 | Colin.Ji | 3
Bug #002 | Update Well Location | 900 | 1 | 1 | Colin.Ji | 1
Refactor.T004 | Re-Schedule Product Haul Load | 900 | 2 | 1 | Colin.Ji | 2
Rests | Familiar with requirement Sanjel | 0 | 0 | 1 | Joe.huang | 68
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间