## Daily Records
ID | Name | Prioritize | Est(Hour) | 2019-07-31 | 2019-08-01 | 2019-08-02 | 2019-08-03 | 2019-08-04 | 2019-08-05 | 2019-08-06 | 2019-08-07 | 2019-08-08 | 2019-08-09 | 2019-08-10 | 2019-08-11 | 2019-08-12 | 2019-08-13 | 2019-08-14 | 2019-08-15 | 2019-08-16 | 2019-08-17 | 2019-08-18 | 2019-08-19 | 2019-08-20 | 2019-08-21 | 2019-08-22 | 2019-08-23 | 2019-08-24 | 2019-08-25 | 2019-08-26 | 2019-08-27 | 2019-08-28 | 2019-08-29 | 2019-08-30 | 2019-08-31 | Total Hours
|  |  |  | 43677 | 43678 | 43679 | 43680 | 43681 | 43682 | 43683 | 43684 | 43685 | 43686 | 43687 | 43688 | 43689 | 43690 | 43691 | 43692 | 43693 | 43694 | 43695 | 43696 | 43697 | 43698 | 43699 | 43700 | 43701 | 43702 | 43703 | 43704 | 43705 | 43706 | 43707 | 43708
| Ideal Burndown |  | 396 | 396 | 384 | 380 | 380 | 380 | 359 | 338 | 317 | 296 | 275 | 275 | 275 | 254 | 233 | 212 | 191 | 170 | 170 | 170 | 157 | 144 | 131 | 118 | 105 | 105 | 105 | 84 | 63 | 42 | 21 | 0 | 0 | 171.5
| Actual |  | 276 | 396 | 384 | 380 | 380 | 380 | 359 | 337.5 | 315.5 | 294 | 268 | 268 | 268 | 268 | 268 | 268 | 260 | 251 | 251 | 251 | 239 | 230.5 | 224.5 | 224.5 | 224.5 | 224.5 | 224.5 | 224.5 | 224.5 | 224.5 | 224.5 | 224.5 | 224.5
|  |  |  | 0 | 12 | 4 | 0 | 0 | 21 | 21.5 | 22 | 21.5 | 26 | 0 | 0 | 0 | 0 | 0 | 8 | 9 | 0 | 0 | 12 | 8.5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.5 | Assign to | Completion Status | Pay by | Module
Phase14.P001 | Meeting-Phase 14 | 1000 | 44 | 2019-08-01: 1; 2019-08-05: 2; 2019-08-06: 2; 2019-08-07: 2; 2019-08-08: 2; 2019-08-09: 4; 2019-08-15: 1.5; 2019-08-16: 1.5; 2019-08-19: 1.5; 2019-08-20: 1; 2019-08-21: 1 | 19.5 | All | 0 | Sanjel | Online
Phase14.P002 | Project management | 1000 | 20 | [32 empty] | 5 | Bella.bi | 0 | Sanjel | Online | bar: 2019-08-05 to 2019-08-09
Phase14.P003 | Analysis requirements | 1000 | 88 | 2019-08-01: 3.5; 2019-08-02: 4; 2019-08-05: 3.5; 2019-08-06: 3.5; 2019-08-07: 8; 2019-08-08: 3.5; 2019-08-09: 7 | 33 | Joe.huang | 0 | Sanjel | Online
Phase14.P004 | 修改Treatment页面中Treatment Reports列表的列宽 | 950 | 8 | [32 empty] | 0 | Bright.Liu | 0 | Sanjel | eService
Phase14.P005 | 熟悉eService和FDAS的引用和逻辑 | 950 | 8 | 2019-08-01: 2.5 | 2.5 | Bright.Liu | 0 | Sanjel | eService
Phase14.P006 | 修改打印PDF图表时，趋势图比例异常问题 | 950 | 5 | 2019-08-01: 5 | 5 | Bright.Liu | 1 | Sanjel | Express
Phase14.P007 | 配合完成代码集成。 | 950 | 3 | 2019-08-05: 3 | 3 | Bright.Liu | 0 | Sanjel | eService
Phase14.P008 | 熟悉eService和FDAS的引用。 | 950 | 4 | 2019-08-05: 4 | 4 | Bright.Liu | 1 | Sanjel | eService
Phase14.P009 | 二次开发MDM，重构Equipment Name逻辑 | 950 | 6 | 2019-08-05: 7.5; 2019-08-06: 7.5 | 15 | Colin.Ji | 1 | Sanjel | Online
Phase14.P010 | Update Equipment Disign Model | 950 | 6 | 2019-08-06: 4; 2019-08-07: 2.5 | 6.5 | Bright.Liu | 1 | Sanjel | Online
Phase14.P011 | Add Equipment MDD | 950 | 2 | 2019-08-06: 3.5; 2019-08-08: 0.5 | 4 | Bright.Liu | 1 | Sanjel | Online
Phase14.P012 | Update CIM | 950 | 2 | 2019-08-07: 1.5 | 1.5 | Bright.Liu | 1 | Sanjel | Online
Phase14.P013 | Update eService MDM | 950 | 2 | [32 empty] | 1 | Bright.Liu | 1 | Sanjel | Online | bar: 2019-08-07
Phase14.P014 | Update eService Database | 950 | 2 | [32 empty] | 1 | Bright.Liu | 1 | Sanjel | Online | bar: 2019-08-07
Phase14.P015 | Display Wits Box Board | 900 | 3 | 2019-08-08: 3 | 3 | colin.Ji | 1 | Sanjel | Online
Phase14.P017 | Display Nubins Board | 900 | 3 | 2019-08-07: 3 | 3 | colin.Ji | 1 | Sanjel | Online
Phase14.P018 | Display Swedge Board | 900 | 3 | 2019-08-07: 2 | 2 | colin.Ji | 1 | Sanjel | Online
Phase14.P019 | Assign WITS Box to RigJob | 900 | 3 | 2019-08-08: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
Phase14.P020 | Assign Nubin to RigJob | 900 | 3 | 2019-08-08: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
Phase14.P021 | Assign Swedge to RigJob | 900 | 3 | 2019-08-08: 2 | 2 | Bright.Liu | 1 | Sanjel | Online
Phase14.P022 | Update Notes(Equipment) | 900 | 4 | 2019-08-08: 4.5 | 4.5 | Colin.Ji | 1 | Sanjel | Online
Phase14.P023 | Return Equipment | 900 | 6 | 2019-07-31: 6; 2019-08-09: 7 | 7 | Colin.Ji | 1 | Sanjel | Online
Phase14.P024 | Update Script | 900 | 2 | [32 empty] | 1 | Bright.Liu | 1 | Sanjel | Online | bar: 2019-08-08
Phase14.P025 | Study Jekins | 900 | 8 | 2019-07-31: 8; 2019-08-09: 7 | 7 | Bright.Liu | 1 | Sanjel | Online
Phase14.P026 | Add Rig Name to Job Chart Header | 850 | 2 | 2019-07-31: 2; 2019-08-16: 3 | 3 | Colin.Ji | 1 | Sanjel | Express
Phase14.P027 | Add the "CSV" check box on the Job Monitor page to control the data source | 850 | 8 | 2019-07-31: 8; 2019-08-16: 4.5; 2019-08-19: 7.5; 2019-08-20: 0 | 12 | Colin.Ji | 0 | Sanjel | Express
Phase14.P029 | Add Reset From Service Report function in Post Job page | 850 | 5 | 2019-08-15: 4.5 | 4.5 | Colin.Ji | 1 | Sanjel | Express
Phase14.P030 | When printing out, control the Comments format | 850 | 3 | 2019-08-15: 2 | 2 | Colin.Ji | 1 | Sanjel | Express
Phase14.P031 | Write automatic update scripts | 850 | 3 | 2019-08-19: 3 | 3 | Yu.lei | 0 | Sanjel | Express
Phase14.P032 | Modify print Settings | 850 | 4 | 2019-08-20: 3.5 | 3.5 | Colin.Ji | 1 | Sanjel | Express
Phase14.P033 | Fix debug run error | 850 | 8 | 2019-08-20: 4 | 4 | Colin.Ji | 1 | Sanjel | Express
Phase14.P034 | 修改打印设置页面IsFromCSV和Monitor页面IsFromCSV的依赖关系。 | 850 | 2.5 | 2019-08-21: 2.5 | 2.5 | Colin.Ji | 1 | Sanjel | Express
Phase14.P035 | 修复设置当前Job时打印设置被覆盖的问题 | 850 | 2.5 | 2019-08-21: 2.5 | 2.5 | Colin.Ji | 1 | Sanjel | Express
Phase14.P036 | [35 empty] | 0 |  |  | Sanjel | Express
Phase14.P037 | [35 empty] | 0 |  |  | Sanjel | Express
Phase14.P038 | [35 empty] | 0 |  |  | Sanjel | Express
Phase14.P039 | [35 empty] | 0 |  |  | Sanjel | Express
Phase14.P040 | [35 empty] | 0 |  |  | Sanjel | Express
Phase14.P041 | [35 empty] | 0 |  |  | Sanjel | Express
Phase14.P042 | [35 empty] | 0 |  |  | Sanjel | Express
Phase14.P043 | [35 empty] | 0 |  |  | Sanjel | Express
Phase14.P044 | [35 empty] | 0 |  |  | Sanjel | Express
Phase14.P045 | [35 empty] | 0 |  |  | Sanjel | Express
Note on L8: joe.huang: Joe：4h Bright：4h
Note on L15: joe.huang: Colin

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2019-07-31 | 2019-08-01 | 2019-08-02 | 2019-08-03 | 2019-08-04 | 2019-08-05 | 2019-08-06 | 2019-08-07 | 2019-08-08 | 2019-08-09 | 2019-08-10 | 2019-08-11 | 2019-08-12 | 2019-08-13 | 2019-08-14 | 2019-08-15 | 2019-08-16 | 2019-08-17 | 2019-08-18 | 2019-08-19 | 2019-08-20 | 2019-08-21 | 2019-08-22 | 2019-08-23 | 2019-08-24 | 2019-08-25 | 2019-08-26 | 2019-08-27 | 2019-08-28 | 2019-08-29 | 2019-08-30 | 2019-08-31
|  |  |  | 43677 | 43678 | 43679 | 43680 | 43681 | 43682 | 43683 | 43684 | 43685 | 43686 | 43687 | 43688 | 43689 | 43690 | 43691 | 43692 | 43693 | 43694 | 43695 | 43696 | 43697 | 43698 | 43699 | 43700 | 43701 | 43702 | 43703 | 43704 | 43705 | 43706 | 43707 | 43708
| Ideal Burndown |  | 396 | 396 | 384 | 380 | 380 | 380 | 359 | 338 | 317 | 296 | 275 | 275 | 275 | 254 | 233 | 212 | 191 | 170 | 170 | 170 | 157 | 144 | 131 | 118 | 105 | 105 | 105 | 84 | 63 | 42 | 21 | 0 | 0
| Actual burndown |  | 276 | 253 | 243.5 | 232 | 232 | 232 | 225.5 | 210 | 194.5 | 172 | 147.5 | 15 | 15 | 15 | 15 | 15 | 14.5 | 7.5 | 8 | 8 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase14.P001 | Meeting-Phase 14 | 1000 | 44 | 2019-07-31: 44; 2019-08-01: 44; 2019-08-02: 44; 2019-08-03: 44; 2019-08-04: 44; 2019-08-05: 42.5; 2019-08-06: 41; 2019-08-07: 39.5; 2019-08-08: 37.5; 2019-08-09: 35.5
Phase14.P002 | Project management | 1000 | 20 | 2019-07-31: 20; 2019-08-01: 20; 2019-08-02: 20; 2019-08-03: 20; 2019-08-04: 20; 2019-08-05: 19; 2019-08-06: 18; 2019-08-07: 17; 2019-08-08: 16; 2019-08-09: 15
Phase14.P003 | Analysis requirements | 1000 | 88 | 2019-07-31: 88; 2019-08-01: 84; 2019-08-02: 80; 2019-08-03: 80; 2019-08-04: 80; 2019-08-05: 76; 2019-08-06: 72; 2019-08-07: 68; 2019-08-08: 64; 2019-08-09: 60
Phase14.P004 | 修改Treatment页面中Treatment Reports列表的列宽 | 950 | 8 | 2019-07-31: 8; 2019-08-01: 8; 2019-08-02: 8; 2019-08-03: 8; 2019-08-04: 8; 2019-08-05: 8; 2019-08-06: 8; 2019-08-07: 8; 2019-08-08: 8; 2019-08-09: 8
Phase14.P005 | 熟悉eService和FDAS的引用和逻辑 | 950 | 8 | 2019-07-31: 8; 2019-08-01: 2.5; 2019-08-02: 0
Phase14.P006 | 修改打印PDF图表时，趋势图比例异常问题 | 950 | 5 | 2019-07-31: 5; 2019-08-01: 5; 2019-08-02: 0
Phase14.P007 | 配合完成代码集成。 | 950 | 3 | 2019-07-31: 3; 2019-08-01: 3; 2019-08-02: 3; 2019-08-03: 3; 2019-08-04: 3; 2019-08-05: 3; 2019-08-06: 0
Phase14.P008 | 熟悉eService和FDAS的引用。 | 950 | 4 | 2019-07-31: 4; 2019-08-01: 4; 2019-08-02: 4; 2019-08-03: 4; 2019-08-04: 4; 2019-08-05: 4; 2019-08-06: 0
Phase14.P009 | 二次开发MDM，重构Equipment Name逻辑 | 950 | 6 | 2019-07-31: 6; 2019-08-01: 6; 2019-08-02: 6; 2019-08-03: 6; 2019-08-04: 6; 2019-08-05: 6; 2019-08-06: 6; 2019-08-07: 0
Phase14.P010 | Update Equipment Disign Model | 950 | 6 | 2019-07-31: 6; 2019-08-01: 6; 2019-08-02: 6; 2019-08-03: 6; 2019-08-04: 6; 2019-08-05: 6; 2019-08-06: 4; 2019-08-07: 3; 2019-08-08: 0
Phase14.P011 | Add Equipment MDD | 950 | 2 | 2019-07-31: 2; 2019-08-01: 2; 2019-08-02: 2; 2019-08-03: 2; 2019-08-04: 2; 2019-08-05: 2; 2019-08-06: 2; 2019-08-07: 0; 2019-08-08: 0.5; 2019-08-09: 0
Phase14.P012 | Update CIM | 950 | 2 | 2019-07-31: 2; 2019-08-01: 2; 2019-08-02: 2; 2019-08-03: 2; 2019-08-04: 2; 2019-08-05: 2; 2019-08-06: 2; 2019-08-07: 2; 2019-08-08: 0
Phase14.P013 | Update eService MDM | 950 | 2 | 2019-07-31: 2; 2019-08-01: 2; 2019-08-02: 2; 2019-08-03: 2; 2019-08-04: 2; 2019-08-05: 2; 2019-08-06: 2; 2019-08-07: 2; 2019-08-08: 0
Phase14.P014 | Update eService Database | 950 | 2 | 2019-07-31: 2; 2019-08-01: 2; 2019-08-02: 2; 2019-08-03: 2; 2019-08-04: 2; 2019-08-05: 2; 2019-08-06: 2; 2019-08-07: 2; 2019-08-08: 0
Phase14.P015 | Display Wits Box Board | 900 | 3 | 2019-07-31: 3; 2019-08-01: 3; 2019-08-02: 3; 2019-08-03: 3; 2019-08-04: 3; 2019-08-05: 3; 2019-08-06: 3; 2019-08-07: 3; 2019-08-08: 3; 2019-08-09: 0
Phase14.P017 | Display Nubins Board | 900 | 3 | 2019-07-31: 3; 2019-08-01: 3; 2019-08-02: 3; 2019-08-03: 3; 2019-08-04: 3; 2019-08-05: 3; 2019-08-06: 3; 2019-08-07: 3; 2019-08-08: 0
Phase14.P018 | Display Swedge Board | 900 | 3 | 2019-07-31: 3; 2019-08-01: 3; 2019-08-02: 3; 2019-08-03: 3; 2019-08-04: 3; 2019-08-05: 3; 2019-08-06: 3; 2019-08-07: 3; 2019-08-08: 0
Phase14.P019 | Assign WITS Box to RigJob | 900 | 3 | 2019-07-31: 3; 2019-08-01: 3; 2019-08-02: 3; 2019-08-03: 3; 2019-08-04: 3; 2019-08-05: 3; 2019-08-06: 3; 2019-08-07: 3; 2019-08-08: 3; 2019-08-09: 0
Phase14.P020 | Assign Nubin to RigJob | 900 | 3 | 2019-07-31: 3; 2019-08-01: 3; 2019-08-02: 3; 2019-08-03: 3; 2019-08-04: 3; 2019-08-05: 3; 2019-08-06: 3; 2019-08-07: 3; 2019-08-08: 3; 2019-08-09: 0
Phase14.P021 | Assign Swedge to RigJob | 900 | 3 | 2019-07-31: 3; 2019-08-01: 3; 2019-08-02: 3; 2019-08-03: 3; 2019-08-04: 3; 2019-08-05: 3; 2019-08-06: 3; 2019-08-07: 3; 2019-08-08: 3; 2019-08-09: 0
Phase14.P022 | Update Notes(Equipment) | 900 | 4 | 2019-07-31: 4; 2019-08-01: 4; 2019-08-02: 4; 2019-08-03: 4; 2019-08-04: 4; 2019-08-05: 4; 2019-08-06: 4; 2019-08-07: 4; 2019-08-08: 4; 2019-08-09: 0
Phase14.P023 | Return Equipment | 900 | 6 | 2019-07-31: 6; 2019-08-01: 6; 2019-08-02: 6; 2019-08-03: 6; 2019-08-04: 6; 2019-08-05: 6; 2019-08-06: 6; 2019-08-07: 6; 2019-08-08: 6; 2019-08-09: 7; 2019-08-10: 0
Phase14.P024 | Update Script | 900 | 2 | 2019-07-31: 2; 2019-08-01: 2; 2019-08-02: 2; 2019-08-03: 2; 2019-08-04: 2; 2019-08-05: 2; 2019-08-06: 2; 2019-08-07: 2; 2019-08-08: 1; 2019-08-09: 0
Phase14.P025 | Study Jekins | 900 | 8 | 2019-07-31: 8; 2019-08-01: 8; 2019-08-02: 8; 2019-08-03: 8; 2019-08-04: 8; 2019-08-05: 8; 2019-08-06: 8; 2019-08-07: 8; 2019-08-08: 8; 2019-08-09: 7; 2019-08-10: 0
Phase14.P026 | Add Rig Name to Job Chart Header | 850 | 2 | 2019-07-31: 2; 2019-08-01: 2; 2019-08-02: 2; 2019-08-03: 2; 2019-08-04: 2; 2019-08-05: 2; 2019-08-06: 2; 2019-08-07: 2; 2019-08-08: 2; 2019-08-09: 2; 2019-08-10: 2; 2019-08-11: 2; 2019-08-12: 2; 2019-08-13: 2; 2019-08-14: 2; 2019-08-15: 2; 2019-08-16: 3; 2019-08-17: 0
Phase14.P027 | Add the "CSV" check box on the Job Monitor page to control the data source | 850 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4.5 | 8 | 8 | 7.5 | 0
Phase14.P029 | Add Reset From Service Report function in Post Job page | 850 | 5 | 2019-07-31: 5; 2019-08-01: 5; 2019-08-02: 5; 2019-08-03: 5; 2019-08-04: 5; 2019-08-05: 5; 2019-08-06: 5; 2019-08-07: 5; 2019-08-08: 5; 2019-08-09: 5; 2019-08-10: 5; 2019-08-11: 5; 2019-08-12: 5; 2019-08-13: 5; 2019-08-14: 5; 2019-08-15: 4.5; 2019-08-16: 0
Phase14.P030 | When printing out, control the Comments format | 850 | 3 | 2019-07-31: 3; 2019-08-01: 3; 2019-08-02: 3; 2019-08-03: 3; 2019-08-04: 3; 2019-08-05: 3; 2019-08-06: 3; 2019-08-07: 3; 2019-08-08: 3; 2019-08-09: 3; 2019-08-10: 3; 2019-08-11: 3; 2019-08-12: 3; 2019-08-13: 3; 2019-08-14: 3; 2019-08-15: 2; 2019-08-16: 0
Phase14.P031 | Write automatic update scripts | 850 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
Phase14.P032 | Modify print Settings | 850 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3.5 | 0
Phase14.P033 | Fix debug run error | 850 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
Phase14.P034 | 修改打印设置页面IsFromCSV和Monitor页面IsFromCSV的依赖关系。 | 850 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0
Phase14.P035 | 修复设置当前Job时打印设置被覆盖的问题 | 850 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0
Phase14.P036 | 0 | 0 | 0
Phase14.P037 | 0 | 0 | 0
Phase14.P038 | 0 | 0 | 0
Phase14.P039 | 0 | 0 | 0
Phase14.P040 | 0 | 0 | 0
Phase14.P041 | 0 | 0 | 0
Phase14.P042 | 0 | 0 | 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。
Note on L15: joe.huang: Colin

## Resources
SPRINT
StartDate | 2019-08-01
EndDate | 2019-08-31
Est Time
Name | Role | Total Hours | 2019-08-01 | 2019-08-02 | 2019-08-03 | 2019-08-04 | 2019-08-05 | 2019-08-06 | 2019-08-07 | 2019-08-08 | 2019-08-09 | 2019-08-10 | 2019-08-11 | 2019-08-12 | 2019-08-13 | 2019-08-14 | 2019-08-15 | 2019-08-16 | 2019-08-17 | 2019-08-18 | 2019-08-19 | 2019-08-20 | 2019-08-21 | 2019-08-22 | 2019-08-23 | 2019-08-24 | 2019-08-25 | 2019-08-26 | 2019-08-27 | 2019-08-28 | 2019-08-29 | 2019-08-30 | 2019-08-31
|  |  | 43678 | 43679 | 43680 | 43681 | 43682 | 43683 | 43684 | 43685 | 43686 | 43687 | 43688 | 43689 | 43690 | 43691 | 43692 | 43693 | 43694 | 43695 | 43696 | 43697 | 43698 | 43699 | 43700 | 43701 | 43702 | 43703 | 43704 | 43705 | 43706 | 43707 | 43708
Ideal Burndown |  | 396 | 384 | 380 | 380 | 380 | 359 | 338 | 317 | 296 | 275 | 275 | 275 | 254 | 233 | 212 | 191 | 170 | 170 | 170 | 157 | 144 | 131 | 118 | 105 | 105 | 105 | 84 | 63 | 42 | 21 | 0 | 0
Hours consumed |  | 396 | 12 | 4 | 0 | 0 | 21 | 21 | 21 | 21 | 21 | 0 | 0 | 21 | 21 | 21 | 21 | 21 | 0 | 0 | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 21 | 21 | 21 | 21 | 21 | 0
Bella.Bi |  | 20 | bar: 2019-08-05 to 2019-08-09; 2019-08-12 to 2019-08-16; 2019-08-19 to 2019-08-23; 2019-08-26 to 2019-08-30
Bela.Zhao |  | 0
Bright.Liu |  | 128 | 2019-08-01: 8; 2019-08-05: 8; 2019-08-06: 8; 2019-08-07: 8; 2019-08-08: 8; 2019-08-09: 8; 2019-08-12: 8; 2019-08-13: 8; 2019-08-14: 8; 2019-08-15: 8; 2019-08-16: 8; 2019-08-26: 8; 2019-08-27: 8; 2019-08-28: 8; 2019-08-29: 8; 2019-08-30: 8
Colin.Ji |  | 160 |  |  |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8
Bessie.yin |  | 0
Joe.huang |  | 88 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4
Yu.lei |  | 0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase14.P001 | Meeting-Phase 14 | 1000 | 44 | 0 | All | 19.5
Phase14.P002 | Project management | 1000 | 20 | 0 | Bella.bi | 5
Phase14.P003 | Analysis requirements | 1000 | 88 | 0 | Joe.huang | 33
Phase14.P004 | 修改Treatment页面中Treatment Reports列表的列宽 | 950 | 8 | 0 | Bright.Liu | 0
Phase14.P005 | 熟悉eService和FDAS的引用和逻辑 | 950 | 8 | 0 | Bright.Liu | 2.5
Phase14.P006 | 修改打印PDF图表时，趋势图比例异常问题 | 950 | 5 | 1 | Bright.Liu | 5
Phase14.P007 | 配合完成代码集成。 | 950 | 3 | 0 | Bright.Liu | 3
Phase14.P008 | 熟悉eService和FDAS的引用。 | 950 | 4 | 1 | Bright.Liu | 4
Phase14.P009 | 二次开发MDM，重构Equipment Name逻辑 | 950 | 6 | 1 | Colin.Ji | 15
Phase14.P010 | Update Equipment Disign Model | 950 | 6 | 1 | Bright.Liu | 6.5
Phase14.P011 | Add Equipment MDD | 950 | 2 | 1 | Bright.Liu | 4
Phase14.P012 | Update CIM | 950 | 2 | 1 | Bright.Liu | 1.5
Phase14.P013 | Update eService MDM | 950 | 2 | 1 | Bright.Liu | 1
Phase14.P014 | Update eService Database | 950 | 2 | 1 | Bright.Liu | 1
Phase14.P015 | Display Wits Box Board | 900 | 3 | 1 | colin.Ji | 3
Phase14.P017 | Display Nubins Board | 900 | 3 | 1 | colin.Ji | 3
Phase14.P018 | Display Swedge Board | 900 | 3 | 1 | colin.Ji | 2
Phase14.P019 | Assign WITS Box to RigJob | 900 | 3 | 1 | Bright.Liu | 2
Phase14.P020 | Assign Nubin to RigJob | 900 | 3 | 1 | Bright.Liu | 2
Phase14.P021 | Assign Swedge to RigJob | 900 | 3 | 1 | Bright.Liu | 2
Phase14.P022 | Update Notes(Equipment) | 900 | 4 | 1 | Colin.Ji | 4.5
Phase14.P023 | Return Equipment | 900 | 6 | 1 | Colin.Ji | 7
Phase14.P024 | Update Script | 900 | 2 | 1 | Bright.Liu | 1
Phase14.P025 | Study Jekins | 900 | 8 | 1 | Bright.Liu | 7
Phase14.P026 | Add Rig Name to Job Chart Header | 850 | 2 | 1 | Colin.Ji | 3
Phase14.P027 | Add the "CSV" check box on the Job Monitor page to control the data source | 850 | 8 | 0 | Colin.Ji | 12
Phase14.P029 | Add Reset From Service Report function in Post Job page | 850 | 5 | 1 | Colin.Ji | 4.5
Phase14.P030 | When printing out, control the Comments format | 850 | 3 | 1 | Colin.Ji | 2
Phase14.P031 | Write automatic update scripts | 850 | 3 | 0 | Yu.lei | 3
Phase14.P032 | Modify print Settings | 850 | 4 | 1 | Colin.Ji | 3.5
Phase14.P033 | Fix debug run error | 850 | 8 | 1 | Colin.Ji | 4
Phase14.P034 | 修改打印设置页面IsFromCSV和Monitor页面IsFromCSV的依赖关系。 | 850 | 2.5 | 1 | Colin.Ji | 2.5
Phase14.P035 | 修复设置当前Job时打印设置被覆盖的问题 | 850 | 2.5 | 1 | Colin.Ji | 2.5
Phase14.P036 | 0 | 0 | 0 | 0 | 0 | 0
Phase14.P037 | 0 | 0 | 0 | 0 | 0 | 0
Phase14.P038 | 0 | 0 | 0 | 0 | 0 | 0
Phase14.P039 | 0 | 0 | 0 | 0 | 0 | 0
Phase14.P038 | 0 | 0 | 0 | 0 | 0 | 0
Phase14.P039 | 0 | 0 | 0 | 0 | 0 | 0
Phase14.P040 | 0 | 0 | 0 | 0 | 0 | 0
Phase14.P041 | 0 | 0 | 0 | 0 | 0 | 0
Phase14.P042 | 0 | 0 | 0 | 0 | 0 | 0
Phase14.P043 | 0 | 0 | 0 | 0 | 0 | 0
Phase14.P044 | 0 | 0 | 0 | 0 | 0 | 0
Phase14.P045 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间