## Daily Records
ID | Name | Prioritize | Est(Hour) | 2019-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-08 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-15 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31 | Total Hours
|  |  |  | 43799 | 43800 | 43801 | 43802 | 43803 | 43804 | 43805 | 43806 | 43807 | 43808 | 43809 | 43810 | 43811 | 43812 | 43813 | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830
| Ideal Burndown |  | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 81 | 78 | 74 | 70 | 64 | 64 | 64 | 56 | 48 | 40 | 32 | 24 | 24 | 24 | 8 | 0 | 209
| Actual |  | 276 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 68 | 52 | 44 | 36 | 28 | 28 | 28 | 20 | 4 | -12 | -29 | -29 | -29 | -29 | -33 | -41 | -49 | -57 | -65 | -65 | -65 | -69 | -69
|  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 8 | 8 | 8 | 0 | 0 | 8 | 16 | 16 | 17 | 0 | 0 | 0 | 4 | 8 | 8 | 8 | 8 | 0 | 0 | 4 | 0 | 209 | Assign to | Completion Status | Pay by | Module
Phase18.P001 | 会议 | 1000 | 11 | 2019-12-19: 3 | 3 | Joe.huang | 0 | Sanjel | eService
Phase18.P002 | 项目管理 | 1000 | 11 | [32 empty] | 0 | Joe.huang | 1 | Sanjel | eService
Phase18.P003 | 搭建项目环境 | 1000 | 8 | 2019-12-02: 8 | 8 | Malone.wang | 1 | Shared | eService
Phase18.P004 | 熟悉Sanjel | 980 | 40 | 2019-12-03: 8; 2019-12-04: 8; 2019-12-05: 8; 2019-12-13: 8; 2019-12-19: 7 | 39 | Malone.wang | 1 | Shared | eService
Phase18.P005 | 发布eService Online | 980 | 40 | 2019-12-06: 8; 2019-12-09: 8; 2019-12-10: 8; 2019-12-11: 8; 2019-12-12: 8 | 40 | Malone.wang | 1 | Shared | eService
Phase18.P006 | MMC - GITHUB: CHECK PREVIOUS LOGIN | 980 | 16 | 2019-12-05: 8; 2019-12-06: 7; 2019-12-09: 6 | 21 | Migue | 0 | Shared | eService
Phase18.P007 | Convert document file to MD format | 980 | 1 | [32 empty] | 1 | Migue | 1 | MetaShare | eService | bar: 2019-12-06
Phase18.P008 | Cloning Repositories | 980 | 4 | 2019-12-09: 2 | 2 | Migue | 0 | Sanjel | eService
Phase18.P009 | Compile and Publish with new repositories | 980 | 8 | 2019-12-10: 7 | 7 | Migue | 1 | Shared | eService
Phase18.P010 | MMC - GITHUB: Check login | 980 | 1 | [32 empty] | 1 | Migue | 0 | Shared | eService | bar: 2019-12-10
Phase18.P011 | 部署eService | 980 | 16 | 2019-12-17: 8; 2019-12-18: 8 | 16 | Malone.wang | 0 | Shared | eService
Phase18.P012 | MMC - GITHUB: Commit for new repostories and testing the whole application | 980 | 8 | 2019-12-16: 8 | 8 | Migue | 0 | Shared | eService
Phase18.P013 | Sanjel: Installation procedures | 980 | 4 | 2019-12-17: 3 | 3 | Migue | 1 | Sanjel | eService
Phase18.P014 | MMC - GITHUB: testing | 980 | 4 | 2019-12-17: 5 | 5 | Migue | 0 | Shared | eService
Phase18.P015 | MMC - GITHUB: Send many request without crash | 980 | 8 | 2019-12-18: 6 | 6 | Migue | 1 | Shared | eService
Phase18.P016 | Sanjel: Install Sustainment eService clickonce and database download and restore | 980 | 4 | 2019-12-18: 2 | 2 | Migue | 1 | Sanjel | eService
Phase18.P017 | MMC - GITHUB: Get Directory | 950 | 4 | 2019-12-19: 4 | 4 | Migue | 0 | Shared | eService
Phase18.P018 | Sanjel: Create eService Local Data Manager analysis | 950 | 16 | 2019-12-19: 3; 2019-12-30: 4 | 7 | Migue | 0 | Sanjel | eService
Phase18.P019 | (#654)Display “Risk Matrix” on the eProgram | 950 | 8 | 2019-12-23: 1; 2019-12-24: 2; 2019-12-25: 2; 2019-12-26: 2; 2019-12-27: 2 | 9 | Malone.wang | 1 | Sanjel | eService
Phase18.P020 | (#655)Dispaly "Risk Matrix" on the eProgram | 950 | 8 | 2019-12-23: 1; 2019-12-24: 2; 2019-12-25: 2; 2019-12-26: 2; 2019-12-27: 2 | 9 | Malone.wang | 1 | Sanjel | eService
Phase18.P021 | (#656)Read and Save metrics to the database | 950 | 8 | 2019-12-23: 1; 2019-12-24: 2; 2019-12-25: 2; 2019-12-26: 2; 2019-12-27: 2 | 9 | Malone.wang | 1 | Sanjel | eService
Phase18.P022 | (#657)Check metrics on the program | 950 | 8 | [32 empty] | 0 | Malone.wang | 1 | Sanjel | eService
Phase18.P023 | (#658)Display "Field Blend Test" in the eProgram | 950 | 8 | 2019-12-23: 1; 2019-12-24: 2; 2019-12-25: 2; 2019-12-26: 2; 2019-12-27: 2 | 9 | Malone.wang | 1 | Sanjel | eService
Phase18.P024 | (#659)Present “Need Field Blend Test” on Rig Board | 950 | 8 | [32 empty] | 0 | Malone.wang | 1 | Sanjel | eService
Phase18.P025 | (#660)Display “Need Field Blend Test” on the eProgram | 950 | 8 | [32 empty] | 0 | Malone.wang | 1 | Sanjel | eService
Phase18.P026 | (#661)Display detail items on the Program | 950 | 8 | [32 empty] | 0 | Malone.wang | 1 | Sanjel | eService
Phase18.P027 | (#662)Display detail items on the Program | 950 | 8 | [32 empty] | 0 | Malone.wang | 1 | Sanjel | eService

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2019-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-08 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-15 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31
|  |  |  | 43799 | 43800 | 43801 | 43802 | 43803 | 43804 | 43805 | 43806 | 43807 | 43808 | 43809 | 43810 | 43811 | 43812 | 43813 | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830
| Ideal Burndown |  | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 81 | 78 | 74 | 70 | 64 | 64 | 64 | 56 | 48 | 40 | 32 | 24 | 24 | 24 | 8 | 0
| Actual burndown |  | 276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase18.P001 | 会议 | 1000 | 11 | 2019-12-19: 3
Phase18.P002 | 项目管理 | 1000 | 11
Phase18.P003 | 搭建项目环境 | 1000 | 8 | 2019-12-02: 8
Phase18.P004 | 熟悉Sanjel | 980 | 40 | 2019-12-03: 8; 2019-12-04: 8; 2019-12-05: 8; 2019-12-13: 8; 2019-12-19: 7
Phase18.P005 | 发布eService Online | 980 | 40 | 2019-12-06: 8; 2019-12-09: 8; 2019-12-10: 8; 2019-12-11: 8; 2019-12-12: 8
Phase18.P006 | MMC - GITHUB: CHECK PREVIOUS LOGIN | 980 | 16 | 2019-12-05: 8; 2019-12-06: 7; 2019-12-09: 6
Phase18.P007 | Convert document file to MD format | 980 | 1 | bar: 2019-12-06
Phase18.P008 | Cloning Repositories | 980 | 4 | 2019-12-09: 2
Phase18.P009 | Compile and Publish with new repositories | 980 | 8 | 2019-12-10: 7
Phase18.P010 | MMC - GITHUB: Check login | 980 | 1 | bar: 2019-12-10
Phase18.P011 | 部署eService | 980 | 16 | 2019-12-17: 8; 2019-12-18: 8
Phase18.P012 | MMC - GITHUB: Commit for new repostories and testing the whole application | 980 | 8 | 2019-12-16: 8
Phase18.P013 | Sanjel: Installation procedures | 980 | 4 | 2019-12-17: 3
Phase18.P014 | MMC - GITHUB: testing | 980 | 4 | 2019-12-17: 5
Phase18.P015 | MMC - GITHUB: Send many request without crash | 980 | 8 | 2019-12-18: 6
Phase18.P016 | Sanjel: Install Sustainment eService clickonce and database download and restore | 980 | 4 | 2019-12-18: 2
Phase18.P017 | MMC - GITHUB: Get Directory | 950 | 4 | 2019-12-19: 4
Phase18.P018 | Sanjel: Create eService Local Data Manager analysis | 950 | 16 | 2019-12-19: 3
Phase18.P019 | (#654)Display “Risk Matrix” on the eProgram | 950 | 8 | 2019-12-23: 1; 2019-12-24: 2; 2019-12-25: 2; 2019-12-26: 2; 2019-12-27: 2
Phase18.P020 | (#655)Dispaly "Risk Matrix" on the eProgram | 950 | 8 | 2019-12-23: 1; 2019-12-24: 2; 2019-12-25: 2; 2019-12-26: 2; 2019-12-27: 2
Phase18.P021 | (#656)Read and Save metrics to the database | 950 | 8 | 2019-12-23: 1; 2019-12-24: 2; 2019-12-25: 2; 2019-12-26: 2; 2019-12-27: 2
Phase18.P022 | (#657)Check metrics on the program | 950 | 8
Phase18.P023 | (#658)Display "Field Blend Test" in the eProgram | 950 | 8 | 2019-12-23: 1; 2019-12-24: 2; 2019-12-25: 2; 2019-12-26: 2; 2019-12-27: 2
Phase18.P024 | (#659)Present “Need Field Blend Test” on Rig Board | 950 | 8
Phase18.P025 | (#660)Display “Need Field Blend Test” on the eProgram | 950 | 8
Phase18.P026 | (#661)Display detail items on the Program | 950 | 8
Phase18.P027 | (#662)Display detail items on the Program | 950 | 8
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT
StartDate | 2019-12-01
EndDate | 2019-12-30
Est Time
Name | Role | Total Hours | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-08 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-15 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31
|  |  | 43800 | 43801 | 43802 | 43803 | 43804 | 43805 | 43806 | 43807 | 43808 | 43809 | 43810 | 43811 | 43812 | 43813 | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830
Ideal Burndown |  | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 81 | 78 | 74 | 70 | 64 | 64 | 64 | 56 | 48 | 40 | 32 | 24 | 24 | 24 | 8 | 0
Hours consumed |  | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 4 | 4 | 6 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 16 | 8
Malone.wang |  | 74 | 2019-12-16: 3; 2019-12-17: 3; 2019-12-18: 4; 2019-12-19: 4; 2019-12-20: 4; 2019-12-23: 8; 2019-12-24: 8; 2019-12-25: 8; 2019-12-26: 8; 2019-12-27: 8; 2019-12-30: 8; 2019-12-31: 8
Migue |  | 10 | 2019-12-20: 2; 2019-12-30: 8
Joe.huang |  | 0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase18.P001 | 会议 | 1000 | 11 | 0 | Joe.huang | 3
Phase18.P002 | 项目管理 | 1000 | 11 | 1 | Joe.huang | 0
Phase18.P003 | 搭建项目环境 | 1000 | 8 | 1 | Malone.wang | 8
Phase18.P004 | 熟悉Sanjel | 980 | 40 | 1 | Malone.wang | 39
Phase18.P005 | 发布eService Online | 980 | 40 | 1 | Malone.wang | 40
Phase18.P006 | MMC - GITHUB: CHECK PREVIOUS LOGIN | 980 | 16 | 0 | Migue | 21
Phase18.P007 | Convert document file to MD format | 980 | 1 | 1 | Migue | 1
Phase18.P008 | Cloning Repositories | 980 | 4 | 0 | Migue | 2
Phase18.P009 | Compile and Publish with new repositories | 980 | 8 | 1 | Migue | 7
Phase18.P010 | MMC - GITHUB: Check login | 980 | 1 | 0 | Migue | 1
Phase18.P011 | 部署eService | 980 | 16 | 0 | Malone.wang | 16
Phase18.P012 | MMC - GITHUB: Commit for new repostories and testing the whole application | 980 | 8 | 0 | Migue | 8
Phase18.P013 | Sanjel: Installation procedures | 980 | 4 | 1 | Migue | 3
Phase18.P014 | MMC - GITHUB: testing | 980 | 4 | 0 | Migue | 5
Phase18.P015 | MMC - GITHUB: Send many request without crash | 980 | 8 | 1 | Migue | 6
Phase18.P016 | Sanjel: Install Sustainment eService clickonce and database download and restore | 980 | 4 | 1 | Migue | 2
Phase18.P017 | MMC - GITHUB: Get Directory | 950 | 4 | 0 | Migue | 4
Phase18.P018 | Sanjel: Create eService Local Data Manager analysis | 950 | 16 | 0 | Migue | 7
Phase18.P019 | (#654)Display “Risk Matrix” on the eProgram | 950 | 8 | 1 | Malone.wang | 9
Phase18.P020 | (#655)Dispaly "Risk Matrix" on the eProgram | 950 | 8 | 1 | Malone.wang | 9
Phase18.P021 | (#656)Read and Save metrics to the database | 950 | 8 | 1 | Malone.wang | 9
Phase18.P022 | (#657)Check metrics on the program | 950 | 8 | 1 | Malone.wang | 0
Phase18.P023 | (#658)Display "Field Blend Test" in the eProgram | 950 | 8 | 1 | Malone.wang | 9
Phase18.P024 | (#659)Present “Need Field Blend Test” on Rig Board | 950 | 8 | 1 | Malone.wang | 0
Phase18.P025 | (#660)Display “Need Field Blend Test” on the eProgram | 950 | 8 | 1 | Malone.wang | 0
Phase18.P026 | (#661)Display detail items on the Program | 950 | 8 | 1 | Malone.wang | 0
Phase18.P027 | (#662)Display detail items on the Program | 950 | 8 | 1 | Malone.wang | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间