## Daily Records
ID | Name | Prioritize | Est(Hour) | 2020-01-31 | 2020-02-01 | 2020-02-02 | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16 | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02 | Total Hours
|  |  |  | 43861 | 43862 | 43863 | 43864 | 43865 | 43866 | 43867 | 43868 | 43869 | 43870 | 43871 | 43872 | 43873 | 43874 | 43875 | 43876 | 43877 | 43878 | 43879 | 43880 | 43881 | 43882 | 43883 | 43884 | 43885 | 43886 | 43887 | 43888 | 43889 | 43890 | 43891 | 43892
| Ideal Burndown |  | 145 | 145 | 145 | 145 | 135 | 125 | 115 | 105 | 95 | 95 | 95 | 89 | 83 | 77 | 71 | 65 | 65 | 65 | 56 | 47 | 38 | 29 | 20 | 20 | 20 | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 152
| Actual |  | 230 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 140 | 136 | 132 | 128 | 125 | 125 | 125 | 121 | 116 | 113 | 109 | 98 | 98 | 98 | 83 | 70 | 51 | 39 | 25 | 25 | 25 | 25
|  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 4 | 4 | 3 | 0 | 0 | 4 | 5 | 3 | 4 | 11 | 0 | 0 | 15 | 13 | 19 | 12 | 14 | 0 | 0 | 0 | 152 | Assign to | Completion Status | Pay by | Module
Phase19.P001 | 会议 | 1000 | 11 | [32 empty] | 0
Phase19.P002 | 项目管理 | 1000 | 11 | [32 empty] | 0
Phase19.P003 | #680 (Display Revision info. on the eProgram) | 1000 | 8 | 2020-02-03: 2; 2020-02-04: 2; 2020-02-05: 2; 2020-02-06: 1; 2020-02-07: 1 | 8 | Malone.wang | 1 | Sanjel | eService
Phase19.P004 | #681 (Import program file with revision number) | 1000 | 8 | 2020-02-03: 2; 2020-02-04: 2; 2020-02-05: 2; 2020-02-06: 1; 2020-02-07: 1 | 8 | Malone.wang | 1 | Sanjel | eService
Phase19.P005 | #682 (Display revision info. on eProgram) | 1000 | 8 | 2020-02-06: 2; 2020-02-07: 4 | 6 | Malone.wang | 1 | Sanjel | eService
Phase19.P006 | #683 (Update Rig Job to new Revision) | 1000 | 8 | 2020-02-06: 4; 2020-02-07: 2 | 6 | Malone.wang | 1 | Sanjel | eService
Phase19.P007 | #684 (Select Revision to Create Call Sheet) | 1000 | 8 | 2020-02-06: 2; 2020-02-07: 2 | 4 | Malone.wang | 1 | Sanjel | eService
Phase19.P008 | #685 (Display revision on the eService) | 1000 | 8 | 2020-02-10: 2; 2020-02-11: 2; 2020-02-14: 2; 2020-02-17: 1; 2020-02-18: 1 | 8 | Malone.wang | 1 | Sanjel | eService
Phase19.P009 | #686 (Display revision on the eService) | 1000 | 8 | 2020-02-10: 2; 2020-02-11: 1; 2020-02-12: 1; 2020-02-13: 1; 2020-02-14: 1; 2020-02-18: 1; 2020-02-19: 1 | 8 | Malone.wang | 1 | Sanjel | eService
Phase19.P010 | #687 (Display Revision on the EService) | 1000 | 8 | 2020-02-12: 2; 2020-02-13: 2; 2020-02-17: 2; 2020-02-18: 2; 2020-02-19: 1 | 9 | Malone.wang | 1 | Sanjel | eService
Phase19.P011 | #688 (Display Revision Count on eProgram) | 1000 | 8 | [32 empty] | 7 | Malone.wang | 1 | Sanjel | eService | bar: 2020-02-10 to 2020-02-13; 2020-02-17 to 2020-02-19
Phase19.P012 | #689 (Import program file with the same prgID and different revision) | 1000 | 8 | 2020-01-31: 8; 2020-02-20: 4; 2020-02-21: 4 | 8 | Malone.wang | 1 | Sanjel | eService
Phase19.P013 | #690 (Improve Blend display on RigBoard)BA | 950 | 8 | 2020-01-31: 8; 2020-02-21: 1; 2020-02-24: 1; 2020-02-25: 1; 2020-02-26: 1 | 4 | daisy.huang | 1 | Sanjel | eService
Phase19.P014 | #691 (Display PREFL 、BLEND and DISPL on RigBoad) | 950 | 8 | [32 empty] | 4 | daisy.huang | 1 | Sanjel | eService | bar: 2020-02-21; 2020-02-24 to 2020-02-26
Phase19.P015 | #692 (Improve product display on RigBoad) | 950 | 8 | [32 empty] | 4 | daisy.huang | 1 | Sanjel | eService | bar: 2020-02-21; 2020-02-24 to 2020-02-26
Phase19.P016 | #693 (Display Based BLend on Tooptip) | 950 | 8 | [32 empty] | 4 | daisy.huang | 1 | Sanjel | eService | bar: 2020-02-21; 2020-02-24 to 2020-02-26
Phase19.P017 | #694 (Display PREFL、BLEND and DISPL on RigBoad) | 950 | 8 | [32 empty] | 4 | daisy.huang | 1 | Sanjel | eService | bar: 2020-02-21; 2020-02-24 to 2020-02-26
Phase19.P018 | #695 (Display products in PREFL、BLEND and DISPL | 950 | 8 | [32 empty] | 4 | daisy.huang | 1 | Sanjel | eService | bar: 2020-02-21; 2020-02-24 to 2020-02-26
Phase19.P019 | #696 (Improve Based Blend display on Tooptip) | 950 | 8 | [32 empty] | 4 | daisy.huang | 1 | Sanjel | eService | bar: 2020-02-21; 2020-02-24 to 2020-02-26
Phase19.P020 | #697 (Display PREFL 、BLEND and DISPL on RigBoad) | 950 | 8 | 2020-02-26: 2; 2020-02-27: 2 | 4 | Malone.wang | 1 | Sanjel | eService
Phase19.P021 | #699 (Improve blend description in Tooptip) | 950 | 8 | 2020-02-26: 2; 2020-02-27: 2 | 4 | Malone.wang | 1 | Sanjel | eService
Phase19.P022 | #701 (Add revision description in template) | 950 | 8 | 2020-02-26: 2; 2020-02-27: 2 | 4 | Malone.wang | 1 | Sanjel | eService
Phase19.P023 | Data migration | 1000 | 40 | 2020-02-24: 8; 2020-02-25: 6; 2020-02-26: 6; 2020-02-27: 6; 2020-02-28: 6 | 32 | Migue | 1 | Sanjel | eService
Phase19.P024 | #700 (Add revision description) | 1000 | 8 | 2020-02-28: 8 | 8 | Malone.wang | 1 | Sanjel | eService

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2020-01-31 | 2020-02-01 | 2020-02-02 | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16 | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02
|  |  |  | 43861 | 43862 | 43863 | 43864 | 43865 | 43866 | 43867 | 43868 | 43869 | 43870 | 43871 | 43872 | 43873 | 43874 | 43875 | 43876 | 43877 | 43878 | 43879 | 43880 | 43881 | 43882 | 43883 | 43884 | 43885 | 43886 | 43887 | 43888 | 43889 | 43890 | 43891 | 43892
| Ideal Burndown |  | 145 | 145 | 145 | 145 | 135 | 125 | 115 | 105 | 95 | 95 | 95 | 89 | 83 | 77 | 71 | 65 | 65 | 65 | 56 | 47 | 38 | 29 | 20 | 20 | 20 | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0
| Actual burndown |  | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase19.P001 | 会议 | 1000 | 11
Phase19.P002 | 项目管理 | 1000 | 11
Phase19.P003 | #680 (Display Revision info. on the eProgram) | 1000 | 8
Phase19.P004 | #681 (Import program file with revision number) | 1000 | 8
Phase19.P005 | #682 (Display revision info. on eProgram) | 1000 | 8
Phase19.P006 | #683 (Update Rig Job to new Revision) | 1000 | 8
Phase19.P007 | #684 (Select Revision to Create Call Sheet) | 1000 | 8
Phase19.P008 | #685 (Display revision on the eService) | 1000 | 8
Phase19.P009 | #686 (Display revision on the eService) | 1000 | 8
Phase19.P010 | #687 (Display Revision on the EService) | 1000 | 8
Phase19.P011 | #688 (Display Revision Count on eProgram) | 1000 | 8
Phase19.P012 | #689 (Import program file with the same prgID and different revision) | 1000 | 8
Phase19.P013 | #690 (Improve Blend display on RigBoard)BA | 950 | 8
Phase19.P014 | #691 (Display PREFL 、BLEND and DISPL on RigBoad) | 950 | 8
Phase19.P015 | #692 (Improve product display on RigBoad) | 950 | 8
Phase19.P016 | #693 (Display Based BLend on Tooptip) | 950 | 8
Phase19.P017 | #694 (Display PREFL、BLEND and DISPL on RigBoad) | 950 | 8
Phase19.P018 | #695 (Display products in PREFL、BLEND and DISPL | 950 | 8
Phase19.P019 | #696 (Improve Based Blend display on Tooptip) | 950 | 8
Phase19.P020 | #697 (Display PREFL 、BLEND and DISPL on RigBoad) | 950 | 8
Phase19.P021 | #699 (Improve blend description in Tooptip) | 950 | 8
Phase19.P022 | #701 (Add revision description in template) | 950 | 8
Phase19.P023 | Data migration | 1000 | 40
Phase19.P024 | #700 (Add revision description) | 1000 | 8
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT
StartDate | 2020-02-01
EndDate | 2020-03-01
Est Time
Name | Role | Total Hours | 2020-02-01 | 2020-02-02 | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16 | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02
|  |  | 43862 | 43863 | 43864 | 43865 | 43866 | 43867 | 43868 | 43869 | 43870 | 43871 | 43872 | 43873 | 43874 | 43875 | 43876 | 43877 | 43878 | 43879 | 43880 | 43881 | 43882 | 43883 | 43884 | 43885 | 43886 | 43887 | 43888 | 43889 | 43890 | 43891 | 43892
Ideal Burndown |  | 145 | 145 | 145 | 135 | 125 | 115 | 105 | 95 | 95 | 95 | 89 | 83 | 77 | 71 | 65 | 65 | 65 | 56 | 47 | 38 | 29 | 20 | 20 | 20 | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0
Hours consumed |  | 145 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
Malone.wang |  | 120 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 4 | 4 | 4 | 4 | 4
Migue |  | 0
daisy.huang |  | 25 | 2020-02-03: 2; 2020-02-04: 2; 2020-02-05: 2; 2020-02-06: 2; 2020-02-07: 2; 2020-02-10: 2; 2020-02-11: 2; 2020-02-12: 2; 2020-02-13: 2; 2020-02-14: 2; 2020-02-17: 1; 2020-02-18: 1; 2020-02-19: 1; 2020-02-20: 1; 2020-02-21: 1

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase19.P001 | 会议 | 1000 | 11 | 0 | 0 | 0
Phase19.P002 | 项目管理 | 1000 | 11 | 0 | 0 | 0
Phase19.P003 | #680 (Display Revision info. on the eProgram) | 1000 | 8 | 1 | Malone.wang | 8
Phase19.P004 | #681 (Import program file with revision number) | 1000 | 8 | 1 | Malone.wang | 8
Phase19.P005 | #682 (Display revision info. on eProgram) | 1000 | 8 | 1 | Malone.wang | 6
Phase19.P006 | #683 (Update Rig Job to new Revision) | 1000 | 8 | 1 | Malone.wang | 6
Phase19.P007 | #684 (Select Revision to Create Call Sheet) | 1000 | 8 | 1 | Malone.wang | 4
Phase19.P008 | #685 (Display revision on the eService) | 1000 | 8 | 1 | Malone.wang | 8
Phase19.P009 | #686 (Display revision on the eService) | 1000 | 8 | 1 | Malone.wang | 8
Phase19.P010 | #687 (Display Revision on the EService) | 1000 | 8 | 1 | Malone.wang | 9
Phase19.P011 | #688 (Display Revision Count on eProgram) | 1000 | 8 | 1 | Malone.wang | 7
Phase19.P012 | #689 (Import program file with the same prgID and different revision) | 1000 | 8 | 1 | Malone.wang | 8
Phase19.P013 | #690 (Improve Blend display on RigBoard)BA | 950 | 8 | 1 | daisy.huang | 4
Phase19.P014 | #691 (Display PREFL 、BLEND and DISPL on RigBoad) | 950 | 8 | 1 | daisy.huang | 4
Phase19.P015 | #692 (Improve product display on RigBoad) | 950 | 8 | 1 | daisy.huang | 4
Phase19.P016 | #693 (Display Based BLend on Tooptip) | 950 | 8 | 1 | daisy.huang | 4
Phase19.P017 | #694 (Display PREFL、BLEND and DISPL on RigBoad) | 950 | 8 | 1 | daisy.huang | 4
Phase19.P018 | #695 (Display products in PREFL、BLEND and DISPL | 950 | 8 | 1 | daisy.huang | 4
Phase19.P019 | #696 (Improve Based Blend display on Tooptip) | 950 | 8 | 1 | daisy.huang | 4
Phase19.P020 | #697 (Display PREFL 、BLEND and DISPL on RigBoad) | 950 | 8 | 1 | Malone.wang | 4
Phase19.P021 | #699 (Improve blend description in Tooptip) | 950 | 8 | 1 | Malone.wang | 4
Phase19.P022 | #701 (Add revision description in template) | 950 | 8 | 1 | Malone.wang | 4
Phase19.P023 | Data migration | 1000 | 40 | 1 | Migue | 32
Phase19.P024 | #700 (Add revision description) | 1000 | 8 | 1 | Malone.wang | 8
0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间