## Daily Records
ID | Name | Prioritize | Est(Hour) | 2017-01-02 | 2017-01-03 | 2017-01-04 | 2017-01-05 | 2017-01-06 | Total Hours
|  |  |  | 周日 | 42738 | 42739 | 42740 | 42741
| Est |  | 108 | 104 | 76 | 49 | 22 | 0 | 93.7
| Actual |  | 81.5 | 104 | 77 | 63 | 37.8 | 10.3
|  |  | 108 | 0 | 27 | 14 | 25.2 | 27.5
I004 | Meeting | 1000 | 14 |  | 7 |  |  |  | 7 | All
S003 | Requirements analysis | 1000 | 4 |  |  |  | 3.5 | 3 | 6.5 | Bella.bi & Bela.zhao & Olivia.ge
UC001.US01 | Code refactoring to separate framework | 1000 | 10 |  | 0.5 | 2 |  |  | 2.5 | Olivia.ge
UC003.US01 | Add Net Price | 950 | 1 |  |  | 1 |  |  | 1 | Bela.zhao
UC007.US01 | Create multiple call sheet from a multiple job type program | 800 | 6.5 |  | 5.5 | 1 | 5 |  | 11.5 | Olivia.ge
UC009.US01 | Validation ProgramID for Importing excel | 800 | 10 |  |  |  | 6 | 1 | 7 | Bela.zhao
UC003.US03 | Add Template ID _implement | 790 | 12 |  | 5 | 1.5 |  |  | 6.5 | Shawn.shao
UC003.US01-DAO | Add net price dao | 790 | 1 |  | 1.5 | 1 |  |  | 2.5 | Leo.tian
T002 | Fix test of importing program with new template | 780 | 10 |  | 6 | 1 |  |  | 7 | Bela.zhao
UC003.US04 | Update DepthBaseCharge | 780 | 3 |  |  | 2.5 |  |  | 2.5 | Bela.zhao
UC003.US05 | Update NetPrice Calculation | 750 | 10 |  |  |  | 5 | 5 | 10 | Shawn.shao
UC003.US06 | Update NetPrice Historical data | 750 | [6 empty] | 0 | Bela.zhao
UC007.US02 | Create call sheet from program_Default Call Sheet Type | 740 | 2 |  |  |  | 1 |  | 1 | Olivia.ge
UC007.US04 | Create call sheet from program_Job Designer,Chargemethod and Client Solutions Representative | 740 | 5 |  |  |  |  | 5 | 5 | Olivia.ge
UC003.US07 | Update GroupedLineItemControl | 730 | 3 |  |  |  | 3 | 2 | 5 | Bela.zhao
T001 | Fix bug which left over by history | 600 | 7 |  |  | 4 | 1.5 | 1 | 6.5 | Shawn.shao &Bela.zhao & Olivia.ge
T002 | Fix bug which caused by requirement | 600 | 2 |  |  |  | 0.2 | 1 | 1.2
I005 | Study for eService | 500 | 5 |  | 1.5 |  |  | 7 | 8.5 | Jack.yu
UC003.US02 | Add Template ID _design | 500 | 2.5 |  |  |  |  | 2.5 | 2.5
Note on H7: Bella Bi: Olivia 0.5h Bella 3h
Note on I7: Bella Bi: 1H Olivia 熟悉计算相关的需求 1H Bela 熟悉计算相关的需求 1H Bella 任务安排
Note on G8: Bella Bi: Olivia 2h将CheckBox提到工具类
Note on H10: Bella Bi: 修改需求补充文档中第7个Bug：Create call sheet from program, root group is missing. No matter what, root group is always there.
Note on G12: Bella Bi: Randy 0.5h Review code Shawn 1h Implement
Note on B13: Bella Bi: 写NetPrice
Note on B14: Bella Bi: 根据新的Excel Template修改测试代码
Note on H16: Bella Bi: 熟悉计算相关的需求
Note on I16: Bella Bi: 修复需求补充说明的问题2
Note on B21: Bella Bi: 修改遗留问题
Note on G21: Bella Bi: Shawn 1.5h修复导入的测试不通过的问题 Shawn 2h Create callsheet第四步无法继续的问题
Note on H21: Bella Bi: Olivia 0.5h修改报错问题 Shawn 1h Create callsheet第四步无法继续的问题
Note on I21: Bella Bi: 1H Bela 修复问题5，将默认0改为1
Note on H22: Bella Bi: Bela 0.2h 客户提出的两处UI的修改
Note on I22: Bella Bi: 1H Olivia 修改Create
Note on I23: Bella： 2h Jack 完成UC003.US07一部分功能 5H Frank修复问题5

## Resources
SPRINT | 1
StartDate | 2017-01-03
EndDate | 2017-01-07
Est Time
Name | Role | Total Hours | 2017-01-03 | 2017-01-04 | 2017-01-05 | 2017-01-06
|  |  | 42738 | 42739 | 42740 | 42741
合计 |  | 104 | 76 | 49 | 22 | 0
|  | 104 | 28 | 27 | 27 | 22
Olivia.Ge |  | 28 | 7 | 7 | 7 | 7
Bella.Bi |  | 5 | 2 | 1 | 1 | 1
Bela.Zhao |  | 28 | 7 | 7 | 7 | 7
Shawn.Shao |  | 23 | 7 | 7 | 7 | 2
Randy.Ling |  | 4 | 1 | 1 | 1 | 1
Jack.Yu |  | 8 | 2 | 2 | 2 | 2
Leo.Tian |  | 8 | 2 | 2 | 2 | 2
Actual Time
Name | Role | Total Hours | 2017-01-03 | 2017-01-04 | 2017-01-05 | 2017-01-06
|  |  | 42738 | 42739 | 42740 | 42741
合计 |  | 93.7 | 66.7 | 52.7 | 27.5 | 0
|  | 93.7 | 27 | 14 | 25.2 | 27.5
Olivia.Ge |  | 24 | 7 | 3 | 7 | 7
Bella.Bi |  | 5 | 1 | 0 | 3 | 1
Bela.Zhao |  | 22.7 | 7 | 4.5 | 6.2 | 5
Shawn.Shao |  | 22 | 6 | 5 | 6 | 5
Randy.Ling |  | 4 | 1 | 0.5 | 0 | 2.5
Jack.Yu |  | 7.5 | 2.5 | 0 | 3 | 2
Leo.Tian |  | 3.5 | 2.5 | 1 | 0 | 0
Frank.Zhang |  | 5 | 0 | 0 | 0 | 5

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | StartDate | EndDate | Assign To | Actual(Hour) | Remark
I004 | Meeting | 1000 | 14 | 1 | 2017-01-03 | 2017-01-06 | All | 7
S003 | Requirements analysis | 1000 | 4 | 4 | 2017-01-05 | 2017-01-06 | Bella.bi & Bela.zhao & Olivia.ge | 6.5
UC001.US01 | Code refactoring to separate framework | 1000 | 10 | 1 | 2017-01-03 | 2017-01-04 | Olivia.ge | 2.5
UC003.US01 | Add Net Price | 950 | 1 | 1 | 2017-01-04 | 2017-01-04 | Bela.zhao | 1 | 还差数据库，单元测试
UC007.US01 | Create multiple call sheet from a multiple job type program | 800 | 6.5 | 1 | 2017-01-03 | 2017-01-04 | Olivia.ge | 11.5
UC009.US01 | Validation ProgramID for Importing excel | 800 | 10 | 1 | 2017-01-05 | 2017-01-06 | Bela.zhao | 7
UC003.US03 | Add Template ID _implement | 790 | 12 | 1 | 2017-01-04 | 2017-01-05 | Shawn.shao | 6.5
UC003.US01-DAO | Add net price dao | 790 | 1 | 1 | 2017-01-03 | 2017-01-04 | Leo.tian | 2.5
T002 | Fix test of importing program with new template | 780 | 10 | 1 | 2017-01-03 | 2017-01-04 | Bela.zhao | 7
UC003.US04 | Update DepthBaseCharge | 780 | 3 | 1 | 2017-01-04 | 2017-01-04 | Bela.zhao | 2.5
UC003.US05 | Update NetPrice Calculation | 750 | 10 | 1 | 2017-01-05 | 2017-01-06 | Shawn.shao | 10 | 需求补充第二个问题
UC003.US06 | Update NetPrice Historical data | 750 | 0 | 0 |  |  | Bela.zhao | 0
UC007.US02 | Create call sheet from program_Default Call Sheet Type | 740 | 2 | 1 | 2017-01-05 | 2017-01-05 | Olivia.ge | 1
UC007.US04 | Create call sheet from program_Job Designer,Chargemethod and Client Solutions Representative | 740 | 5 | 1 | 2017-01-06 | 2017-01-06 | Olivia.ge | 5
UC003.US07 | Update GroupedLineItemControl | 730 | 3 | 1 | 2017-01-05 | 2017-01-06 | Bela.zhao | 5
T001 | Fix bug which left over by history | 600 | 7 | 1 | 2017-01-04 | 2017-01-06 | Shawn.shao &Bela.zhao & Olivia.ge | 6.5 | 2
T002 | Fix bug which caused by requirement | 600 | 2 | 1 | 2017-01-05 | 2017-01-06 | Bela.zhao & Olivia.ge | 1.2
I005 | Study for eService | 500 | 5 | 1 | 2017-01-03 | 2017-01-06 | Jack.yu | 8.5
UC003.US02 | Add Template ID _design | 500 | 2.5 | 1 | 2017-01-06 | 2017-01-06 | Randy.ling | 2.5
Total Backlogs | 3 | Total Estimate Hours |  | 108
Finished Backlogs | 20 | Total Hours of Finished Backlogs |  | 93.7
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务开始时间
Note on G1: Ying Li: 任务结束时间
Note on H1: Ying Li: 任务负责人
Note on I1: Ying Li: 任务投入总时间
Note on A24: Ying Li: 公式计算，迭代计划完成的任务数量
Note on A25: Ying Li: 根据完成状态计算，已完成的任务数量