## Daily Records
ID | Name | Prioritize | Est(Hour) | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29 | 2020-03-30 | 2020-03-31 | Total Hours
|  |  |  | 43890 | 43891 | 43892 | 43893 | 43894 | 43895 | 43896 | 43897 | 43898 | 43899 | 43900 | 43901 | 43902 | 43903 | 43904 | 43905 | 43906 | 43907 | 43908 | 43909 | 43910 | 43911 | 43912 | 43913 | 43914 | 43915 | 43916 | 43917 | 43918 | 43919 | 43920 | 43921
| Ideal Burndown |  | 331 | 331 | 331 | 315 | 299 | 283 | 266 | 249 | 249 | 249 | 233 | 217 | 200 | 183 | 166 | 166 | 166 | 150 | 134 | 117 | 100 | 83 | 83 | 83 | 67 | 51 | 34 | 17 | 0 | 0 | 0 | 0 | 0 | 330.5
| Actual |  | 346 | 331 | 331 | 330.5 | 330 | 329.5 | 329 | 328.5 | 328.5 | 328.5 | 307 | 282.5 | 257.5 | 245.5 | 236 | 236 | 236 | 214.5 | 197 | 182 | 167 | 156.5 | 156.5 | 156.5 | 146 | 133.5 | 120.5 | 105.5 | 91.5 | 91.5 | 91.5 | 75.5 | 59.5
|  |  |  | #REF! | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 21.5 | 24.5 | 25 | 12 | 9.5 | 0 | 0 | 21.5 | 17.5 | 15 | 15 | 10.5 | 0 | 0 | 10.5 | 12.5 | 13 | 15 | 14 | 0 | 0 | 16 | 16 | 330.5 | Assign to | Completion Status | Pay by | Module
Phase19.P001 | 会议 | 1000 | 11 | 2020-03-02: 0.5; 2020-03-03: 0.5; 2020-03-04: 0.5; 2020-03-05: 0.5; 2020-03-06: 0.5; 2020-03-09: 0.5; 2020-03-10: 0.5; 2020-03-11: 0.5; 2020-03-12: 0.5; 2020-03-13: 0.5; 2020-03-16: 0.5; 2020-03-17: 0.5; 2020-03-18: 0.5; 2020-03-19: 0.5; 2020-03-20: 0.5; 2020-03-23: 0.5; 2020-03-24: 0.5; 2020-03-25: 0.5; 2020-03-26: 0.5 | 9.5
Phase19.P002 | 项目管理 | 1000 | 11 | 2020-03-04: 0.5; 2020-03-05: 0.5; 2020-03-11: 0.5; 2020-03-12: 0.5; 2020-03-18: 0.5; 2020-03-19: 0.5; 2020-03-25: 0.5; 2020-03-26: 0.5 | 4
Phase19.P003 | #701 (Add revision description in template) | 1000 | 8 | 2020-02-29: 8; 2020-03-02: 2; 2020-03-03: 2 | 4 | Malone.wang | 1 | Sanjel | eService
Phase19.P004 | #703 (Show alert on Rigboard for new program revision available) | 1000 | 8 | 2020-03-05: 2; 2020-03-06: 3 | 5 | Malone.wang | 1 | Sanjel | eService
Phase19.P005 | #704 (Show alert on Rigboard for new program revision available) | 1000 | 8 | 2020-03-05: 2; 2020-03-06: 3 | 5 | daisy.huang | 1 | Sanjel | eService
Phase19.P006 | #706 (Import "Mix Water", "Yield" and "Sack Weight" to Program) | 1000 | 8 | 2020-03-05: 1; 2020-03-06: 1; 2020-03-09: 2; 2020-03-10: 2; 2020-03-11: 2 | 8 | daisy.huang | 1 | Sanjel | eService
Phase19.P007 | #707 (Display "Mix Water", "Yield" and "Sack Weight" on eService) | 1000 | 8 | 2020-03-05: 1; 2020-03-06: 1; 2020-03-09: 2; 2020-03-10: 2; 2020-03-11: 2 | 8 | daisy.huang | 1 | Sanjel | eService
Phase19.P008 | #708 (Display Mix Water on eService Online) | 1000 | 8 | 2020-03-05: 1; 2020-03-06: 1; 2020-03-09: 2; 2020-03-10: 2; 2020-03-11: 2; 2020-03-16: 1; 2020-03-17: 1 | 10 | daisy.huang | 1 | Sanjel | eService
Phase19.P009 | #709 ("Mix Water", "Yield" and "Sack Weight" value need to print on Blend Breakdown Sheet.) | 1000 | 8 | 2020-03-05: 1; 2020-03-06: 1; 2020-03-09: 2; 2020-03-10: 2; 2020-03-11: 2; 2020-03-16: 1; 2020-03-17: 1 | 10 | daisy.huang | 1 | Sanjel | eService
Phase19.P010 | #710 (Show alert on Rigboard for new program revision available) | 1000 | 8 | 2020-03-05: 1; 2020-03-06: 1; 2020-03-09: 2; 2020-03-10: 2; 2020-03-11: 2; 2020-03-16: 1; 2020-03-17: 1 | 10 | daisy.huang | 1 | Sanjel | eService
Phase19.P011 | #711 (Import "Mix Water", "Yield" and "Sack Weight" to Program) | 1000 | 16 | 2020-03-09: 1; 2020-03-10: 2; 2020-03-11: 2; 2020-03-12: 1; 2020-03-13: 1; 2020-03-16: 2; 2020-03-17: 2; 2020-03-18: 2; 2020-03-19: 2 | 15 | Malone.wang | 1 | Sanjel | eService
Phase19.P012 | #712 (Complete Program Blend Import Paramters on eService) | 1000 | 16 | 2020-03-09: 1; 2020-03-10: 2; 2020-03-11: 2; 2020-03-12: 1; 2020-03-13: 1; 2020-03-16: 2; 2020-03-17: 2; 2020-03-18: 2; 2020-03-19: 2 | 15 | Malone.wang | 1 | Sanjel | eService
Phase19.P013 | #713 (Display Mix Water on eService Online) | 1000 | 16 | 2020-03-09: 1; 2020-03-10: 2; 2020-03-11: 2; 2020-03-12: 1; 2020-03-13: 1; 2020-03-16: 2; 2020-03-17: 2; 2020-03-18: 2; 2020-03-19: 2 | 15 | Malone.wang | 1 | Sanjel | eService
Phase19.P014 | #714 (Add Bulk Density to Blend Chemical) | 1000 | 2 | 2020-03-20: 2 | 2 | Malone.wang | 1 | Sanjel | eService
Phase19.P015 | #715 (Add BulkDensity property to BlendChemical) | 1000 | 2 | 2020-03-20: 2 | 2 | Malone.wang | 1 | Sanjel | eService
Phase19.P016 | #716 (Confirm and Update program change from new version) | 1000 | 2 | 2020-03-20: 2 | 2 | Malone.wang | 1 | Sanjel | eService
Phase19.P017 | #722 (Update Call Sheet from latest program revision) | 950 | 4 | 2020-03-23: 2; 2020-03-26: 1; 2020-03-27: 1 | 4 | daisy.huang | 1 | Sanjel | eService
Phase19.P018 | #724 (Update Call Sheet from latest program revision) created by daisy.huang | 950 | 4 | 2020-03-24: 2; 2020-03-26: 1; 2020-03-27: 1 | 4 | Malone.wang | 1 | Sanjel | eService
Phase19.P019 | #725 (Add the “View Changes” ContextMenuItem) created by malone.wang | 950 | 4 | 2020-03-24: 2; 2020-03-26: 1; 2020-03-27: 1 | 4 | daisy.huang | 1 | Sanjel | eService
Phase19.P020 | #726 (Show the program revision review page) | 950 | 2 | 2020-03-25: 2; 2020-03-30: 2 | 4 | Malone.wang | 1 | Sanjel | eService
Phase19.P021 | #727 (verify and update if accept changes) created by malone.wang | 950 | 6 | 2020-03-25: 2; 2020-03-30: 2; 2020-03-31: 2 | 6 | Malone.wang | 1 | Sanjel | eService
Phase19.P022 | #728 (Stop alerting if ignore changes) created by malone.wang | 950 | 6 | 2020-03-26: 1; 2020-03-27: 1; 2020-03-30: 2; 2020-03-31: 2 | 6 | Malone.wang | 1 | Sanjel | eService
Phase19.P023 | #729 (Continue alerting if work on it later) created by malone.wang | 950 | 6 | 2020-03-26: 1; 2020-03-27: 1; 2020-03-30: 2; 2020-03-31: 2 | 6 | Malone.wang | 1 | Sanjel | eService
Phase19.P024 | #730 (Data Fields to verify changes) created by malone.wang | 950 | 6 | 2020-03-26: 1; 2020-03-27: 1; 2020-03-31: 2 | 4 | Malone.wang | 1 | Sanjel | eService
Phase19.P025 | Loggin research and PoC | 950 | 24 | 2020-03-02: 8; 2020-03-03: 6; 2020-03-09: 2; 2020-03-17: 2 | 18 | Migue | 1 | Sanjel | eService
Phase19.P026 | Evaluationg, Testing and POoC of Azure for eService | 950 | 36 | 2020-03-03: 2; 2020-03-04: 4; 2020-03-05: 4; 2020-03-06: 4; 2020-03-09: 4; 2020-03-10: 4; 2020-03-11: 4; 2020-03-12: 2; 2020-03-13: 2; 2020-03-30: 2; 2020-03-31: 2 | 34 | Migue | 1 | Sanjel | eService
Phase19.P027 | eService Winforms Azure AD user authentication | 950 | 36 | 2020-03-16: 8; 2020-03-17: 2; 2020-03-18: 4; 2020-03-19: 4; 2020-03-23: 6; 2020-03-24: 6; 2020-03-30: 2; 2020-03-31: 2 | 34 | Migue | 1 | Sanjel | eService
Phase19.P028 | Once the user is authenticated while login, how credential can be retained on local? | 950 | 40 | 2020-03-09: 2; 2020-03-10: 4; 2020-03-11: 4; 2020-03-12: 4; 2020-03-13: 4; 2020-03-17: 2; 2020-03-18: 2; 2020-03-19: 2; 2020-03-20: 2; 2020-03-25: 4; 2020-03-26: 4; 2020-03-27: 4; 2020-03-30: 2; 2020-03-31: 2 | 42 | Migue | 1 | Sanjel | eService
Phase19.P029 | eService Offline authentication | 950 | 24 | 2020-03-17: 2; 2020-03-18: 2; 2020-03-19: 2; 2020-03-20: 2; 2020-03-23: 2; 2020-03-24: 2; 2020-03-25: 4; 2020-03-26: 4; 2020-03-27: 4; 2020-03-30: 2; 2020-03-31: 2 | 28 | Migue | 1 | Sanjel | eService
Phase19.P030 | some hours helping Malone | 950 | 8 | 2020-03-04: 2; 2020-03-05: 2; 2020-03-06: 2; 2020-03-12: 2; 2020-03-16: 4 | 12 | Migue | 1 | Sanjel | eService

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29 | 2020-03-30 | 2020-03-31
|  |  |  | 43890 | 43891 | 43892 | 43893 | 43894 | 43895 | 43896 | 43897 | 43898 | 43899 | 43900 | 43901 | 43902 | 43903 | 43904 | 43905 | 43906 | 43907 | 43908 | 43909 | 43910 | 43911 | 43912 | 43913 | 43914 | 43915 | 43916 | 43917 | 43918 | 43919 | 43920 | 43921
| Ideal Burndown |  | 331 | 331 | 331 | 315 | 299 | 283 | 266 | 249 | 249 | 249 | 233 | 217 | 200 | 183 | 166 | 166 | 166 | 150 | 134 | 117 | 100 | 83 | 83 | 83 | 67 | 51 | 34 | 17 | 0 | 0 | 0 | 0 | 0
| Actual burndown |  | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase19.P001 | 会议 | 1000 | 11
Phase19.P002 | 项目管理 | 1000 | 11
Phase19.P003 | #701 (Add revision description in template) | 1000 | 8
Phase19.P004 | #703 (Show alert on Rigboard for new program revision available) | 1000 | 8
Phase19.P005 | #704 (Show alert on Rigboard for new program revision available) | 1000 | 8
Phase19.P006 | #706 (Import "Mix Water", "Yield" and "Sack Weight" to Program) | 1000 | 8
Phase19.P007 | #707 (Display "Mix Water", "Yield" and "Sack Weight" on eService) | 1000 | 8
Phase19.P008 | #708 (Display Mix Water on eService Online) | 1000 | 8
Phase19.P009 | #709 ("Mix Water", "Yield" and "Sack Weight" value need to print on Blend Breakdown Sheet.) | 1000 | 8
Phase19.P010 | #710 (Show alert on Rigboard for new program revision available) | 1000 | 8
Phase19.P011 | #711 (Import "Mix Water", "Yield" and "Sack Weight" to Program) | 1000 | 16
Phase19.P012 | #712 (Complete Program Blend Import Paramters on eService) | 1000 | 16
Phase19.P013 | #713 (Display Mix Water on eService Online) | 1000 | 16
Phase19.P014 | #714 (Add Bulk Density to Blend Chemical) | 1000 | 2
Phase19.P015 | #715 (Add BulkDensity property to BlendChemical) | 1000 | 2
Phase19.P016 | #716 (Confirm and Update program change from new version) | 1000 | 2
Phase19.P017 | #722 (Update Call Sheet from latest program revision) | 950 | 4
Phase19.P018 | #724 (Update Call Sheet from latest program revision) created by daisy.huang | 950 | 4
Phase19.P019 | #725 (Add the “View Changes” ContextMenuItem) created by malone.wang | 950 | 4
Phase19.P020 | #726 (Show the program revision review page) | 950 | 2
Phase19.P021 | #727 (verify and update if accept changes) created by malone.wang | 950 | 6
Phase19.P022 | #728 (Stop alerting if ignore changes) created by malone.wang | 950 | 6
Phase19.P023 | #729 (Continue alerting if work on it later) created by malone.wang | 950 | 6
Phase19.P024 | #730 (Data Fields to verify changes) created by malone.wang | 950 | 6
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT
StartDate | 2020-03-01
EndDate | 2020-03-30
Est Time
Name | Role | Total Hours | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29 | 2020-03-30 | 2020-03-31
|  |  | 43891 | 43892 | 43893 | 43894 | 43895 | 43896 | 43897 | 43898 | 43899 | 43900 | 43901 | 43902 | 43903 | 43904 | 43905 | 43906 | 43907 | 43908 | 43909 | 43910 | 43911 | 43912 | 43913 | 43914 | 43915 | 43916 | 43917 | 43918 | 43919 | 43920 | 43921
Ideal Burndown |  | 331 | 331 | 315 | 299 | 283 | 266 | 249 | 249 | 249 | 233 | 217 | 200 | 183 | 166 | 166 | 166 | 150 | 134 | 117 | 100 | 83 | 83 | 83 | 67 | 51 | 34 | 17 | 0 | 0 | 0 | 0 | 0
Hours consumed |  | 331 | 0 | 16 | 16 | 16 | 17 | 17 | 0 | 0 | 16 | 16 | 17 | 17 | 17 | 0 | 0 | 16 | 16 | 17 | 17 | 17 | 0 | 0 | 16 | 16 | 17 | 17 | 17 | 0 | 0 | 0 | 0
Malone.wang |  | 160 |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8
Migue |  | 160 |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8
daisy.huang |  | 11 | bar: 2020-03-05 to 2020-03-06; 2020-03-11 to 2020-03-13; 2020-03-18 to 2020-03-20; 2020-03-25 to 2020-03-27

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase19.P001 | 会议 | 1000 | 11 | 0 | 0 | 9.5
Phase19.P002 | 项目管理 | 1000 | 11 | 0 | 0 | 4
Phase19.P003 | #701 (Add revision description in template) | 1000 | 8 | 1 | Malone.wang | 4
Phase19.P004 | #703 (Show alert on Rigboard for new program revision available) | 1000 | 8 | 1 | Malone.wang | 5
Phase19.P005 | #704 (Show alert on Rigboard for new program revision available) | 1000 | 8 | 1 | daisy.huang | 5
Phase19.P006 | #706 (Import "Mix Water", "Yield" and "Sack Weight" to Program) | 1000 | 8 | 1 | daisy.huang | 8
Phase19.P007 | #707 (Display "Mix Water", "Yield" and "Sack Weight" on eService) | 1000 | 8 | 1 | daisy.huang | 8
Phase19.P008 | #708 (Display Mix Water on eService Online) | 1000 | 8 | 1 | daisy.huang | 10
Phase19.P009 | #709 ("Mix Water", "Yield" and "Sack Weight" value need to print on Blend Breakdown Sheet.) | 1000 | 8 | 1 | daisy.huang | 10
Phase19.P010 | #710 (Show alert on Rigboard for new program revision available) | 1000 | 8 | 1 | daisy.huang | 10
Phase19.P011 | #711 (Import "Mix Water", "Yield" and "Sack Weight" to Program) | 1000 | 16 | 1 | Malone.wang | 15
Phase19.P012 | #712 (Complete Program Blend Import Paramters on eService) | 1000 | 16 | 1 | Malone.wang | 15
Phase19.P013 | #713 (Display Mix Water on eService Online) | 1000 | 16 | 1 | Malone.wang | 15
Phase19.P014 | #714 (Add Bulk Density to Blend Chemical) | 1000 | 2 | 1 | Malone.wang | 2
Phase19.P015 | #715 (Add BulkDensity property to BlendChemical) | 1000 | 2 | 1 | Malone.wang | 2
Phase19.P016 | #716 (Confirm and Update program change from new version) | 1000 | 2 | 1 | Malone.wang | 2
Phase19.P017 | #722 (Update Call Sheet from latest program revision) | 950 | 4 | 1 | daisy.huang | 4
Phase19.P018 | #724 (Update Call Sheet from latest program revision) created by daisy.huang | 950 | 4 | 1 | Malone.wang | 4
Phase19.P019 | #725 (Add the “View Changes” ContextMenuItem) created by malone.wang | 950 | 4 | 1 | daisy.huang | 4
Phase19.P020 | #726 (Show the program revision review page) | 950 | 2 | 1 | Malone.wang | 4
Phase19.P021 | #727 (verify and update if accept changes) created by malone.wang | 950 | 6 | 1 | Malone.wang | 6
Phase19.P022 | #728 (Stop alerting if ignore changes) created by malone.wang | 950 | 6 | 1 | Malone.wang | 6
Phase19.P023 | #729 (Continue alerting if work on it later) created by malone.wang | 950 | 6 | 1 | Malone.wang | 6
Phase19.P024 | #730 (Data Fields to verify changes) created by malone.wang | 950 | 6 | 1 | Malone.wang | 4
Phase19.P025 | Loggin research and PoC | 950 | 24 | 1 | Migue | 18
Phase19.P026 | Evaluationg, Testing and POoC of Azure for eService | 950 | 36 | 1 | Migue | 34
Phase19.P027 | eService Winforms Azure AD user authentication | 950 | 36 | 1 | Migue | 34
Phase19.P028 | Once the user is authenticated while login, how credential can be retained on local? | 950 | 40 | 1 | Migue | 42
Phase19.P029 | eService Offline authentication | 950 | 24 | 1 | Migue | 28
Phase19.P030 | some hours helping Malone | 950 | 8 | 1 | Migue | 12
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间