## Daily Records
ID | Name | Prioritize | Est(Hour) | [66 empty] | Total Hours | time axis 2021-09-26 to 2021-11-30
 | time axis 2021-09-26 to 2021-11-30
| Ideal Burndown |  | 512 | 512 | 504 | 504 | 496 | 488 | 488 | 488 | 488 | 488 | 488 | 488 | 488 | 480 | 472 | 472 | 464 | 456 | 448 | 440 | 432 | 432 | 432 | 424 | 416 | 408 | 400 | 392 | 392 | 392 | 384 | 376 | 368 | 360 | 352 | 352 | 352 | 336 | 320 | 304 | 288 | 272 | 272 | 272 | 256 | 240 | 224 | 208 | 192 | 192 | 192 | 176 | 160 | 144 | 128 | 112 | 112 | 112 | 96 | 80 | 64 | 48 | 32 | 32 | 32 | 16 | 0 | 280
| Actual |  | 269.5 | 512 | 511.5 | 511.5 | 509 | 504 | 504 | 504 | 504 | 504 | 504 | 504 | 504 | 496.5 | 488.5 | 488.5 | 480.5 | 472.5 | 465.5 | 461 | 454 | 454 | 454 | 446 | 438 | 430 | 424 | 416 | 416 | 416 | 408 | 400 | 392 | 384 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376 | 376
|  |  |  | 2021-09-26: 0; 2021-09-27: 0.5; 2021-09-28: 0; 2021-09-29: 2.5; 2021-09-30: 5; 2021-10-01: 0; 2021-10-02: 0; 2021-10-03: 0; 2021-10-04: 0; 2021-10-05: 0; 2021-10-06: 0; 2021-10-07: 0; 2021-10-08: 7.5; 2021-10-09: 8; 2021-10-10: 0; 2021-10-11: 8; 2021-10-12: 8; 2021-10-13: 7; 2021-10-14: 4.5; 2021-10-15: 7; 2021-10-16: 0; 2021-10-17: 0; 2021-10-18: 8; 2021-10-19: 8; 2021-10-20: 8; 2021-10-21: 6; 2021-10-22: 8; 2021-10-23: 0; 2021-10-24: 0; 2021-10-25: 8; 2021-10-26: 8; 2021-10-27: 8; 2021-10-28: 8; 2021-10-29: 8; 2021-10-30: 0; 2021-10-31: 0 | 280 | Assign to | Completion Status | Pay by | Module
#14430 | Reset and Update github | 1000 | 0.5 | 2021-09-27: 0.5 | 0.5 | Miguel | 1 | Sanjel | Online
#14460 | Setup Environment | 1000 | 5 | 2021-09-29: 2.5; 2021-09-30: 5 | 7.5 | Miguel | 1 | Sanjel | Online
#14515 | Refactor Views Javascript | 1000 | 48 | 2021-10-08: 7.5; 2021-10-09: 8; 2021-10-11: 8; 2021-10-12: 8; 2021-10-13: 7; 2021-10-14: 4.5; 2021-10-15: 7; 2021-10-18: 8; 2021-10-19: 5; 2021-10-29: 8; 2021-11-01: 6; 2021-11-02: 7; 2021-11-03: 6; 2021-11-04: 2; 2021-11-08: 8; 2021-11-09: 6; 2021-11-10: 5; 2021-11-11: 5; 2021-11-12: 8; 2021-11-15: 4 | 71 | Miguel | 1 | Sanjel | Online
#14595 | Publish web application to website configuration | 950 | 64 | 2021-10-19: 3; 2021-10-20: 8; 2021-10-21: 6; 2021-10-22: 8; 2021-10-25: 8; 2021-10-26: 8; 2021-10-27: 8; 2021-10-28: 8; 2021-11-04: 2.5; 2021-11-15: 4 | 57 | Miguel |  | Sanjel | Online
#14960 | Support | 950 | 3 | 2021-11-01: 1; 2021-11-02: 1; 2021-11-03: 1; 2021-11-04: 3; 2021-11-05: 5; 2021-11-09: 2; 2021-11-10: 3; 2021-11-11: 3 |  | Miguel |  | Sanjel
#15001 | Commit CommonCore on GitHub | 950 | 5 | [69 empty] | Sanjel
#14981 | Setup Environment | 950 | 8 | 2021-11-01: 8 | 8 | Evan.Zhang |  | Sanjel | Online
#14982 | Get Database And Study document | 950 | 8 | 2021-11-02: 8 | 8 | Evan.Zhang |  | Sanjel | Online
#14984 | Git Clone Code And Debug | 950 | 8 | 2021-11-03: 8 | 8 | Evan.Zhang |  | Sanjel | Online
#14985 | Git New Branch And Study Code | 950 | 16 | 2021-11-04: 8; 2021-11-05: 8; 2021-11-08: 0 | 16 | Evan.Zhang |  | Sanjel | Online
#15049 | Refactor Views Javascript | 950 | 40 | 2021-11-08: 8; 2021-11-09: 8; 2021-11-10: 8; 2021-11-11: 8; 2021-11-12: 8; 2021-11-15: 8 | 48 | Evan.Zhang |  | Sanjel | Online
#15193 | Bulk Plant Board | 950 | 64 | 2021-11-22: 8; 2021-11-23: 8; 2021-11-24: 8; 2021-11-25: 8; 2021-11-26: 8; 2021-11-29: 8; 2021-11-30: 8 | 56 | Evan.Zhang |  | Sanjel | Online
|  | 950 | [70 empty] | Sanjel
|  | 950 | [70 empty] | Sanjel
|  | 900 | [70 empty] | Sanjel
|  | 900 | [70 empty] | Sanjel
|  | 900 | [70 empty] | Sanjel
|  | 900 | [70 empty] | Sanjel
|  | 900 | [70 empty] | Sanjel
|  | 900 | [70 empty] | Sanjel
|  | 900 | [70 empty] | Sanjel
|  | 900 |  | 2021-09-26: 6 |  |  |  | Sanjel
|  | 900 | [70 empty] | Sanjel
|  | 900 |  | 2021-09-26: 8 |  |  |  | Sanjel
|  | 850 |  | 2021-09-26: 2 |  |  |  | Sanjel
|  | 850 |  | 2021-09-26: 8 |  |  |  | Sanjel
|  | 850 | [70 empty] | Sanjel
|  | 850 | [70 empty] | Sanjel
|  | 850 | [70 empty] | Sanjel
|  | 850 | [70 empty] | Sanjel
|  | 850 | [70 empty] | Sanjel
|  | 850 | [70 empty] | Sanjel
|  | 850 | [70 empty] | Sanjel
Sanjel
Sanjel
Sanjel
Sanjel
Sanjel
Sanjel
Sanjel
Sanjel
Sanjel
Sanjel
Note on L8: joe.huang: Joe：4h Bright：4h
Note on L15: joe.huang: Colin

## Task Remaining
ID | Name | Prioritize | Est(Hour) | time axis 2021-09-26 to 2021-11-30
 | time axis 2021-09-26 to 2021-11-30
| Ideal Burndown |  | 512 | 512 | 504 | 504 | 496 | 488 | 488 | 488 | 488 | 488 | 488 | 488 | 488 | 480 | 472 | 472 | 464 | 456 | 448 | 440 | 432 | 432 | 432 | 424 | 416 | 408 | 400 | 392 | 392 | 392 | 384 | 376 | 368 | 360 | 352 | 352 | 352 | 336 | 320 | 304 | 288 | 272 | 272 | 272 | 256 | 240 | 224 | 208 | 192 | 192 | 192 | 176 | 160 | 144 | 128 | 112 | 112 | 112 | 96 | 80 | 64 | 48 | 32 | 32 | 32 | 16 | 0
| Actual burndown |  | 221.5 | 69.5 | 69.5 | 69 | 69 | 69 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 56 | 56 | 48 | 40 | 32 | 26 | 22.5 | 16 | 16 | 17 | 16 | 8 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 10 | 8 | 6 | 0 | 8 | 11 | 9 | 16 | 15 | 0 | 0 | 40 | 32 | 24 | 16 | 8 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 56 | 48 | 32 | 24 | 0 | 0 | 16 | 8
#14430 | Reset and Update github | 1000 | 0.5 | 2021-09-26: 0.5; 2021-09-27: 0.5; 2021-09-28: 0
#14460 | Setup Environment | 1000 | 5 | 2021-09-26: 5; 2021-09-27: 5; 2021-09-28: 5; 2021-09-29: 5; 2021-09-30: 5; 2021-10-01: 0
#14515 | Refactor Views Javascript | 1000 | 48 | 2021-09-26: 48; 2021-09-27: 48; 2021-09-28: 48; 2021-09-29: 48; 2021-09-30: 48; 2021-10-01: 48; 2021-10-02: 48; 2021-10-03: 48; 2021-10-04: 48; 2021-10-05: 48; 2021-10-06: 48; 2021-10-07: 48; 2021-10-08: 48; 2021-10-09: 40; 2021-10-10: 40; 2021-10-11: 32; 2021-10-12: 24; 2021-10-13: 16; 2021-10-14: 10; 2021-10-15: 6.5; 2021-10-18: 1; 2021-10-19: 0; 2021-11-02: 1; 2021-11-03: 0; 2021-11-04: 0; 2021-11-08: 0; 2021-11-09: 0; 2021-11-10: 0; 2021-11-11: 0; 2021-11-12: 0; 2021-11-15: 0
#14595 | Publish web application to website configuration | 950 | 16 | 2021-09-26: 16; 2021-09-27: 16; 2021-09-28: 16; 2021-09-29: 16; 2021-09-30: 16; 2021-10-01: 16; 2021-10-02: 16; 2021-10-03: 16; 2021-10-04: 16; 2021-10-05: 16; 2021-10-06: 16; 2021-10-07: 16; 2021-10-08: 16; 2021-10-09: 16; 2021-10-10: 16; 2021-10-11: 16; 2021-10-12: 16; 2021-10-13: 16; 2021-10-14: 16; 2021-10-15: 16; 2021-10-16: 16; 2021-10-17: 16; 2021-10-18: 16; 2021-10-19: 16; 2021-10-20: 8; 2021-10-21: 4; 2021-10-22: 8; 2021-10-23: 8; 2021-10-24: 8; 2021-10-25: 8; 2021-10-26: 8; 2021-10-27: 8; 2021-10-28: 10; 2021-10-29: 8; 2021-10-30: 6; 2021-11-05: 6; 2021-11-15: 2
#14960 | Support | 950 | 3 | 2021-11-02: 2; 2021-11-03: 1; 2021-11-04: 0; 2021-11-09: 0; 2021-11-10: 0; 2021-11-11: 0
#15001 | Commit CommonCore on GitHub | 950 | 5 | 2021-11-05: 1; 2021-11-08: 0
#14981 | Setup Environment | 950 | 8 | 2021-11-01: 8; 2021-11-02: 0
#14982 | Get Database And Study document | 950 | 8 | 2021-11-02: 8; 2021-11-03: 0
#14984 | Git Clone Code And Debug | 950 | 8 | 2021-11-03: 8; 2021-11-04: 0
#14985 | Git New Branch And Study Code | 950 | 16 | 2021-11-04: 16; 2021-11-05: 8; 2021-11-08: 0
#15049 | Refactor Views Javascript | 950 | 40 | 2021-11-08: 40; 2021-11-09: 32; 2021-11-10: 24; 2021-11-11: 16; 2021-11-12: 8; 2021-11-15: 0
#15193 | Bulk Plant Board | 950 | 64 | 2021-11-22: 64; 2021-11-23: 56; 2021-11-24: 48; 2021-11-25: 32; 2021-11-26: 24; 2021-11-29: 16; 2021-11-30: 8
0 | 0 | 950 | 0
0 | 0 | 950 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。
Note on L15: joe.huang: Colin

## Resources
SPRINT
StartDate | 2021-09-27
EndDate | 2021-11-30
Est Time
Name | Role | Total Hours | time axis 2021-09-27 to 2021-11-30
 | time axis 2021-09-27 to 2021-11-30
Ideal Burndown |  | 512 | 504 | 504 | 496 | 488 | 488 | 488 | 488 | 488 | 488 | 488 | 488 | 480 | 472 | 472 | 464 | 456 | 448 | 440 | 432 | 432 | 432 | 424 | 416 | 408 | 400 | 392 | 392 | 392 | 384 | 376 | 368 | 360 | 352 | 352 | 352 | 336 | 320 | 304 | 288 | 272 | 272 | 272 | 256 | 240 | 224 | 208 | 192 | 192 | 192 | 176 | 160 | 144 | 128 | 112 | 112 | 112 | 96 | 80 | 64 | 48 | 32 | 32 | 32 | 16 | 0
Hours consumed |  | 160 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 16 | 16
Olivia.Ge |  | 0
Miguel |  | 336 | 8 |  | 8 | 8 | [7 empty] | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8
Evan.Zhang |  | 176 | 2021-11-01: 8; 2021-11-02: 8; 2021-11-03: 8; 2021-11-04: 8; 2021-11-05: 8; 2021-11-08: 8; 2021-11-09: 8; 2021-11-10: 8; 2021-11-11: 8; 2021-11-12: 8; 2021-11-15: 8; 2021-11-16: 8; 2021-11-17: 8; 2021-11-18: 8; 2021-11-19: 8; 2021-11-22: 8; 2021-11-23: 8; 2021-11-24: 8; 2021-11-25: 8; 2021-11-26: 8; 2021-11-29: 8; 2021-11-30: 8
0
0
0
0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
#14430 | Reset and Update github | 1000 | 0.5 | 1 | Miguel | 0.5
#14460 | Setup Environment | 1000 | 5 | 1 | Miguel | 7.5
#14515 | Refactor Views Javascript | 1000 | 48 | 1 | Miguel | 71
#14595 | Publish web application to website configuration | 950 | 64 | 0 | Miguel | 57
#14960 | Support | 950 | 3 | 0 | Miguel | 0
#15001 | Commit CommonCore on GitHub | 950 | 5 | 0 | 0 | 0
#14981 | Setup Environment | 950 | 8 | 0 | Evan.Zhang | 8
#14982 | Get Database And Study document | 950 | 8 | 0 | Evan.Zhang | 8
#14984 | Git Clone Code And Debug | 950 | 8 | 0 | Evan.Zhang | 8
#14985 | Git New Branch And Study Code | 950 | 16 | 0 | Evan.Zhang | 16
#15049 | Refactor Views Javascript | 950 | 40 | 0 | Evan.Zhang | 48
#15193 | Bulk Plant Board | 950 | 64 | 0 | Evan.Zhang | 56
0 | 0 | 950 | 0 | 0 | 0 | 0
0 | 0 | 950 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间