## Daily Records
ID | Name | Prioritize | Est(Hour) | [67 empty] | Total Hours | time axis 2021-10-26 to 2021-12-31
 | time axis 2021-10-26 to 2021-12-31
| Ideal Burndown |  | 344 | 344 | 336 | 336 | 328 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 312 | 304 | 304 | 296 | 288 | 280 | 272 | 264 | 264 | 264 | 256 | 248 | 240 | 232 | 224 | 224 | 224 | 216 | 208 | 200 | 192 | 184 | 184 | 184 | 176 | 168 | 160 | 160 | 160 | 152 | 144 | 136 | 128 | 120 | 120 | 120 | 112 | 104 | 96 | 88 | 80 | 80 | 80 | 72 | 64 | 56 | 48 | 40 | 40 | 40 | 32 | 24 | 16 | 8 | 0 | 310
| Actual |  | 64 | 344 | 343.5 | 343.5 | 341 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 328.5 | 320.5 | 320.5 | 312.5 | 304.5 | 297.5 | 293 | 286 | 286 | 286 | 278 | 270 | 262 | 256 | 248 | 248 | 248 | 240 | 232 | 224 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216
|  |  |  | 2021-10-26: 0; 2021-10-27: 0.5; 2021-10-28: 0; 2021-10-29: 2.5; 2021-10-30: 5; 2021-10-31: 0; 2021-11-01: 0; 2021-11-02: 0; 2021-11-03: 0; 2021-11-04: 0; 2021-11-05: 0; 2021-11-06: 0; 2021-11-07: 7.5; 2021-11-08: 8; 2021-11-09: 0; 2021-11-10: 8; 2021-11-11: 8; 2021-11-12: 7; 2021-11-13: 4.5; 2021-11-14: 7; 2021-11-15: 0; 2021-11-16: 0; 2021-11-17: 8; 2021-11-18: 8; 2021-11-19: 8; 2021-11-20: 6; 2021-11-21: 8; 2021-11-22: 0; 2021-11-23: 0; 2021-11-24: 8; 2021-11-25: 8; 2021-11-26: 8; 2021-11-27: 8; 2021-11-28: 0; 2021-11-29: 0; 2021-11-30: 0 | 310 | Assign to | Completion Status | Pay by | Module
#14430 | Reset and Update github | 1000 | 0 | 2021-10-27: 0.5 | 0.5 | Miguel | 1 | Sanjel | Online
#14460 | Setup Environment | 1000 | 0 | 2021-10-29: 2.5; 2021-10-30: 5 | 7.5 | Miguel | 1 | Sanjel | Online
#14515 | Refactor Views Javascript | 1000 | 0 | 2021-11-07: 7.5; 2021-11-08: 8; 2021-11-10: 8; 2021-11-11: 8; 2021-11-12: 7; 2021-11-13: 4.5; 2021-11-14: 7; 2021-11-17: 8; 2021-11-18: 5 | 63 | Miguel | 1 | Sanjel | Online
#14595 | Publish web application to website configuration | 950 | 0 | 2021-11-18: 3; 2021-11-19: 8; 2021-11-20: 6; 2021-11-21: 8; 2021-11-24: 8; 2021-11-25: 8; 2021-11-26: 8; 2021-11-27: 8 | 57 | Miguel |  | Sanjel | Online
#14960 | Support | 950 | 0 | [68 empty] | Miguel |  | Sanjel
#15001 | Commit CommonCore on GitHub | 950 | 0 | [70 empty] | Sanjel
#14981 | Setup Environment | 950 | 0 | [67 empty] | 0 | Evan.Zhang |  | Sanjel | Online
#14982 | Get Database And Study document | 950 | 0 | [67 empty] | 0 | Evan.Zhang |  | Sanjel | Online
#14984 | Git Clone Code And Debug | 950 | 0 | [67 empty] | 0 | Evan.Zhang |  | Sanjel | Online
#14985 | Git New Branch And Study Code | 950 | 0 | [67 empty] | 0 | Evan.Zhang |  | Sanjel | Online
#15049 | Refactor Views Javascript | 950 | 0 | [67 empty] | 0 | Evan.Zhang |  | Sanjel | Online
#15193 | Bulk Plant Board | 950 | 64 | 2021-12-01: 8; 2021-12-02: 8; 2021-12-03: 8; 2021-12-06: 8; 2021-12-07: 8; 2021-12-08: 8; 2021-12-09: 8; 2021-12-10: 8; 2021-12-13: 8; 2021-12-14: 8; 2021-12-15: 8; 2021-12-16: 8; 2021-12-17: 8; 2021-12-20: 8; 2021-12-21: 8; 2021-12-22: 6; 2021-12-23: 8; 2021-12-24: 8; 2021-12-27: 8; 2021-12-28: 8; 2021-12-29: 8; 2021-12-30: 8; 2021-12-31: 8 | 182 | Evan.Zhang |  | Sanjel | Online
|  | 950 | [71 empty] | Sanjel
|  | 950 | [71 empty] | Sanjel
|  | 900 | [71 empty] | Sanjel
|  | 900 | [71 empty] | Sanjel
|  | 900 | [71 empty] | Sanjel
|  | 900 | [71 empty] | Sanjel
|  | 900 | [71 empty] | Sanjel
|  | 900 | [71 empty] | Sanjel
|  | 900 | [71 empty] | Sanjel
|  | 900 | [71 empty] | Sanjel
|  | 900 | [71 empty] | Sanjel
|  | 900 | [71 empty] | Sanjel
|  | 850 | [71 empty] | Sanjel
|  | 850 | [71 empty] | Sanjel
|  | 850 | [71 empty] | Sanjel
|  | 850 | [71 empty] | Sanjel
|  | 850 | [71 empty] | Sanjel
|  | 850 | [71 empty] | Sanjel
|  | 850 | [71 empty] | Sanjel
|  | 850 | [71 empty] | Sanjel
|  | 850 | [71 empty] | Sanjel
Sanjel
Sanjel
Sanjel
Sanjel
Sanjel
Sanjel
Sanjel
Sanjel
Sanjel
Sanjel
Note on L8: joe.huang: Joe：4h Bright：4h
Note on L15: joe.huang: Colin

## Task Remaining
ID | Name | Prioritize | Est(Hour) | time axis 2021-10-26 to 2021-12-31
 | time axis 2021-10-26 to 2021-12-31
| Ideal Burndown |  | 344 | 344 | 336 | 336 | 328 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 312 | 304 | 304 | 296 | 288 | 280 | 272 | 264 | 264 | 264 | 256 | 248 | 240 | 232 | 224 | 224 | 224 | 216 | 208 | 200 | 192 | 184 | 184 | 184 | 176 | 168 | 160 | 160 | 160 | 152 | 144 | 136 | 128 | 120 | 120 | 120 | 112 | 104 | 96 | 88 | 80 | 80 | 80 | 72 | 64 | 56 | 48 | 40 | 40 | 40 | 32 | 24 | 16 | 8 | 0
| Actual burndown |  | 120 | 69.5 | 69.5 | 69 | 69 | 69 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 56 | 56 | 48 | 40 | 32 | 26 | 22.5 | 16 | 16 | 17 | 16 | 8 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#14430 | Reset and Update github | 1000 | 0 | 2021-10-26: 0.5; 2021-10-27: 0.5; 2021-10-28: 0
#14460 | Setup Environment | 1000 | 0 | 2021-10-26: 5; 2021-10-27: 5; 2021-10-28: 5; 2021-10-29: 5; 2021-10-30: 5; 2021-10-31: 0
#14515 | Refactor Views Javascript | 1000 | 0 | 2021-10-26: 48; 2021-10-27: 48; 2021-10-28: 48; 2021-10-29: 48; 2021-10-30: 48; 2021-10-31: 48; 2021-11-01: 48; 2021-11-02: 48; 2021-11-03: 48; 2021-11-04: 48; 2021-11-05: 48; 2021-11-06: 48; 2021-11-07: 48; 2021-11-08: 40; 2021-11-09: 40; 2021-11-10: 32; 2021-11-11: 24; 2021-11-12: 16; 2021-11-13: 10; 2021-11-14: 6.5; 2021-11-17: 1; 2021-11-18: 0
#14595 | Publish web application to website configuration | 950 | 16 | 2021-10-26: 16; 2021-10-27: 16; 2021-10-28: 16; 2021-10-29: 16; 2021-10-30: 16; 2021-10-31: 16; 2021-11-01: 16; 2021-11-02: 16; 2021-11-03: 16; 2021-11-04: 16; 2021-11-05: 16; 2021-11-06: 16; 2021-11-07: 16; 2021-11-08: 16; 2021-11-09: 16; 2021-11-10: 16; 2021-11-11: 16; 2021-11-12: 16; 2021-11-13: 16; 2021-11-14: 16; 2021-11-15: 16; 2021-11-16: 16; 2021-11-17: 16; 2021-11-18: 16; 2021-11-19: 8; 2021-11-20: 4; 2021-11-21: 8; 2021-11-22: 8; 2021-11-23: 8; 2021-11-24: 8; 2021-11-25: 8; 2021-11-26: 8; 2021-11-27: 10
#14960 | Support | 950 | 0
#15001 | Commit CommonCore on GitHub | 950 | 0
#14981 | Setup Environment | 950 | 8
#14982 | Get Database And Study document | 950 | 8
#14984 | Git Clone Code And Debug | 950 | 8
#14985 | Git New Branch And Study Code | 950 | 16
#15049 | Refactor Views Javascript | 950 | 0
#15193 | Bulk Plant Board | 950 | 64 | 2021-12-01: 0; 2021-12-02: 0; 2021-12-03: 0
0 | 0 | 950 | 0
0 | 0 | 950 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 900 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 850 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。
Note on L15: joe.huang: Colin

## Resources
SPRINT
StartDate | 2021-10-27
EndDate | 2021-12-30
Est Time
Name | Role | Total Hours | time axis 2021-10-27 to 2021-12-31
 | time axis 2021-10-27 to 2021-12-31
Ideal Burndown |  | 344 | 336 | 336 | 328 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 312 | 304 | 304 | 296 | 288 | 280 | 272 | 264 | 264 | 264 | 256 | 248 | 240 | 232 | 224 | 224 | 224 | 216 | 208 | 200 | 192 | 184 | 184 | 184 | 176 | 168 | 160 | 160 | 160 | 152 | 144 | 136 | 128 | 120 | 120 | 120 | 112 | 104 | 96 | 88 | 80 | 80 | 80 | 72 | 64 | 56 | 48 | 40 | 40 | 40 | 32 | 24 | 16 | 8 | 0
Hours consumed |  | 160 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8
Olivia.Ge |  | 0
Miguel |  | 160 | 2021-10-27: 8; 2021-10-29: 8; 2021-10-30: 8; 2021-11-07: 8; 2021-11-08: 8; 2021-11-10: 8; 2021-11-11: 8; 2021-11-12: 8; 2021-11-13: 8; 2021-11-14: 8; 2021-11-17: 8; 2021-11-18: 8; 2021-11-19: 8; 2021-11-20: 8; 2021-11-21: 8; 2021-11-24: 8; 2021-11-25: 8; 2021-11-26: 8; 2021-11-27: 8; 2021-11-28: 8
Evan.Zhang |  | 184 | 2021-12-01: 8; 2021-12-02: 8; 2021-12-03: 8; 2021-12-06: 8; 2021-12-07: 8; 2021-12-08: 8; 2021-12-09: 8; 2021-12-10: 8; 2021-12-13: 8; 2021-12-14: 8; 2021-12-15: 8; 2021-12-16: 8; 2021-12-17: 8; 2021-12-20: 8; 2021-12-21: 8; 2021-12-22: 8; 2021-12-23: 8; 2021-12-24: 8; 2021-12-27: 8; 2021-12-28: 8; 2021-12-29: 8; 2021-12-30: 8; 2021-12-31: 8
0
0
0
0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
#14430 | Reset and Update github | 1000 | 0 | 1 | Miguel | 0.5
#14460 | Setup Environment | 1000 | 0 | 1 | Miguel | 7.5
#14515 | Refactor Views Javascript | 1000 | 0 | 1 | Miguel | 63
#14595 | Publish web application to website configuration | 950 | 0 | 0 | Miguel | 57
#14960 | Support | 950 | 0 | 0 | Miguel | 0
#15001 | Commit CommonCore on GitHub | 950 | 0 | 0 | 0 | 0
#14981 | Setup Environment | 950 | 0 | 0 | Evan.Zhang | 0
#14982 | Get Database And Study document | 950 | 0 | 0 | Evan.Zhang | 0
#14984 | Git Clone Code And Debug | 950 | 0 | 0 | Evan.Zhang | 0
#14985 | Git New Branch And Study Code | 950 | 0 | 0 | Evan.Zhang | 0
#15049 | Refactor Views Javascript | 950 | 0 | 0 | Evan.Zhang | 0
#15193 | Bulk Plant Board | 950 | 64 | 0 | Evan.Zhang | 182
0 | 0 | 950 | 0 | 0 | 0 | 0
0 | 0 | 950 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 900 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 850 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间