## Daily Records
ID | Name | Prioritize | Est(Hour) | [67 empty] | Total Hours | time axis 2022-02-23 to 2022-04-30
 | time axis 2022-02-23 to 2022-04-30
| Ideal Burndown |  | 328 | 328 | 320 | 320 | 312 | 304 | 304 | 304 | 304 | 304 | 304 | 304 | 304 | 296 | 288 | 288 | 280 | 272 | 264 | 256 | 248 | 248 | 248 | 240 | 232 | 224 | 216 | 208 | 208 | 208 | 200 | 192 | 184 | 176 | 168 | 168 | 168 | 168 | 160 | 160 | 160 | 152 | 144 | 136 | 128 | 120 | 120 | 120 | 112 | 104 | 96 | 88 | 80 | 80 | 80 | 72 | 64 | 56 | 48 | 40 | 40 | 40 | 32 | 24 | 16 | 8 | 0 | 0 | 160
| Actual |  | 424 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328 | 328
|  |  |  | 2022-02-23: #REF!; 2022-02-24: 0; 2022-02-25: 0; 2022-02-26: 0; 2022-02-27: 0; 2022-02-28: 0; 2022-03-01: 0; 2022-03-02: 0; 2022-03-03: 0; 2022-03-04: 0; 2022-03-05: 0; 2022-03-06: 0; 2022-03-07: 0; 2022-03-08: 0; 2022-03-09: 0; 2022-03-10: 0; 2022-03-11: 0; 2022-03-12: 0; 2022-03-13: 0; 2022-03-14: 0; 2022-03-15: 0; 2022-03-16: 0; 2022-03-17: 0; 2022-03-18: 0; 2022-03-19: 0; 2022-03-20: 0; 2022-03-21: 0; 2022-03-22: 0; 2022-03-23: 0; 2022-03-24: 0; 2022-03-25: 0; 2022-03-26: 0; 2022-03-27: 0; 2022-03-28: 0; 2022-03-29: 0; 2022-03-30: 0 | 160 | Assign to | Completion Status | Pay by | Module
#15193 | Bulk Plant Board | 950 | 64 | [67 empty] | 0 | Evan.Zhang |  | Sanjel | Online
#15633 | Sanjel | 950 | 200 | [67 empty] | 0 |  |  | Sanjel
4.1 | study angular cli to run and run lab loacal | 950 | 8 | 2022-04-01: 8 | 8 | Evan.Zhang |  | Sanjel
4.2 | preliminary study angular project of lab front end | 900 | 8 | 2022-04-02: 8 | 8 | Evan.Zhang |  | Sanjel
4.6 | preliminary study api project of back end | 900 | 8 | 2022-04-06: 8 | 8 | Evan.Zhang |  | Sanjel
4.7 | write UML of lab project | 900 | 8 | 2022-04-07: 8 | 8 | Evan.Zhang |  | Sanjel
4.8 | study MMC technology | 900 | 8 | 2022-04-08: 8 | 8 | Evan.Zhang |  | Sanjel
4.11 | study lab object to MMC problem | 900 | 8 | 2022-04-11: 8 | 8 | Evan.Zhang |  | Sanjel
4.12 | study lab object framework | 900 | 8 | 2022-04-12: 8 | 8 | Evan.Zhang |  | Sanjel
4.13 | study lab indentity technology | 900 | 8 | 2022-04-13: 8 | 8 | Evan.Zhang |  | Sanjel
4.14 | study lab object of back end | 900 | 8 | 2022-04-14: 8 | 8 | Evan.Zhang |  | Sanjel
4.15 | study front end identity | 900 | 8 | 2022-04-15: 8 | 8 | Evan.Zhang |  | Sanjel
4.18 | design Solution and Evaluation time | 900 | 8 | 2022-04-18: 8 | 8 | Evan.Zhang |  | Sanjel
4.19 | study whole project continue | 850 | 8 | 2022-04-19: 8 | 8 | Evan.Zhang |  | Sanjel
4.2 | study api and hangfire project | 850 | 8 | 2022-04-20: 8 | 8 | Evan.Zhang |  | Sanjel
4.21 | study angular technology | 850 | 8 | 2022-04-21: 8 | 8 | Evan.Zhang |  | Sanjel
4.24 | study angular technology and design framework | 850 | 8 | 2022-04-24: 8 | 8 | Evan.Zhang |  | Sanjel
4.25 | perfect design framework and study technology | 850 | 8 | 2022-04-25: 8 | 8 | Evan.Zhang |  | Sanjel
4.26 | Scheme prototype coding | 850 | 8 | 2022-04-26: 8 | 8 | Evan.Zhang |  | Sanjel
4.27 | Scheme prototype debugging | 850 | 8 | 2022-04-27: 8 | 8 | Evan.Zhang |  | Sanjel
4.28 | Scheme prototype debugging continue | 850 | 8 | 2022-04-28: 8 | 8 | Evan.Zhang |  | Sanjel
4.29 | Scheme prototype integration MMC | 850 | 8 | 2022-04-29: 8 | 8 | Evan.Zhang |  | Sanjel
[71 empty] | 0 | Evan.Zhang |  | Sanjel
[71 empty] | 0 | Evan.Zhang |  | Sanjel
[71 empty] | 0 | Evan.Zhang |  | Sanjel
[71 empty] | 0 | Evan.Zhang |  | Sanjel
[71 empty] | 0 |  |  | Sanjel
[71 empty] | 0 |  |  | Sanjel
[71 empty] | 0 |  |  | Sanjel
[71 empty] | 0 |  |  | Sanjel
[71 empty] | 0 |  |  | Sanjel
Sanjel

## Task Remaining
ID | Name | Prioritize | Est(Hour) | time axis 2022-02-23 to 2022-04-30
 | time axis 2022-02-23 to 2022-04-30
| Ideal Burndown |  | 328 | 328 | 320 | 320 | 312 | 304 | 304 | 304 | 304 | 304 | 304 | 304 | 304 | 296 | 288 | 288 | 280 | 272 | 264 | 256 | 248 | 248 | 248 | 240 | 232 | 224 | 216 | 208 | 208 | 208 | 200 | 192 | 184 | 176 | 168 | 168 | 168 | 168 | 160 | 160 | 160 | 152 | 144 | 136 | 128 | 120 | 120 | 120 | 112 | 104 | 96 | 88 | 80 | 80 | 80 | 72 | 64 | 56 | 48 | 40 | 40 | 40 | 32 | 24 | 16 | 8 | 0 | 0
| Actual burndown |  | 424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#15193 | Bulk Plant Board | 950 | 64
#15633 | Sanjel | 950 | 200
4.1 | study angular cli to run and run lab loacal | 950 | 8
4.2 | preliminary study angular project of lab front end | 900 | 8
4.6 | preliminary study api project of back end | 900 | 8
4.7 | write UML of lab project | 900 | 8
4.8 | study MMC technology | 900 | 8
4.11 | study lab object to MMC problem | 900 | 8
4.12 | study lab object framework | 900 | 8
4.13 | study lab indentity technology | 900 | 8
4.14 | study lab object of back end | 900 | 8
4.15 | study front end identity | 900 | 8
4.18 | design Solution and Evaluation time | 900 | 8
4.19 | study whole project continue | 850 | 8
4.2 | study api and hangfire project | 850 | 8
4.21 | study angular technology | 850 | 8
4.24 | study angular technology and design framework | 850 | 8
4.25 | perfect design framework and study technology | 850 | 8
4.26 | Scheme prototype coding | 850 | 8
4.27 | Scheme prototype debugging | 850 | 8
4.28 | Scheme prototype debugging continue | 850 | 8
4.29 | Scheme prototype integration MMC | 850 | 8
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT
StartDate | 2022-02-24
EndDate | 2022-04-30
Est Time
Name | Role | Total Hours | time axis 2022-02-24 to 2022-04-30
 | time axis 2022-02-24 to 2022-04-30
Ideal Burndown |  | 328 | 320 | 320 | 312 | 304 | 304 | 304 | 304 | 304 | 304 | 304 | 304 | 296 | 288 | 288 | 280 | 272 | 264 | 256 | 248 | 248 | 248 | 240 | 232 | 224 | 216 | 208 | 208 | 208 | 200 | 192 | 184 | 176 | 168 | 168 | 168 | 168 | 160 | 160 | 160 | 152 | 144 | 136 | 128 | 120 | 120 | 120 | 112 | 104 | 96 | 88 | 80 | 80 | 80 | 72 | 64 | 56 | 48 | 40 | 40 | 40 | 32 | 24 | 16 | 8 | 0 | 0
Hours consumed |  | 160 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0
Olivia.Ge |  | 0
Miguel |  | 160 | 2022-02-24: 8; 2022-02-26: 8; 2022-02-27: 8; 2022-03-07: 8; 2022-03-08: 8; 2022-03-10: 8; 2022-03-11: 8; 2022-03-12: 8; 2022-03-13: 8; 2022-03-14: 8; 2022-03-17: 8; 2022-03-18: 8; 2022-03-19: 8; 2022-03-20: 8; 2022-03-21: 8; 2022-03-24: 8; 2022-03-25: 8; 2022-03-26: 8; 2022-03-27: 8; 2022-03-28: 8
Evan.Zhang |  | 168 | 2022-04-01: 8; 2022-04-04: 8; 2022-04-05: 8; 2022-04-06: 8; 2022-04-07: 8; 2022-04-08: 8; 2022-04-11: 8; 2022-04-12: 8; 2022-04-13: 8; 2022-04-14: 8; 2022-04-15: 8; 2022-04-18: 8; 2022-04-19: 8; 2022-04-20: 8; 2022-04-21: 8; 2022-04-22: 8; 2022-04-25: 8; 2022-04-26: 8; 2022-04-27: 8; 2022-04-28: 8; 2022-04-29: 8
0
0
0
0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
#15193 | Bulk Plant Board | 950 | 64 | 0 | Evan.Zhang | 0
#15633 | Sanjel | 950 | 200 | 0 | 0 | 0
4.1 | study angular cli to run and run lab loacal | 950 | 8 | 0 | Evan.Zhang | 8
4.2 | preliminary study angular project of lab front end | 900 | 8 | 0 | Evan.Zhang | 8
4.6 | preliminary study api project of back end | 900 | 8 | 0 | Evan.Zhang | 8
4.7 | write UML of lab project | 900 | 8 | 0 | Evan.Zhang | 8
4.8 | study MMC technology | 900 | 8 | 0 | Evan.Zhang | 8
4.11 | study lab object to MMC problem | 900 | 8 | 0 | Evan.Zhang | 8
4.12 | study lab object framework | 900 | 8 | 0 | Evan.Zhang | 8
4.13 | study lab indentity technology | 900 | 8 | 0 | Evan.Zhang | 8
4.14 | study lab object of back end | 900 | 8 | 0 | Evan.Zhang | 8
4.15 | study front end identity | 900 | 8 | 0 | Evan.Zhang | 8
4.18 | design Solution and Evaluation time | 900 | 8 | 0 | Evan.Zhang | 8
4.19 | study whole project continue | 850 | 8 | 0 | Evan.Zhang | 8
4.2 | study api and hangfire project | 850 | 8 | 0 | Evan.Zhang | 8
4.21 | study angular technology | 850 | 8 | 0 | Evan.Zhang | 8
4.24 | study angular technology and design framework | 850 | 8 | 0 | Evan.Zhang | 8
4.25 | perfect design framework and study technology | 850 | 8 | 0 | Evan.Zhang | 8
4.26 | Scheme prototype coding | 850 | 8 | 0 | Evan.Zhang | 8
4.27 | Scheme prototype debugging | 850 | 8 | 0 | Evan.Zhang | 8
4.28 | Scheme prototype debugging continue | 850 | 8 | 0 | Evan.Zhang | 8
4.29 | Scheme prototype integration MMC | 850 | 8 | 0 | Evan.Zhang | 8
0 | 0 | 0 | 0 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间