## Daily Records
ID | Name | Prioritize | Est(Hour) | [67 empty] | Total Hours | time axis 2022-03-26 to 2022-05-31
 | time axis 2022-03-26 to 2022-05-31
| Ideal Burndown |  | 336 | 336 | 328 | 328 | 320 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 304 | 296 | 296 | 288 | 280 | 272 | 264 | 256 | 256 | 256 | 248 | 240 | 232 | 224 | 216 | 216 | 216 | 208 | 200 | 192 | 184 | 176 | 176 | 176 | 176 | 168 | 160 | 152 | 144 | 136 | 136 | 136 | 128 | 120 | 112 | 104 | 96 | 96 | 96 | 88 | 80 | 72 | 64 | 56 | 56 | 56 | 48 | 40 | 32 | 24 | 16 | 16 | 16 | 8 | 0 | 104
| Actual |  | 152 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336 | 336
|  |  |  | 2022-03-26: #REF!; 2022-03-27: 0; 2022-03-28: 0; 2022-03-29: 0; 2022-03-30: 0; 2022-03-31: 0; 2022-04-01: 0; 2022-04-02: 0; 2022-04-03: 0; 2022-04-04: 0; 2022-04-05: 0; 2022-04-06: 0; 2022-04-07: 0; 2022-04-08: 0; 2022-04-09: 0; 2022-04-10: 0; 2022-04-11: 0; 2022-04-12: 0; 2022-04-13: 0; 2022-04-14: 0; 2022-04-15: 0; 2022-04-16: 0; 2022-04-17: 0; 2022-04-18: 0; 2022-04-19: 0; 2022-04-20: 0; 2022-04-21: 0; 2022-04-22: 0; 2022-04-23: 0; 2022-04-24: 0; 2022-04-25: 0; 2022-04-26: 0; 2022-04-27: 0; 2022-04-28: 0; 2022-04-29: 0; 2022-04-30: 0 | 104 | Assign to | Completion Status | Pay by | Module
5.5 | net 6 of nullable And lab database select order by | 850 | 8 | 2022-05-05: 8 | 8 | Evan.Zhang |  | Sanjel | Online
5.6 | study common.core of mmc | 850 | 8 | 2022-05-06: 8 | 8 | Evan.Zhang |  | Sanjel
5.7 | test common.core of mmc | 850 | 8 | 2022-05-07: 8 | 8 | Evan.Zhang |  | Sanjel
2022-05-09 | Integrated MMC function of select count | 850 | 8 | 2022-05-09: 8 | 8 | Evan.Zhang |  | Sanjel
2022-05-10 | Summarize lab project and design Task Breakdown | 850 | 8 | 2022-05-10: 8 | 8 | Evan.Zhang |  | Sanjel
2022-05-11 | Sort the original data type to MMC data type | 850 | 8 | 2022-05-11: 8 | 8 | Evan.Zhang |  | Sanjel
2022-05-12 | TrackedEntity dependent ObjectVersion | 850 | 8 | 2022-05-12: 8 | 8 | Evan.Zhang |  | Sanjel
2022-05-13 | change save file byte[] to other solution | 850 | 8 | 2022-05-13: 8 | 8 | Evan.Zhang |  | Sanjel
2022-05-16 | Previous Business Model And Domain Model | 850 | 8 | 2022-05-16: 8 | 8 | Evan.Zhang |  | Sanjel
2022-05-17 | Perfect Implementation Model | 850 | 8 | 2022-05-17: 8 | 8 | Evan.Zhang |  | Sanjel
2022-05-18 | Enter entity model in SanjelData model in MMC | 850 | 8 | 2022-05-18: 8 | 8 | Evan.Zhang |  | Sanjel
2022-05-19 | write Import data sql | 850 | 8 | 2022-05-19: 8 | 8 | Evan.Zhang |  | Sanjel
2022-05-20 | Database Table Structure Mapping | 850 | 8 | 2022-05-20: 8 | 8 | Evan.Zhang |  | Sanjel
|  | 850 | 8 | [67 empty] | 0 | Evan.Zhang |  | Sanjel
|  | 850 | 8 | [67 empty] | 0 | Evan.Zhang |  | Sanjel
|  | 850 | 8 | [67 empty] | 0 | Evan.Zhang |  | Sanjel
|  | 850 | 8 | [67 empty] | 0 | Evan.Zhang |  | Sanjel
|  | 850 | 8 | [67 empty] | 0 | Evan.Zhang |  | Sanjel
|  | 850 | 8 | [67 empty] | 0 | Evan.Zhang |  | Sanjel
[71 empty] | 0 | Evan.Zhang |  | Sanjel
[71 empty] | 0 | Evan.Zhang |  | Sanjel
[71 empty] | 0 | Evan.Zhang |  | Sanjel
[71 empty] | 0 | Evan.Zhang |  | Sanjel
[71 empty] | 0 | Evan.Zhang |  | Sanjel
[71 empty] | 0 | Evan.Zhang |  | Sanjel
[71 empty] | 0 | Evan.Zhang |  | Sanjel
[71 empty] | 0 |  |  | Sanjel
[71 empty] | 0 |  |  | Sanjel
[71 empty] | 0 |  |  | Sanjel
[71 empty] | 0 |  |  | Sanjel
[71 empty] | 0 |  |  | Sanjel
Sanjel

## Task Remaining
ID | Name | Prioritize | Est(Hour) | time axis 2022-03-26 to 2022-05-31
 | time axis 2022-03-26 to 2022-05-31
| Ideal Burndown |  | 336 | 336 | 328 | 328 | 320 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 304 | 296 | 296 | 288 | 280 | 272 | 264 | 256 | 256 | 256 | 248 | 240 | 232 | 224 | 216 | 216 | 216 | 208 | 200 | 192 | 184 | 176 | 176 | 176 | 176 | 168 | 160 | 152 | 144 | 136 | 136 | 136 | 128 | 120 | 112 | 104 | 96 | 96 | 96 | 88 | 80 | 72 | 64 | 56 | 56 | 56 | 48 | 40 | 32 | 24 | 16 | 16 | 16 | 8 | 0
| Actual burndown |  | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.5 | net 6 of nullable And lab database select order by | 850 | 8
5.6 | study common.core of mmc | 850 | 8
5.7 | test common.core of mmc | 850 | 8
44690 | Integrated MMC function of select count | 850 | 8
44691 | Summarize lab project and design Task Breakdown | 850 | 8
44692 | Sort the original data type to MMC data type | 850 | 8
44693 | TrackedEntity dependent ObjectVersion | 850 | 8
44694 | change save file byte[] to other solution | 850 | 8
44697 | Previous Business Model And Domain Model | 850 | 8
44698 | Perfect Implementation Model | 850 | 8
44699 | Enter entity model in SanjelData model in MMC | 850 | 8
44700 | write Import data sql | 850 | 8
44701 | Database Table Structure Mapping | 850 | 8
0 | 0 | 850 | 8
0 | 0 | 850 | 8
0 | 0 | 850 | 8
0 | 0 | 850 | 8
0 | 0 | 850 | 8
0 | 0 | 850 | 8
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT
StartDate | 2022-03-27
EndDate | 2022-05-31
Est Time
Name | Role | Total Hours | time axis 2022-03-27 to 2022-05-31
 | time axis 2022-03-27 to 2022-05-31
Ideal Burndown |  | 336 | 328 | 328 | 320 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 312 | 304 | 296 | 296 | 288 | 280 | 272 | 264 | 256 | 256 | 256 | 248 | 240 | 232 | 224 | 216 | 216 | 216 | 208 | 200 | 192 | 184 | 176 | 176 | 176 | 176 | 168 | 160 | 152 | 144 | 136 | 136 | 136 | 128 | 120 | 112 | 104 | 96 | 96 | 96 | 88 | 80 | 72 | 64 | 56 | 56 | 56 | 48 | 40 | 32 | 24 | 16 | 16 | 16 | 8 | 0
Hours consumed |  | 160 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8
Olivia.Ge |  | 0
Miguel |  | 160 | 2022-03-27: 8; 2022-03-29: 8; 2022-03-30: 8; 2022-04-07: 8; 2022-04-08: 8; 2022-04-10: 8; 2022-04-11: 8; 2022-04-12: 8; 2022-04-13: 8; 2022-04-14: 8; 2022-04-17: 8; 2022-04-18: 8; 2022-04-19: 8; 2022-04-20: 8; 2022-04-21: 8; 2022-04-24: 8; 2022-04-25: 8; 2022-04-26: 8; 2022-04-27: 8; 2022-04-28: 8
Evan.Zhang |  | 176 | 2022-05-02: 8; 2022-05-03: 8; 2022-05-04: 8; 2022-05-05: 8; 2022-05-06: 8; 2022-05-09: 8; 2022-05-10: 8; 2022-05-11: 8; 2022-05-12: 8; 2022-05-13: 8; 2022-05-16: 8; 2022-05-17: 8; 2022-05-18: 8; 2022-05-19: 8; 2022-05-20: 8; 2022-05-23: 8; 2022-05-24: 8; 2022-05-25: 8; 2022-05-26: 8; 2022-05-27: 8; 2022-05-30: 8; 2022-05-31: 8
0
0
0
0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
5.5 | net 6 of nullable And lab database select order by | 850 | 8 | 0 | Evan.Zhang | 8
5.6 | study common.core of mmc | 850 | 8 | 0 | Evan.Zhang | 8
5.7 | test common.core of mmc | 850 | 8 | 0 | Evan.Zhang | 8
44690 | Integrated MMC function of select count | 850 | 8 | 0 | Evan.Zhang | 8
44691 | Summarize lab project and design Task Breakdown | 850 | 8 | 0 | Evan.Zhang | 8
44692 | Sort the original data type to MMC data type | 850 | 8 | 0 | Evan.Zhang | 8
44693 | TrackedEntity dependent ObjectVersion | 850 | 8 | 0 | Evan.Zhang | 8
44694 | change save file byte[] to other solution | 850 | 8 | 0 | Evan.Zhang | 8
44697 | Previous Business Model And Domain Model | 850 | 8 | 0 | Evan.Zhang | 8
44698 | Perfect Implementation Model | 850 | 8 | 0 | Evan.Zhang | 8
44699 | Enter entity model in SanjelData model in MMC | 850 | 8 | 0 | Evan.Zhang | 8
44700 | write Import data sql | 850 | 8 | 0 | Evan.Zhang | 8
44701 | Database Table Structure Mapping | 850 | 8 | 0 | Evan.Zhang | 8
0 | 0 | 850 | 8 | 0 | Evan.Zhang | 0
0 | 0 | 850 | 8 | 0 | Evan.Zhang | 0
0 | 0 | 850 | 8 | 0 | Evan.Zhang | 0
0 | 0 | 850 | 8 | 0 | Evan.Zhang | 0
0 | 0 | 850 | 8 | 0 | Evan.Zhang | 0
0 | 0 | 850 | 8 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan.Zhang | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间