## Daily Records
ID | Name | Prioritize | Est(Hour) | 2017-01-15 | 2017-01-16 | 2017-01-17 | 2017-01-18 | 2017-01-19 | 2017-01-20 | 2017-01-22 | 2017-01-23 | 2017-01-24 | Total Hours
|  |  |  | 周日 | 42751 | 42752 | 42753 | 42754 | 42755 | 42757 | 42758 | 42759
| Est |  | 122.5 | 169 | 143 | 121 | 106 | 88 | 64 | 43 | 22 | 0 | 189.2
| Actual |  | 118 | 169 | 149.8 | 134.8 | 123.8 | 92.8 | 71.8 | 45.8 | 26.8 | -20.2
|  |  | 122.5 | 0 | 19.2 | 15 | 11 | 31 | 21 | 26 | 19 | 47
I004 | Meeting | 1000 | 14 | 2017-01-16: 2.5; 2017-01-19: 7.5; 2017-01-22: 7.5 | 17.5 | All
S003 | Requirements analysis | 1000 | 10 | [9 empty] | 0 | Bella.Bi
P001 | Project management | 1000 | 6 | 2017-01-16: 1; 2017-01-18: 0.5; 2017-01-19: 4; 2017-01-20: 2 | 7.5 | Bella.Bi
UC015.US01 | Disable Create Program with “NO JDT File” | 900 | 5 | 2017-01-16: 2; 2017-01-17: 2; 2017-01-18: 1 | 5 | Shawn.Shao
UC015.US02 | Validation fatal error for importing program | 900 | 5 | 2017-01-17: 2.5; 2017-01-18: 2.5 | 5 | Shawn.Shao
UC015.US03 | Validation mandatory fields for importing program | 900 | 10 | 2017-01-17: 2.5; 2017-01-18: 5; 2017-01-20: 1.5 | 9 | Olivia.Ge
UC016.US01 | Re-organize the program treeview | 900 | 2 | [9 empty] | 0 | Olivia.ge
UC005.US04 | Remove well profile page from directly under program | 800 | 1 | 2017-01-16: 0.2 | 0.2 | Olivia.Ge
UC003.US03 | Add Template ID _implement | 790 | 4 | 2017-01-16: 2 | 2 | Shawn.shao
UC004.US04 | Add values to “eService Import Sheet” | 730 | 3 | 2017-01-17: 3 | 3 | Bela.Zhao
UC004.US05 | Add product entity,testdata,service,dao | 710 | 7 | 2017-01-16: 6; 2017-01-17: 1 | 7 | Bela.Zhao
UC004.US01 | Add product page in Program | 700 | 7 | 2017-01-16: 4 | 4 | Olivia.Ge
UC004.US02 | Import Product information_BlendSection | 700 | 6 | 2017-01-17: 1.5; 2017-01-19: 3; 2017-01-20: 2 | 6.5 | Bela.Zhao
UC006.US03 | Create Call Sheet from Program to carry over product information | 700 | 10 | 2017-01-16: 1; 2017-01-17: 2.5 | 3.5 | Olivia.Ge
UC011.US04 | Unit Test for recalculation | 700 | 5 | [9 empty] | 0 | Shawn.Shao
UC013.US01 | Micellenous fixes _program update error | 600 | 1 | 2017-01-16: 0.5 | 0.5 | Olivia.ge
UC004.US03 | Add four JDT file | 600 | 3 | 2017-01-19: 2 | 2 | Bela.zhao
UC004.US04 | Populate JDT to entity | 600 | 7 | 2017-01-19: 6; 2017-01-20: 3 | 9 | Olivia.ge
UC004.US05 | Import Product information_BlendAdditiveSection | 600 | 6 | 2017-01-19: 4; 2017-01-20: 2 | 6 | Bela.zhao
T001 | Test for tasks | 500 | 6 | 2017-01-18: 2; 2017-01-20: 3; 2017-01-23: 5; 2017-01-24: 27 | 37 | Bella.bi
T002 | Micellenous fixes _Program Id fixed&Program Validation | 500 | 1 | [9 empty] | 1 | Olivia.ge | bar: 2017-01-19
T003 | Micellenous fixes _Excel.exe not closed properly | 500 | 0.5 | 2017-01-19: 0.5 | 0.5 | Randy.ling
I006 | Discussion &Match the template and entity | 500 | 3 | 2017-01-19: 3 | 3 | Bela.Zhao&Olivia.Ge
I005 | Code review | 400 | [10 empty] | 0 | 0
T004 | Micellenous fixes_fix bug 4,8 | 400 |  | 2017-01-20: 2.5 | 2.5 | Olivia.ge
T005 | Micellenous fixes_fix bug 6,9,10 | 400 |  | 2017-01-20: 2 | 2 | Randy.ling
T006 | Micellenous fixes_fix bug 2,7 | 400 |  | 2017-01-20: 3 | 3 | Bela.zhao
I007 | Environment problem | 400 |  | 2017-01-22: 8.5 | 8.5
I008 | Database Update | 300 |  | 2017-01-22: 0.5 | 0.5
T007 | Micellenous fixes_fix bug 12,13 | 300 |  | 2017-01-22: 4 | 4
T008 | Micellenous fixes_fix bug 14,15,16 | 300 |  | 2017-01-22: 5.5 | 5.5
T009 | Micellenous fixes_fix bug 21,22 | 300 |  | 2017-01-23: 7 | 7
T010 | Micellenous fixes_fix bug 18,19,20 | 300 |  | 2017-01-23: 7 | 7
T011 | Micellenous fixes_fix bug 23 | 300 |  | 2017-01-24: 10 | 10
T012 | Micellenous fixes_fix bug 21 | 300 |  | 2017-01-24: 10 | 10
Note on I6: Bella Bi: 开会讨论目前的问题以及解决方案
Note on I8: Bella Bi: 安排任务、细化任务、回复邮件
Note on J11: Bella Bi: 修正bug
Note on B14: Bella Bi: 重构TemplateId
Note on B21: Bella Bi: 修改program update时报错的问题
Note on M25: Bella Bi: Bella 7h Shawn 10h Randy 10h
Note on B28: Bella Bi: 将Excel模板与实体对应，讨论实现方案
Note on I28: Bella Bi: Bela 1.5 Olivia 1.5
Note on K33: Bella Bi: Shawn 3.5h Bella 3h Randy 1h Bela 1h

## Resources
SPRINT | 1
StartDate | 2017-01-16
EndDate | 2017-01-24
Est Time
Name | Role | Total Hours | 2017-01-16 | 2017-01-17 | 2017-01-18 | 2017-01-19 | 2017-01-20 | 2017-01-22 | 2017-01-23 | 2017-01-24
|  |  | 42751 | 42752 | 42753 | 42754 | 42755 | 42757 | 42758 | 42759
合计 |  | 169 | 143 | 121 | 106 | 88 | 64 | 43 | 22 | 0
|  | 169 | 26 | 22 | 15 | 18 | 24 | 21 | 21 | 22
Olivia.Ge |  | 56 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
Bella.Bi |  | 16 | 4 | 1 | 1 | 2 | 2 | 2 | 2 | 2
Bela.Zhao |  | 49 | 7 | 7 | 0 | 7 | 7 | 7 | 7 | 7
Shawn.Shao |  | 29 | 5 | 5 | 5 | 0 | 5 | 3 | 3 | 3
Randy.Ling |  | 3 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1
Leo.Tian |  | 8 | bar: 2017-01-16 to 2017-01-24
Frank.Zhang |  | 8 | bar: 2017-01-16 to 2017-01-24
Actual Time
Name | Role | Total Hours | 2017-01-16 | 2017-01-17 | 2017-01-18 | 2017-01-19 | 2017-01-20 | 2017-01-22 | 2017-01-23 | 2017-01-24
|  |  | 42751 | 42752 | 42753 | 42754 | 42755 | 42757 | 42758 | 42759
合计 |  | 189.2 | 170 | 155 | 144 | 113 | 92 | 66 | 47 | 0
|  | 189.2 | 19.2 | 15 | 11 | 31 | 21 | 26 | 19 | 47
Olivia.Ge |  | 57.2 | 6.2 | 5 | 5 | 10 | 7 | 7 | 7 | 10
Bella.Bi |  | 34 | 1.5 |  | 2.5 | 5.5 | 5 | 4.5 | 5 | 10
Bela.Zhao |  | 55 | 6.5 | 5.5 |  | 12 | 7 | 7 | 7 | 10
Shawn.Shao |  | 29 | 4.5 | 4.5 | 3.5 | 1.5 | 0 | 5 |  | 10
Randy.Ling |  | 14 | 0.5 |  |  | 2 | 2 | 2.5 |  | 7
Leo.Tian |  | 0 | 2017-01-16: 0
Frank.Zhang |  | 0 | 2017-01-16: 0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | StartDate | EndDate | Assign To | Actual(Hour) | Remark
I004 | Meeting | 1000 | 14 | 0 | 2017-01-16 |  | All | 17.5
S003 | Requirements analysis | 1000 | 10 | 0 |  |  | Bella.Bi | 0
P001 | Project management | 1000 | 6 | 0 | 2017-01-16 |  | Bella.Bi | 7.5
UC015.US01 | Disable Create Program with “NO JDT File” | 900 | 5 | 1 | 2017-01-16 | 2017-01-18 | Shawn.Shao | 5
UC015.US02 | Validation fatal error for importing program | 900 | 5 | 1 | 2017-01-17 | 2017-01-18 | Shawn.Shao | 5
UC015.US03 | Validation mandatory fields for importing program | 900 | 10 | 1 | 2017-01-17 | 2017-01-18 | Olivia.Ge | 9
UC016.US01 | Re-organize the program treeview | 900 | 2 | 1 |  |  | Olivia.ge | 0
UC005.US04 | Remove well profile page from directly under program | 800 | 1 | 1 | 2017-01-16 | 2017-01-16 | Olivia.Ge | 0.2
UC003.US03 | Add Template ID _implement | 790 | 4 | 1 | 2017-01-16 | 2017-01-16 | Shawn.shao | 2
UC004.US04 | Add values to “eService Import Sheet” | 730 | 3 | 1 | 2017-01-17 | 2017-01-17 | Bela.Zhao | 3
UC004.US05 | Add product entity,testdata,service,dao | 710 | 7 | 1 | 2017-01-16 | 2017-01-17 | Bela.Zhao | 7
UC004.US01 | Add product page in Program | 700 | 7 | 1 | 2017-01-16 | 2017-01-16 | Olivia.Ge | 4
UC004.US02 | Import Product information_BlendSection | 700 | 6 | 1 | 2017-01-17 | 2017-01-20 | Bela.Zhao | 6.5 | 预计还需要
UC006.US03 | Create Call Sheet from Program to carry over product information | 700 | 10 | 1 | 2017-01-16 | 2017-01-17 | Olivia.Ge | 3.5
UC011.US04 | Unit Test for recalculation | 700 | 5 | 1 |  |  | Shawn.Shao | 0
UC013.US01 | Micellenous fixes _program update error | 600 | 1 | 1 | 2017-01-16 | 2017-01-16 | Olivia.ge | 0.5
UC004.US03 | Add four JDT file | 600 | 3 | 1 | 2017-01-19 | 2017-01-19 | Bela.zhao | 2
UC004.US04 | Populate JDT to entity | 600 | 7 | 1 | 2017-01-19 | 2017-01-20 | Olivia.ge | 9
UC004.US05 | Import Product information_BlendAdditiveSection | 600 | 6 | 1 | 2017-01-19 | 2017-01-20 | Bela.zhao | 6
T001 | Test for tasks | 500 | 6 | 0 | 2017-01-18 |  | Bella.bi | 37
T002 | Micellenous fixes _Program Id fixed&Program Validation | 500 | 1 | 1 | 2017-01-19 | 2017-01-19 | Olivia.ge | 1
T003 | Micellenous fixes _Excel.exe not closed properly | 500 | 0.5 | 1 | 2017-01-19 | 2017-01-19 | Randy.ling | 0.5
I006 | Discussion &Match the template and entity | 500 | 3 | 1 | 2017-01-19 | 2017-01-19 | Bela.Zhao&Olivia.Ge | 3
I005 | Code review | 400 | 0 |  |  |  |  | 0
T004 | Micellenous fixes_fix bug 4,8 | 400 | 0 |  |  |  | Olivia.ge | 2.5
T005 | Micellenous fixes_fix bug 6,9,10 | 400 | 0 |  |  |  | Randy.ling | 2
T006 | Micellenous fixes_fix bug 2,7 | 400 | 0 |  |  |  | Bela.zhao | 3
I007 | Environment problem | 400 | 0 |  |  |  | Bella.Bi&Randy.ling&Shawn.shao&Bela.zhao | 8.5
I008 | Database Update | 300 | 0 |  |  |  | Bela.zhao | 0.5
T007 | Micellenous fixes_fix bug 12,13 | 300 | 0 |  |  |  | Bela.zhao | 4
T008 | Micellenous fixes_fix bug 14,15,16 | 300 | 0 |  |  |  | Olivia.ge | 5.5
T009 | Micellenous fixes_fix bug 21,22 | 300 | 0 |  |  |  |  | 7
T010 | Micellenous fixes_fix bug 18,19,20 | 300 | 0 |  |  |  |  | 7
T011 | Micellenous fixes_fix bug 23 | 300 | 0 |  |  |  |  | 10
T012 | Micellenous fixes_fix bug 21 | 300 | 0 |  |  |  |  | 10
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0
0
Total Backlogs | 4 | Total Estimate Hours |  | 122.5
Finished Backlogs | 16 | Total Hours of Finished Backlogs |  | 189.2
0 | 0 | 0 | 0
0 | 0 | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务开始时间
Note on G1: Ying Li: 任务结束时间
Note on H1: Ying Li: 任务负责人
Note on I1: Ying Li: 任务投入总时间
Note on A44: Ying Li: 公式计算，迭代计划完成的任务数量
Note on A45: Ying Li: 根据完成状态计算，已完成的任务数量