## Daily Records
ID | Name | Prioritize | Est(Hour) | 2017-02-19 | 2017-02-20 | 2017-02-21 | 2017-02-22 | 2017-02-23 | 2017-02-24 | Total Hours
|  |  |  | 周日 | 42786 | 42787 | 42788 | 42789 | 42790
| Est |  | 97 | 151 | 113 | 72 | 48 | 24 | 0 | 155
| Actual |  | 97 | 151 | 108.5 | 70 | 36.5 | 11.5 | -4
|  |  | 97 | 0 | 42.5 | 38.5 | 33.5 | 25 | 15.5
I004 | Meeting | 1000 | 8 |  | 4 |  |  | 7 |  | 11 | All
S002 | Update product backlog | 900 | 6 |  | 3 |  |  |  |  | 3 | Bella.Bi
T013 | Fix bug for print | 900 | 6 |  | 2 | 2 | 1 |  |  | 5 | Shawn.Shao
P003 | Merge from trunk to branch | 900 | 6 |  |  |  | 1 | 2 |  | 3 | Olivia.Ge
UC005.US10 | Import Well Information to Jdt | 660 | 6 |  | 5 |  |  |  |  | 5 | Bela.Zhao
UC005.US04 | Add WellSpecificsPage in Program_presenter&test | 650 | 4 |  | 4.5 | 1 |  |  |  | 5.5 | Leo.Tian
UC005.US15 | Add WellHardwarePage in Program_presenter&test | 650 | 4 |  | 5 | 0.5 |  |  |  | 5.5 | Frank.Zhang
UC017.US01 | Add Formation Section UI to Call Sheet | 640 | 1 |  | 1.5 |  |  |  |  | 1.5 | Linsee&Olivia
UC017.US03 | Update export /import call sheet for formation | 640 | 5 |  | 2 |  |  |  |  | 2 | Olivia.Ge
UC005.US11 | Transfer Jdt to WellHardware | 630 | 5 |  |  | 3 | 6 |  | 1 | 10 | Bela.Zhao
UC005.US12 | Transfer Jdt to WelInformation | 630 | 5 |  |  | 4 |  |  |  | 4 | Bela.Zhao
UC005.US13 | Transfer Jdt to WellSpecifics | 630 | 5 |  |  | 4.5 |  |  |  | 4.5 | Olivia.Ge
UC019.US01 | Carry over well information to proper section in Call Sheet | 450 | 4 |  | 1.5 |  |  |  |  | 1.5 | Olivia.Ge
UC019.US02 | Carry over well hardware to proper section in Call Sheet | 450 | 4 |  | 1 |  |  |  |  | 1 | Olivia.Ge
UC019.US03 | Carry over well specifics to proper section in Call Sheet | 450 | 4 |  | 1.5 |  |  |  |  | 1.5 | Olivia.Ge
UC020.US01 | Carry over all imported well information to proper section in Job/Service Report | 450 | 6 |  | 4.5 |  |  |  |  | 4.5 | Olivia.Ge
I006 | Pair programming_Olivia | 400 | 8 |  |  | 0.5 |  |  |  | 0.5 | Olivia.Ge
I007 | Pair programming_Bela | 400 | 8 | [6 empty] | 0 | Bela.Zhao
I010 | Add testdata | 300 | 2 |  | 0.5 |  |  |  |  | 0.5 | Olivia.Ge
T014 | Fix test | 300 |  |  | 1.5 |  |  |  |  | 1.5 | Linsee
I005 | Prepare environment | 300 |  |  | 3 | 14.5 | 8 | 1.5 |  | 27 | Bela&Leo&Frank&Leo
T015 | Fix bug | 200 |  |  | 2 | 4.5 |  | 2.5 |  | 9 | Bela&Olivia
T016 | Test | 200 |  |  |  | 4 | 10 | 10.5 | 0.5 | 25 | All
I011 | Review code | 200 |  |  |  |  | 7.5 | 1.5 |  | 9 | All
S003 | HardWare Section analysis | 200 | [6 empty] | 14 | 14
Note on F6: Bella Bi: Planning 0.5*8
Note on I6: Bella Bi: 对Eservice过程简介
Note on F13: Bella Bi: Linsee 1h Olivia 0.5h
Note on F21: Bella Bi: Linsee 3h Olivia 1.5h
Note on G22: Bella Bi: Olivia 0.5h review code
Note on F25: Bella Bi: 修改测试
Note on F26: Bella Bi: Leo 2h Bela 1h 连接数据库的问题
Note on G26: Bella Bi: Frank 3h Leo 6h Randy 4h Linsee 1.5h 本地环境配置，与数据库、IIS相关
Note on H26: Bella Bi: Leo 6h Randy 2h
Note on I26: Bella Bi: Leo 1h Frank 0.5h 配置本地环境
Note on G27: Bella Bi: Bela 1h Olivia 0.5h 修复Formation报错的问题 Olivia 2h 导入时报错的问题 Frank 1h dll文件报错问题
Note on I27: Bella Bi: Olivia 0.5h 修改PriceItem相关的bug Bela 1h 修复导入时的问题 Bela 1h修改导不进去的数据库的问题
Note on H28: Bella Bi: Frank 2h Leo 1h Linsee 2h Olivia 4h Bela 1h
Note on I28: Bella Bi: Linsee 1h Leo 2h Frank 1h Bela 3h Olivia 3.5h
Note on J28: Bella Bi: Linsee 0.5h
Note on H29: Bella Bi: Frank 2h Linsee 3.5h Olivia 2h
Note on I29: Bella Bi: Frank 0.5h Bela 1h
Note on B30: Bella Bi: 结合代码理解HardWare部分的需求
Note on J30: Bella Bi: Bela 7h Olivia 7h

## Resources
SPRINT | 1 | 本次迭代主要完成第三期任务
StartDate | 2017-02-20
EndDate | 2017-02-25
Est Time
Name | Role | Total Hours | 2017-02-20 | 2017-02-21 | 2017-02-22 | 2017-02-23 | 2017-02-24
|  |  | 42786 | 42787 | 42788 | 42789 | 42790
合计 |  | 151 | 113 | 72 | 48 | 24 | 0
|  | 151 | 38 | 41 | 24 | 24 | 24
Olivia.Ge |  | 26 | 7 | 7 | 4 | 4 | 4
Bella.Bi |  | 11 | 3 | 2 | 2 | 2 | 2
Bela.Zhao |  | 26 | 7 | 7 | 4 | 4 | 4
Shawn.Shao |  | 15 | 0 | 3 | 4 | 4 | 4
Randy.Ling |  | 4 | 0 | 1 | 1 | 1 | 1
Leo.Tian |  | 23 | 7 | 7 | 3 | 3 | 3
Frank.Zhang |  | 23 | 7 | 7 | 3 | 3 | 3
Linsee.Lin |  | 23 | 7 | 7 | 3 | 3 | 3
Actual Time
Name | Role | Total Hours | 2017-02-20 | 2017-02-21 | 2017-02-22 | 2017-02-23 | 2017-02-24
|  |  | 42786 | 42787 | 42788 | 42789 | 42790
合计 |  | 155 | 112.5 | 74 | 40.5 | 15.5 | 0
|  | 155 | 42.5 | 38.5 | 33.5 | 25 | 15.5
Olivia.Ge |  | 38 | 9.5 | 7.5 | 7 | 7 | 7
Bella.Bi |  | 8.5 | 3.5 | 4 | 0 | 1 | 0
Bela.Zhao |  | 37.5 | 7.5 | 8 | 7 | 7 | 8
Shawn.Shao |  | 6.5 | 2.5 | 2 | 1 | 1 | 0
Randy.Ling |  | 6 | 0 | 4 | 2 | 0 | 0
Leo.Tian |  | 25 | 7 | 7 | 7 | 4 | 0
Frank.Zhang |  | 17 | 5.5 | 4.5 | 4 | 3 | 0
Linsee.Lin |  | 16.5 | 7 | 1.5 | 5.5 | 2 | 0.5

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | StartDate | EndDate | Assign To | Actual(Hour) | Remark
I004 | Meeting | 1000 | 8 | 1 | 2017-02-20 | 2017-02-23 | All | 11
S002 | Update product backlog | 900 | 6 | 1 | 2017-02-20 | 2017-02-20 | Bella.Bi | 3
T013 | Fix bug for print | 900 | 6 | 0 |  |  | Shawn.Shao | 5
P003 | Merge from trunk to branch | 900 | 6 | 1 | 2017-02-20 | 2017-02-23 | Olivia.Ge | 3
UC005.US10 | Import Well Information to Jdt | 660 | 6 | 1 | 2017-02-20 | 2017-02-20 | Bela.Zhao | 5
UC005.US04 | Add WellSpecificsPage in Program_presenter&test | 650 | 4 | 1 | 2017-02-18 | 2017-02-21 | Leo.Tian | 5.5
UC005.US15 | Add WellHardwarePage in Program_presenter&test | 650 | 4 | 1 | 2017-02-17 | 2017-02-21 | Frank.Zhang | 5.5
UC017.US01 | Add Formation Section UI to Call Sheet | 640 | 1 | 1 | 2017-02-20 | 2017-02-20 | Linsee&Olivia | 1.5
UC017.US03 | Update export /import call sheet for formation | 640 | 5 | 1 | 2017-02-20 | 2017-02-20 | Olivia.Ge | 2
UC005.US11 | Transfer Jdt to WellHardware | 630 | 5 | 0 | 2017-02-21 |  | Bela.Zhao | 10
UC005.US12 | Transfer Jdt to WelInformation | 630 | 5 | 1 | 2017-02-21 | 2017-02-21 | Bela.Zhao | 4
UC005.US13 | Transfer Jdt to WellSpecifics | 630 | 5 | 1 | 2017-02-21 | 2017-02-21 | Olivia.Ge | 4.5
UC019.US01 | Carry over well information to proper section in Call Sheet | 450 | 4 | 1 | 2017-02-20 | 2017-02-20 | Olivia.Ge | 1.5
UC019.US02 | Carry over well hardware to proper section in Call Sheet | 450 | 4 | 1 | 2017-02-20 | 2017-02-20 | Olivia.Ge | 1
UC019.US03 | Carry over well specifics to proper section in Call Sheet | 450 | 4 | 1 | 2017-02-20 | 2017-02-20 | Olivia.Ge | 1.5
UC020.US01 | Carry over all imported well information to proper section in Job/Service Report | 450 | 6 | 1 | 2017-02-20 | 2017-02-20 | Olivia.Ge | 4.5
I006 | Pair programming_Olivia | 400 | 8 | 1 | 2017-02-21 | 2017-02-21 | Olivia.Ge | 0.5
I007 | Pair programming_Bela | 400 | 8 | 1 |  |  | Bela.Zhao | 0
I010 | Add testdata | 300 | 2 | 1 | 2017-02-20 | 2017-02-20 | Olivia.Ge | 0.5
T014 | Fix test | 300 | 0 | 1 | 2017-02-20 | 2017-02-20 | Linsee | 1.5
I005 | Prepare environment | 300 | 0 | 1 | 2017-02-20 | 2017-02-23 | Bela&Leo&Frank&Leo | 27
T015 | Fix bug | 200 | 0 | 1 | 2017-02-20 | 2017-02-23 | Bela&Olivia | 9
T016 | Test | 200 | 0 | 1 | 2017-02-21 | 2017-02-24 | All | 25
I011 | Review code | 200 | 0 | 1 | 2017-02-22 | 2017-02-23 | All | 9
S003 | HardWare Section analysis | 200 | 18 | 0 | 2017-02-24 |  | All | 14
|  |  |  | 0 |  |  |  | 0
0
Total Backlogs | 3 | Total Estimate Hours |  | 97
Finished Backlogs | 22 | Total Hours of Finished Backlogs |  | 155
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务开始时间
Note on G1: Ying Li: 任务结束时间
Note on H1: Ying Li: 任务负责人
Note on I1: Ying Li: 任务投入总时间
Note on A29: Ying Li: 公式计算，迭代计划完成的任务数量
Note on A30: Ying Li: 根据完成状态计算，已完成的任务数量