## Daily Records
ID | Name | Prioritize | Est(Hour) | 2017-02-26 | 2017-02-27 | 2017-02-28 | 2017-03-01 | 2017-03-02 | 2017-03-03 | Total Hours
|  |  |  | 周日 | 42793 | 42794 | 42795 | 42796 | 42797
| Est |  | 36 | 37 | 20 | 5 | 0 | 0 | 0 | 16
| Actual |  | 32 | 37 | 21 | 21 | 21 | 21 | 21
|  |  | 36 | 0 | 16 | 0 | 0 | 0 | 0
I004 | Meeting | 1000 | 4 | [6 empty] | 0 | All
S002 | Update product backlog | 900 | 3 |  | 1 |  |  |  |  | 1 | Bella.Bi
T013 | Fix bug for print | 900 | 4 | [6 empty] | 0 | Shawn.Shao
UC005.US11 | Transfer Jdt to WellHardware | 630 | 7 |  | 6 |  |  |  |  | 6 | Bela.Zhao
UC001.US02 | Code refactoring for WellHardWare | 400 | 10 |  | 7 |  |  |  |  | 7 | Olivia.Ge
T016 | Test | 200 | 4 | [6 empty] | 0 | All
S003 | HardWare Section analysis | 200 | 4 |  | 2 |  |  |  |  | 2 | Olivia&Bela
Note on B12: Bella Bi: 结合代码理解HardWare部分的需求
Note on F12: Bella Bi: Olivia 1h Bela 1h

## Resources
SPRINT | 1 | 本次迭代主要完成第三期任务
StartDate | 2017-02-27
EndDate | 2017-03-03
Est Time
Name | Role | Total Hours | 2017-02-27 | 2017-02-28 | 2017-03-01 | 2017-03-02 | 2017-03-03
|  |  | 42793 | 42794 | 42795 | 42796 | 42797
合计 |  | 37 | 20 | 5 | 0 | 0 | 0
|  | 37 | 17 | 15 | 5 | 0 | 0
Olivia.Ge |  | 16 | 7 | 7 | 2 | 0 | 0
Bella.Bi |  | 5 | 3 | 1 | 1 | 0 | 0
Bela.Zhao |  | 16 | 7 | 7 | 2 | 0 | 0
Shawn.Shao |  | 0 | 0 | 0 | 0 | 0 | 0
Randy.Ling |  | 0 | 0 | 0 | 0 | 0 | 0
Leo.Tian |  | 0 | 0 | 0 | 0 | 0 | 0
Frank.Zhang |  | 0 | 0 | 0 | 0 | 0 | 0
Linsee.Lin |  | 0 | 0 | 0 | 0 | 0 | 0
Actual Time
Name | Role | Total Hours | 2017-02-27 | 2017-02-28 | 2017-03-01 | 2017-03-02 | 2017-03-03
|  |  | 42793 | 42794 | 42795 | 42796 | 42797
合计 |  | 16 | 0 | 0 | 0 | 0 | 0
|  | 16 | 16 | 0 | 0 | 0 | 0
Olivia.Ge |  | 8 | 8
Bella.Bi |  | 1 | 1
Bela.Zhao |  | 7 | 7
Shawn.Shao |  | 0
Randy.Ling |  | 0
Leo.Tian |  | 0
Frank.Zhang |  | 0
Linsee.Lin |  | 0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | StartDate | EndDate | Assign To | Actual(Hour) | Remark
I004 | Meeting | 1000 | 4 | 0 |  |  | All | 0
S002 | Update product backlog | 900 | 3 | 0 |  |  | Bella.Bi | 1
T013 | Fix bug for print | 900 | 4 | 0 |  |  | Shawn.Shao | 0
UC005.US11 | Transfer Jdt to WellHardware | 630 | 7 | 0 |  |  | Bela.Zhao | 6
UC001.US02 | Code refactoring for WellHardWare | 400 | 10 | 0 |  |  | Olivia.Ge | 7
T016 | Test | 200 | 4 | 0 |  |  | All | 0
S003 | HardWare Section analysis | 200 | 4 | 0 |  |  | Olivia&Bela | 2
0 | 0 | 0 | 0 | 0 |  |  |  | 0
0 | 0 | 0 | 0 | 0 |  |  |  | 0
0 | 0 | 0 | 0 | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
|  |  |  | 0 |  |  |  | 0
0
Total Backlogs | 3 | Total Estimate Hours |  | 36
Finished Backlogs | 0 | Total Hours of Finished Backlogs |  | 16
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务开始时间
Note on G1: Ying Li: 任务结束时间
Note on H1: Ying Li: 任务负责人
Note on I1: Ying Li: 任务投入总时间
Note on A29: Ying Li: 公式计算，迭代计划完成的任务数量
Note on A30: Ying Li: 根据完成状态计算，已完成的任务数量