## Daily Records
ID | Name | Prioritize | Est(Hour) | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-06 | 2022-06-07 | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-13 | 2022-06-14 | 2022-06-15 | 2022-06-16 | 2022-06-17 | 2022-06-20 | 2022-06-21 | 2022-06-22 | 2022-06-23 | 2022-06-24 | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | Total Hours
|  |  |  | 44686 | 44687 | 44688 | 44690 | 44691 | 44692 | 44693 | 44694 | 44697 | 44698 | 44699 | 44700 | 44701 | 44704 | 44705 | 44706 | 44707 | 44708 | 44711 | 44712 | 44713 | 44714 | 44718 | 44719 | 44720 | 44721 | 44722 | 44725 | 44726 | 44727 | 44728 | 44729 | 44732 | 44733 | 44734 | 44735 | 44736 | 44739 | 44740 | 44741 | 44742
| Ideal Burndown |  | 264 | 256 | 248 | 240 | 232 | 224 | 216 | 208 | 200 | 192 | 184 | 176 | 168 | 160 | 152 | 144 | 136 | 128 | 120 | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual |  | 200 | 200 | 192 | 184 | 176 | 168 | 160 | 152 | 144 | 136 | 128 | 120 | 112 | 104 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | -8 | -16 | -24 | -32 | -40 | -48 | -56 | -64 | -72 | -80 | -88 | -96 | -104 | -112
|  |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | Assign to | Completion Status | Pay by
5.5 | net 6 of nullable And lab database select order by | 850 | 0 | 2022-05-05: 0
5.6 | study common.core of mmc | 850 | 8
5.7 | test common.core of mmc | 850 | 8 | 2022-05-05: 8
44690 | Architecture design | 850 | 40 | 2022-05-06: 8; 2022-05-07: 8; 2022-05-09: 8; 2022-05-10: 8; 2022-05-11: 8
44691 | Abstract SLD entity model for MMC | 850 | 16 | 2022-05-12: 8; 2022-05-13: 8
44692 | Enter entity model in SanjelData model in MMC | 850 | 16 | 2022-05-16: 8; 2022-05-17: 8; 2022-05-24: 4; 2022-05-25: 4
44693 | Generate SanjelData code in MMC to update SanjelMDM project | 850 | 8 | 2022-05-26: 8; 2022-06-06: 4
44694 | Add GateWay project in Lab project and references to SanjelData projects. | 850 | 16 | 2022-05-27: 8; 2022-06-07: 4
44697 | Organize data and import to new table. | 850 | 24 | 2022-05-18: 8; 2022-05-19: 8; 2022-05-20: 8; 2022-05-23: 8; 2022-05-31: 4; 2022-06-01: 0; 2022-06-07: 4; 2022-06-08: 6; 2022-06-09: 4
44698 | Change SLD entity data of entity framework to GateWay function. | 850 | 32 | 2022-06-08: 2; 2022-06-09: 4; 2022-06-10: 8; 2022-06-13: 8; 2022-06-14: 8; 2022-06-15: 8
44699 | Testing and debug. | 850 | 32 | 2022-06-16: 8; 2022-06-17: 8; 2022-06-20: 8; 2022-06-21: 8; 2022-06-22: 8; 2022-06-23: 8; 2022-06-24: 8; 2022-06-27: 8; 2022-06-28: 8; 2022-06-29: 8; 2022-06-30: 8
| Recover versioned flag |  |  | 2022-05-24: 4; 2022-05-25: 4
| Layering labtest projects |  |  | 2022-05-30: 8; 2022-05-31: 4; 2022-06-01: 8; 2022-06-02: 8; 2022-06-06: 4
Note on G12: Bella Bi: 更新开发规范 更新底层重构记录及问题
Note on A17: Bella Bi: 需要分析Bug,新增Task Ticket
Note on N23: Colin Ji: Olivia.Ge:4h Bright.liu:6h
Note on T25: Colin Ji: Olivia.Ge:1h
Note on S29: Colin Ji: Bright.Liu:8h Olivia.Ge:3h
Note on T29: Colin Ji: Bright:Liu:8h Olivia.Ge:2h
Note on A50: Bella Bi: 需要分析Bug,新增Task Ticket

## Task Remaining
ID | Name | Prioritize |  | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-06 | 2022-06-07 | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-13 | 2022-06-14 | 2022-06-15 | 2022-06-16 | 2022-06-17 | 2022-06-20 | 2022-06-21 | 2022-06-22 | 2022-06-23 | 2022-06-24 | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30
|  |  | EST | 44686 | 44687 | 44688 | 44690 | 44691 | 44692 | 44693 | 44694 | 44697 | 44698 | 44699 | 44700 | 44701 | 44704 | 44705 | 44706 | 44707 | 44708 | 44711 | 44712 | 44713 | 44714 | 44718 | 44719 | 44720 | 44721 | 44722 | 44725 | 44726 | 44727 | 44728 | 44729 | 44732 | 44733 | 44734 | 44735 | 44736 | 44739 | 44740 | 44741 | 44742
| Ideal Burndown |  | 264 | 256 | 248 | 240 | 232 | 224 | 216 | 208 | 200 | 192 | 184 | 176 | 168 | 160 | 152 | 144 | 136 | 128 | 120 | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual burndown |  | 200 | 192 | 184 | 176 | 168 | 160 | 152 | 144 | 136 | 128 | 120 | 116 | 112 | 112 | 106 | 104 | 104 | 127 | 118 | 106 | 96 | 92 | 88 | 80 | 76 | 68 | 60 | 52 | 44 | 36 | 32 | 24 | 16 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0
5.5 | net 6 of nullable And lab database select order by | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.6 | study common.core of mmc | 850 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.7 | test common.core of mmc | 850 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44690 | Architecture design | 850 | 40 | 40 | 40 | 32 | 24 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44691 | Abstract SLD entity model for MMC | 850 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44692 | Enter entity model in SanjelData model in MMC | 850 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44693 | Generate SanjelData code in MMC to update SanjelMDM project | 850 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44694 | Add GateWay project in Lab project and references to SanjelData projects. | 850 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44697 | Organize data and import to new table. | 850 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 20 | 16 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44698 | Change SLD entity data of entity framework to GateWay function. | 850 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 28 | 20 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44699 | Testing and debug. | 850 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 24 | 16 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0
| Recover versioned flags | [14 empty] | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Layering labtest projects | [18 empty] | 24 | 16 | 10 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成第11期FDAS的反馈需求
StartDate | 2022-05-05
EndDate | 2022-06-06
Est Time
Name | Role | Total Hours | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-06 | 2022-06-07 | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-13 | 2022-06-14 | 2022-06-15 | 2022-06-16 | 2022-06-17 | 2022-06-20 | 2022-06-21 | 2022-06-22 | 2022-06-23 | 2022-06-24 | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30
|  |  | 44686 | 44687 | 44688 | 44690 | 44691 | 44692 | 44693 | 44694 | 44697 | 44698 | 44699 | 44700 | 44701 | 44704 | 44705 | 44706 | 44707 | 44708 | 44711 | 44712 | 44713 | 44714 | 44718 | 44719 | 44720 | 44721 | 44722 | 44725 | 44726 | 44727 | 44728 | 44729 | 44732 | 44733 | 44734 | 44735 | 44736 | 44739 | 44740 | 44741 | 44742
Ideal Burndown |  | 264 | 256 | 248 | 240 | 232 | 224 | 216 | 208 | 200 | 192 | 184 | 176 | 168 | 160 | 152 | 144 | 136 | 128 | 120 | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours consumed |  | 264 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Evan Zhang |  | 264 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
5.5 | net 6 of nullable And lab database select order by | 850 | 0 | 0 | 0 | 0
5.6 | study common.core of mmc | 850 | 8 | 0 | 0 | 0
5.7 | test common.core of mmc | 850 | 8 | 0 | 0 | 0
44690 | Architecture design | 850 | 40 | 0 | 0 | 0
44691 | Abstract SLD entity model for MMC | 850 | 16 | 0 | 0 | 0
44692 | Enter entity model in SanjelData model in MMC | 850 | 16 | 0 | 0 | 0
44693 | Generate SanjelData code in MMC to update SanjelMDM project | 850 | 8 | 0 | 0 | 0
44694 | Add GateWay project in Lab project and references to SanjelData projects. | 850 | 16 | 0 | 0 | 0
44697 | Organize data and import to new table. | 850 | 24 | 0 | 0 | 0
44698 | Change SLD entity data of entity framework to GateWay function. | 850 | 32 | 0 | 0 | 0
44699 | Testing and debug. | 850 | 32 | 0 | 0 | 0
0 | Recover versioned flag | 0 | 0 | 0 | 0 | 0
0 | Layering labtest projects | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间