## Daily Records
ID | Name | Prioritize | Est(Hour) | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-22 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-29 | 2022-08-30 | 2022-08-31 | #REF! | Total Hours
|  |  |  | 44774 | 44775 | 44776 | 44777 | 44778 | 44781 | 44782 | 44783 | 44784 | 44785 | 44788 | 44789 | 44790 | 44791 | 44792 | 44795 | 44796 | 44797 | 44798 | 44799 | 44802 | 44803 | 44804 | #REF!
| Ideal Burndown |  | 184 | 176 | 168 | 160 | 152 | 144 | 136 | 128 | 120 | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | #REF! | 0
| Actual |  | 96 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | 0 | -8 | -16 | -24 | -32 | -40 | -48 | -56 | -64 | -72 | -56
|  |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 |  | Assign to | Completion Status | Pay by
| schedule blend、reSchedule blend、Hual blend from bulk plant or from rig board blend | 850 | 96 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [12 empty] | Evan Zhang |  | Sanjel
| schedule product haul、cancel product haul、cancel product haul load、onload product haul、onload product haul load、reschedule product haul、reschedule product haul load | 850 | [14 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | Evan Zhang |  | Sanjel
[29 empty] | Evan Zhang |  | Sanjel
[29 empty] | Evan Zhang |  | Sanjel
[29 empty] | Evan Zhang |  | Sanjel
Evan Zhang
Note on G12: Bella Bi: 更新开发规范 更新底层重构记录及问题
Note on A17: Bella Bi: 需要分析Bug,新增Task Ticket
Note on N23: Colin Ji: Olivia.Ge:4h Bright.liu:6h
Note on T25: Colin Ji: Olivia.Ge:1h
Note on S29: Colin Ji: Bright.Liu:8h Olivia.Ge:3h
Note on T29: Colin Ji: Bright:Liu:8h Olivia.Ge:2h
Note on A50: Bella Bi: 需要分析Bug,新增Task Ticket

## Task Remaining
ID | Name | Prioritize |  | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-22 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-29 | 2022-08-30 | 2022-08-31 | #REF!
|  |  | EST | 44774 | 44775 | 44776 | 44777 | 44778 | 44781 | 44782 | 44783 | 44784 | 44785 | 44788 | 44789 | 44790 | 44791 | 44792 | 44795 | 44796 | 44797 | 44798 | 44799 | 44802 | 44803 | 44804 | #REF!
| Ideal Burndown |  | 184 | 176 | 168 | 160 | 152 | 144 | 136 | 128 | 120 | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | #REF!
| Actual burndown |  | 176 | 176 | 168 | 160 | 152 | 144 | 136 | 128 | 120 | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | 0
| schedule blend、reSchedule blend、Hual blend from bulk plant or from rig board blend | 850 | 96 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| schedule product haul、cancel product haul、cancel product haul load、onload product haul、onload product haul load、reschedule product haul、reschedule product haul load | 850 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | 0
0
0
0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成第11期FDAS的反馈需求
StartDate | 2022-08-01
EndDate | 2022-09-01
Est Time
Name | Role | Total Hours | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-22 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-29 | 2022-08-30 | 2022-08-31
|  |  | 44774 | 44775 | 44776 | 44777 | 44778 | 44781 | 44782 | 44783 | 44784 | 44785 | 44788 | 44789 | 44790 | 44791 | 44792 | 44795 | 44796 | 44797 | 44798 | 44799 | 44802 | 44803 | 44804
Ideal Burndown |  | 184 | 176 | 168 | 160 | 152 | 144 | 136 | 128 | 120 | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0
Hours consumed |  | 184 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Evan Zhang |  | 184 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
0 | schedule blend、reSchedule blend、Hual blend from bulk plant or from rig board blend | 850 | 96 | 0 | Evan Zhang | 0
0 | schedule product haul、cancel product haul、cancel product haul load、onload product haul、onload product haul load、reschedule product haul、reschedule product haul load | 850 | 0 | 0 | Evan Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan Zhang | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间