## Daily Records
ID | Name | Prioritize | Est(Hour) | 2022-09-01 | 2022-09-02 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | #REF! | #REF! | Total Hours
|  |  |  | 44805 | 44806 | 44809 | 44810 | 44811 | 44812 | 44813 | 44816 | 44817 | 44818 | 44819 | 44820 | 44823 | 44824 | 44825 | 44826 | 44827 | 44830 | 44831 | 44832 | 44833 | 44834 | #REF! | #REF!
| Ideal Burndown |  | 176 | 168 | 160 | 152 | 144 | 136 | 128 | 120 | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | #REF! | #REF! | 0
| Actual |  | 0 | 0 | -8 | -16 | -24 | -32 | -40 | -48 | -48 | -56 | -64 | -72 | -80 | -88 | -88 | -96 | -104 | -108 | -116 | -124 | -124 | -132 | -140 | -140 | -132
|  |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 8 | 8 | 0 | 8 | 8 | 0 | 0 |  | Assign to | Completion Status | Pay by
| debug and fix schedule product haul,reschedule product haul,schedule blend,re-schedule blend,cancel blend. |  | -16: 8; -24: 8; -32: 8; -40: 8; -48: 8; -116: 8; -124: 8; -140: 4 |  | Evan Zhang |  | Sanjel
| build remote running environment |  | 0: 8; -8: 8; -56: 8; -64: 8 |  | Evan Zhang |  | Sanjel
| debug .NET 6 MMD library |  | -72: 8; -80: 8; -88: 8; -88: 2; -96: 2; -104: 2 |  | Evan Zhang |  | Sanjel
| bulk plant bin menu and methord、rig board bin menu and methord |  | -88: 6; -96: 6; -104: 6 |  | Evan Zhang |  | Sanjel
| sanjel eservice eprogram |  | -108: 4; -132: 8; -140: 4 |  | Evan Zhang |  | Sanjel
Evan Zhang
Note on G12: Bella Bi: 更新开发规范 更新底层重构记录及问题
Note on A17: Bella Bi: 需要分析Bug,新增Task Ticket
Note on N23: Colin Ji: Olivia.Ge:4h Bright.liu:6h
Note on T25: Colin Ji: Olivia.Ge:1h
Note on S29: Colin Ji: Bright.Liu:8h Olivia.Ge:3h
Note on T29: Colin Ji: Bright:Liu:8h Olivia.Ge:2h
Note on A50: Bella Bi: 需要分析Bug,新增Task Ticket

## Task Remaining
ID | Name | Prioritize |  | 2022-09-01 | 2022-09-02 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | #REF! | #REF!
|  |  | EST | 44805 | 44806 | 44809 | 44810 | 44811 | 44812 | 44813 | 44816 | 44817 | 44818 | 44819 | 44820 | 44823 | 44824 | 44825 | 44826 | 44827 | 44830 | 44831 | 44832 | 44833 | 44834 | #REF! | #REF!
| Ideal Burndown |  | 176 | 168 | 160 | 152 | 144 | 136 | 128 | 120 | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0 | #REF! | #REF!
| Actual burndown |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| debug and fix schedule product haul,reschedule product haul,schedule blend,re-schedule blend,cancel blend. | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| build remote running environment | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| debug .NET 6 MMD library | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| bulk plant bin menu and methord、rig board bin menu and methord | 850
sanjel eservice eprogram
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成第11期FDAS的反馈需求
StartDate | 2022-09-01
EndDate | 2022-10-02
Est Time
Name | Role | Total Hours | 2022-09-01 | 2022-09-02 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30
|  |  | 44805 | 44806 | 44809 | 44810 | 44811 | 44812 | 44813 | 44816 | 44817 | 44818 | 44819 | 44820 | 44823 | 44824 | 44825 | 44826 | 44827 | 44830 | 44831 | 44832 | 44833 | 44834
Ideal Burndown |  | 176 | 168 | 160 | 152 | 144 | 136 | 128 | 120 | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0
Hours consumed |  | 176 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Evan Zhang |  | 176 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
0 | debug and fix schedule product haul,reschedule product haul,schedule blend,re-schedule blend,cancel blend. | 0 | 0 | 0 | Evan Zhang | 0
0 | build remote running environment | 0 | 0 | 0 | Evan Zhang | 0
0 | debug .NET 6 MMD library | 0 | 0 | 0 | Evan Zhang | 0
0 | bulk plant bin menu and methord、rig board bin menu and methord | 0 | 0 | 0 | Evan Zhang | 0
0 | sanjel eservice eprogram | 0 | 0 | 0 | Evan Zhang | 0
0 | 0 | 0 | 0 | 0 | Evan Zhang | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间