## Daily Records
ID | Name | Prioritize | Est(Hour) | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-31 | Total Hours
|  |  |  | 44842 | 44843 | 44844 | 44845 | 44846 | 44847 | 44848 | 44851 | 44852 | 44853 | 44854 | 44855 | 44858 | 44859 | 44860 | 44861 | 44862 | 44865
| Ideal Burndown |  | 288 | 280 | 272 | 256 | 240 | 224 | 208 | 192 | 176 | 160 | 144 | 128 | 112 | 96 | 78 | 61 | 31 | 15 | -1 | 194.5
| Actual |  | 0 | 0 | -16 | -32 | -48 | -64 | -80 | -96 | -100 | -108 | -116 | -116 | -120 | -128 | -130 | -135 | -153 | -156 | -163
|  |  |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 4 | 8 | 8 | 0 | 4 | 8 | 10 | 5 | 18 | 3 | 7 |  | Assign to | Completion Status | Pay by
| SanjeleProgram |  |  | 2022-10-08: 4; 2022-10-09: 1; 2022-10-10: 1; 2022-10-11: 5 | 11 | Evan Zhang |  | Sanjel
| helper xian Create environment |  |  | 2022-10-08: 2; 2022-10-09: 7; 2022-10-10: 6; 2022-10-11: 3 | 18 | Evan Zhang |  | Sanjel
| fix bug for eServiceOnline |  |  | 2022-10-08: 2; 2022-10-10: 1; 2022-10-12: 8; 2022-10-13: 8; 2022-10-14: 8 | 27 | Evan Zhang |  | Sanjel
| Schedule Product Haul,Schedule Blend Request需求整理 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 8 | 8 | 0 | 4 | 8 | 8 | 4 | 4 |  | 2 | 106 | Serena.li |  | Sanjel
| Create environment and meeting |  |  | 2022-10-27: 7 | 7 | Hunter.Zhao |  | Sanjel
| Get code branches and install VS 2022 |  |  | 2022-10-25: 2 | 2 | Miguel Anguiano |  | Sanjel
| Compile code and share it with Hunter | [20 empty] | 1 | Miguel Anguiano |  | Sanjel | bar: 2022-10-26
| Create environment and meeting |  |  | 2022-10-27: 7 | 7 | Miguel Anguiano |  | Sanjel
| Disable save button on eService online pop-up's |  |  | 2022-10-28: 2 | 2 | Miguel Anguiano |  | Sanjel
| LabDataBase Item meeting | [20 empty] | 1 | Hunter.Zhao | bar: 2022-10-28
| Requirements Meeting | [20 empty] | 1 | Hunter.Zhao | bar: 2022-10-31
| Master Data Update |  |  | 2022-10-31: 4 | 4 | Hunter.Zhao
| Master Data Update analysis | [20 empty] | 2 | Miguel Anguiano
| Common library and Eservice Code analysis | [20 empty] | 3.5 | Miguel Anguiano
| Requirements Meeting | [20 empty] | 2 | Miguel Anguiano
Note on G12: Bella Bi: 更新开发规范 更新底层重构记录及问题
Note on A17: Bella Bi: 需要分析Bug,新增Task Ticket
Note on N23: Colin Ji: Olivia.Ge:4h Bright.liu:6h
Note on T25: Colin Ji: Olivia.Ge:1h
Note on S29: Colin Ji: Bright.Liu:8h Olivia.Ge:3h
Note on T29: Colin Ji: Bright:Liu:8h Olivia.Ge:2h
Note on A50: Bella Bi: 需要分析Bug,新增Task Ticket

## Task Remaining
ID | Name | Prioritize |  | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-31
|  |  | EST | 44842 | 44843 | 44844 | 44845 | 44846 | 44847 | 44848 | 44851 | 44852 | 44853 | 44854 | 44855 | 44858 | 44859 | 44860 | 44861 | 44862 | 44865
| Ideal Burndown |  | 288 | 280 | 272 | 256 | 240 | 224 | 208 | 192 | 176 | 160 | 144 | 128 | 112 | 96 | 78 | 61 | 31 | 15 | -1
| Actual burndown |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
| SanjeleProgram | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| helper xian Create environment | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| fix bug for eServiceOnline | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Schedule Product Haul,Schedule Blend Request需求整理 | 850 |  | 2022-10-25: 2; 2022-10-26: 0; 2022-10-27: 0; 2022-10-28: 0; 2022-10-31: 0
Create environment and meeting
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成第11期FDAS的反馈需求
StartDate | 2022-10-08
EndDate | 2022-10-31
Est Time
Name | Role | Total Hours | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-31
|  |  | 44842 | 44843 | 44844 | 44845 | 44846 | 44847 | 44848 | 44851 | 44852 | 44853 | 44854 | 44855 | 44858 | 44859 | 44860 | 44861 | 44862 | 44865
Ideal Burndown |  | 288 | 280 | 272 | 256 | 240 | 224 | 208 | 192 | 176 | 160 | 144 | 128 | 112 | 96 | 78 | 61 | 31 | 15 | -1
Hours consumed |  | 289 | 8 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 18 | 17 | 30 | 16 | 16
Evan Zhang |  | 144 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Serena.li |  | 144 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Hunter.Zhao |  |  | 2022-10-27: 7
Miguel Anguiano |  |  | 2022-10-25: 2; 2022-10-26: 1; 2022-10-27: 7

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
0 | SanjeleProgram | 0 | 0 | 0 | Evan Zhang | 11
0 | helper xian Create environment | 0 | 0 | 0 | Evan Zhang | 18
0 | fix bug for eServiceOnline | 0 | 0 | 0 | Evan Zhang | 27
0 | Schedule Product Haul,Schedule Blend Request需求整理 | 0 | 0 | 0 | Serena.li | 106
0 | Create environment and meeting | 0 | 0 | 0 | Hunter.Zhao | 7
0 | Get code branches and install VS 2022 | 0 | 0 | 0 | Miguel Anguiano | 2
0 | Compile code and share it with Hunter | 0 | 0 | 0 | Miguel Anguiano | 1
0 | Create environment and meeting | 0 | 0 | 0 | Miguel Anguiano | 7
0 | Disable save button on eService online pop-up's | 0 | 0 | 0 | Miguel Anguiano | 2
0 | LabDataBase Item meeting | 0 | 0 | 0 | Hunter.Zhao | 1
0 | Requirements Meeting | 0 | 0 | 0 | Hunter.Zhao | 1
0 | Master Data Update | 0 | 0 | 0 | Hunter.Zhao | 4
0 | Master Data Update analysis | 0 | 0 | 0 | Miguel Anguiano | 2
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
#REF! | #REF! | #REF! | #REF! |  | #REF! | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间