## Daily Records
ID | Name | Prioritize | Est(Hour) | 2017-05-21 | 2017-05-22 | 2017-05-23 | 2017-05-24 | 2017-05-25 | 2017-05-26 | 2017-05-27 | 2017-05-31 | 2017-06-01 | 2017-06-02 | 2017-06-05 | 2017-06-06 | 2017-06-07 | 2017-06-08 | 2017-06-09 | Total Hours
|  |  |  | 周日 | 42877 | 42878 | 42879 | 42880 | 42881 | 42882 | 42886 | 42887 | 42888 | 42891 | 42892 | 42893 | 42894 | 42895
| Est |  | 200 | 279 | 272 | 251 | 237 | 220 | 199 | 176 | 154 | 132 | 110 | 88 | 66 | 44 | 22 | 0 | 247
| Actual |  | 200 | 279 | 276 | 260.5 | 247.5 | 229.5 | 210.5 | 198.5 | 179.5 | 160.5 | 135 | 116.5 | 94 | 72 | 51 | 32
|  |  | 200 | 0 | 3 | 15.5 | 13 | 18 | 19 | 12 | 19 | 19 | 25.5 | 18.5 | 22.5 | 22 | 21 | 19
I001 | Meeting | 5000 | 9 | 2017-05-23: 6; 2017-05-25: 2; 2017-05-31: 5; 2017-06-07: 1.5 | 14.5 | All
I002 | Prepare environment | 5000 | 2 | 2017-05-22: 2; 2017-06-06: 3.5 | 5.5 | Bela.Zhao
S001 | Prepare usecase and backlog | 5000 | 8 | 2017-05-23: 1.5; 2017-05-24: 3; 2017-05-25: 2; 2017-05-31: 1; 2017-06-02: 1; 2017-06-05: 0.5; 2017-06-07: 0.5 | 9.5 | Bella.Bi
S002 | Requirements analysis | 5000 | 8 | 2017-05-22: 1; 2017-05-24: 2; 2017-05-25: 0.5; 2017-05-31: 1 | 4.5 | All
D001 | Update design model_local manage | 5000 | 11 | 2017-05-24: 4; 2017-05-25: 2; 2017-05-26: 6; 2017-05-27: 7; 2017-05-31: 2 | 21 | Bela.Zhao
I003 | Implement architecture prototype_local manage | 5000 | 7 | 2017-05-27: 2 | 2 | Bela.Zhao
SY01.UC026.US01.T01 | Research for MSI installation for .net core | 4900 | 2 | 2017-05-31: 4; 2017-06-01: 3; 2017-06-02: 3 | 10 | Linsee.lin
SY01.UC026.US01.T02 | Eservice Express website_installed as a Windows Service | 4900 | 3 | 2017-06-05: 3; 2017-06-09: 5 | 8 | Linsee.lin
SY01.UC026.US01.T03 | Deployment package packed up as MSI installation file | 4900 | 7 | 2017-06-02: 7; 2017-06-05: 1.5; 2017-06-08: 5 | 13.5 | Linsee.lin
SY02.UC002.US01 | View empty Pricing Items list | 4800 | 7 | 2017-05-24: 4; 2017-05-25: 2; 2017-05-26: 1 | 7 | Olivia.Ge
SY02.UC002.US02 | View Pricing Items list with data | 4800 | 8 | 2017-05-25: 3.5; 2017-05-26: 1; 2017-06-09: 2 | 6.5 | Olivia.Ge
SY01.UC026.US01 | Click“Eservice Express” button | 4750 | 5 | 2017-05-26: 2 | 2 | Olivia.Ge
SY01.UC023.US02 | New job package from local | 4700 | 2 | 2017-05-23: 2 | 2 | Olivia.Ge
SY01.UC024.US01 | Update job package | 4700 | 5 | 2017-05-23: 2; 2017-05-31: 2 | 4 | Bela.Zhao
SY01.UC023.US01 | Remove “Add Service Ticket” and “Add Service Report” buttons | 4700 | 2 | 2017-05-23: 2 | 2 | Linsee.Lin
SY04.UC002.US01 | Save “Adjusted Quantity” changes | 4600 | 8 | 2017-05-31: 2; 2017-06-01: 7 | 9 | Olivia.Ge
SY04.UC003.US01 | Implement lock mechanism | 4500 | 4 | 2017-06-05: 5 | 5 | Bela.zhao
SY04.UC003.US01.T01 | Add version property | 4550 | 2 | 2017-06-01: 2 | 2 | Bela.zhao
SY04.UC003.US01.T02 | Pop up the Message box when version not same | 4550 | 4 | 2017-06-01: 4; 2017-06-02: 2 | 6 | Bela.zhao
SY04.UC003.US01.T03 | Update version when save data | 4550 | 5 | 2017-06-02: 5; 2017-06-06: 1; 2017-06-09: 1 | 7 | Bela.zhao
SY04.UC002.US02 | Validation for “Adjusted Quantity” | 4500 | 7 | 2017-06-02: 2; 2017-06-05: 1; 2017-06-06: 6; 2017-06-07: 5 | 14 | Olivia.ge
SY04.UC002.US03 | Data Sync when save data | 4500 | 5 | 2017-06-02: 5; 2017-06-05: 1.5 | 6.5 | Olivia.ge
SY04.UC002.US03.T01 | Data Sync when edit pricelineitem | 4400 | 4 | 2017-06-05: 4 | 4 | Olivia.ge
SY01.UC025.US01 | Enable /Disabled“Eservice Express” button by service | 4000 | 7 | 2017-05-23: 2; 2017-05-26: 2; 2017-05-31: 2 | 6 | Olivia.Ge
SY01.UC025.US02 | Enable /Disabled“Eservice Express” button by sending status | 4000 | 7 | 2017-05-25: 3; 2017-05-26: 3; 2017-05-27: 2; 2017-06-07: 1 | 9 | Linsee.lin
SY01.UC025.US03 | Update “Eservice Express”button status when swich different job package | 4000 | 7 | 2017-05-25: 3; 2017-05-26: 4; 2017-05-27: 1; 2017-06-09: 1 | 9 | Linsee.lin
SY01.UC025.US04 | Enable /Disabled“Eservice Express” button by web site status | 4000 | 7 | 2017-06-06: 3 | 3 | Bela.zhao
SY02.UC002.US05 | Enable Tab key | 4000 | 5 | 2017-06-02: 0.5; 2017-06-06: 2; 2017-06-07: 4 | 6.5 | Oliver.ye
SY02.UC002.US05.T01 | Research for Tab key | 4000 | 2 | 2017-06-01: 2 | 2 | Oliver.ye
SY02.UC002.US03 | Open Pricing Page in Chrome browser from URL | 4000 | 7 | [15 empty] | 0 | 0
SY02.UC002.US03.T01 | Research for check win form status in web page | 4000 | 4 | [15 empty] | 1 | Linsee/Olivia | bar: 2017-06-01
SY03.UC001.US01 | Update version when enter job update page | 3900 | 2 | 2017-06-05: 2; 2017-06-07: 1 | 3 | Bela.zhao
D002 | Design model reverse engineering | 3800 | 8 | [15 empty] | 0 | 0
E001 | Deployment eservice | 3800 | 7 | 2017-06-06: 5; 2017-06-07: 9; 2017-06-08: 11 | 25 | All
T001 | Test | 3800 | 10 | 2017-06-08: 5; 2017-06-09: 10 | 15 | All
SY04.UC003.US01.T04 | Refactor for Pop Up box | 3700 | 2 | 2017-06-06: 2 | 2 | Bela.Zhao
Note on I6: Bella Bi: 0.5*4 预估时间
Note on Q6: Bella Bi: Bella 0.5h Bela 0.5h Olivia 0.5h
Note on P7: Bella Bi: Oliver 3h Bela 0.5h
Note on H9: Bella Bi: Olivia 2h
Note on L9: Bella Bi: Olivia 0.5h Bela 0.5h
Note on N12: Bella Bi: Oliver
Note on Q30: Bella Bi: Bela 1h修复问题
Note on S31: Bella Bi: Bela 1h
Note on Q33: Bella Bi: Bela 2h Oliver 2h
Note on D38: Bella Bi: 由于时间原因将此任务在本次迭代移除
Note on P39: Bella Bi: Linsee 4h Olivia 1h
Note on Q39: Bella Bi: Linsee 7h Bela 1h Oliver 1h
Note on R39: Bella Bi: Oliver 4h Bela 1h Olivia 6h
Note on R40: Bella Bi: Bela 4h Bella 1h
Note on S40: Bella Bi: Bela 4h Bella 2h Linsee 1h Olivia 3h

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2017-05-21 | 2017-05-22 | 2017-05-23 | 2017-05-24 | 2017-05-25 | 2017-05-26 | 2017-05-27 | 2017-05-31 | 2017-06-01 | 2017-06-02 | 2017-06-05 | 2017-06-06 | 2017-06-07 | 2017-06-08 | 2017-06-09 | Total Hours
|  |  |  | 周日 | 42877 | 42878 | 42879 | 42880 | 42881 | 42882 | 42886 | 42887 | 42888 | 42891 | 42892 | 42893 | 42894 | 42895
| Task Remaining |  | 207 | 209 | 204 | 189 | 177 | 151 | 148 | 143 | 118 | 108 | 95 | 63.5 | 41 | 31 | 10 | 0
|  |  | 209 | 209 | 204 | 189 | 177 | 151 | 148 | 143 | 118 | 108 | 95 | 63.5 | 41 | 31 | 10 | 0
I001 | Meeting | 5000 | 18 | 18 | 18 | 12 | 12 | 10 | 10 | 10 | 8 | 8 | 8 | 5 | 5 | 3 | 0 | 0 | 109 | All
I002 | Prepare environment | 5000 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Bela.Zhao
S001 | Prepare usecase and backlog | 5000 | 8 | 8 | 8 | 7 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 43 | Bella.Bi
S002 | Requirements analysis | 5000 | 8 | 8 | 7 | 7 | 5 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 46 | All
D001 | Update design model_local manage | 5000 | 11 | 11 | 11 | 11 | 7 | 2 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | Bela.Zhao
I003 | Implement architecture prototype_local manage | 5000 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | Bela.Zhao
SY01.UC026.US01.T01 | Research for MSI installation for .net core | 4900 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 35 | Linsee.lin
SY01.UC026.US01.T02 | Eservice Express website_installed as a Windows Service | 4900 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 27 | Linsee.lin
SY01.UC026.US01.T03 | Deployment package packed up as MSI installation file | 4900 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 0 | 0 | 7 | 0 | 0 | 68 | Linsee.lin
SY02.UC002.US01 | View empty Pricing Items list | 4800 | 7 | 7 | 7 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | Olivia.Ge
SY02.UC002.US02 | View Pricing Items list with data | 4800 | 8 | 8 | 8 | 8 | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | Olivia.Ge
SY01.UC026.US01 | Click“Eservice Express” button | 4750 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | Olivia.Ge
SY01.UC023.US02 | New job package from local | 4700 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Olivia.Ge
SY01.UC024.US01 | Update job package | 4700 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Bela.Zhao
SY01.UC023.US01 | Remove “Add Service Ticket” and “Add Service Report” buttons | 4700 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Linsee.Lin
SY04.UC002.US01 | Save “Adjusted Quantity” changes | 4600 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | Olivia.Ge
SY04.UC003.US01 | Implement lock mechanism | 4500 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 36 | Bela.zhao
SY04.UC003.US01.T01 | Add version property | 4550 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | Bela.zhao
SY04.UC003.US01.T02 | Pop up the Message box when version not same | 4550 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | Bela.zhao
SY04.UC003.US01.T03 | Update version when save data | 4550 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | Bela.zhao
SY04.UC002.US02 | Validation for “Adjusted Quantity” | 4500 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 4 | 4 | 0 | 0 | 0 | 69 | Olivia.ge
SY04.UC002.US03 | Data Sync when save data | 4500 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 43 | Olivia.ge
SY04.UC002.US03.T01 | Data Sync when edit pricelineitem | 4400 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 36 | Olivia.ge
SY01.UC025.US01 | Enable /Disabled“Eservice Express” button by service | 4000 | 7 | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | Olivia.Ge
SY01.UC025.US02 | Enable /Disabled“Eservice Express” button by sending status | 4000 | 7 | 7 | 7 | 7 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | Linsee.lin
SY01.UC025.US03 | Update “Eservice Express”button status when swich different job package | 4000 | 7 | 7 | 7 | 7 | 7 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | Linsee.lin
SY01.UC025.US04 | Enable /Disabled“Eservice Express” button by web site status | 4000 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 70 | Bela.zhao
SY02.UC002.US05 | Enable Tab key | 4000 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4.5 | 3 | 3 | 0 | 0 | 55.5 | Oliver.ye
SY02.UC002.US05.T01 | Research for Tab key | 4000 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | Oliver.ye
SY02.UC002.US03 | Open Pricing Page in Chrome browser from URL | 4000 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 70 | 0
SY02.UC002.US03.T01 | Research for check win form status in web page | 4000 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 40 | Linsee/Olivia
SY03.UC001.US01 | Update version when enter job update page | 3900 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 19 | Bela.zhao
D002 | Design model reverse engineering | 3800 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 88 | 0
E001 | Deployment eservice | 3800 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 3 | 7 | 2 | 0 | 82 | All
T001 | Test | 3800 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 0 | 128 | All
SY04.UC003.US01.T04 | Refactor for Pop Up box | 3700 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 22 | Bela.Zhao
Note on L10: Bella Bi: 设计的工作暂停，本期由Adam完成部分设计工作
Note on P32: Bella Bi: web页面已经用version进行判断，所以不需要再根据web页面的状态来判断
Note on R33: Bella Bi: Tab key目前的实现效果先这样
Note on P36: Bella Bi: 目前已经实现用version进行判断，所以不需要再根据win form中数据的状态来判断
Note on Q38: Bella Bi: 由于时间原因将此任务从本次迭代移除

## Resources
SPRINT | 1 | 本次迭代主要完成第四期任务：Express架构搭建
StartDate | 2017-05-22
EndDate | 2017-06-09
Est Time
Name | Role | Total Hours | 2017-05-22 | 2017-05-23 | 2017-05-24 | 2017-05-25 | 2017-05-26 | 2017-05-27 | 2017-05-31 | 2017-06-01 | 2017-06-02 | 2017-06-05 | 2017-06-06 | 2017-06-07 | 2017-06-08 | 2017-06-09
|  |  | 42877 | 42878 | 42879 | 42880 | 42881 | 42882 | 42886 | 42887 | 42888 | 42891 | 42892 | 42893 | 42894 | 42895
合计 |  | 279 | 272 | 251 | 237 | 220 | 199 | 176 | 154 | 132 | 110 | 88 | 66 | 44 | 22 | 0
|  | 279 | 7 | 21 | 14 | 17 | 21 | 23 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
Olivia.Ge |  | 75 | 0 | 7 | 4 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Bella.Bi |  | 30 | 0 | 2 | 2 | 2 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bela.Zhao |  | 75 | 0 | 7 | 4 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Shawn.Shao |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Oliver.Ye |  | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Linsee.Lin |  | 66 | 7 | 4 | 4 | 5 | 7 | 7 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Actual Time
Name | Role | Total Hours | 2017-05-22 | 2017-05-23 | 2017-05-24 | 2017-05-25 | 2017-05-26 | 2017-05-27 | 2017-05-31 | 2017-06-01 | 2017-06-02 | 2017-06-05 | 2017-06-06 | 2017-06-07 | 2017-06-08 | 2017-06-09
|  |  | 42877 | 42878 | 42879 | 42880 | 42881 | 42882 | 42886 | 42887 | 42888 | 42891 | 42892 | 42893 | 42894 | 42895
合计 |  | 247 | 244 | 228.5 | 215.5 | 197.5 | 178.5 | 166.5 | 147.5 | 128.5 | 103 | 84.5 | 62 | 40 | 19 | 0
|  | 80.5 | 3 | 15.5 | 13 | 18 | 19 | 12 | 19 | 19 | 25.5 | 18.5 | 22.5 | 22 | 21 | 19
Olivia.Ge |  | 75.5 |  | 5.5 | 6 | 6.5 | 6 | 2 | 5.5 | 7 | 7 | 6.5 | 7 | 5.5 | 6 | 5
Bella.Bi |  | 16 |  | 3 | 3 | 2.5 |  |  | 2 |  | 1 | 0.5 |  | 1 | 1 | 2
Bela.Zhao |  | 73 | 3 | 3.5 | 4 | 3 | 6 | 7 | 5.5 | 6 | 7 | 7 | 6.5 | 5.5 | 5 | 4
Shawn.Shao |  | 2 | 2017-06-01: 2
Oliver.Ye |  | 17.5 | 2017-05-31: 1; 2017-06-02: 3.5; 2017-06-05: 0; 2017-06-06: 5; 2017-06-07: 3; 2017-06-08: 4; 2017-06-09: 1
Linsee.Lin |  | 63 |  | 3.5 |  | 6 | 7 | 3 | 5 | 4 | 7 | 4.5 | 4 | 7 | 5 | 7

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | StartDate | EndDate | Assign To | Actual(Hour) | Remark
I001 | Meeting | 5000 | 9 | 1 |  |  | All | 14.5
I002 | Prepare environment | 5000 | 2 | 1 |  |  | Bela.Zhao | 5.5
S001 | Prepare usecase and backlog | 5000 | 8 | 1 |  |  | Bella.Bi | 9.5
S002 | Requirements analysis | 5000 | 8 | 1 |  |  | All | 4.5
D001 | Update design model_local manage | 5000 | 11 | 1 |  |  | Bela.Zhao | 21
I003 | Implement architecture prototype_local manage | 5000 | 7 | 1 |  |  | Bela.Zhao | 2
SY01.UC026.US01.T01 | Research for MSI installation for .net core | 4900 | 2 | 1 |  |  | Linsee.lin | 10
SY01.UC026.US01.T02 | Eservice Express website_installed as a Windows Service | 4900 | 3 | 1 |  |  | Linsee.lin | 8
SY01.UC026.US01.T03 | Deployment package packed up as MSI installation file | 4900 | 7 | 1 |  |  | Linsee.lin | 13.5
SY02.UC002.US01 | View empty Pricing Items list | 4800 | 7 | 1 |  |  | Olivia.Ge | 7
SY02.UC002.US02 | View Pricing Items list with data | 4800 | 8 | 1 |  |  | Olivia.Ge | 6.5
SY01.UC026.US01 | Click“Eservice Express” button | 4750 | 5 | 1 |  |  | Olivia.Ge | 2
SY01.UC023.US02 | New job package from local | 4700 | 2 | 1 |  |  | Olivia.Ge | 2
SY01.UC024.US01 | Update job package | 4700 | 5 | 1 |  |  | Bela.Zhao | 4
SY01.UC023.US01 | Remove “Add Service Ticket” and “Add Service Report” buttons | 4700 | 2 | 1 |  |  | Linsee.Lin | 2
SY04.UC002.US01 | Save “Adjusted Quantity” changes | 4600 | 8 | 1 |  |  | Olivia.Ge | 9
SY04.UC003.US01 | Implement lock mechanism | 4500 | 4 | 1 |  |  | Bela.zhao | 5
SY04.UC003.US01.T01 | Add version property | 4550 | 2 | 1 |  |  | Bela.zhao | 2
SY04.UC003.US01.T02 | Pop up the Message box when version not same | 4550 | 4 | 1 |  |  | Bela.zhao | 6
SY04.UC003.US01.T03 | Update version when save data | 4550 | 5 | 1 |  |  | Bela.zhao | 7
SY04.UC002.US02 | Validation for “Adjusted Quantity” | 4500 | 7 | 1 |  |  | Olivia.ge | 14
SY04.UC002.US03 | Data Sync when save data | 4500 | 5 | 1 |  |  | Olivia.ge | 6.5
SY04.UC002.US03.T01 | Data Sync when edit pricelineitem | 4400 | 4 | 1 |  |  | Olivia.ge | 4
SY01.UC025.US01 | Enable /Disabled“Eservice Express” button by service | 4000 | 7 | 1 |  |  | Olivia.Ge | 6
SY01.UC025.US02 | Enable /Disabled“Eservice Express” button by sending status | 4000 | 7 | 1 |  |  | Linsee.lin | 9
SY01.UC025.US03 | Update “Eservice Express”button status when swich different job package | 4000 | 7 | 1 |  |  | Linsee.lin | 9
SY01.UC025.US04 | Enable /Disabled“Eservice Express” button by web site status | 4000 | 7 | 1 |  |  | Bela.zhao | 3
SY02.UC002.US05 | Enable Tab key | 4000 | 5 | 1 |  |  | Oliver.ye | 6.5
SY02.UC002.US05.T01 | Research for Tab key | 4000 | 2 | 1 |  |  | Oliver.ye | 2
SY02.UC002.US03 | Open Pricing Page in Chrome browser from URL | 4000 | 7 | 1 |  |  |  | 0
SY02.UC002.US03.T01 | Research for check win form status in web page | 4000 | 4 | 1 |  |  | Linsee/Olivia | 1
SY03.UC001.US01 | Update version when enter job update page | 3900 | 2 | 1 |  |  | Bela.zhao | 3
D002 | Design model reverse engineering | 3800 | 8 | 0 |  |  |  | 0
E001 | Deployment eservice | 3800 | 7 | 1 |  |  | All | 25
T001 | Test | 3800 | 10 | 1 |  |  | All | 15
SY04.UC003.US01.T04 | Refactor for Pop Up box | 3700 | 2 | 1 |  |  | Bela.Zhao | 2
0
Total Backlogs | 3 | Total Estimate Hours |  | 188
Finished Backlogs | 33 | Total Hours of Finished Backlogs |  | 247
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务开始时间
Note on G1: Ying Li: 任务结束时间
Note on H1: Ying Li: 任务负责人
Note on I1: Ying Li: 任务投入总时间
Note on E28: Bella Bi: 删除此任务，通过version进行判断
Note on E31: Bella Bi: 删除此任务，通过version进行判断
Note on A39: Ying Li: 公式计算，迭代计划完成的任务数量
Note on A40: Ying Li: 根据完成状态计算，已完成的任务数量