## Daily Records
ID | Name | Prioritize | Est(Hour) | 2017-10-11 | 2017-10-12 | 2017-10-13 | 2017-10-16 | 2017-10-17 | 2017-10-18 | 2017-10-19 | 2017-10-20 | 2017-10-23 | 2017-10-24 | 2017-10-25 | 2017-10-26 | 2017-10-27 | 2017-10-30 | 2017-10-31 | 2017-11-01 | 2017-11-02 | 2017-11-03 | 2017-11-06 | 2017-11-07 | 2017-11-08 | 2017-11-09 | 2017-11-10 | 2017-11-13 | 2017-11-14 | 2017-11-15 | 2017-11-16 | 2017-11-17 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-27 | 2017-11-28 | 2017-11-29 | 2017-11-30 | 2017-12-01 | Total Hours
|  |  |  | 周日 | 43020 | 43021 | 43024 | 43025 | 43026 | 43027 | 43028 | 43031 | 43032 | 43033 | 43034 | 43035 | 43038 | 43039 | 43040 | 43041 | 43042 | 43045 | 43046 | 43047 | 43048 | 43049 | 43052 | 43053 | 43054 | 43055 | 43056 | 43059 | 43060 | 43061 | 43062 | 43063 | 43066 | 43067 | 43068 | 43069 | 43070
| Ideal Burndown |  | 1000 | 1000 | 988 | 976 | 964 | 952 | 940 | 928 | 912 | 900 | 884 | 868 | 852 | 836 | 820 | 804 | 786 | 753 | 720 | 683 | 646 | 607 | 568 | 529 | 491 | 455 | 419 | 383 | 347 | 307 | 269 | 233 | 199 | 165 | 132 | 99 | 66 | 33 | 0 | 1000
| Actual |  | 1132 | 1000 | 989 | 977 | 966 | 954 | 943 | 924 | 911 | 899 | 883.5 | 871.5 | 859.5 | 844.5 | 829 | 812.5 | 796.5 | 766.5 | 728 | 685.5 | 646 | 605 | 564 | 517 | 470 | 431 | 389.5 | 359.5 | 307.5 | 262 | 220 | 192.5 | 165.5 | 132 | 103.5 | 66 | 42 | 15 | 0
|  |  |  | 0 | 11 | 12 | 11 | 12 | 11 | 19 | 13 | 12 | 15.5 | 12 | 12 | 15 | 15.5 | 16.5 | 16 | 30 | 38.5 | 42.5 | 39.5 | 41 | 41 | 47 | 47 | 39 | 41.5 | 30 | 52 | 45.5 | 42 | 27.5 | 27 | 33.5 | 28.5 | 37.5 | 24 | 27 | 15
SY05.P003 | Meeting-Phase 6 | 2700 | 90 |  | 3 | [5 empty] | 2 |  |  |  |  | 4.5 | 4.5 | 5 | 8 | 4 | 2.5 | 3 | 5 | 3 | 6 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 3 | 3 | 7 | 5 | 2.5 | 2 | 3 |  | 102 | All
SY05.S003 | Requirements analysis | 2700 | 100 |  | 3 | 2 | 3 | 4 | 3 | 4 | 2 | 4 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 7 | 2 | 2 | 2 | 2 | 1 | 1 |  | 1 |  | 1 |  |  | 1 |  |  | 2 | 1 | 2 |  |  | 71 | Bella.bi
SY05.S004 | Task documentation | 2700 | 30 | 2017-11-06: 4; 2017-11-07: 2; 2017-11-08: 2; 2017-11-09: 1; 2017-11-10: 2; 2017-11-13: 3; 2017-11-14: 3; 2017-11-15: 2; 2017-11-17: 1.5; 2017-11-20: 1; 2017-11-21: 1; 2017-11-22: 1; 2017-11-23: 2; 2017-11-24: 1; 2017-11-27: 2; 2017-11-28: 1; 2017-11-29: 1; 2017-11-30: 1 | 31.5 | Bella.bi
SY05.P005 | Project Management | 2700 | 45 | 2017-10-24: 1; 2017-10-25: 1; 2017-10-26: 1; 2017-10-27: 1; 2017-10-30: 1; 2017-10-31: 1; 2017-11-01: 1; 2017-11-02: 2; 2017-11-03: 2; 2017-11-06: 1; 2017-11-07: 2; 2017-11-08: 2; 2017-11-09: 2; 2017-11-10: 2; 2017-11-13: 2; 2017-11-14: 1; 2017-11-15: 2; 2017-11-16: 1; 2017-11-17: 1; 2017-11-20: 1; 2017-11-22: 1; 2017-12-01: 1 | 30 | Bella.bi
SY05.D001 | Data grid control research | 2700 | 6 | 2017-10-13: 5 | 5 | Linsee.lin
SY05.I007 | Prepare the environment | 2700 | 10 | 2017-10-12: 5; 2017-10-13: 5 | 10 | Linsee.lin
SY05.I008 | Data grid control demo | 2700 | 8 | 2017-10-16: 8 | 8 | Linsee.lin
SY05.UC010.US01 | Display Rig list in Rig Board | 2600 | 16 | 2017-10-17: 7; 2017-10-18: 1; 2017-10-19: 8; 2017-11-24: 6.5 | 22.5 | Linsee.lin
SY05.S004 | Familiar with the requirements_linsee | 2600 | 6 | [38 empty] | 1 | Linsee.lin | bar: 2017-10-17
SY06.UC013.US01 | Rig service/dao/testdata/database | 2600 | 13 | 2017-10-18: 7; 2017-11-07: 3.5; 2017-11-09: 3 | 13.5 | Linsee.Lin&Bright.Liu
SY05.UC010.US01.T01 | Design for MergeStyledCell | 2600 | 10 | 2017-10-19: 7; 2017-10-20: 3 | 10 | Linsee.lin
SY05.UC012.US01.T01 | Display menu by Right click research | 2600 | 6 | 2017-10-20: 6 | 6 | Linsee.lin
SY05.UC010.US02 | Display call sheet in proper status color | 2600 | 8 | 2017-10-23: 4; 2017-10-24: 4.5; 2017-10-26: 4 | 12.5 | Linsee.lin
SY05.UC010.US02.T01 | Display data in proper status color | 2600 | 20 | 2017-10-25: 6; 2017-10-27: 4; 2017-10-30: 3; 2017-11-01: 2 | 15 | Linsee.lin
SY05.UC010.US01.T02 | Modify the style of rig board | 2600 | 10 | 2017-10-24: 3.5; 2017-10-30: 4; 2017-10-31: 2.5 | 10 | Linsee.lin
SY05.UC010.US01.T03 | Display data from call sheet | 2600 | 8 | 2017-10-25: 2; 2017-10-31: 4.5; 2017-11-01: 1.5 | 8 | Linsee.lin
SY05.UC012.US01.T02 | Display menu by Right click design | 2600 | 8 | 2017-10-23: 4; 2017-10-26: 4; 2017-10-27: 2.5 | 10.5 | Linsee.lin
SY05.UI002.RigBoard | UI Design for RigBoard | 2500 | 8 | 2017-10-24: 4.5; 2017-10-31: 1.5; 2017-11-02: 3; 2017-11-03: 1 | 10 | Niki.Wang
SY05.UC027.US01 | Display hover over content for cell of rig board | 2400 | 8 | 2017-11-01: 1.5; 2017-11-10: 1; 2017-11-14: 0.5; 2017-11-15: 3.5 | 6.5 | Linsee.lin
SY06.UC022.US01.T01 | Define interface in RigJobMicroservice | 2300 | 12 | 2017-11-02: 1; 2017-11-10: 5.5; 2017-11-13: 0.5 | 7 | Olivia.ge
SY01.UC027.US02 | Modify Company Information_Add short name | 2300 | 3 | 2017-11-02: 2.5 | 2.5 | Oliver.ye
SY05.UC010.US01.T04 | Architecture design | 2300 | 20 | 2017-11-02: 10; 2017-11-03: 7; 2017-11-10: 5 | 22 | Olivia.ge
SY05.I007 | Prepare the environment-Bright | 2300 | 5 | 2017-11-02: 4.5 | 4.5 | Bright.Liu
SY05.I008 | Data Preparation | 2300 | 4 | 2017-11-03: 2; 2017-11-08: 0.5; 2017-11-15: 0.5; 2017-11-21: 1; 2017-11-28: 0.5; 2017-11-30: 4 | 8.5 | Oliver.ye
SY05.I009 | Fefactor code | 2300 | 20 | 2017-11-06: 10; 2017-11-08: 2; 2017-11-09: 5 | 17 | Olivia.ge
SY01.UC027.US01 | Modify Company Information in Call Sheet | 2250 | 9 | 2017-11-03: 2; 2017-11-06: 6; 2017-11-07: 0.5; 2017-11-28: 0.5 | 9 | Oliver.ye
SY01.UC029.US01 | Add Bin requirements | 2250 | 7 | 2017-11-03: 2; 2017-11-07: 3; 2017-11-21: 2; 2017-11-29: 2.5; 2017-11-30: 1 | 10.5 | Linsee.lin | 它们的作用域都是Call Sheet。在其他实体中不适用
SY01.UC029.US02 | Call sheet validation for bin needed | 2250 | 6 | 2017-11-13: 5; 2017-11-14: 2.5 | 7.5 | Linsee.lin
SY01.UC030.US01 | Flag a haul needed | 2200 | 7 | 2017-11-03: 3; 2017-11-06: 1; 2017-11-21: 3 | 7 | Linsee.lin | 它们的作用域都是Call Sheet。在其他实体中不适用
SY01.UC028.US02 | Create New Rig | 2200 | 16 | 2017-11-06: 4; 2017-11-07: 4; 2017-11-08: 5; 2017-11-24: 1 | 14 | Bright.Liu
SY05.UC033.US01 | Modify COD Cleared status | 2200 | 8 | 2017-11-03: 3.5; 2017-11-08: 3; 2017-11-10: 1 | 7.5 | Olivia.ge
SY05.UC037.US01.T01 | Rig job testdata | 2200 | 6 | 2017-11-07: 5 | 5 | Olivia.ge
SY05.UC020.US01 | Update Well Location | 2100 | 12 | 2017-11-06: 3.5; 2017-11-07: 1; 2017-11-08: 3; 2017-11-17: 1; 2017-11-22: 0.5 | 9 | Linsee.lin | 未保存成功
SY05.UC020.US03 | Validation when update Well Location | 2100 | 12 | 2017-11-09: 2; 2017-11-10: 3.5; 2017-11-13: 2.5 | 8 | Linsee.lin
SY05.UC020.US02.T01 | Update Directions_Pop up window&Save | 2100 | 7 | 2017-11-06: 7 | 7 | Linsee.lin
SY05.UC020.US02.T02 | Update Directions_UI Frontend | 2100 | 5 | 2017-11-08: 2 | 2 | Carl.Chai
SY05.UC020.US02.T03 | Update Directions | 2100 | 8 | 2017-11-07: 2; 2017-11-08: 4; 2017-11-09: 1 | 7 | Olivia.ge
SY05.UC029.US01 | Schedule Product Haul | 2100 | 12 | 2017-11-07: 3; 2017-11-08: 3.5; 2017-11-09: 1; 2017-11-20: 3; 2017-11-21: 2.5; 2017-11-28: 1 | 14 | Linsee.lin | 验证未完成
SY05.UC029.US03 | Schedule Product Haul_when right click BL3 | 2100 | 8 | 2017-11-14: 4.5; 2017-11-21: 3 | 7.5 | Linsee.lin&Olivia.ge
Test005 | System test | 2100 | 60 | 2017-11-03: 4; 2017-11-10: 4; 2017-11-16: 3; 2017-11-17: 2; 2017-11-20: 4; 2017-11-21: 4; 2017-11-22: 4; 2017-11-23: 3; 2017-11-24: 2; 2017-11-27: 1; 2017-11-28: 4; 2017-12-01: 7 | 42 | Bella.bi
SY01.UC028.US02 | Update Rig information to link up with Rig Database | 2100 | 16 | 2017-11-03: 2.5; 2017-11-06: 1; 2017-11-07: 3; 2017-11-08: 2; 2017-11-09: 7; 2017-11-10: 2.5; 2017-11-16: 3.5; 2017-11-21: 1; 2017-11-28: 1 | 23.5 | Oliver.ye
SY05.UC013.US01 | Create New Rig | 2000 | 12 | 2017-11-08: 3.5; 2017-11-09: 3; 2017-11-10: 1.5; 2017-11-15: 3; 2017-11-16: 0.5; 2017-11-17: 1.5; 2017-11-20: 2 | 15 | Bright.liu&Oliver | 未加自动联想及验证
SY05.UC014.US01 | Update rig information | 2000 | 8 | 2017-11-07: 3.5; 2017-11-08: 3.5; 2017-11-09: 2; 2017-11-20: 1 | 10 | Bright.liu | is top drive点击后未保存
SY05.UC028.US01 | Add flag a haul needed | 2000 | 8 | 2017-11-09: 1; 2017-11-10: 1; 2017-11-17: 2.5; 2017-11-21: 1 | 5.5 | Bright.liu
SY05.UC034.US01 | Change status of "Need bins" | 2000 | 8 | 2017-11-09: 4; 2017-11-17: 1.5; 2017-11-30: 0.5 | 6 | Linsee.lin
SY01.UC031.US01 | Update client consultant_Service/Dao/Database | 1950 | 8 | 2017-11-10: 4 | 4 | Bright.liu
SY01.UC031.US01.T02 | Update client consultant_Testdata | 1950 | 4 | [38 empty] | 1 | bar: 2017-11-10
SY05.UC012.US03 | Display context menu by Right click Consultant Contacts cell | 1950 | 3 | 2017-11-13: 0.5 | 0.5 | Bright.liu
SY05.UC012.US04 | Modify the style of menu | 1950 | 8 | 2017-11-09: 1; 2017-11-14: 2.5; 2017-11-15: 1.5; 2017-11-21: 3 | 8 | Olivia.ge
SY05.UC023.US01 | Update Notes | 1900 | 12 | 2017-11-14: 4.5; 2017-11-17: 1.5 | 6 | Bright.liu
SY05.UC019.US01 | Create client consultant | 1900 | 12 | 2017-11-13: 4; 2017-11-17: 1.5 | 5.5 | Bright.liu
SY05.UC024.US01 | Update client consultant | 1900 | 8 | 2017-11-13: 2; 2017-11-14: 1.5; 2017-11-15: 3; 2017-11-20: 2.5 | 9 | Bright.liu | 保存报错
SY05.UC030.US01 | Add On Location and time in ProductLoadSheet | 1900 | 4 | 2017-11-17: 3 | 3 | Linsee.lin
SY05.UC010.US07 | Display Consultant Contacts column data in Rig list | 1850 | 8 | 2017-11-15: 5; 2017-11-16: 1.5 | 6.5 | Olivia.ge
SY05.UC010.US08 | Display Bin column data in Rig list | 1850 | 8 | 2017-11-13: 4; 2017-11-14: 2 | 6 | Olivia.ge | 当一个CallSheet对应两个Consultant时，Bin列数据显示错误
SY05.UC032.US01 | Modify the rig's status | 1800 | 12 | 2017-11-10: 3 | 3 | Bright.liu
SY05.UC035.US01 | Add a bin | 1800 | 8 | 2017-11-10: 6; 2017-11-13: 1; 2017-11-20: 0.5; 2017-11-24: 5 | 12.5 | Oliver.ye
SY05.UC036.US01 | Remove a bin | 1500 | 3 | [38 empty] | 1 | Olivia.ge | bar: 2017-11-13
SY05.UC026.US01 | Remove client consultant | 1500 | 6 | 2017-11-13: 1.5; 2017-11-14: 1.5; 2017-11-17: 2 | 5 | Linsee.Lin&Bright.Liu
SY05.UC042.US02 | Display proper styles in BL column | 1500 | 8 | 2017-11-13: 2; 2017-11-14: 3 | 5 | Olivia.ge
SY01.UC031.US02 | Update client consultant in eservice | 1500 | 12 | 2017-11-13: 6; 2017-11-14: 7.5; 2017-11-15: 0.5 | 14 | Oliver.ye
| Implement pop up window UI | 1500 | 10 | 2017-11-13: 8; 2017-11-14: 2; 2017-11-16: 2; 2017-11-17: 2 | 14 | Carl.Chai
TUC.WF.FR.CREW.01 | Validate Call Sheet Readiness | 1450 | 6 | 2017-11-15: 3 | 3 | Linsee.lin
TUC.WF.FR.CALL.01 | Add a date time box and a check box_create crew time | 1450 | 4 | 2017-11-15: 4; 2017-11-21: 0.5 | 4.5 | Oliver.ye
TUC.WF.FR.CALL.02 | Update the “Call Crew At Date/Time” and “Is this call made?” | 1450 | 6 | 2017-11-15: 3; 2017-11-16: 3 | 6 | Oliver.ye | 默认时间应该为当前时间，与eservice保持一致
TUC.OL.FR.RB.01 | Reference data loaded into the cache to improve the loading speed | 1450 | 30 | 2017-11-22: 7.5; 2017-11-23: 4.5; 2017-11-24: 2.5; 2017-11-28: 8 | 22.5 | Olivia.ge&Bright.Liu
TUC.OL.BA.RB.01 | Add client consultant to a rig job | 1450 | 12 | 2017-11-15: 4; 2017-11-17: 3; 2017-11-21: 1.5; 2017-11-29: 0.5; 2017-11-30: 1 | 10 | Linsee.Lin&Bright.Liu | 只有“Alert By 1 (Consultant)”, “Alert By 2 (Consultant)”这两个，严格按这个次序操作，添加一个时，添到1里，添加第二个时，添到2里，不允许添加第三个。删掉1时，如果有2，则递补进1。
TUC.OL.FR.RB.03 | Dropdown list when add client consultant to a rig job | 1450 | 8 | 2017-11-20: 4; 2017-11-21: 4 | 8 | Carl.Chai
TUC.OL.BA.CC.02 | Delete consultant | 1450 | 2 | [38 empty] | 2 | Bright.liu | bar: 2017-11-15; 2017-11-20
TUC.OL.DAO.RJ.01 | Rig Job Service/Dao/Database | 1450 | 8 | 2017-11-16: 5; 2017-11-17: 2; 2017-11-20: 1 | 8 | Olivia.ge
TUC.WF.BA.RJ.01 | Create RigJob when Update Information of CallSheet | 1450 | 6 | 2017-11-17: 2 | 2 | Olivia.ge
TUC.OL.FR.RJ.08 | Display menu by right click Date cell | 1450 | 6 | 2017-11-17: 5; 2017-11-21: 1.5 | 6.5 | Olivia.ge
TUC.OL.CT.RJ.01 | Get the status of RigJob | 1450 | 8 | 2017-11-20: 5 | 5 | Olivia.ge
TUC.OL.FR.RJ.01 | On hold operation when right click Date cell | 1450 | 6 | 2017-11-17: 2; 2017-11-21: 1.5 | 3.5 | Linsee.Lin&Bright.Liu
TUC.OL.FR.RJ.02 | Confirm operation when right click Date cell | 1450 | 6 | 2017-11-17: 3; 2017-11-20: 5 | 8 | Oliver.ye
TUC.OL.FR.RJ.03 | Reschedule operation when right click Date cell | 1450 | 6 | [38 empty] | 1 | Bright.liu | bar: 2017-11-21
TUC.OL.FR.RJ.05 | Call out operation when right click Date cell | 1450 | 6 | 2017-11-21: 2; 2017-11-29: 2; 2017-11-30: 0.5 | 4.5 | Bright.liu
TUC.OL.FR.RJ.09 | Update on location flag and time | 1450 | 5 | 2017-11-17: 1; 2017-11-21: 1; 2017-11-27: 2; 2017-11-29: 2.5 | 6.5 | Linsee.lin | On location页面需要显示LoadSheet的信息
TUC.WF.FR.CC.01 | Update the On location time for bin in eservice | 1420 | 4 | 2017-11-17: 3 | 3 | Oliver.ye
SY06.UC012.US01 | Filter in Rig Board by Service Point | 1420 | 8 | 2017-11-15: 1.5; 2017-11-16: 7.5 | 9 | Linsee.lin
TUC.OL.BA.RB.02 | Filter in Rig Board by Service Point service | 1420 | 6 | 2017-11-20: 9 | 9 | Linsee.lin&Olivia.ge
TUC.OL.FR.RB.02 | Display the secondary menu | 1420 | 6 | 2017-11-17: 4 | 4 | Carl.Chai
SY01.UC027.US03 | Validation for making call sheet ready | 1400 | 24 | 2017-11-22: 6; 2017-11-23: 4; 2017-11-24: 3 | 13 | Olivia.ge
SY06.UC012.US03 | Filter in Rig Board by JobStatus | 1400 | 12 | 2017-11-21: 4; 2017-11-22: 3.5 | 7.5 | Linsee.lin
SY05.UC029.US02 | Assign Driver and Bulker | 1000 | 6 | 2017-11-28: 3 | 3 | Bright.liu
| Fix bugs | 1000 | 6 | 2017-11-20: 2.5; 2017-11-21: 0.5; 2017-11-23: 1; 2017-11-28: 4; 2017-11-29: 1; 2017-11-30: 2; 2017-12-01: 7 | 18
| Research Version control in Online | 1000 |  | 2017-11-23: 3.5 | 3.5 | Linsee.lin
| Refactor WebContext | 1000 | 12 | 2017-11-23: 6; 2017-11-24: 3; 2017-11-29: 2 | 11 | Olivia.ge&Bright.Liu
| Refactor MicroService | 1000 | 12 | 2017-11-27: 6; 2017-11-28: 5 | 11 | Olivia.ge&Bright.Liu&Linsee.Lin
TUC.OL.BA.RJ.02 | Create RigJob when Update the status of Rig | 1000 | 4 | [38 empty] | 1 | Bright.liu | bar: 2017-10-11 to 2017-12-01
TUC.OL.FR.RB.03 | Order by Column Name in RigBoard | 1000 | 6 | 2017-11-24: 2.5 | 2.5 | Bright.liu
TUC.OL.FR.RB.03 | Display JOB cell style in Rig Board | 900 | 5 | 2017-11-27: 3.5 | 3.5 | Linsee.lin
TUC.OL.FR.RJ.10 | Change rigjob from in progress to Completed | 900 | 2 | [38 empty] | 0 | Bright.liu
TUC.OL.FR.RJ.11 | Display proper color by consultant worktype in rigboard | 900 | 6 | 2017-11-27: 5 | 5 | Bright.liu
TUC.OL.FR.CC.01 | Update the work type of consultant by context menu | 900 | 2 | 2017-11-27: 2 | 2 | Bright.liu
TUC.OL.DAO.PH.01 | Add a product haul_dao | 900 | 5 | 2017-11-28: 2; 2017-11-29: 2.5 | 4.5 | Bright.liu
TUC.OL.FR.PH.03 | Choose a bin in product haul page | 900 | 5 | 2017-11-28: 3; 2017-11-30: 1 | 4 | Oliver.ye
TUC.OL.FR.PH.06 | Don't need a haul operation | 900 | 6 | 2017-11-29: 5 | 5 | Olivia.ge
TUC.OL.FR.PH.04 | Cancel a product haul | 900 | 7 | 2017-11-29: 1; 2017-11-30: 2.5 | 3.5 | Linsee.lin
| Refactor Rig Job | 900 | 20 | 2017-11-30: 10.5 | 10.5 | Olivia.ge
Note on T6: Bella Bi:讨论设计
Note on Z6: Bella Bi: 早会 实现模式讲解
Note on AL6: Bella Bi: 开早会 讲解需求 估时间
Note on AO6: Bella Bi: 跟Adam开会讨论重构
Note on V7: Bella Bi: Olivia 5h熟悉需求 Bella 2h讲解需求及问题整理
Note on G11: Bella Bi: 由于环境位置一直配置不成功，加班解决
Note on B12: Bella Bi: 按照要求先做Demo实现Data Grid的样式。
Note on K13: Bella Bi: 修改单元格样式的设计及实现
Note on AK13: Bella Bi: 显示Notes内容自动换行 2h jobtype 短名字展示 2 rig短名字展示 2.5
Note on L16: Bella Bi: 研究合并单元格
Note on L17: Bella Bi: Olivia协助Linsee 2h Linsee 4h
Note on B19: Bella Bi: 1109 BIN列确认状态的获取：当它的值是最小值时表示not on location，如果不是最小值则认为它是on location状态。
Note on T21: Bella Bi: 重构Microservice
Note on B24: Bella Bi: Hover over content显示格式应类似于表格
Note on U27: Bella Bi: Linsee 6h Bela 3h Olivia 1h
Note on V27: Bella Bi: Olivia 重构目前的架构设计
Note on AA27: Bella Bi: 切换真Dao
Note on AD29: Bella Bi: 整理sql script
Note on AO29: Bella Bi: Bright 重构Rig Job，修改数据库表结构及数据清理
Note on AM31: Bella Bi: 修改bug
Note on AH32: Bella Bi: Olivia 作用域修改
Note on AN32: Bella Bi: 修改bug，当need bin选中状态时才可以修改number
Note on AO32: Bella Bi: 修改bug：选择框被选中之后才可以修改number
Note on AH34: Bella Bi: Oliver 作用域修改
Note on D35: Bella Bi: 11.6 实体变动，修改底层
Note on Y36: Bella Bi: Olivia 修改模式
Note on AA36: Bella Bi: Linsee
Note on AI38: Bella Bi: 修改bug
Note on AG43: Bella Bi: 验证
Note on AH43: Bella Bi: 加验证
Note on AM43: Bella Bi: 1128 新增Expected on location字段
Note on AH44: Bella Bi: 改为二级菜单显示，未选中Need haul的Blend不显示在菜单中
Note on AI45: Bella Bi: Olivia 1h
Note on AL45: Bella Bi: Olivia
Note on AE46: Bella Bi: Rig保存时的非空验证
Note on AH46: Bella Bi: 控件的设置方式修改
Note on AM46: Bella Bi: 修改Bug
Note on AD47: Bella Bi: Carl 自动联想
Note on AE47: Bella Bi: Oliver 修改页面
Note on AF47: Bella Bi: Oliver 加验证
Note on AG47: Bella Bi: 加自动联想
Note on AG48: Bella Bi: 修改bug
Note on AF49: Bella Bi: Olivia 改为二级菜单显示
Note on AH49: Bella Bi: Olivia 菜单上显示出Base blend的值
Note on AF50: Bella Bi: 前台
Note on AO50: Bella Bi: Bright 修改bug，不显示时间
Note on AD54: Bella Bi: 修改菜单项的显示样式，如果数据为空则某些菜单项置为不可用
Note on AH54: Bella Bi: BL列右击菜单显示Base blend name
Note on AF55: Bella Bi: 保存到Rig Job中
Note on AF56: Bella Bi: Oliver 加验证
Note on AG57: Bella Bi: 修改保存报错问题
Note on AG62: Bella Bi: 加日历控件
Note on AK62: Bella Bi: 添加不成功，修复 bug
Note on AF64: Bella Bi: Linsee 按照需求修改
Note on AF67: Bella Bi: Carl
Note on AF72: Bella Bi: Linsee 修改需求
Note on AH72: Bella Bi: Bright 1h 下拉框选择的内容可修改 Olivia 0.5h 修复bug：点击菜单后无反应
Note on AN72: Bella Bi: Bright修改bug，按照字母排序
Note on AO72: Bella Bi: Bright Consultant列表中显示所有的Consultant
Note on AG75: Bella Bi: Bright
Note on AH77: Bella Bi: Bright 根据需求修改菜单
Note on AH79: Bella Bi: Bright 1.5
Note on AN82: Bella Bi: 修改Bug，下拉框中的值应该显示employee
Note on AO82: Bella Bi: Bright 下拉框加字母排序
Note on AH83: Bella Bi: Linsee 页面上添加LoadSheet的信息
Note on AN83: Bella Bi: 修改时间为当前时间
Note on AG86: Bella Bi: Linsee 7.5 Olivia 1.5
Note on AF87: Bella Bi: Carl 显示二级菜单样式
Note on AG91: Bella Bi: 1.5 Oliver 1 Olivia
Note on AH91: Bella Bi: 修改页面上筛选条件中的状态标识 Bright
Note on AM91: Bella Bi: Oliver 1h改24hour clock Linsee 3h改页面样式
Note on AN91: Bella Bi: ProductHaul右键菜单修改 1h Bright
Note on AO91: Bella Bi Bright
Note on AJ93: Bella Bi: Olivia 3h Bright 3h
Note on AM94: Bella Bi: Linsee 3h Bright 2h
Note on AK96: Bella Bi: 暂停此功能
Note on AN101: Bella Bi: 修改BinSectionId to Bin Id
Note on B102: Bella Bi:
Note on AO102: Bella Bi: Bright BinSection改为Bin

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2017-10-11 | 2017-10-12 | 2017-10-13 | 2017-10-16 | 2017-10-17 | 2017-10-18 | 2017-10-19 | 2017-10-20 | 2017-10-23 | 2017-10-24 | 2017-10-25 | 2017-10-26 | 2017-10-27 | 2017-10-30 | 2017-10-31 | 2017-11-01 | 2017-11-02 | 2017-11-03 | 2017-11-06 | 2017-11-07 | 2017-11-08 | 2017-11-09 | 2017-11-10 | 2017-11-13 | 2017-11-14 | 2017-11-15 | 2017-11-16 | 2017-11-17 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-27 | 2017-11-28 | 2017-11-29 | 2017-11-30
|  |  |  | 43019 | 43020 | 43021 | 43024 | 43025 | 43026 | 43027 | 43028 | 43031 | 43032 | 43033 | 43034 | 43035 | 43038 | 43039 | 43040 | 43041 | 43042 | 43045 | 43046 | 43047 | 43048 | 43049 | 43052 | 43053 | 43054 | 43055 | 43056 | 43059 | 43060 | 43061 | 43062 | 43063 | 43066 | 43067 | 43068 | 43069
| Ideal Burndown |  |  | 1000 | 988 | 976 | 964 | 952 | 940 | 928 | 912 | 900 | 884 | 868 | 852 | 836 | 820 | 804 | 786 | 753 | 720 | 683 | 646 | 607 | 568 | 529 | 491 | 455 | 419 | 383 | 347 | 307 | 269 | 233 | 199 | 165 | 132 | 99 | 66 | 33
| Actual burndown |  | 1132 | 989 | 978 | 967 | 952 | 939 | 928 | 910 | 896 | 888 | 872 | 857 | 845 | 830 | 815 | 800 | 778 | 733 | 711 | 670 | 610 | 572 | 536 | 461 | 404 | 359 | 332 | 347 | 323 | 279 | 205 | 174 | 108 | 99 | 83 | 56 | 37 | 23
|  |  | 1016 | 989 | 978 | 967 | 952 | 939 | 928 | 910 | 896 | 888 | 872 | 857 | 845 | 830 | 815 | 800 | 778 | 733 | 711 | 670 | 610 | 572 | 536 | 461 | 404 | 359 | 332 | 347 | 323 | 279 | 205 | 174 | 108 | 99 | 83 | 56 | 37 | 23
SY05.P003 | Meeting-Phase 6 | 2700 | 90 | 90 | 87 | 87 | 87 | 87 | 87 | 87 | 85 | 85 | 85 | 85 | 85 | 80 | 75 | 70 | 65 | 60 | 67 | 64 | 60 | 57 | 51 | 48 | 45 | 42 | 39 | 36 | 31 | 28 | 25 | 25 | 15 | 10 | 10 | 8 | 2 | 1
SY05.S003 | Requirements analysis | 2700 | 100 | 100 | 97 | 92 | 90 | 87 | 84 | 81 | 78 | 75 | 70 | 67 | 64 | 61 | 57 | 54 | 50 | 46 | 43 | 40 | 37 | 35 | 33 | 31 | 29 | 28 | 26 | 26 | 24 | 20 | 18 | 15 | 10 | 5 | 6 | 5 | 1 | 1
SY05.S004 | Task documentation | 2700 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 25 | 23 | 20 | 19 | 18 | 16 | 14 | 14 | 14 | 14 | 14 | 13 | 12 | 7 | 5 | 5 | 4 | 1 | 1
SY05.P005 | Project Management | 2700 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 43 | 40 | 38 | 36 | 34 | 32 | 30 | 29 | 28 | 27 | 25 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 13 | 12 | 8 | 7 | 5 | 5 | 4 | 0 | 0
SY05.D001 | Data grid control research | 2700 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.I007 | Prepare the environment | 2700 | 10 | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.I008 | Data grid control demo | 2700 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC010.US01 | Display Rig list in Rig Board | 2600 | 16 | 16 | 16 | 16 | 16 | 9 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
SY05.S004 | Familiar with the requirements_linsee | 2600 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY06.UC013.US01 | Rig service/dao/testdata/database | 2600 | 13 | 13 | 13 | 13 | 13 | 13 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC010.US01.T01 | Design for MergeStyledCell | 2600 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC012.US01.T01 | Display menu by Right click research | 2600 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC010.US02 | Display call sheet in proper status color | 2600 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC010.US02.T01 | Display data in proper status color | 2600 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 14 | 14 | 10 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC010.US01.T02 | Modify the style of rig board | 2600 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC010.US01.T03 | Display data from call sheet | 2600 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC012.US01.T02 | Display menu by Right click design | 2600 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 7 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UI002.RigBoard | UI Design for RigBoard | 2500 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC027.US01 | Display hover over content for cell of rig board | 2400 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
SY06.UC022.US01.T01 | Define interface in RigJobMicroservice | 2300 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY01.UC027.US02 | Modify Company Information_Add short name | 2300 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC010.US01.T04 | Architecture design | 2300 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.I007 | Prepare the environment-Bright | 2300 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.I008 | Data Preparation | 2300 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 4 | 4
SY05.I009 | Fefactor code | 2300 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 2 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY01.UC027.US01 | Modify Company Information in Call Sheet | 2250 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY01.UC029.US01 | Add Bin requirements | 2250 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SY01.UC029.US02 | Call sheet validation for bin needed | 2250 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY01.UC030.US01 | Flag a haul needed | 2200 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SY01.UC028.US02 | Create New Rig | 2200 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 12 | 9 | 7 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
SY05.UC033.US01 | Modify COD Cleared status | 2200 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 5 | 5 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC037.US01.T01 | Rig job testdata | 2200 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC020.US01 | Update Well Location | 2100 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC020.US03 | Validation when update Well Location | 2100 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC020.US02.T01 | Update Directions_Pop up window&Save | 2100 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC020.US02.T02 | Update Directions_UI Frontend | 2100 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC020.US02.T03 | Update Directions | 2100 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC029.US01 | Schedule Product Haul | 2100 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 4 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0
SY05.UC029.US03 | Schedule Product Haul_when right click BL3 | 2100 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 1 | 1 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test005 | System test | 2100 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 55 | 55 | 55 | 55 | 55 | 50 | 50 | 50 | 50 | 45 | 45 | 36 | 33 | 25 | 14 | 12 | 10 | 10 | 2 | 8
SY01.UC028.US02 | Update Rig information to link up with Rig Database | 2100 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC013.US01 | Create New Rig | 2000 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC014.US01 | Update rig information | 2000 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC028.US01 | Add flag a haul needed | 2000 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 6 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC034.US01 | Change status of "Need bins" | 2000 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 5 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0
SY01.UC031.US01 | Update client consultant_Service/Dao/Database | 1950 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY01.UC031.US01.T02 | Update client consultant_Testdata | 1950 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC012.US03 | Display context menu by Right click Consultant Contacts cell | 1950 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC012.US04 | Modify the style of menu | 1950 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC023.US01 | Update Notes | 1900 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC019.US01 | Create client consultant | 1900 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
SY05.UC024.US01 | Update client consultant | 1900 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC030.US01 | Add On Location and time in ProductLoadSheet | 1900 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC010.US07 | Display Consultant Contacts column data in Rig list | 1850 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC010.US08 | Display Bin column data in Rig list | 1850 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
SY05.UC032.US01 | Modify the rig's status | 1800 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC035.US01 | Add a bin | 1800 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 1 | 0
SY05.UC036.US01 | Remove a bin | 1500 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC026.US01 | Remove client consultant | 1500 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SY05.UC042.US02 | Display proper styles in BL column | 1500 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SY01.UC031.US02 | Update client consultant in eservice | 1500 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
0 | Implement pop up window UI | 1500 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 3 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.WF.FR.CREW.01 | Validate Call Sheet Readiness | 1450 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.WF.FR.CALL.01 | Add a date time box and a check box_create crew time | 1450 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.WF.FR.CALL.02 | Update the “Call Crew At Date/Time” and “Is this call made?” | 1450 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.RB.01 | Reference data loaded into the cache to improve the loading speed | 1450 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 16 | 8 | 4 | 4 | 0 | 0 | 0
TUC.OL.BA.RB.01 | Add client consultant to a rig job | 1450 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
TUC.OL.FR.RB.03 | Dropdown list when add client consultant to a rig job | 1450 | 8 | 2017-11-17: 8; 2017-11-20: 4; 2017-11-21: 0; 2017-11-22: 0; 2017-11-23: 0; 2017-11-24: 0; 2017-11-27: 0; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0
TUC.OL.BA.CC.02 | Delete consultant | 1450 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.DAO.RJ.01 | Rig Job Service/Dao/Database | 1450 | 8 | 2017-11-13: 8; 2017-11-14: 8; 2017-11-15: 8; 2017-11-16: 8; 2017-11-17: 8; 2017-11-20: 8; 2017-11-21: 8; 2017-11-22: 8; 2017-11-23: 0; 2017-11-24: 0; 2017-11-27: 0; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0
TUC.WF.BA.RJ.01 | Create RigJob when Update Information of CallSheet | 1450 | 6 | 2017-11-15: 6; 2017-11-16: 6; 2017-11-17: 6; 2017-11-20: 6; 2017-11-21: 0; 2017-11-22: 0; 2017-11-23: 0; 2017-11-24: 0; 2017-11-27: 0; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0
TUC.OL.FR.RJ.08 | Display menu by right click Date cell | 1450 | 6 | 2017-11-17: 6; 2017-11-20: 2; 2017-11-21: 0; 2017-11-22: 0; 2017-11-23: 0; 2017-11-24: 0; 2017-11-27: 0; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0
TUC.OL.CT.RJ.01 | Get the status of RigJob | 1450 | 8 | 2017-11-20: 2; 2017-11-21: 0; 2017-11-22: 0; 2017-11-23: 0; 2017-11-24: 0; 2017-11-27: 0; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0
TUC.OL.FR.RJ.01 | On hold operation when right click Date cell | 1450 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.RJ.02 | Confirm operation when right click Date cell | 1450 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.RJ.03 | Reschedule operation when right click Date cell | 1450 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.RJ.05 | Call out operation when right click Date cell | 1450 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 2 | 0 | 0 | 0 | 2 | 1 | 0
TUC.OL.FR.RJ.09 | Update on location flag and time | 1450 | 5 | 2017-11-14: 5; 2017-11-15: 5; 2017-11-16: 5; 2017-11-17: 1; 2017-11-20: 1; 2017-11-21: 0; 2017-11-22: 0; 2017-11-23: 0; 2017-11-24: 0; 2017-11-27: 0; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0
TUC.WF.FR.CC.01 | Update the On location time for bin in eservice | 1420 | 4 | 2017-11-15: 4; 2017-11-16: 4; 2017-11-17: 1; 2017-11-20: 1; 2017-11-21: 1; 2017-11-22: 0; 2017-11-23: 0; 2017-11-24: 0; 2017-11-27: 0; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0
SY06.UC012.US01 | Filter in Rig Board by Service Point | 1420 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.RB.02 | Filter in Rig Board by Service Point service | 1420 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
TUC.OL.FR.RB.02 | Display the secondary menu | 1420 | 6 | 2017-11-16: 6; 2017-11-17: 4; 2017-11-20: 2; 2017-11-21: 0; 2017-11-22: 0; 2017-11-23: 0; 2017-11-24: 0; 2017-11-27: 0; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0
SY01.UC027.US03 | Validation for making call sheet ready | 1400 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 8 | 8 | 0 | 0 | 0 | 0 | 0
SY06.UC012.US03 | Filter in Rig Board by JobStatus | 1400 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 8 | 4 | 4 | 0 | 0 | 0 | 0
SY05.UC029.US02 | Assign Driver and Bulker | 1000 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0
0 | Fix bugs | 1000 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 6 | 8 | 1 | 0
0 | Research Version control in Online | 1000 | 0
0 | Refactor WebContext | 1000 | 12 | 2017-11-22: 16; 2017-11-23: 8; 2017-11-24: 4; 2017-11-27: 4; 2017-11-28: 4; 2017-11-29: 0; 2017-11-30: 0
0 | Refactor MicroService | 1000 | 12 | 2017-11-24: 12; 2017-11-27: 6; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0
TUC.OL.BA.RJ.02 | Create RigJob when Update the status of Rig | 1000 | 4 | 2017-11-24: 4; 2017-11-27: 4; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0
TUC.OL.FR.RB.03 | Order by Column Name in RigBoard | 1000 | 6 | 2017-11-23: 6; 2017-11-24: 2; 2017-11-27: 1; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0
TUC.OL.FR.RB.03 | Display JOB cell style in Rig Board | 900 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5 | 0 | 0 | 0 | 0
TUC.OL.FR.RJ.10 | Change rigjob from in progress to Completed | 900 | 2 | 2017-11-24: 2; 2017-11-27: 2; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0
TUC.OL.FR.RJ.11 | Display proper color by consultant worktype in rigboard | 900 | 6 | 2017-11-24: 6; 2017-11-27: 0; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0
TUC.OL.FR.CC.01 | Update the work type of consultant by context menu | 900 | 2 | 2017-11-24: 2; 2017-11-27: 0; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0
TUC.OL.DAO.PH.01 | Add a product haul_dao | 900 | 5 | 2017-11-24: 5; 2017-11-27: 5; 2017-11-28: 2; 2017-11-29: 0; 2017-11-30: 0
TUC.OL.FR.PH.03 | Choose a bin in product haul page | 900 | 5 | 2017-11-24: 5; 2017-11-27: 5; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0
TUC.OL.FR.PH.06 | Don't need a haul operation | 900 | 6 | 2017-11-28: 5; 2017-11-29: 0; 2017-11-30: 0
TUC.OL.FR.PH.04 | Cancel a product haul | 900 | 7 | 2017-11-29: 3; 2017-11-30: 0
0 | Refactor Rig Job | 900 | 20 | 2017-11-29: 20; 2017-11-30: 8
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT | 1 | 本次迭代主要完成第六期的准备工作
StartDate | 2017-10-12
EndDate | 2017-10-20
Est Time
Name | Role | Total Hours | 2017-10-12 | 2017-10-13 | 2017-10-16 | 2017-10-17 | 2017-10-18 | 2017-10-19 | 2017-10-20 | 2017-10-23 | 2017-10-24 | 2017-10-25 | 2017-10-26 | 2017-10-27 | 2017-10-30 | 2017-10-31 | 2017-11-01 | 2017-11-02 | 2017-11-03 | 2017-11-06 | 2017-11-07 | 2017-11-08 | 2017-11-09 | 2017-11-10 | 2017-11-13 | 2017-11-14 | 2017-11-15 | 2017-11-16 | 2017-11-17 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-27 | 2017-11-28 | 2017-11-29 | 2017-11-30 | 2017-12-01
|  |  | 43020 | 43021 | 43024 | 43025 | 43026 | 43027 | 43028 | 43031 | 43032 | 43033 | 43034 | 43035 | 43038 | 43039 | 43040 | 43041 | 43042 | 43045 | 43046 | 43047 | 43048 | 43049 | 43052 | 43053 | 43054 | 43055 | 43056 | 43059 | 43060 | 43061 | 43062 | 43063 | 43066 | 43067 | 43068 | 43069 | 43070
Ideal Burndown |  | 1000 | 988 | 976 | 964 | 952 | 940 | 928 | 912 | 900 | 884 | 868 | 852 | 836 | 820 | 804 | 786 | 753 | 720 | 683 | 646 | 607 | 568 | 529 | 491 | 455 | 419 | 383 | 347 | 307 | 269 | 233 | 199 | 165 | 132 | 99 | 66 | 33 | 0
Hours consumed |  | 164 | 12 | 12 | 12 | 12 | 12 | 12 | 16 | 12 | 16 | 16 | 16 | 16 | 16 | 16 | 18 | 33 | 33 | 37 | 37 | 39 | 39 | 39 | 38 | 36 | 36 | 36 | 36 | 40 | 38 | 36 | 34 | 34 | 33 | 33 | 33 | 33 | 33
Bella.Bi |  | 186 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Linsee.Lin |  | 296 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Olivia.Ge |  | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 7 | 5 | 5 | 4 | 4 | 4 | 4 | 4
Oliver.Ye |  | 152 | 2017-11-02: 6; 2017-11-03: 6; 2017-11-06: 7; 2017-11-07: 7; 2017-11-08: 7; 2017-11-09: 7; 2017-11-10: 7; 2017-11-13: 7; 2017-11-14: 7; 2017-11-15: 7; 2017-11-16: 7; 2017-11-17: 7; 2017-11-20: 7; 2017-11-21: 7; 2017-11-22: 7; 2017-11-23: 7; 2017-11-24: 7; 2017-11-27: 7; 2017-11-28: 7; 2017-11-29: 7; 2017-11-30: 7; 2017-12-01: 7
Bright.Liu |  | 170 | 2017-11-02: 5; 2017-11-03: 5; 2017-11-06: 8; 2017-11-07: 8; 2017-11-08: 8; 2017-11-09: 8; 2017-11-10: 8; 2017-11-13: 8; 2017-11-14: 8; 2017-11-15: 8; 2017-11-16: 8; 2017-11-17: 8; 2017-11-20: 8; 2017-11-21: 8; 2017-11-22: 8; 2017-11-23: 8; 2017-11-24: 8; 2017-11-27: 8; 2017-11-28: 8; 2017-11-29: 8; 2017-11-30: 8; 2017-12-01: 8
Bela.Zhao |  | 32 | 2017-11-08: 2; 2017-11-09: 2; 2017-11-10: 2; 2017-11-13: 4; 2017-11-14: 4; 2017-11-15: 4; 2017-11-16: 4; 2017-11-17: 4; 2017-11-20: 4; 2017-11-21: 2; 2017-11-22: 0; 2017-11-23: 0; 2017-11-24: 0; 2017-11-27: 0; 2017-11-28: 0; 2017-11-29: 0; 2017-11-30: 0; 2017-12-01: 0
0
Actual Time
Name | Role | Total Hours | 2017-10-12 | 2017-10-13 | 2017-10-16 | 2017-10-17 | 2017-10-18 | 2017-10-19 | 2017-10-20 | 2017-10-23 | 2017-10-24 | 2017-10-25 | 2017-10-26 | 2017-10-27 | 2017-10-30 | 2017-10-31 | 2017-11-01 | 2017-11-02 | 2017-11-03 | 2017-11-06 | 2017-11-07 | 2017-11-08 | 2017-11-09 | 2017-11-10 | 2017-11-13 | 2017-11-14 | 2017-11-15 | 2017-11-16 | 2017-11-17 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-27 | 2017-11-28 | 2017-11-29 | 2017-11-30 | 2017-12-01
|  |  | 43020 | 43021 | 43024 | 43025 | 43026 | 43027 | 43028 | 43031 | 43032 | 43033 | 43034 | 43035 | 43038 | 43039 | 43040 | 43041 | 43042 | 43045 | 43046 | 43047 | 43048 | 43049 | 43052 | 43053 | 43054 | 43055 | 43056 | 43059 | 43060 | 43061 | 43062 | 43063 | 43066 | 43067 | 43068 | 43069 | 43070
Ideal Burndown |  | 89 | 78 | 66 | 55 | 43 | 32 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours consumed |  | 89 | 11 | 12 | 11 | 12 | 11 | 19 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bella.Bi |  | 23.5 | 2017-10-12: 4.5; 2017-10-13: 2; 2017-10-16: 3; 2017-10-17: 4; 2017-10-18: 3; 2017-10-19: 4; 2017-10-20: 3
Linsee.Lin |  | 54.5 | 2017-10-12: 6.5; 2017-10-13: 8; 2017-10-16: 8; 2017-10-17: 8; 2017-10-18: 8; 2017-10-19: 8; 2017-10-20: 8
Olivia.Ge |  | 11 | 2017-10-13: 2; 2017-10-19: 7; 2017-10-20: 2
0
0
0
0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | StartDate | EndDate | Assign To | Actual(Hour)
SY05.P003 | Meeting-Phase 6 | 2700 | 90 | 1 |  |  | All | 102
SY05.S003 | Requirements analysis | 2700 | 100 | 1 |  |  | Bella.bi | 71
SY05.S004 | Task documentation | 2700 | 30 | 1 |  |  | Bella.bi | 31.5
SY05.P005 | Project Management | 2700 | 45 | 1 |  |  | Bella.bi | 30
SY05.D001 | Data grid control research | 2700 | 6 | 1 |  |  | Linsee.lin | 5
SY05.I007 | Prepare the environment | 2700 | 10 | 1 |  |  | Linsee.lin | 10
SY05.I008 | Data grid control demo | 2700 | 8 | 1 |  |  | Linsee.lin | 8
SY05.UC010.US01 | Display Rig list in Rig Board | 2600 | 16 | 1 |  |  | Linsee.lin | 22.5
SY05.S004 | Familiar with the requirements_linsee | 2600 | 6 | 1 |  |  | Linsee.lin | 1
SY06.UC013.US01 | Rig service/dao/testdata/database | 2600 | 13 | 1 |  |  | Linsee.Lin&Bright.Liu | 13.5
SY05.UC010.US01.T01 | Design for MergeStyledCell | 2600 | 10 | 1 |  |  | Linsee.lin | 10
SY05.UC012.US01.T01 | Display menu by Right click research | 2600 | 6 | 1 |  |  | Linsee.lin | 6
SY05.UC010.US02 | Display call sheet in proper status color | 2600 | 8 | 1 |  |  | Linsee.lin | 12.5
SY05.UC010.US02.T01 | Display data in proper status color | 2600 | 20 | 1 |  |  | Linsee.lin | 15
SY05.UC010.US01.T02 | Modify the style of rig board | 2600 | 10 | 1 |  |  | Linsee.lin | 10
SY05.UC010.US01.T03 | Display data from call sheet | 2600 | 8 | 1 |  |  | Linsee.lin | 8
SY05.UC012.US01.T02 | Display menu by Right click design | 2600 | 8 | 1 |  |  | Linsee.lin | 10.5
SY05.UI002.RigBoard | UI Design for RigBoard | 2500 | 8 | 1 |  |  | Niki.Wang | 10
SY05.UC027.US01 | Display hover over content for cell of rig board | 2400 | 8 | 1 |  |  | Linsee.lin | 6.5
SY06.UC022.US01.T01 | Define interface in RigJobMicroservice | 2300 | 12 | 1 |  |  | Olivia.ge | 7
SY01.UC027.US02 | Modify Company Information_Add short name | 2300 | 3 | 1 |  |  | Oliver.ye | 2.5
SY05.UC010.US01.T04 | Architecture design | 2300 | 20 | 1 |  |  | Olivia.ge | 22
SY05.I007 | Prepare the environment-Bright | 2300 | 5 | 1 |  |  | Bright.Liu | 4.5
SY05.I008 | Data Preparation | 2300 | 4 | 1 |  |  | Oliver.ye | 8.5
SY05.I009 | Fefactor code | 2300 | 20 | 1 |  |  | Olivia.ge | 17
SY01.UC027.US01 | Modify Company Information in Call Sheet | 2250 | 9 | 1 |  |  | Oliver.ye | 9
SY01.UC029.US01 | Add Bin requirements | 2250 | 7 | 1 |  |  | Linsee.lin | 10.5
SY01.UC029.US02 | Call sheet validation for bin needed | 2250 | 6 | 1 |  |  | Linsee.lin | 7.5
SY01.UC030.US01 | Flag a haul needed | 2200 | 7 | 1 |  |  | Linsee.lin | 7
SY01.UC028.US02 | Create New Rig | 2200 | 16 | 1 |  |  | Bright.Liu | 14
SY05.UC033.US01 | Modify COD Cleared status | 2200 | 8 | 1 |  |  | Olivia.ge | 7.5
SY05.UC037.US01.T01 | Rig job testdata | 2200 | 6 | 1 |  |  | Olivia.ge | 5
SY05.UC020.US01 | Update Well Location | 2100 | 12 | 1 |  |  | Linsee.lin | 9
SY05.UC020.US03 | Validation when update Well Location | 2100 | 12 | 1 |  |  | Linsee.lin | 8
SY05.UC020.US02.T01 | Update Directions_Pop up window&Save | 2100 | 7 | 1 |  |  | Linsee.lin | 7
SY05.UC020.US02.T02 | Update Directions_UI Frontend | 2100 | 5 | 1 |  |  | Carl.Chai | 2
SY05.UC020.US02.T03 | Update Directions | 2100 | 8 | 1 |  |  | Olivia.ge | 7
SY05.UC029.US01 | Schedule Product Haul | 2100 | 12 | 1 |  |  | Linsee.lin | 14
SY05.UC029.US03 | Schedule Product Haul_when right click BL3 | 2100 | 8 | 1 |  |  | Linsee.lin&Olivia.ge | 7.5
Test005 | System test | 2100 | 60 | 1 |  |  | Bella.bi | 42
SY01.UC028.US02 | Update Rig information to link up with Rig Database | 2100 | 16 | 1 |  |  | Oliver.ye | 23.5
SY05.UC013.US01 | Create New Rig | 2000 | 12 | 1 |  |  | Bright.liu&Oliver | 15
SY05.UC014.US01 | Update rig information | 2000 | 8 | 1 |  |  | Bright.liu | 10
SY05.UC028.US01 | Add flag a haul needed | 2000 | 8 | 1 |  |  | Bright.liu | 5.5
SY05.UC034.US01 | Change status of "Need bins" | 2000 | 8 | 1 |  |  | Linsee.lin | 6
SY01.UC031.US01 | Update client consultant_Service/Dao/Database | 1950 | 8 | 1 |  |  | Bright.liu | 4
SY01.UC031.US01.T02 | Update client consultant_Testdata | 1950 | 4 | 1 |  |  | 0 | 1
SY05.UC012.US03 | Display context menu by Right click Consultant Contacts cell | 1950 | 3 | 1 |  |  | Bright.liu | 0.5
SY05.UC012.US04 | Modify the style of menu | 1950 | 8 | 1 |  |  | Olivia.ge | 8
SY05.UC023.US01 | Update Notes | 1900 | 12 | 1 |  |  | Bright.liu | 6
SY05.UC019.US01 | Create client consultant | 1900 | 12 | 1 |  |  | Bright.liu | 5.5
SY05.UC024.US01 | Update client consultant | 1900 | 8 | 1 |  |  | Bright.liu | 9
SY05.UC030.US01 | Add On Location and time in ProductLoadSheet | 1900 | 4 | 1 |  |  | Linsee.lin | 3
SY05.UC010.US07 | Display Consultant Contacts column data in Rig list | 1850 | 8 | 1 |  |  | Olivia.ge | 6.5
SY05.UC010.US08 | Display Bin column data in Rig list | 1850 | 8 | 1 |  |  | Olivia.ge | 6
SY05.UC032.US01 | Modify the rig's status | 1800 | 12 | 1 |  |  | Bright.liu | 3
SY05.UC035.US01 | Add a bin | 1800 | 8 | 1 |  |  | Oliver.ye | 12.5
SY05.UC036.US01 | Remove a bin | 1500 | 3 | 1 |  |  | Olivia.ge | 1
SY05.UC026.US01 | Remove client consultant | 1500 | 6 | 1 |  |  | Linsee.Lin&Bright.Liu | 5
SY05.UC042.US02 | Display proper styles in BL column | 1500 | 8 | 1 |  |  | Olivia.ge | 5
SY01.UC031.US02 | Update client consultant in eservice | 1500 | 12 | 1 |  |  | Oliver.ye | 14
0 | Implement pop up window UI | 1500 | 10 | 1 |  |  | Carl.Chai | 14
TUC.WF.FR.CREW.01 | Validate Call Sheet Readiness | 1450 | 6 | 1 |  |  | Linsee.lin | 3
TUC.WF.FR.CALL.01 | Add a date time box and a check box_create crew time | 1450 | 4 | 1 |  |  | Oliver.ye | 4.5
TUC.WF.FR.CALL.02 | Update the “Call Crew At Date/Time” and “Is this call made?” | 1450 | 6 | 1 |  |  | Oliver.ye | 6
TUC.OL.FR.RB.01 | Reference data loaded into the cache to improve the loading speed | 1450 | 30 | 1 |  |  | Olivia.ge&Bright.Liu | 22.5
TUC.OL.BA.RB.01 | Add client consultant to a rig job | 1450 | 12 | 1 |  |  | Linsee.Lin&Bright.Liu | 10
TUC.OL.FR.RB.03 | Dropdown list when add client consultant to a rig job | 1450 | 8 | 1 |  |  | Carl.Chai | 8
TUC.OL.BA.CC.02 | Delete consultant | 1450 | 2 | 1 |  |  | Bright.liu | 2
TUC.OL.DAO.RJ.01 | Rig Job Service/Dao/Database | 1450 | 8 | 1 |  |  | Olivia.ge | 8
TUC.WF.BA.RJ.01 | Create RigJob when Update Information of CallSheet | 1450 | 6 | 1 |  |  | Olivia.ge | 2
TUC.OL.FR.RJ.08 | Display menu by right click Date cell | 1450 | 6 | 1 |  |  | Olivia.ge | 6.5
TUC.OL.CT.RJ.01 | Get the status of RigJob | 1450 | 8 | 1 |  |  | Olivia.ge | 5
TUC.OL.FR.RJ.01 | On hold operation when right click Date cell | 1450 | 6 | 1 |  |  | Linsee.Lin&Bright.Liu | 3.5
TUC.OL.FR.RJ.02 | Confirm operation when right click Date cell | 1450 | 6 | 1 |  |  | Oliver.ye | 8
TUC.OL.FR.RJ.03 | Reschedule operation when right click Date cell | 1450 | 6 | 0 |  |  | Bright.liu | 1
TUC.OL.FR.RJ.05 | Call out operation when right click Date cell | 1450 | 6 | 1 |  |  | Bright.liu | 4.5
TUC.OL.FR.RJ.09 | Update on location flag and time | 1450 | 5 | 1 |  |  | Linsee.lin | 6.5
TUC.WF.FR.CC.01 | Update the On location time for bin in eservice | 1420 | 4 | 1 |  |  | Oliver.ye | 3
SY06.UC012.US01 | Filter in Rig Board by Service Point | 1420 | 8 | 1 |  |  | Linsee.lin | 9
TUC.OL.BA.RB.02 | Filter in Rig Board by Service Point service | 1420 | 6 | 1 |  |  | Linsee.lin&Olivia.ge | 9
TUC.OL.FR.RB.02 | Display the secondary menu | 1420 | 6 | 1 |  |  | Carl.Chai | 4
SY01.UC027.US03 | Validation for making call sheet ready | 1400 | 24 | 1 |  |  | Olivia.ge | 13
SY06.UC012.US03 | Filter in Rig Board by JobStatus | 1400 | 12 | 1 |  |  | Linsee.lin | 7.5
SY05.UC029.US02 | Assign Driver and Bulker | 1000 | 6 | 1 |  |  | Bright.liu | 3
0 | Fix bugs | 1000 | 6 | 1 |  |  | 0 | 18
0 | Research Version control in Online | 1000 | 0 | 1 |  |  | Linsee.lin | 3.5
0 | Refactor WebContext | 1000 | 12 | 1 |  |  | Olivia.ge&Bright.Liu | 11
0 | Refactor MicroService | 1000 | 12 | 1 |  |  | Olivia.ge&Bright.Liu&Linsee.Lin | 11
TUC.OL.BA.RJ.02 | Create RigJob when Update the status of Rig | 1000 | 4 | 1 |  |  | Bright.liu | 1
TUC.OL.FR.RB.03 | Order by Column Name in RigBoard | 1000 | 6 | 1 |  |  | Bright.liu | 2.5
TUC.OL.FR.RB.03 | Display JOB cell style in Rig Board | 900 | 5 | 1 |  |  | Linsee.lin | 3.5
TUC.OL.FR.RJ.10 | Change rigjob from in progress to Completed | 900 | 2 | 1 |  |  | Bright.liu | 0
TUC.OL.FR.RJ.11 | Display proper color by consultant worktype in rigboard | 900 | 6 | 1 |  |  | Bright.liu | 5
TUC.OL.FR.CC.01 | Update the work type of consultant by context menu | 900 | 2 | 1 |  |  | Bright.liu | 2
TUC.OL.DAO.PH.01 | Add a product haul_dao | 900 | 5 | 1 |  |  | Bright.liu | 4.5
TUC.OL.FR.PH.03 | Choose a bin in product haul page | 900 | 5 | 1 |  |  | Oliver.ye | 4
TUC.OL.FR.PH.06 | Don't need a haul operation | 900 | 6 | 1 |  |  | Olivia.ge | 5
TUC.OL.FR.PH.04 | Cancel a product haul | 900 | 7 | 1 |  |  | Linsee.lin | 3.5
0 | Refactor Rig Job | 900 | 20 | 1 |  |  | Olivia.ge | 10.5
0 | 0 | 0 | 0 |  |  |  | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务开始时间
Note on G1: Ying Li: 任务结束时间
Note on H1: Ying Li: 任务负责人
Note on I1: Ying Li: 任务投入总时间

## Sheet1
列 | 操作
COMPANY | Cod Cleared | Bright
LSD | Update well location | Linsee
| Update direction | Linsee
DATE | Confirmation Call | Bright
| Reschedule | Bright
| On Hold | Bright
| Call Out | Bright
BL | Need a haul | Linsee
| Don't need a haul | Linsee
| Cancel a haul | Linsee
BIN | Need bins | Linsee
| Add a bin | Linsee
OSR | Add a consultant | Bright
| Remove consultant | Bright