## Daily Records
ID | Name | Prioritize | Est(Hour) | 2017-12-17 | 2017-12-18 | 2017-12-19 | 2017-12-20 | 2017-12-21 | 2017-12-22 | 2017-12-25 | 2017-12-26 | 2017-12-27 | 2017-12-28 | 2017-12-29 | Total Hours
|  |  |  | 43086 | 43087 | 43088 | 43089 | 43090 | 43091 | 43094 | 43095 | 43096 | 43097 | 43098
| Ideal Burndown |  | 130 | 130 | 117 | 104 | 91 | 78 | 65 | 52 | 39 | 26 | 13 | 0 | 84.5
| Actual |  | 113 | 130 | 120 | 108.5 | 95.5 | 80.5 | 64.5 | 51.5 | 45.5 | 45.5 | 45.5 | 45.5
|  |  |  | 0 | 10 | 11.5 | 13 | 15 | 16 | 13 | 6 | 0 | 0 | 0
Phase7.P006 | Meeting-Phase 6 | 900 | 10 |  | 1 | 1 | 1.5 | 1 | 3 | 1 | 1.5 |  |  |  | 10 | All
Phase7.S005 | Requirements analysis | 900 | 10 | [11 empty] | 0 | Bella.bi
Phase7.S006 | Task documentation | 900 | 10 | 2017-12-18: 0.5; 2017-12-19: 0.5; 2017-12-21: 0.5; 2017-12-22: 1; 2017-12-25: 0.5; 2017-12-26: 0.5 | 3.5 | Bella.bi
Phase7.Test005 | System test | 900 | 10 | [11 empty] | 0
Phase7.Bug003 | Fix bugs_Linsee | 900 | 10 | 2017-12-18: 1.5; 2017-12-19: 2; 2017-12-20: 3.5; 2017-12-25: 4 | 11 | Linsee.lin
TUC.OL.FR.PH.07 | Display product haul list in Product Hauls page | 880 | 4 | 2017-12-18: 3 | 3 | Linsee.lin
TUC.OL.FR.PH.05 | Implement Go with job | 880 | 3 | 2017-12-19: 4 | 4
TUC.OL.BA.SC.01 | Implement Security Control prototype | 880 | 16 | 2017-12-18: 4; 2017-12-19: 4; 2017-12-20: 2 | 10 | Bright.liu
Phase7.D002 | Research for Transaction logging functionality | 880 | 8 | 2017-12-20: 2; 2017-12-21: 4; 2017-12-22: 2; 2017-12-25: 4; 2017-12-26: 3 | 15 | Bright.liu
TUC.OL.BA.SC.02 | Implement Transaction logging functionality | 880 | 16 | 2017-12-22: 5; 2017-12-25: 3.5; 2017-12-26: 1 | 9.5 | Bright.liu
| Add new record in Product Hauls Page | 880 | 8 | 2017-12-20: 4; 2017-12-21: 4.5; 2017-12-22: 2 | 10.5 | Linsee.lin
| Edit new record in Product Hauls Page | 880 | 8 | 2017-12-21: 5; 2017-12-22: 3 | 8 | Linsee.lin
0
0

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2017-12-17 | 2017-12-17 | 2017-12-18 | 2017-12-19 | 2017-12-20 | 2017-12-21 | 2017-12-22 | 2017-12-25 | 2017-12-26 | 2017-12-27 | 2017-12-28 | 2017-12-29
|  |  |  | 43086 | 2017-12-17 | 43087 | 43088 | 43089 | 43090 | 43091 | 43094 | 43095 | 43096 | 43097 | 43098
| Ideal Burndown |  | 130 | 130 | 130 | 117 | 104 | 91 | 78 | 65 | 52 | 39 | 26 | 13 | 0
| Actual burndown |  | 113 | 109 | 99 | 94 | 83 | 71 | 63 | 49 | 40 | 33 | #N/A | #N/A | #N/A
|  |  | 113 | 109 |  | 94 | 83 | 71 | 63 | 49 | 40 | 33 | 34 | 34 | 34
Phase7.P006 | Meeting-Phase 6 | 900 | 10 | 10 | 9 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 4 | 4 | 4
Phase7.S005 | Requirements analysis | 900 | 10 | 10 | 9 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 3 | 3 | 3
Phase7.S006 | Task documentation | 900 | 10 | 10 | 9 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 3 | 3 | 3
Phase7.Test005 | System test | 900 | 10 | 10 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
Phase7.Bug003 | Fix bugs_Linsee | 900 | 10 | 10 | 10 | 9 | 7 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 4
TUC.OL.FR.PH.07 | Display product haul list in Product Hauls page | 880 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TUC.OL.FR.PH.05 | Implement Go with job | 880 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.SC.01 | Implement Security Control prototype | 880 | 16 | 12 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
Phase7.D002 | Research for Transaction logging functionality | 880 | 8 | 8 | 8 | 8 | 8 | 6 | 5 | 4 | 2 | 0 | 0 | 0 | 0
TUC.OL.BA.SC.02 | Implement Transaction logging functionality | 880 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 12 | 10 | 10 | 10 | 10 | 10
0 | Add new record in Product Hauls Page | 880 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0
0 | Edit new record in Product Hauls Page | 880 | 8 | 8 | 8 | 8 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT | 1 | 本次迭代主要完成第七期的工作
StartDate | 2017-12-18
EndDate | 2017-12-29
Est Time
Name | Role | Total Hours | 2017-12-18 | 2017-12-19 | 2017-12-20 | 2017-12-21 | 2017-12-22 | 2017-12-25 | 2017-12-26 | 2017-12-27 | 2017-12-28 | 2017-12-29
|  |  | 43087 | 43088 | 43089 | 43090 | 43091 | 43094 | 43095 | 43096 | 43097 | 43098
Ideal Burndown |  | 130 | 117 | 104 | 91 | 78 | 65 | 52 | 39 | 26 | 13 | 0
Hours consumed |  | 130 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
Bella.Bi |  | 10 | bar: 2017-12-18 to 2017-12-29
Linsee.Lin |  | 60 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Olivia.Ge |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bright.Liu |  | 60 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
0
0
Actual Time
Name | Role | Total Hours | 2017-12-18 | 2017-12-19 | 2017-12-20 | 2017-12-21 | 2017-12-22 | 2017-12-25 | 2017-12-26 | 2017-12-27 | 2017-12-28 | 2017-12-29
|  |  | 43087 | 43088 | 43089 | 43090 | 43091 | 43094 | 43095 | 43096 | 43097 | 43098
Ideal Burndown |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours consumed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bella.Bi |  | 0
Linsee.Lin |  | 0
Olivia.Ge |  | 0
Bright.Liu |  | 0
0
0
0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | StartDate | EndDate | Assign To | Actual(Hour)
Phase7.P006 | Meeting-Phase 6 | 900 | 10 | 0 |  |  | All | 10
Phase7.S005 | Requirements analysis | 900 | 10 | 0 |  |  | Bella.bi | 0
Phase7.S006 | Task documentation | 900 | 10 | 0 |  |  | Bella.bi | 3.5
Phase7.Test005 | System test | 900 | 10 | 0 |  |  | 0 | 0
Phase7.Bug003 | Fix bugs_Linsee | 900 | 10 | 0 |  |  | Linsee.lin | 11
TUC.OL.FR.PH.07 | Display product haul list in Product Hauls page | 880 | 4 | 0 |  |  | Linsee.lin | 3
TUC.OL.FR.PH.05 | Implement Go with job | 880 | 3 | 0 |  |  | 0 | 4
TUC.OL.BA.SC.01 | Implement Security Control prototype | 880 | 16 | 0 |  |  | Bright.liu | 10
Phase7.D002 | Research for Transaction logging functionality | 880 | 8 | 0 |  |  | Bright.liu | 15
TUC.OL.BA.SC.02 | Implement Transaction logging functionality | 880 | 16 | 0 |  |  | Bright.liu | 9.5
0 | Add new record in Product Hauls Page | 880 | 8 | 0 |  |  | Linsee.lin | 10.5
0 | Edit new record in Product Hauls Page | 880 | 8 | 0 |  |  | Linsee.lin | 8
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务开始时间
Note on G1: Ying Li: 任务结束时间
Note on H1: Ying Li: 任务负责人
Note on I1: Ying Li: 任务投入总时间