## Daily Records
ID | Name | Prioritize | Est(Hour) | 2018-01-02 | 2018-01-03 | 2018-01-04 | 2018-01-05 | 2018-01-08 | 2018-01-09 | 2018-01-10 | 2018-01-11 | 2018-01-12 | 2018-01-15 | 2018-01-16 | 2018-01-17 | 2018-01-18 | 2018-01-19 | Total Hours
|  |  |  | 43102 | 43103 | 43104 | 43105 | 43108 | 43109 | 43110 | 43111 | 43112 | 43115 | 43116 | 43117 | 43118 | 43119
| Ideal Burndown |  | 229 | 229 | 214 | 198 | 180 | 162 | 144 | 126 | 108 | 90 | 72 | 54 | 36 | 18 | 0 | 178.5
| Actual |  | 218 | 229 | 224 | 218 | 209 | 192 | 178 | 163.5 | 149 | 132 | 115.5 | 96.5 | 80 | 63.5 | 49.5
|  |  |  | 0 | 5 | 6 | 9 | 17 | 14 | 14.5 | 14.5 | 17 | 16.5 | 19 | 16.5 | 16.5 | 14
Phase7.P007 | Meeting-Phase 7 | 900 | 30 |  | 2 | 3 | 1.5 | 7.5 | 1.5 | 7.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 33.5 | All
Phase7.S006 | Requirements analysis | 900 | 10 |  |  |  | 1 | 2.5 | 2 | 1.5 | 0.5 | 0.5 |  | 2.5 | 1 |  | 1 | 12.5 | Bella.bi
Phase7.S008 | Task documentation_Bright | 900 | 10 |  |  |  | 0.5 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 10 | Bright.liu
Phase7.S009 | Task documentation_Linsee | 900 | 5 | [14 empty] | 1 | Linsee.lin | bar: 2018-01-12
Phase7.D001 | Research for .Net Core Security Control_Bright | 880 | 4 | 2018-01-04: 2 | 2 | Bright.liu
Phase7.D001 | Research for .Net Core Security Control_Linsee | 880 | 2 | [14 empty] | 1 | Linsee.lin | bar: 2018-01-04
TUC.OL.BA.SC.01 | Implement Security Control prototype | 880 | 10 | 2018-01-03: 1; 2018-01-08: 2 | 3 | Bright.liu
Phase7.D002 | Research for Transaction logging functionality | 880 | 8 | 2018-01-03: 2 | 2 | Bright.liu
TUC.OL.BA.SC.04 | Tab page accessibility control | 850 | 6 | 2018-01-05: 1; 2018-01-09: 3; 2018-01-12: 0.5 | 4.5 | Bright.liu
TUC.OL.BA.SC.05 | Pop-up menu items construction control | 850 | 8 | 2018-01-05: 1; 2018-01-09: 4; 2018-01-12: 2 | 7 | Bright.liu
TUC.OL.BA.SC.06 | Data form page level data CRUD control | 850 | 5 | 2018-01-11: 3; 2018-01-12: 1.5 | 4.5 | Bright.liu
TUC.OL.BA.SC.07 | Read/Write control against real-time interaction | 850 | 8 | [14 empty] | 0 | Bright.liu
TUC.OL.BA.SC.08 | User security cache | 850 | 10 | 2018-01-11: 5; 2018-01-12: 2.5 | 7.5 | Bright.liu
Phase7.D003 | Security Control Design Model_Bright | 850 | 8 | 2018-01-05: 3; 2018-01-08: 1 | 4 | Bright.liu
Phase7.D003 | Security Control Design Model_Bella | 850 | 5 | [14 empty] | 2 | Bella.bi | bar: 2018-01-05 to 2018-01-08
Phase7.S007 | Understand the requirements_Bright | 850 | 5 | 2018-01-08: 1; 2018-01-10: 1.5 | 2.5 | Bright.liu
Phase7.S007 | Understand the requirements_Linsee | 850 | 5 | [14 empty] | 2 | Linsee.lin | bar: 2018-01-08; 2018-01-10
TUC.OL.BA.RJ.16 | Update the rig job status to Completed when Job Package sent to server | 840 | 2 | [14 empty] | 0 | Linsee.lin | bar: 2018-01-12
TUC.OL.FR.CALL.01 | Delete a Call Sheet and Rig Job through pop up menu | 800 | 6 | 2018-01-15: 4; 2018-01-16: 2.5; 2018-01-17: 3 | 9.5 | Linsee.lin
TUC.OL.FR.CALL.02 | Cancel a Call Sheet and Rig Job through pop up menu | 800 | 6 | 2018-01-12: 4; 2018-01-16: 2.5; 2018-01-17: 1.5 | 8 | Linsee.lin
TUC.OL.FR.RIG.04 | Create separate “Activate a Rig” interface for re-activate a rig | 800 | 7 | 2018-01-15: 6.5 | 6.5 | Bright.liu
TUC.OL.BA.RIG.05 | Add 'is service rig' and 'is project rig' to rig | 750 | 6 | 2018-01-10: 2 | 2 | Linsee.lin
TUC.OL.BA.RIG.01 | Carry over Is Project Rig to rig job | 750 | 7 | 2018-01-11: 1; 2018-01-12: 1.5 | 2.5 | Linsee.lin
TUC.OL.BA.RB.16 | Filter rig job by 'Is Project Rig' in rig board | 750 | 7 | 2018-01-15: 3.5; 2018-01-16: 2.5 | 6 | Linsee.lin
Phase7.Bug001 | Fix Bugs_Linsee | 720 | 7 | 2018-01-09: 3; 2018-01-11: 2.5; 2018-01-17: 2; 2018-01-18: 7.5 | 15 | Linsee.lin
Phase7.Bug002 | Fix Bugs_Bright | 720 | 7 | 2018-01-16: 6.5; 2018-01-17: 0.5; 2018-01-18: 5.5 | 12.5 | Bright.liu
TUC.OL.FR.PH.10 | Add default comments in Unit Section Description and edit | 700 | 5 | 2018-01-17: 4 | 4 | Bright.liu
TUC.OL.FR.PH.11 | Edit default comments in Unit Section Description and edit | 700 | 3 | 2018-01-17: 2 | 2 | Bright.liu
TUC.OL.FR.RJ.17 | Sql script for Archive the Rig Jobs | 700 | 8 | 2018-01-19: 4 | 4 | Linsee.lin
TUC.OL.FR.PH.09 | Add one more Unit dropdown list to product haul page | 700 | 8 | 2018-01-18: 1; 2018-01-19: 6.5 | 7.5 | Bright.liu
Note on F6: Bella Bi: 讨论Adam邮件中指出的问题
Note on G6: binliu 讨论Adam邮件中提出的问题，并讨论需求文档
Note on I6: bin liu: olivia,linsee,bella,bela,bright讨论安全控制设计
Note on K6: bin liu: bella,olivia,linsee,bright 早会和估任务

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2018-01-02 | 2018-01-03 | 2018-01-04 | 2018-01-05 | 2018-01-08 | 2018-01-09 | 2018-01-10 | 2018-01-11 | 2018-01-12 | 2018-01-15 | 2018-01-16 | 2018-01-17 | 2018-01-18 | 2018-01-19 | Total Hours | 0 | 0 | 0 | 0 | 0
|  |  |  | 43102 | 43103 | 43104 | 43105 | 43108 | 43109 | 43110 | 43111 | 43112 | 43115 | 43116 | 43117 | 43118 | 43119
| Ideal Burndown |  | 229 | 229 | 214 | 198 | 180 | 162 | 144 | 126 | 108 | 90 | 72 | 54 | 36 | 18 | 0
| Actual burndown |  | 218 | 218 | 210 | 203 | 197 | 181 | 164 | 127 | 105 | 85.5 | 51.5 | 33.5 | 21 | 18.5 | 8
|  |  | 218 | 218 |  | 203 | 197 | 181 | 164 | 127 | 105 | 85.5 | 59.5 | 41.5 |  |  |  | 8
Phase7.P007 | Meeting-Phase 7 | 900 | 30 | 30 | 28 | 25 | 23.5 | 16 | 14.5 | 7 | 5.5 | 4 | 4 | 4 | 3 | 1.5 | 0 | 0
Phase7.S006 | Requirements analysis | 900 | 10 | 10 | 10 | 10 | 9 | 6.5 | 4.5 | 3 | 2.5 | 2 | 2 | 2 | 2 | 1 | 0 | 0
Phase7.S008 | Task documentation_Bright | 900 | 10 | 10 | 13 | 12 | 11.5 | 10.5 | 10 | 9 | 8 | 7 | 4 | 3 | 2 | 1 | 0 | 0
Phase7.S009 | Task documentation_Linsee | 900 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Phase7.D001 | Research for .Net Core Security Control_Bright | 880 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Phase7.D001 | Research for .Net Core Security Control_Linsee | 880 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.SC.01 | Implement Security Control prototype | 880 | 10 | 10 | 9 | 9 | 9 | 7 | 7 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Phase7.D002 | Research for Transaction logging functionality | 880 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.SC.04 | Tab page accessibility control | 850 | 6 | 6 | 6 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.SC.05 | Pop-up menu items construction control | 850 | 8 | 8 | 8 | 8 | 7 | 7 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.SC.06 | Data form page level data CRUD control | 850 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.SC.07 | Read/Write control against real-time interaction | 850 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.SC.08 | User security cache | 850 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 2.5 | 2.5 | 2.5 | 0 | 0 | 0 | 0
Phase7.D003 | Security Control Design Model_Bright | 850 | 8 | 8 | 8 | 8 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase7.D003 | Security Control Design Model_Bella | 850 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase7.S007 | Understand the requirements_Bright | 850 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
Phase7.S007 | Understand the requirements_Linsee | 850 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
TUC.OL.BA.RJ.16 | Update the rig job status to Completed when Job Package sent to server | 840 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.CALL.01 | Delete a Call Sheet and Rig Job through pop up menu | 800 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 1 | 1 | 1 | 1 | 0 | 0
TUC.OL.FR.CALL.02 | Cancel a Call Sheet and Rig Job through pop up menu | 800 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 2 | 1 | 1 | 1 | 0 | 0
TUC.OL.FR.RIG.04 | Create separate “Activate a Rig” interface for re-activate a rig | 800 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.RIG.05 | Add 'is service rig' and 'is project rig' to rig | 750 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.RIG.01 | Carry over Is Project Rig to rig job | 750 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.RB.16 | Filter rig job by 'Is Project Rig' in rig board | 750 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 0 | 0 | 0 | 0 | 0
Phase7.Bug001 | Fix Bugs_Linsee | 720 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase7.Bug002 | Fix Bugs_Bright | 720 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.PH.10 | Add default comments in Unit Section Description and edit | 700 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0
TUC.OL.FR.PH.11 | Edit default comments in Unit Section Description and edit | 700 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
TUC.OL.FR.RJ.17 | Sql script for Archive the Rig Jobs | 700 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
TUC.OL.FR.PH.09 | Add one more Unit dropdown list to product haul page | 700 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 0 | 0
TUC.OL.BA.RIG.05 | Add 'is service rig' and 'is project rig' to rig | 750 | 6
TUC.OL.BA.RIG.01 | Carry over Is Project Rig to rig job | 750 | 7
TUC.OL.BA.RB.16 | Filter rig job by 'Is Project Rig' in rig board | 750 | 7
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT | 1 | 本次迭代主要完成第七期的工作
StartDate | 2018-01-03
EndDate | 2018-01-12
Est Time
Name | Role | Total Hours | 2018-01-03 | 2018-01-04 | 2018-01-05 | 2018-01-08 | 2018-01-09 | 2018-01-10 | 2018-01-11 | 2018-01-12 | 2018-01-15 | 2018-01-16 | 2018-01-17 | 2018-01-18 | 2018-01-19
|  |  | 43103 | 43104 | 43105 | 43108 | 43109 | 43110 | 43111 | 43112 | 43115 | 43116 | 43117 | 43118 | 43119
Ideal Burndown |  | 229 | 214 | 198 | 180 | 162 | 144 | 126 | 108 | 90 | 72 | 54 | 36 | 18 | 0
Hours consumed |  | 229 | 15 | 16 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
Bella.Bi |  | 25 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Linsee.Lin |  | 100 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Olivia.Ge |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bright.Liu |  | 104 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
0
0
Actual Time
Name | Role | Total Hours | 2018-01-03 | 2018-01-04 | 2018-01-05 | 2018-01-08 | 2018-01-09 | 2018-01-10 | 2018-01-11 | 2018-01-12 | 2018-01-15 | 2018-01-16 | 2018-01-17 | 2018-01-18 | 2018-01-19
|  |  | 43103 | 43104 | 43105 | 43108 | 43109 | 43110 | 43111 | 43112 | 43115 | 43116 | 43117 | 43118 | 43119
Ideal Burndown |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours consumed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bella.Bi |  | 0
Linsee.Lin |  | 0
Olivia.Ge |  | 0
Bright.Liu |  | 0
0
0
0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | StartDate | EndDate | Assign To | Actual(Hour)
Phase7.P007 | Meeting-Phase 7 | 900 | 30 | 0 |  |  | All | 33.5
Phase7.S006 | Requirements analysis | 900 | 10 | 0 |  |  | Bella.bi | 12.5
Phase7.S008 | Task documentation_Bright | 900 | 10 | 0 |  |  | Bright.liu | 10
#REF! | #REF! | #REF! | #REF! | 0 |  |  | #REF! | #REF!
Phase7.D001 | Research for .Net Core Security Control_Bright | 880 | 4 | 0 |  |  | Bright.liu | 2
Phase7.D001 | Research for .Net Core Security Control_Linsee | 880 | 2 | 0 |  |  | Linsee.lin | 1
TUC.OL.BA.SC.01 | Implement Security Control prototype | 880 | 10 | 0 |  |  | Bright.liu | 3
Phase7.D002 | Research for Transaction logging functionality | 880 | 8 | 0 |  |  | Bright.liu | 2
#REF! | #REF! | #REF! | #REF! | 0 |  |  | #REF! | #REF!
TUC.OL.BA.SC.04 | Tab page accessibility control | 850 | 6 | 0 |  |  | Bright.liu | 4.5
TUC.OL.BA.SC.05 | Pop-up menu items construction control | 850 | 8 | 0 |  |  | Bright.liu | 7
TUC.OL.BA.SC.06 | Data form page level data CRUD control | 850 | 5 | 0 |  |  | Bright.liu | 4.5
TUC.OL.BA.SC.07 | Read/Write control against real-time interaction | 850 | 8 | 0 |  |  | Bright.liu | 0
Phase7.D003 | Security Control Design Model_Bright | 850 | 8 | 0 |  |  | Bright.liu | 4
Phase7.D003 | Security Control Design Model_Bella | 850 | 5 | 0 |  |  | Bella.bi | 2
Phase7.S007 | Understand the requirements_Bright | 850 | 5 | 0 |  |  | Bright.liu | 2.5
Phase7.S007 | Understand the requirements_Linsee | 850 | 5 | 0 |  |  | Linsee.lin | 2
TUC.OL.BA.RJ.16 | Update the rig job status to Completed when Job Package sent to server | 840 | 2 | 0 |  |  | Linsee.lin | 0
TUC.OL.FR.CALL.01 | Delete a Call Sheet and Rig Job through pop up menu | 800 | 6 | 0 |  |  | Linsee.lin | 9.5
TUC.OL.FR.CALL.02 | Cancel a Call Sheet and Rig Job through pop up menu | 800 | 6 | 0 |  |  | Linsee.lin | 8
TUC.OL.FR.RIG.04 | Create separate “Activate a Rig” interface for re-activate a rig | 800 | 7 | 0 |  |  | Bright.liu | 6.5
TUC.OL.BA.RIG.05 | Add 'is service rig' and 'is project rig' to rig | 750 | 6 | 0 |  |  | Linsee.lin | 2
TUC.OL.BA.RIG.01 | Carry over Is Project Rig to rig job | 750 | 7 | 0 |  |  | Linsee.lin | 2.5
TUC.OL.BA.RB.16 | Filter rig job by 'Is Project Rig' in rig board | 750 | 7 | 0 |  |  | Linsee.lin | 6
#REF! | #REF! | #REF! | #REF! | 0 |  |  | #REF! | #REF!
Phase7.Bug001 | Fix Bugs_Linsee | 720 | 7 | 0 |  |  | Linsee.lin | 15
Phase7.Bug002 | Fix Bugs_Bright | 720 | 7 | 0 |  |  | Bright.liu | 12.5
TUC.OL.FR.PH.10 | Add default comments in Unit Section Description and edit | 700 | 5 | 0 |  |  | Bright.liu | 4
TUC.OL.FR.PH.11 | Edit default comments in Unit Section Description and edit | 700 | 3 | 0 |  |  | Bright.liu | 2
TUC.OL.FR.RJ.17 | Sql script for Archive the Rig Jobs | 700 | 8 | 0 |  |  | Linsee.lin | 4
#REF! | #REF! | #REF! | #REF! | 0 |  |  | #REF! | #REF!
TUC.OL.FR.PH.09 | Add one more Unit dropdown list to product haul page | 700 | 8 | 0 |  |  | Bright.liu | 7.5
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务开始时间
Note on G1: Ying Li: 任务结束时间
Note on H1: Ying Li: 任务负责人
Note on I1: Ying Li: 任务投入总时间