## Daily Records
ID | Name | Prioritize | Est(Hour) | 2018-01-21 | 2018-01-22 | 2018-01-23 | 2018-01-24 | 2018-01-25 | 2018-01-26 | 2018-01-29 | 2018-01-30 | 2018-01-31 | 2018-02-01 | 2018-02-02 | 2018-02-05 | 2018-02-06 | 2018-02-07 | 2018-02-08 | 2018-02-09 | 2018-02-11 | 2018-02-12 | 2018-02-13 | Total Hours
|  |  |  | 43121 | 43122 | 43123 | 43124 | 43125 | 43126 | 43129 | 43130 | 43131 | 43132 | 43133 | 43136 | 43137 | 43138 | 43139 | 43140 | 43142 | 43143 | 43144
| Ideal Burndown |  | 286 | 286 | 269 | 252 | 235 | 218 | 201 | 184 | 167 | 150 | 133 | 116 | 99 | 82 | 65 | 48 | 31 | 14 | 5 | 0 | 276
| Actual |  | 312 | 286 | 272 | 262 | 252 | 235.5 | 219 | 201.5 | 184.5 | 168 | 145 | 128.5 | 112.5 | 97 | 81 | 70 | 46 | 30 | 17 | 9
|  |  |  | 0 | 14 | 10 | 10 | 16.5 | 16.5 | 17.5 | 17 | 16.5 | 23 | 16.5 | 16 | 15.5 | 16 | 11 | 24 | 16 | 13 | 8
Phase7.P007 | Meeting-Phase 7 | 900 | 20 |  | 3 | 1.5 | 1.5 | 1.5 | 1.5 | 5 | 1.5 | 1.5 | 6 | 1.5 | 1 | 1 | 1 | 1 | 1 |  |  |  | 29.5 | All
Phase7.S006 | Requirements analysis | 900 | 7 | 2018-01-23: 1; 2018-01-24: 1; 2018-01-30: 2; 2018-02-01: 2 | 6 | Bella.bi
Phase7.S008 | Task documentation_Bright | 900 | 20 |  | 1 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 18.5 | Bright.liu
Phase7.Test001 | System Test_Bright | 750 | 10 | 2018-01-25: 4; 2018-01-26: 6.5; 2018-02-07: 3; 2018-02-09: 6.5 | 20 | Bright.liu
Phase7.Test002 | System Test_Linsee | 750 | 8 | 2018-01-26: 7.5 | 7.5 | Linsee.lin
TUC.OL.FR.PH.10 | Add default comments in Unit Section Description and edit | 700 | 2 | [19 empty] | 1 | Bright.liu | bar: 2018-01-23
TUC.OL.FR.RJ.17 | Sql script for Archive the Rig Jobs | 700 | 16 | 2018-01-22: 6; 2018-01-25: 7.5 | 13.5 | Linsee.lin
TUC.OL.FR.PH.09 | Add one more Unit dropdown list to product haul page | 700 | 4 | [19 empty] | 1 | Bright.liu | bar: 2018-01-23
TUC.OL.FR.PH.12 | Add third party truck to haul product | 700 | 12 | 2018-01-22: 4; 2018-01-23: 4.5; 2018-01-24: 4; 2018-01-25: 1; 2018-01-29: 1 | 14.5 | Bright.liu
TUC.OL.FR.PH.13 | Reschedule Third Party Product Haul | 700 | 6 | 2018-01-24: 2.5; 2018-01-29: 2 | 4.5 | Bright.liu
TUC.OL.FR.PH.14 | Cancel Third Party Product Haul | 700 | 3 | 2018-02-01: 2 | 2 | Bright.liu
TUC.OL.FR.UP.01 | Display upcoming jobs which not completed | 690 | 16 | 2018-01-29: 3; 2018-02-07: 7.5 | 10.5 | Linsee.lin
TUC.OL.FR.UP.01 | Display flag for Top Rig and High Profile | 690 | 6 | 2018-02-02: 3 | 3 | Linsee.lin
TUC.OL.FR.UP.02 | Filter by service point in Upcoming Jobs Page | 690 | 6 | 2018-02-02: 3 | 3 | Linsee.lin
TUC.OL.FR.UP.03 | Display Crew\Unit information in Upcoming jobs page | 690 | 16 | 2018-02-08: 5; 2018-02-09: 7.5 | 12.5 | Linsee.lin
TUC.OL.FR.UP.04 | Generate notes according to product haul status in blend column | 690 | 6 | [19 empty] | 0 | Linsee.lin
TUC.OL.BA.UP.05 | Implement ContractorCompany database/Entity/Dao/Service/TestData/DaoTest | 690 | 5 | 2018-01-30: 3 | 3 | Bright.liu
TUC.OL.FR.UP.05 | Rig Board_Cache the current page number | 690 | 15 | 2018-01-30: 6; 2018-01-31: 3.5; 2018-02-06: 7.5 | 17 | Linsee.lin
TUC.OL.BA.UP.06 | Don't allow to delete/edit the Unit/Personnel record created by Rig Job/Product Haul scheduling | 690 | 7 | 2018-02-05: 5 | 5 | Bright.liu
TUC.OL.BA.UP.07 | Don't allow to delete/edit the Third Party Units record created by Rig Job/Product Haul scheduling | 690 | 7 | 2018-02-06: 5 | 5 | Bright.liu
TUC.OL.BA.UP.08 | Rig Job Direction flag should be disabled for inactive rigs | 690 | 4 | 2018-02-05: 3 | 3 | Linsee.lin
TUC.OL.BA.UP.09 | Highlight rigs in Down status and add some previous job values | 690 | 2 | 2018-02-05: 1; 2018-02-07: 2.5 | 3.5 | Linsee.lin & Bright.liu
TUC.OL.BA.UP.10 | Enable a down Rig | 690 | 6 | 2018-02-05: 3.5; 2018-02-07: 1 | 4.5 | Linsee.lin & Bright.liu
TUC.OL.FR.UP.06 | Add Rig Status to tooltips | 690 | 2 | [19 empty] | 1 | Bright.liu | bar: 2018-02-06
Phase7.Test003 | Write Test Case_Bright | 690 | 16 | 2018-01-29: 2; 2018-01-30: 3.5; 2018-01-31: 4; 2018-02-01: 3; 2018-02-02: 3; 2018-02-05: 0.5 | 16 | Bright.liu
Phase7.Test004 | Write Test Case_Linsee | 690 | 16 | 2018-01-29: 3.5; 2018-01-31: 4; 2018-02-01: 6; 2018-02-02: 2 | 15.5 | Linsee.lin
Phase7.Test005 | Write Test Case_Bella | 690 | 3 | 2018-02-01: 3 | 3 | Bella.bi
| Fix Bug_Bright | 690 | 10 | 2018-01-31: 2.5; 2018-02-02: 3; 2018-02-05: 1 | 6.5 | Bright.liu
SQL.T001 | Discuss for migration database | 650 | 5 | 2018-02-08: 4 | 4 | All
SQL.T002 | Analyze and organize data types | 650 | 20 | 2018-02-09: 8; 2018-02-12: 4; 2018-02-13: 4 | 16 | Stone.zhao
SQL.T003 | Modify daobase | 650 | 20 | 2018-02-11: 10; 2018-02-12: 8; 2018-02-13: 1 | 19 | Bright.liu&Linsee.lin
SQL.T004 | Modify context | 650 | 8 | 2018-02-11: 1; 2018-02-13: 2 | 3 | Bright.liu&Linsee.lin
SQL.T005 | Prepare test table | 650 | 8 | 2018-02-11: 4 | 4 | Linsee.lin
Note on F6: Bella Bi: 和Adam微信沟通确认需求
Note on K6: bin liu: 讨论重构
Note on R27: bin liu: Bright
Note on R28: bin liu: Bright
Note on U36: Bella Bi: Linsee 3h Bright 7h
Note on V36: bin liu: Bright
Note on W36: bin liu: Bright
Note on W37: bin liu: Bright

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2018-01-21 | 2018-01-22 | 2018-01-23 | 2018-01-24 | 2018-01-25 | 2018-01-26 | 2018-01-29 | 2018-01-30 | 2018-01-31 | 2018-02-01 | 2018-02-02 | 2018-02-05 | 2018-02-06 | 2018-02-07 | 2018-02-08 | 2018-02-09 | 2018-02-11 | 2018-02-12 | 2018-02-13 | Total Hours
|  |  |  | 43121 | 43122 | 43123 | 43124 | 43125 | 43126 | 43129 | 43130 | 43131 | 43132 | 43133 | 43136 | 43137 | 43138 | 43139 | 43140 | 43142 | 43143 | 43144
| Ideal Burndown |  | 286 | 286 | 269 | 252 | 235 | 218 | 201 | 184 | 167 | 150 | 133 | 116 | 99 | 82 | 65 | 48 | 31 | 14 | 5 | 0
| Actual burndown |  | 312 | 306 | 290.5 | 278 | 266.5 | 251 | 239.5 | 210.5 | 196 | 186 | 173 | 158 | 128 | 111 | 92 | 81 | 49 | 34 | 17 | 12
|  |  | 312 | 2018-01-21: 306; 2018-01-23: 278; 2018-01-24: 266.5; 2018-01-25: 251; 2018-01-26: 239.5; 2018-01-29: 210.5; 2018-01-30: 196; 2018-01-31: 186; 2018-02-01: 173; 2018-02-02: 158; 2018-02-08: 81
Phase7.P007 | Meeting-Phase 7 | 900 | 20 | 20 | 15.5 | 14 | 12.5 | 11 | 10.5 | 5.5 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 1 | 0 | 0 | 0 | 0
Phase7.S006 | Requirements analysis | 900 | 7 | 7 | 7 | 6 | 5 | 5 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase7.S008 | Task documentation_Bright | 900 | 20 | 20 | 19 | 18 | 17 | 15 | 14 | 13 | 14 | 11 | 10 | 9 | 8 | 7 | 5 | 3 | 2 | 1 | 1 | 0 | 0
Phase7.Test001 | System Test_Bright | 750 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 0
Phase7.Test002 | System Test_Linsee | 750 | 8 | 8 | 8 | 8 | 8 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.PH.10 | Add default comments in Unit Section Description and edit | 700 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.RJ.17 | Sql script for Archive the Rig Jobs | 700 | 16 | 16 | 10 | 10 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.PH.09 | Add one more Unit dropdown list to product haul page | 700 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.PH.12 | Add third party truck to haul product | 700 | 12 | 12 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.PH.13 | Reschedule Third Party Product Haul | 700 | 6 | 6 | 6 | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.PH.14 | Cancel Third Party Product Haul | 700 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.UP.01 | Display upcoming jobs which not completed | 690 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.UP.01 | Display flag for Top Rig and High Profile | 690 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.UP.02 | Filter by service point in Upcoming Jobs Page | 690 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.UP.03 | Display Crew\Unit information in Upcoming jobs page | 690 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.UP.04 | Generate notes according to product haul status in blend column | 690 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.UP.05 | Implement ContractorCompany database/Entity/Dao/Service/TestData/DaoTest | 690 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.UP.05 | Rig Board_Cache the current page number | 690 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.UP.06 | Don't allow to delete/edit the Unit/Personnel record created by Rig Job/Product Haul scheduling | 690 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.UP.07 | Don't allow to delete/edit the Third Party Units record created by Rig Job/Product Haul scheduling | 690 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.UP.08 | Rig Job Direction flag should be disabled for inactive rigs | 690 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.UP.09 | Highlight rigs in Down status and add some previous job values | 690 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.BA.UP.10 | Enable a down Rig | 690 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TUC.OL.FR.UP.06 | Add Rig Status to tooltips | 690 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase7.Test003 | Write Test Case_Bright | 690 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 10 | 7 | 5 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase7.Test004 | Write Test Case_Linsee | 690 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 10 | 7 | 5 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase7.Test005 | Write Test Case_Bella | 690 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fix Bug_Bright | 690 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 8 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Discuss for migration database | 650 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0
| Analyze and organize data types | 650 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 10 | 4 | 0 | 0
| Modify daobase | 650 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 10 | 10 | 10
| Modify context | 650 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 2 | 2 | 2
| Prepare test table | 650 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT | 1 | 本次迭代主要完成第七期的工作
StartDate | 2018-01-22
EndDate | 2018-02-13
Est Time
Name | Role | Total Hours | 2018-01-22 | 2018-01-23 | 2018-01-24 | 2018-01-25 | 2018-01-26 | 2018-01-29 | 2018-01-30 | 2018-01-31 | 2018-02-01 | 2018-02-02 | 2018-02-05 | 2018-02-06 | 2018-02-07 | 2018-02-08 | 2018-02-09 | 2018-02-11 | 2018-02-12 | 2018-02-13
|  |  | 43122 | 43123 | 43124 | 43125 | 43126 | 43129 | 43130 | 43131 | 43132 | 43133 | 43136 | 43137 | 43138 | 43139 | 43140 | 43142 | 43143 | 43144
Ideal Burndown |  | 286 | 269 | 252 | 235 | 218 | 201 | 184 | 167 | 150 | 133 | 116 | 99 | 82 | 65 | 48 | 31 | 14 | 5 | 0
Hours consumed |  | 286 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 9 | 5
Bella.Bi |  | 18 | bar: 2018-01-22 to 2018-02-13
Linsee.Lin |  | 128 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0
Olivia.Ge |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bright.Liu |  | 140 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4
0
0
Actual Time
Name | Role | Total Hours | 2018-01-22 | 2018-01-23 | 2018-01-24 | 2018-01-25 | 2018-01-26 | 2018-01-29 | 2018-01-30 | 2018-01-31 | 2018-02-01 | 2018-02-02 | 2018-02-05 | 2018-02-06 | 2018-02-07 | 2018-02-08 | 2018-02-09 | 2018-02-11 | 2018-02-12 | 2018-02-13
|  |  | 43122 | 43123 | 43124 | 43125 | 43126 | 43129 | 43130 | 43131 | 43132 | 43133 | 43136 | 43137 | 43138 | 43139 | 43140 | 43142 | 43143 | 43144
Ideal Burndown |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours consumed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bella.Bi |  | 0
Linsee.Lin |  | 0
Olivia.Ge |  | 0
Bright.Liu |  | 0
0
0
0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | StartDate | EndDate | Assign To | Actual(Hour)
Phase7.P007 | Meeting-Phase 7 | 900 | 20 | 1 |  |  | All | 29.5
Phase7.S006 | Requirements analysis | 900 | 7 | 1 |  |  | Bella.bi | 6
Phase7.S008 | Task documentation_Bright | 900 | 20 | 1 |  |  | Bright.liu | 18.5
Phase7.Test001 | System Test_Bright | 750 | 10 | 1 |  |  | Bright.liu | 20
Phase7.Test002 | System Test_Linsee | 750 | 8 | 1 |  |  | Linsee.lin | 7.5
TUC.OL.FR.PH.10 | Add default comments in Unit Section Description and edit | 700 | 2 | 1 |  |  | Bright.liu | 1
TUC.OL.FR.RJ.17 | Sql script for Archive the Rig Jobs | 700 | 16 | 1 |  |  | Linsee.lin | 13.5
TUC.OL.FR.PH.09 | Add one more Unit dropdown list to product haul page | 700 | 4 | 1 |  |  | Bright.liu | 1
TUC.OL.FR.PH.12 | Add third party truck to haul product | 700 | 12 | 1 |  |  | Bright.liu | 14.5
TUC.OL.FR.PH.13 | Reschedule Third Party Product Haul | 700 | 6 | 1 |  |  | Bright.liu | 4.5
TUC.OL.FR.PH.14 | Cancel Third Party Product Haul | 700 | 3 | 1 |  |  | Bright.liu | 2
TUC.OL.FR.UP.01 | Display upcoming jobs which not completed | 690 | 16 | 1 |  |  | Linsee.lin | 10.5
TUC.OL.FR.UP.01 | Display flag for Top Rig and High Profile | 690 | 6 | 1 |  |  | Linsee.lin | 3
TUC.OL.FR.UP.02 | Filter by service point in Upcoming Jobs Page | 690 | 6 | 1 |  |  | Linsee.lin | 3
TUC.OL.FR.UP.03 | Display Crew\Unit information in Upcoming jobs page | 690 | 16 | 1 |  |  | Linsee.lin | 12.5
TUC.OL.FR.UP.04 | Generate notes according to product haul status in blend column | 690 | 6 | 1 |  |  | Linsee.lin | 0
TUC.OL.BA.UP.05 | Implement ContractorCompany database/Entity/Dao/Service/TestData/DaoTest | 690 | 5 | 1 |  |  | Bright.liu | 3
TUC.OL.FR.UP.05 | Rig Board_Cache the current page number | 690 | 15 | 1 |  |  | Linsee.lin | 17
TUC.OL.BA.UP.06 | Don't allow to delete/edit the Unit/Personnel record created by Rig Job/Product Haul scheduling | 690 | 7 | 1 |  |  | Bright.liu | 5
TUC.OL.BA.UP.07 | Don't allow to delete/edit the Third Party Units record created by Rig Job/Product Haul scheduling | 690 | 7 | 1 |  |  | Bright.liu | 5
TUC.OL.BA.UP.08 | Rig Job Direction flag should be disabled for inactive rigs | 690 | 4 | 1 |  |  | Linsee.lin | 3
TUC.OL.BA.UP.09 | Highlight rigs in Down status and add some previous job values | 690 | 2 | 1 |  |  | Linsee.lin & Bright.liu | 3.5
TUC.OL.BA.UP.10 | Enable a down Rig | 690 | 6 | 1 |  |  | Linsee.lin & Bright.liu | 4.5
TUC.OL.FR.UP.06 | Add Rig Status to tooltips | 690 | 2 | 1 |  |  | Bright.liu | 1
Phase7.Test003 | Write Test Case_Bright | 690 | 16 | 1 |  |  | Bright.liu | 16
Phase7.Test004 | Write Test Case_Linsee | 690 | 16 | 1 |  |  | Linsee.lin | 15.5
Phase7.Test005 | Write Test Case_Bella | 690 | 3 | 1 |  |  | Bella.bi | 3
0 | Fix Bug_Bright | 690 | 10 | 1 |  |  | Bright.liu | 6.5
SQL.T001 | Discuss for migration database | 650 | 5 | 1 |  |  | All | 4
SQL.T002 | Analyze and organize data types | 650 | 20 | 1 |  |  | Stone.zhao | 16
SQL.T003 | Modify daobase | 650 | 20 | 1 |  |  | Bright.liu&Linsee.lin | 19
SQL.T004 | Modify context | 650 | 8 | 1 |  |  | Bright.liu&Linsee.lin | 3
SQL.T005 | Prepare test table | 650 | 8 | 1 |  |  | Linsee.lin | 4
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
0 | 0 | 0 | 0 |  |  |  | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务开始时间
Note on G1: Ying Li: 任务结束时间
Note on H1: Ying Li: 任务负责人
Note on I1: Ying Li: 任务投入总时间