## Daily Records
ID | Name | Prioritize | Est(Hour) | 2018-02-21 | 2018-02-22 | 2018-02-23 | 2018-02-24 | 2018-02-26 | 2018-02-27 | 2018-02-28 | 2018-03-01 | 2018-03-02 | 2018-03-05 | 2018-03-06 | 2018-03-07 | 2018-03-08 | 2018-03-09 | 2018-03-12 | 2018-03-13 | 2018-03-14 | 2018-03-15 | 2018-03-16 | 2018-03-19 | 2018-03-20 | 2018-03-21 | 2018-03-22 | 2018-03-23 | 2018-03-24 | 2018-03-26 | 2018-03-27 | 2018-03-28 | 2018-03-29 | 2018-03-30 | Total Hours
|  |  |  | 43152 | 43153 | 43154 | 43155 | 43157 | 43158 | 43159 | 43160 | 43161 | 43164 | 43165 | 43166 | 43167 | 43168 | 43171 | 43172 | 43173 | 43174 | 43175 | 43178 | 43179 | 43180 | 43181 | 43182 | 43183 | 43185 | 43186 | 43187 | 43188 | 43189
| Ideal Burndown |  | 659 | 659 | 650 | 633 | 616 | 591 | 566 | 541 | 516 | 491 | 466 | 441 | 416 | 391 | 366 | 340 | 314 | 288 | 262 | 236 | 215 | 194 | 173 | 152 | 131 | 105 | 84 | 63 | 42 | 21 | 0 | 671.5
| Actual |  | 645 | 659 | 650 | 633 | 616 | 589 | 569 | 543.5 | 517.5 | 503.5 | 477.5 | 451 | 424.5 | 398 | 369.5 | 341 | 311.5 | 283 | 257.5 | 232 | 211 | 188 | 165 | 147.5 | 121 | 93.5 | 74.5 | 48.5 | 21 | 7.5 | -12.5
|  |  |  | 0 | 9 | 17 | 17 | 27 | 20 | 25.5 | 26 | 14 | 26 | 26.5 | 26.5 | 26.5 | 28.5 | 28.5 | 29.5 | 28.5 | 25.5 | 25.5 | 21 | 23 | 23 | 17.5 | 26.5 | 27.5 | 19 | 26 | 27.5 | 13.5 | 20
Phase7.P005 | Meeting-Phase 7 | 900 | 50 | [5 empty] | 5 | 2 | 1.5 | 1.5 | 1.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 2 | 1.5 | 55 | All
Phase7.P006 | Project management | 900 | 20 |  | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  | 2 | 2 | 1 | 1 | 3 | 2 | 3.5 | 27.5 | Bella.bi
Phase7.P007 | Requirements analysis and task document | 900 | 20 | 2018-03-01: 2; 2018-03-02: 2; 2018-03-05: 2; 2018-03-06: 2; 2018-03-07: 2; 2018-03-08: 2; 2018-03-09: 1; 2018-03-19: 1 | 14 | Bella.bi
Phase7.P008 | Requirements analysis and Review Code | 900 | 10 | 2018-02-22: 7; 2018-02-26: 3 | 10 | Linsee.lin & Bright.liu
Phase7.P009 | Task documentation_Bright | 900 | 20 | [5 empty] | 3.5 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 2 | 2.5 |  |  |  | 0.5 | 1 | 24.5 | Bright.liu
SQL.T001 | Discuss for migration database | 750 | 20 | 2018-02-26: 12; 2018-03-09: 8; 2018-03-20: 6 | 26 | All
SQL.T002 | Prepare Development environment | 750 | 8 | 2018-02-23: 4; 2018-03-13: 2; 2018-03-14: 1 | 7 | Stone.zhao
SQL.T004 | Data Type Conversion | 750 | 40 | 2018-02-23: 4; 2018-02-24: 8; 2018-02-26: 5; 2018-02-27: 4; 2018-02-28: 7.5; 2018-03-01: 7.5; 2018-03-02: 3.5; 2018-03-19: 3; 2018-03-20: 3; 2018-03-21: 3 | 48.5 | Stone.zhao
SQL.T005 | Aggregation Type Conversion | 750 | 40 | 2018-03-05: 7.5; 2018-03-06: 7.5; 2018-03-07: 7.5 | 22.5 | Stone.zhao
SQL.T006 | Table Data Conversion | 750 | 40 | 2018-03-08: 7.5; 2018-03-09: 5.5; 2018-03-12: 7.5; 2018-03-13: 7.5; 2018-03-14: 7.5; 2018-03-15: 7.5; 2018-03-16: 7.5; 2018-03-22: 2; 2018-03-23: 7.5; 2018-03-24: 6.5; 2018-03-26: 8; 2018-03-27: 8; 2018-03-28: 7.5; 2018-03-29: 4.5 | 94.5 | Stone.zhao
SQL.T008 | Test SQL Script | 750 | 20 | 2018-03-06: 7; 2018-03-20: 3; 2018-03-21: 8; 2018-03-28: 4; 2018-03-29: 2.5; 2018-03-30: 6.5 | 31 | Linsee.lin & Bright.liu
SQL.T009 | Modify Dao Layer | 750 | 50 | 2018-02-22: 1; 2018-02-23: 4; 2018-02-28: 6.5; 2018-03-01: 6.5; 2018-03-02: 2.5; 2018-03-05: 7; 2018-03-07: 3; 2018-03-08: 6.5; 2018-03-12: 2; 2018-03-13: 3; 2018-03-14: 3 | 45 | Linsee.lin & Bright.liu
SQL.T010 | Modify DaoTest | 750 | 24 | 2018-02-28: 7.5; 2018-03-01: 7.5; 2018-03-02: 3.5; 2018-03-15: 6.5; 2018-03-16: 2.5; 2018-03-29: 2 | 29.5 | Linsee.lin & Bright.liu
SQL.T011 | Increment ID Processing | 750 | 40 | 2018-02-23: 4; 2018-02-27: 2.5; 2018-03-05: 7.5; 2018-03-06: 7.5; 2018-03-07: 7.5; 2018-03-08: 7.5; 2018-03-09: 2 | 38.5 | Linsee.lin & Bright.liu
SQL.T012 | Data type/length/precision analysis | 750 | 24 | 2018-03-09: 3.5; 2018-03-12: 7.5; 2018-03-13: 3.5; 2018-03-14: 1.5; 2018-03-15: 2; 2018-03-16: 3.5 | 21.5 | Linsee.lin & Bright.liu
SQL.T013 | Organize relationships between tables | 750 | 16 | 2018-03-09: 1; 2018-03-12: 3; 2018-03-13: 6; 2018-03-14: 8; 2018-03-15: 5.5 | 23.5 | Bella.bi
SQL.T014 | Organize the foreign keys of the table | 750 | 12 | 2018-02-27: 3; 2018-03-16: 4 | 7 | Linsee.lin & Bright.liu
SQL.T015 | Test for DaoBase and Dao Layer | 750 | 30 | 2018-03-07: 4; 2018-03-09: 4.5; 2018-03-12: 4.5; 2018-03-13: 3.5; 2018-03-14: 3.5; 2018-03-16: 4; 2018-03-24: 2 | 26 | Linsee.lin & Bright.liu
SQL.T007 | Architecteral Prototype | 750 | 24 | 2018-03-19: 14; 2018-03-20: 7 | 21 | Linsee.lin & Bright.liu
SQL.T016 | Security Data Migration | 740 | 8 | 2018-03-21: 8 | 8 | Linsee.lin & Bright.liu
SQL.T017 | Reference Data Migration | 740 | 16 | 2018-03-22: 13; 2018-03-23: 13; 2018-03-24: 1.5 | 27.5 | Linsee.lin & Bright.liu
SQL.T018 | CallSheet Data Migration | 740 | 24 | 2018-03-24: 5; 2018-03-26: 8; 2018-03-27: 11 | 24 | Linsee.lin & Bright.liu
SQL.T019 | RigJob Data Migration | 740 | 4 | 2018-03-30: 0.5 | 0.5 | Linsee.lin & Bright.liu
SQL.T020 | ProductHaul Data Migration | 720 | 4 | 2018-03-30: 2 | 2 | Linsee.lin & Bright.liu
SQL.T021 | Job Data Migration | 720 | 16 | 2018-03-24: 2; 2018-03-27: 4 | 6 | Linsee.lin & Bright.liu
SQL.T022 | ServiceTicket Data Migration | 720 | 8 | [30 empty] | 0
SQL.T023 | ServiceReport Data Migration | 700 | 24 | 2018-03-28: 11 | 11 | Linsee.lin & Bright.liu
SQL.T024 | Program Data Migration | 700 | 16 | 2018-03-30: 5 | 5 | Linsee.lin & Bright.liu
Ticket #38 | Update Job Date Time for Pending Job | 700 | 2 | 2018-02-24: 2 | 2 | Linsee.lin
Ticket #39 | Re-order Service Point checkboxs | 700 | 2 | [30 empty] | 2 | Linsee.lin | bar: 2018-02-24; 2018-02-27
Ticket #40 | Add second driver in Product Haul | 700 | 4 | 2018-02-24: 3; 2018-02-26: 2 | 5 | Linsee.lin
Ticket #42 | Add a Consultant dropdown list needs auto filter | 700 | 3 | 2018-02-24: 2 | 2 | Linsee.lin
Phase7.Test002 | Write Test Case_Bright | 690 | 3 | [30 empty] | 1 | Bright.liu | bar: 2018-02-26
Phase7.Test003 | Write Test Case_Linsee | 690 | 3 | 2018-02-26: 3 | 3 | Linsee.lin
Note on J6: bin liu: Bella 1.5h Bright 1.5h Linsee 1.5h Stone 0.5h
Note on F9: bin liu: Linsee
Note on I9: bin liu: Bright
Note on I11: bin liu: Bella,Olivia,Bela,Stone,Bright,Linsee
Note on R11: bin liu: 和Adam语音通话
Note on Y11: bin liu: 和Adam开会讨论架构原型和DateTime2的问题
Note on T12: bin liu: Oliver.ye
Note on U12: bin liu: Oliver.ye
Note on O16: bin liu: Bright
Note on Y16: bin liu: Lninsee
Note on Z16: bin liu: Bright 3.5h Linsee 7.5h
Note on AF16: bin liu: Linsee
Note on AG16: bin liu: Linsee
Note on AH16: bin liu: Linsee
Note on F17: bin liu: Linsee
Note on G17: bin liu: Linsee
Note on K17: bin liu: Bright
Note on L17: bin liu: Bright
Note on M17: bin liu: Bright
Note on N17: bin liu: Bright
Note on P17: bin liu: Bright
Note on Q17: bin liu: Bright
Note on S17: bin liu: Bright
Note on T17: bin liu: Bright
Note on U17: bin liu: Bright
Note on K18: bin liu: Linsee
Note on L18: bin liu: Linsee
Note on M18: bin liu: Linsee
Note on V18: bin liu: Bright
Note on W18: bin liu: Bright
Note on AG18: bin liu: Bright
Note on G19: bin liu: Linsee
Note on J19: bin liu: Linsee
Note on N19: bin liu: Linsee
Note on O19: bin liu: Linsee
Note on P19: bin liu: Linsee
Note on Q19: bin liu: Linsee
Note on R19: bin liu: Linsee
Note on R20: bin liu: Linsee
Note on S20: bin liu: Linsee
Note on T20: bin liu: Linsee
Note on U20: bin liu: Linsee
Note on V20: bin liu: Linsee
Note on W20: bin liu: Linsee
Note on R21: bin liu: bella
Note on S21: bin liu: Bella
Note on T21: bin liu: Bella 2h Linsee 4h
Note on U21: bin liu: Linsee 6h Bella 2h
Note on V21: bin liu: Linsee
Note on J22: bin liu: Bright
Note on W22: bin liu: Linsee
Note on P23: bin liu: Bright
Note on R23: bin liu: Bright
Note on S23: bin liu: Bright
Note on T23: bin liu: Bright
Note on U23: bin liu: Bright
Note on W23: bin liu: Bright
Note on X24: bin liu: Bright 6.5h Linsee 7.5h
Note on Y24: bin liu: Bright 5h Linsee 2h
Note on Z25: Bella Bi: Bright 3h Linsee 5h
Note on AA26: Bella Bi: Bright 6.5h Linsee 6.5h
Note on AB26: Bella Bi: Linsee 7.5 Bright 5.5
Note on AC27: Bella Bi: Linsee
Note on AD27: Bella Bi: Linsee
Note on AE27: Bella Bi: Linsee 5.5 Bright 5.5
Note on AH28: bin liu: Bright
Note on AH29: bin liu: Bright
Note on AE30: Bella Bi: Bright 2 Linsee 2
Note on AF32: bin liu: Bright 7.5 Linsee 3.5
Note on AH33: bin liu: Bright 4h Linsee 1h

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2018-02-21 | 2018-02-22 | 2018-02-23 | 2018-02-24 | 2018-02-26 | 2018-02-27 | 2018-02-28 | 2018-03-01 | 2018-03-02 | 2018-03-05 | 2018-03-06 | 2018-03-07 | 2018-03-08 | 2018-03-09 | 2018-03-12 | 2018-03-13 | 2018-03-14 | 2018-03-15 | 2018-03-16 | 2018-03-19 | 2018-03-20 | 2018-03-21 | 2018-03-22 | 2018-03-23 | 2018-03-24 | 2018-03-26 | 2018-03-27 | 2018-03-28 | 2018-03-29 | 2018-03-30
|  |  |  | 43152 | 43153 | 43154 | 43155 | 43157 | 43158 | 43159 | 43160 | 43161 | 43164 | 43165 | 43166 | 43167 | 43168 | 43171 | 43172 | 43173 | 43174 | 43175 | 43178 | 43179 | 43180 | 43181 | 43182 | 43183 | 43185 | 43186 | 43187 | 43188 | 43189
| Ideal Burndown |  | 659 | 659 | 650 | 633 | 616 | 591 | 566 | 541 | 516 | 491 | 466 | 441 | 416 | 391 | 366 | 340 | 314 | 288 | 262 | 236 | 215 | 194 | 173 | 152 | 131 | 105 | 84 | 63 | 42 | 21 | 0
| Actual burndown |  | 645 | 645 | 634 | 620 | 605 | 574 | 547 | 524 | 500 | 485 | 458 | 435 | 408 | 376 | 345 | 324 | 298 | 285 | 267 | 238 | 220 | 204 | 163 | 149 | 166 | 139 | 113 | 87 | 55 | 33.5 | 14
Phase7.P005 | Meeting-Phase 7 | 900 | 50 | 50 | 50 | 50 | 50 | 48 | 46 | 44 | 42 | 40 | 38 | 36 | 34 | 32 | 30 | 28 | 26 | 24 | 22 | 20 | 20 | 20 | 20 | 12 | 12 | 10 | 8 | 6 | 4 | 2 | 0
Phase7.P006 | Project management | 900 | 20 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 8 | 7 | 6 | 6 | 8 | 6 | 4 | 3 | 1 | 0
Phase7.P007 | Requirements analysis and task document | 900 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 7 | 7 | 7 | 7 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase7.P008 | Requirements analysis and Review Code | 900 | 10 | 10 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase7.P009 | Task documentation_Bright | 900 | 20 | 20 | 20 | 20 | 20 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 4 | 8 | 8 | 8 | 4 | 3 | 2 | 1 | 0
SQL.T001 | Discuss for migration database | 750 | 20 | 20 | 20 | 20 | 20 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SQL.T002 | Prepare Development environment | 750 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SQL.T004 | Data Type Conversion | 750 | 40 | 40 | 40 | 36 | 30 | 25 | 18 | 12 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 12 | 9 | 6 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0
SQL.T005 | Aggregation Type Conversion | 750 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 25 | 15 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0
SQL.T006 | Table Data Conversion | 750 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 24 | 18 | 12 | 20 | 12 | 12 | 12 | 12 | 8 | 8 | 24 | 16 | 8 | 8 | 4 | 1 | 1
SQL.T008 | Test SQL Script | 750 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0
SQL.T009 | Modify Dao Layer | 750 | 50 | 50 | 46 | 46 | 46 | 46 | 46 | 40 | 33 | 30 | 23 | 23 | 20 | 16 | 16 | 14 | 11 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0
SQL.T010 | Modify DaoTest | 750 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 17 | 10 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 4 | 4 | 4 | 2 | 2 | 1 | 1 | 1 | 3 | 1.5 | 0
SQL.T011 | Increment ID Processing | 750 | 40 | 40 | 40 | 35 | 35 | 35 | 30 | 30 | 30 | 30 | 24 | 20 | 16 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SQL.T012 | Data type/length/precision analysis | 750 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 20 | 16 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SQL.T013 | Organize relationships between tables | 750 | 16 | 16 | 16 | 16 | 16 | 16 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SQL.T014 | Organize the foreign keys of the table | 750 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SQL.T015 | Test for DaoBase and Dao Layer | 750 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 25 | 25 | 20 | 16 | 12 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 1 | 1 | 1 | 0 | 0
SQL.T007 | Architecteral Prototype | 750 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SQL.T016 | Security Data Migration | 740 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
SQL.T017 | Reference Data Migration | 740 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 1 | 1 | 1 | 1 | 0 | 0 | 0
SQL.T018 | CallSheet Data Migration | 740 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 18 | 16 | 1 | 0 | 0 | 0
SQL.T019 | RigJob Data Migration | 740 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 1
SQL.T020 | ProductHaul Data Migration | 720 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 1
SQL.T021 | Job Data Migration | 720 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 2 | 2 | 2 | 0
SQL.T022 | ServiceTicket Data Migration | 720 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 0
SQL.T023 | ServiceReport Data Migration | 700 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 10 | 1 | 1
SQL.T024 | Program Data Migration | 700 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 10
Ticket #38 | Update Job Date Time for Pending Job | 700 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #39 | Re-order Service Point checkboxs | 700 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #40 | Add second driver in Product Haul | 700 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket #42 | Add a Consultant dropdown list needs auto filter | 700 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase7.Test002 | Write Test Case_Bright | 690 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase7.Test003 | Write Test Case_Linsee | 690 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成数据库迁移工作
StartDate | 2018-02-22
EndDate | 2018-03-30
Est Time
Name | Role | Total Hours | 2018-02-22 | 2018-02-23 | 2018-02-24 | 2018-02-26 | 2018-02-27 | 2018-02-28 | 2018-03-01 | 2018-03-02 | 2018-03-05 | 2018-03-06 | 2018-03-07 | 2018-03-08 | 2018-03-09 | 2018-03-12 | 2018-03-13 | 2018-03-14 | 2018-03-15 | 2018-03-16 | 2018-03-19 | 2018-03-20 | 2018-03-21 | 2018-03-22 | 2018-03-23 | 2018-03-24 | 2018-03-26 | 2018-03-27 | 2018-03-28 | 2018-03-29 | 2018-03-30
|  |  | 43153 | 43154 | 43155 | 43157 | 43158 | 43159 | 43160 | 43161 | 43164 | 43165 | 43166 | 43167 | 43168 | 43171 | 43172 | 43173 | 43174 | 43175 | 43178 | 43179 | 43180 | 43181 | 43182 | 43183 | 43185 | 43186 | 43187 | 43188 | 43189
Ideal Burndown |  | 659 | 650 | 633 | 616 | 591 | 566 | 541 | 516 | 491 | 466 | 441 | 416 | 391 | 366 | 340 | 314 | 288 | 262 | 236 | 215 | 194 | 173 | 152 | 131 | 105 | 84 | 63 | 42 | 21 | 0
Hours consumed |  | 659 | 9 | 17 | 17 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 21 | 21 | 21 | 21 | 21 | 26 | 21 | 21 | 21 | 21 | 21
Bella.Bi |  | 45 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Linsee.Lin |  | 232 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Olivia.Ge |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bright.Liu |  | 208 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Stone.zhao |  | 174 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 3 | 3 | 3 | 3 | 3 | 8 | 3 | 3 | 3 | 3 | 3
0
Actual Time
Name | Role | Total Hours | 2018-02-22 | 2018-02-23 | 2018-02-24 | 2018-02-26 | 2018-02-27 | 2018-02-28 | 2018-03-01 | 2018-03-02 | 2018-03-05 | 2018-03-06 | 2018-03-07 | 2018-03-08 | 2018-03-09 | 2018-03-12 | 2018-03-13 | 2018-03-14 | 2018-03-15 | 2018-03-16 | 2018-03-19 | 2018-03-20 | 2018-03-21 | 2018-03-22 | 2018-03-23 | 2018-03-26 | 2018-03-27
|  |  | 43153 | 43154 | 43155 | 43157 | 43158 | 43159 | 43160 | 43161 | 43164 | 43165 | 43166 | 43167 | 43168 | 43171 | 43172 | 43173 | 43174 | 43175 | 43178 | 43179 | 43180 | 43181 | 43182 | 43185 | 43186
Ideal Burndown |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours consumed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bella.Bi |  | 0
Linsee.Lin |  | 0
Olivia.Ge |  | 0
Bright.Liu |  | 0
0
0
0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase7.P005 | Meeting-Phase 7 | 900 | 50 | 1 | All | 55
Phase7.P006 | Project management | 900 | 20 | 1 | Bella.bi | 27.5
Phase7.P007 | Requirements analysis and task document | 900 | 20 | 1 | Bella.bi | 14
Phase7.P008 | Requirements analysis and Review Code | 900 | 10 | 1 | Linsee.lin & Bright.liu | 10
Phase7.P009 | Task documentation_Bright | 900 | 20 | 1 | Bright.liu | 24.5
SQL.T001 | Discuss for migration database | 750 | 20 | 1 | All | 26
SQL.T002 | Prepare Development environment | 750 | 8 | 1 | Stone.zhao | 7
SQL.T004 | Data Type Conversion | 750 | 40 | 1 | Stone.zhao | 48.5
SQL.T005 | Aggregation Type Conversion | 750 | 40 | 1 | Stone.zhao | 22.5
SQL.T006 | Table Data Conversion | 750 | 40 | 0 | Stone.zhao | 94.5
SQL.T008 | Test SQL Script | 750 | 20 | 0 | Linsee.lin & Bright.liu | 31
SQL.T009 | Modify Dao Layer | 750 | 50 | 1 | Linsee.lin & Bright.liu | 45
SQL.T010 | Modify DaoTest | 750 | 24 | 1 | Linsee.lin & Bright.liu | 29.5
SQL.T011 | Increment ID Processing | 750 | 40 | 1 | Linsee.lin & Bright.liu | 38.5
SQL.T012 | Data type/length/precision analysis | 750 | 24 | 1 | Linsee.lin & Bright.liu | 21.5
SQL.T013 | Organize relationships between tables | 750 | 16 | 1 | Bella.bi | 23.5
SQL.T014 | Organize the foreign keys of the table | 750 | 12 | 1 | Linsee.lin & Bright.liu | 7
SQL.T015 | Test for DaoBase and Dao Layer | 750 | 30 | 1 | Linsee.lin & Bright.liu | 26
SQL.T007 | Architecteral Prototype | 750 | 24 | 1 | Linsee.lin & Bright.liu | 21
SQL.T016 | Security Data Migration | 740 | 8 | 1 | Linsee.lin & Bright.liu | 8
SQL.T017 | Reference Data Migration | 740 | 16 | 1 | Linsee.lin & Bright.liu | 27.5
SQL.T018 | CallSheet Data Migration | 740 | 24 | 1 | Linsee.lin & Bright.liu | 24
SQL.T019 | RigJob Data Migration | 740 | 4 | 0 | Linsee.lin & Bright.liu | 0.5
SQL.T020 | ProductHaul Data Migration | 720 | 4 | 1 | Linsee.lin & Bright.liu | 2
SQL.T021 | Job Data Migration | 720 | 16 | 1 | Linsee.lin & Bright.liu | 6
SQL.T022 | ServiceTicket Data Migration | 720 | 8 | 1 | 0 | 0
SQL.T023 | ServiceReport Data Migration | 700 | 24 | 1 | Linsee.lin & Bright.liu | 11
SQL.T024 | Program Data Migration | 700 | 16 | 0 | Linsee.lin & Bright.liu | 5
Ticket #38 | Update Job Date Time for Pending Job | 700 | 2 | 0 | Linsee.lin | 2
Ticket #39 | Re-order Service Point checkboxs | 700 | 2 | 1 | Linsee.lin | 2
Ticket #40 | Add second driver in Product Haul | 700 | 4 | 1 | Linsee.lin | 5
Ticket #42 | Add a Consultant dropdown list needs auto filter | 700 | 3 | 1 | Linsee.lin | 2
Phase7.Test002 | Write Test Case_Bright | 690 | 3 | 1 | Bright.liu | 1
Phase7.Test003 | Write Test Case_Linsee | 690 | 3 | 1 | Linsee.lin | 3
0 | 0 | 0 | 0
0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间