## Daily Records
ID | Name | Prioritize | Est(Hour) | 2018-04-01 | 2018-04-02 | 2018-04-03 | 2018-04-04 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | Total Hours
|  |  |  | 43191 | 43192 | 43193 | 43194 | 43198 | 43199 | 43200 | 43201 | 43202 | 43203 | 43206 | 43207 | 43208 | 43209 | 43210 | 43213 | 43214 | 43215 | 43216 | 43217 | 43218
| Ideal Burndown |  | 399 | 399 | 374 | 349 | 324 | 307 | 289 | 269 | 249 | 229 | 209 | 189 | 169 | 150 | 131 | 112 | 93 | 74 | 55 | 36 | 18 | 0 | 387
| Actual |  | 413.5 | 399 | 374.5 | 346 | 319.5 | 303 | 286.5 | 265.5 | 244.5 | 229.5 | 209 | 187.5 | 169 | 151.5 | 134 | 117.5 | 101 | 84.5 | 67 | 50 | 32.5 | 12
|  |  |  | 0 | 24.5 | 28.5 | 26.5 | 16.5 | 16.5 | 21 | 21 | 15 | 20.5 | 21.5 | 18.5 | 17.5 | 17.5 | 16.5 | 16.5 | 16.5 | 17.5 | 17 | 17.5 | 20.5 |  | Assign to | Completion Status
Phase9.P001 | Meeting-Phase 9 | 900 | 30 |  | 2 | 2 | 2 | 1.5 | 1.5 | 6 | 6 | 4.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 43 | All | 1
Phase9.P002 | Project management | 900 | 15 | 2018-04-03: 1; 2018-04-04: 2; 2018-04-12: 2; 2018-04-18: 1; 2018-04-19: 1 | 7 | Bella.bi | 1
Phase9.S001 | Analysis requirements | 900 | 24 | 2018-04-10: 3; 2018-04-11: 3; 2018-04-12: 4.5; 2018-04-13: 4; 2018-04-16: 5; 2018-04-17: 2; 2018-04-26: 0.5; 2018-04-27: 1 | 23 | Bella.bi | 1
Phase9.S002 | Review and analysis requirements_Bright | 900 | 24 | 2018-04-10: 1; 2018-04-13: 7.5; 2018-04-16: 7.5; 2018-04-18: 1 | 17 | Bright.liu | 1
Phase9.S003 | Review and analysis requirements_Linsee | 900 | 24 | 2018-04-10: 1; 2018-04-13: 7.5; 2018-04-16: 7.5 | 16 | Linsee.lin | 1
Phase9.P006 | Task documentation_Bright | 900 | 10 | 2018-04-04: 0.5; 2018-04-08: 0.5; 2018-04-09: 0.5; 2018-04-10: 1; 2018-04-11: 1; 2018-04-12: 1; 2018-04-23: 0.5 | 5 | Bright.liu | 1
Phase9.P001 | Merge the trunk code into the branch | 800 | 5 | [21 empty] | 1 | Bright.liu | 1 | bar: 2018-04-09
SQL.T001 | System Test | 750 | 32 | 2018-04-03: 16; 2018-04-04: 9.5; 2018-04-08: 14.5 | 40 | All | 1
SQL.T006 | Table Data Conversion | 750 | 24 | 2018-04-02: 7.5; 2018-04-03: 7.5; 2018-04-04: 7.5 | 22.5 | Stone.zhao | 1
SQL.T019 | RigJob Data Migration | 750 | 1.5 | 2018-04-02: 1.5 | 1.5 | Bright.liu | 1
SQL.T020 | ProductHaul Data Migration | 750 | 1.5 | 2018-04-02: 1.5 | 1.5 | Bright.liu | 1
SQL.T024 | Program Data Migration | 750 | 5 | 2018-04-02: 4.5 | 4.5 | Linsee.lin & Bright.liu | 1
SQL.T008 | Test for script | 750 | 10 | 2018-04-02: 7.5; 2018-04-03: 2; 2018-04-04: 5 | 14.5 | Linsee.lin | 1
Ticket49 | Phone Number and email is not populated properly | 700 | 6 | 2018-04-09: 1.5; 2018-04-11: 4.5; 2018-04-12: 0.5 | 6.5 | Linsee.lin | 1
Ticket102 | Display Program Number, Call Sheet Number and Job Number in Job Date tooltip | 700 | 6 | 2018-04-09: 6; 2018-04-11: 1.5; 2018-04-12: 0.5 | 8 | Linsee.lin | 1
Ticket103 | Adjust Tonnage from Rig Board | 700 | 6 | 2018-04-09: 6 | 6 | Bright.liu | 1
Ticket104 | Propagate Consultant Information while updating | 700 | 10 | 2018-04-10: 2.5; 2018-04-17: 3.5 | 6 | Linsee.lin | 1
Ticket105 | Move Rig Job from Confirmed to Scheduled status on Rig Board | 650 | 8 | 2018-04-10: 3; 2018-04-18: 5 | 8 | Bright.liu | 1
Ticket108 | Add rig name validation to create rig | 650 | 3 | 2018-04-12: 1; 2018-04-17: 2 | 3 | Bright.liu | 1
Ticket109 | Add rig name validation to update rig | 650 | 3 | 2018-04-12: 1; 2018-04-17: 2 | 3 | Bright.liu | 1
Ticket112 | Update Top Drive flag to all related job | 650 | 5.5 | 2018-04-10: 2.5; 2018-04-17: 3 | 5.5 | Linsee.lin | 1
Ticket116 | Add attachment from Rig Board to call sheet | 650 | 8 | [21 empty] | 0 |  | 0
Ticket119 | Confirmation for deactivating a rig | 650 | 6 | 2018-04-10: 1; 2018-04-17: 3.5 | 4.5 | Bright.liu | 1
Ticket123 | Update Reference data is not loaded for use | 650 | 8 | 2018-04-11: 5 | 5 | Bright.liu | 0
Ticket128 | Refactor Product Haul_Background | 630 | 15 | 2018-04-18: 1.5; 2018-04-19: 5; 2018-04-20: 4; 2018-04-23: 4; 2018-04-24: 4.5; 2018-04-26: 1; 2018-04-28: 3 | 23 | Bright.liu | 1
Ticket131 | Refactor Product Load_Background | 630 | 9 | 2018-04-19: 2.5; 2018-04-20: 3.5; 2018-04-23: 3; 2018-04-24: 3; 2018-04-25: 1; 2018-04-26: 1 | 14 | Bright.liu | 1
Ticket107 | Modify Schedule product haul page | 630 | 6 | 2018-04-26: 4; 2018-04-27: 2 | 6 | Bright.liu | 1
Ticket93 | Add a "Create Job Alert" page | 630 | 8 | 2018-04-17: 1; 2018-04-18: 1.5; 2018-04-19: 5.5; 2018-04-28: 4 | 12 | Linsee.lin | 0
Ticket120 | Align Create Rig Job logic with Create Job Alert page | 630 | 4 | 2018-04-18: 2; 2018-04-19: 2 | 4 | Linsee.lin | 1
Ticket111 | Schedule a new product haul- create product haul&product load &Unit/ThirdParty | 600 | 4 | 2018-04-25: 2; 2018-04-26: 1.5 | 3.5 | Bright.liu | 1
Ticket113 | Schedule a load to an existing haul-update product haul&create product load | 600 | 6 | 2018-04-27: 5.5; 2018-04-28: 4 | 9.5 | Bright.liu | 1
Ticket114 | Modify Reschedule a Product Haul page and right click menu | 600 | 10 | 2018-04-24: 3; 2018-04-25: 8.5 | 11.5 | Linsee.lin | 1
Ticket125 | View rig board-get job alert data_RigJobProcess | 600 | 6 | 2018-04-18: 2; 2018-04-20: 2; 2018-04-23: 0.5 | 4.5 | Linsee.lin | 1
Ticket129 | Display rigjob list | 600 | 10 | 2018-04-18: 2; 2018-04-20: 5.5; 2018-04-23: 1; 2018-04-27: 3; 2018-04-28: 2 | 13.5 | Linsee.lin | 1
Ticket118 | Reschedule a Product Haul | 550 | 8 | 2018-04-25: 1.5 | 1.5 | Bright.liu | 0
Ticket124 | Reschedule a Product load-modify to use existing haul or not-update product haul&product load | 550 | 6 | [21 empty] | 0 | Bright.liu | 0
Ticket126 | Modify Cancel a Product Haul right click menu | 550 | 6 | 2018-04-26: 3 | 3 | Linsee.lin | 1
Ticket130 | Cancel product haul | 500 | 6 | 2018-04-26: 2; 2018-04-27: 2; 2018-04-28: 2 | 6 | Linsee.lin | 1
Ticket132 | Cancel a product load-update product load&product haul | 500 | 4 | 2018-04-26: 2.5; 2018-04-27: 2.5; 2018-04-28: 0.5 | 5.5 | Linsee.lin | 1
Ticket133 | Product haul on location | 500 | 4 | 2018-04-25: 3; 2018-04-28: 2 | 5 | Bright.liu | 1
Ticket140 | Product load on location | 500 | 4 | 2018-04-28: 2 | 2 | Bright.liu | 1
Ticket127 | Rigjob Dao modify about JobAlert status | 500 | 8 | 2018-04-24: 1.5 | 1.5 | Linsee.lin | 1
Ticket121 | Update job alert | 500 | 6 | 2018-04-23: 3; 2018-04-24: 3 | 6 | Linsee.lin | 1
Ticket122 | Delete a job alert | 500 | 4 | 2018-04-23: 3 | 3 | Linsee.lin | 1
Ticket135 | Print LoadSheet | 450 | 4 | [21 empty] | 0 |  | 0
Note on G13: bin liu: Bella 3h Bright 7.5h Linsee 5.5h
Note on H13: bin liu: Bright 7h Linsee 2.5h
Note on I13: bin liu: Bright 7h Linsee 7.5h
Note on F17: bin liu: Bright
Note on B19: Bella Bi： 红色背景：与Product Haul相关的； 蓝色背景：与Job Alert相关的； 绿色背景：其他任务
Note on B27: Bella Bi: 灰色字体的任务暂时不在本迭代实现，如果有时间再做
Note on V37: Bella Bi: Linsee 7.5h Carl协助 1h

## Task Remaining
ID | Name | Prioritize | Est(Hour) | 2018-04-01 | 2018-04-02 | 2018-04-03 | 2018-04-04 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28
|  |  |  | 43191 | 43192 | 43193 | 43194 | 43198 | 43199 | 43200 | 43201 | 43202 | 43203 | 43206 | 43207 | 43208 | 43209 | 43210 | 43213 | 43214 | 43215 | 43216 | 43217 | 43218
| Ideal Burndown |  | 399 | 399 | 374 | 349 | 324 | 307 | 289 | 269 | 249 | 229 | 209 | 189 | 169 | 150 | 131 | 112 | 93 | 74 | 55 | 36 | 18 | 0
| Actual burndown |  | 413.5 | 405.5 | 369.5 | 345.5 | 330.5 | 327.5 | 322.5 | 294 | 283 | 271 | 250 | 239 | 170.5 | 147 | 133 | 119 | 97 | 82 | 65 | 37 | 25 | 12
Phase9.P001 | Meeting-Phase 9 | 900 | 30 | 30 | 28 | 26 | 25 | 24 | 22 | 20 | 18 | 16 | 14 | 12 | 9 | 9 | 9 | 8 | 7 | 6 | 4 | 3 | 1 | 0
Phase9.P002 | Project management | 900 | 15 | 15 | 15 | 14 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 4.5 | 4.5 | 4 | 4 | 4 | 3 | 2 | 1 | 1 | 0
Phase9.S001 | Analysis requirements | 900 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 17 | 14 | 10 | 5 | 10 | 5 | 5 | 5 | 4 | 2 | 1 | 1 | 1 | 0 | 0
Phase9.S002 | Review and analysis requirements_Bright | 900 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 17 | 10 | 5 | 5 | 5 | 4 | 2 | 1 | 1 | 1 | 0 | 0
Phase9.S003 | Review and analysis requirements_Linsee | 900 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 17 | 10 | 5 | 5 | 5 | 4 | 2 | 1 | 1 | 1 | 0 | 0
Phase9.P006 | Task documentation_Bright | 900 | 10 | 10 | 2 | 1 | 1 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 5 | 5 | 3 | 3 | 2 | 2 | 1 | 1 | 0
Phase9.P001 | Merge the trunk code into the branch | 800 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
SQL.T001 | System Test | 750 | 32 | 32 | 32 | 20 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SQL.T006 | Table Data Conversion | 750 | 24 | 24 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SQL.T019 | RigJob Data Migration | 750 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SQL.T020 | ProductHaul Data Migration | 750 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SQL.T024 | Program Data Migration | 750 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SQL.T008 | Test for script | 750 | 10 | 10 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket49 | Phone Number and email is not populated properly | 700 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket102 | Display Program Number, Call Sheet Number and Job Number in Job Date tooltip | 700 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket103 | Adjust Tonnage from Rig Board | 700 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket104 | Propagate Consultant Information while updating | 700 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket105 | Move Rig Job from Confirmed to Scheduled status on Rig Board | 650 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket108 | Add rig name validation to create rig | 650 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket109 | Add rig name validation to update rig | 650 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket112 | Update Top Drive flag to all related job | 650 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket116 | Add attachment from Rig Board to call sheet | 650 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket119 | Confirmation for deactivating a rig | 650 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket123 | Update Reference data is not loaded for use | 650 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket128 | Refactor Product Haul_Background | 630 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 5 | 4 | 3 | 3 | 0 | 0 | 0 | 0
Ticket131 | Refactor Product Load_Background | 630 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 5 | 4 | 2 | 2 | 1 | 0 | 0 | 0
Ticket107 | Modify Schedule product haul page | 630 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 0 | 0
Ticket93 | Add a "Create Job Alert" page | 630 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5.5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Ticket120 | Align Create Rig Job logic with Create Job Alert page | 630 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ticket111 | Schedule a new product haul- create product haul&product load &Unit/ThirdParty | 600 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 1 | 0
Ticket113 | Schedule a load to an existing haul-update product haul&create product load | 600 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 1 | 0
Ticket114 | Modify Reschedule a Product Haul page and right click menu | 600 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 0 | 0 | 0 | 0
Ticket125 | View rig board-get job alert data_RigJobProcess | 600 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Ticket129 | Display rigjob list | 600 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Ticket118 | Reschedule a Product Haul | 550 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 6
Ticket124 | Reschedule a Product load-modify to use existing haul or not-update product haul&product load | 550 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Ticket126 | Modify Cancel a Product Haul right click menu | 550 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0 | 0 | 0
Ticket130 | Cancel product haul | 500 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 1 | 0
Ticket132 | Cancel a product load-update product load&product haul | 500 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 1 | 0
Ticket133 | Product haul on location | 500 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 1 | 0
Ticket140 | Product load on location | 500 | 4 | 2018-04-25: 4; 2018-04-26: 4; 2018-04-27: 4; 2018-04-28: 0
Ticket127 | Rigjob Dao modify about JobAlert status | 500 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 1 | 0
Ticket121 | Update job alert | 500 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 0 | 0 | 0 | 0 | 0
Ticket122 | Delete a job alert | 500 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Ticket135 | Print LoadSheet | 450 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B3: Bella Bi: Idearl Burndown这列数据是资源的预估剩余时间，比如12号时间为988，表示12号燃烧完之后还剩下988小时
Note on B4: Bella Bi: Actual Burndown获取的数据是任务预计还需要的时间总和，比如13号早上开完早会，会更新12号的任务剩余时间，意思是12号结束后还需要多少时间。BurndownChart中未到时间的显示为=NA()，这样Chart中就不会显示出来。

## Resources
SPRINT |  | 本次迭代主要完成第9期Job Alert、Product Hual的需求
StartDate | 2018-04-02
EndDate | 2018-04-28
Est Time
Name | Role | Total Hours | 2018-04-02 | 2018-04-03 | 2018-04-04 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28
|  |  | 43192 | 43193 | 43194 | 43198 | 43199 | 43200 | 43201 | 43202 | 43203 | 43206 | 43207 | 43208 | 43209 | 43210 | 43213 | 43214 | 43215 | 43216 | 43217 | 43218
Ideal Burndown |  | 399 | 374 | 349 | 324 | 307 | 289 | 269 | 249 | 229 | 209 | 189 | 169 | 150 | 131 | 112 | 93 | 74 | 55 | 36 | 18 | 0
Hours consumed |  | 399 | 25 | 25 | 25 | 17 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 18 | 18
Bella.Bi |  | 55 | 1 | 1 | 1 | 1 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2
Linsee.Lin |  | 160 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Olivia.Ge |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bright.Liu |  | 160 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Stone.zhao |  | 24 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Actual Time
Name | Role | Total Hours | 2018-04-02 | 2018-04-03 | 2018-04-04 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28
|  |  | 43192 | 43193 | 43194 | 43198 | 43199 | 43200 | 43201 | 43202 | 43203 | 43206 | 43207 | 43208 | 43209 | 43210 | 43213 | 43214 | 43215 | 43216 | 43217 | 43218
Ideal Burndown |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours consumed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bella.Bi |  | 0
Linsee.Lin |  | 0
Olivia.Ge |  | 0
Bright.Liu |  | 0
0
0
0

## Sprint Backlog
ID | Name | Prioritize | Est(Hour) | Completion Status | Assign To | Actual(Hour)
Phase9.P001 | Meeting-Phase 9 | 900 | 30 | 1 | All | 43
Phase9.P002 | Project management | 900 | 15 | 1 | Bella.bi | 7
Phase9.S001 | Analysis requirements | 900 | 24 | 1 | Bella.bi | 23
Phase9.S002 | Review and analysis requirements_Bright | 900 | 24 | 1 | Bright.liu | 17
Phase9.S003 | Review and analysis requirements_Linsee | 900 | 24 | 1 | Linsee.lin | 16
Phase9.P006 | Task documentation_Bright | 900 | 10 | 1 | Bright.liu | 5
Phase9.P001 | Merge the trunk code into the branch | 800 | 5 | 1 | Bright.liu | 1
SQL.T001 | System Test | 750 | 32 | 1 | All | 40
SQL.T006 | Table Data Conversion | 750 | 24 | 1 | Stone.zhao | 22.5
SQL.T019 | RigJob Data Migration | 750 | 1.5 | 1 | Bright.liu | 1.5
SQL.T020 | ProductHaul Data Migration | 750 | 1.5 | 1 | Bright.liu | 1.5
SQL.T024 | Program Data Migration | 750 | 5 | 1 | Linsee.lin & Bright.liu | 4.5
SQL.T008 | Test for script | 750 | 10 | 1 | Linsee.lin | 14.5
Ticket49 | Phone Number and email is not populated properly | 700 | 6 | 1 | Linsee.lin | 6.5
Ticket102 | Display Program Number, Call Sheet Number and Job Number in Job Date tooltip | 700 | 6 | 1 | Linsee.lin | 8
Ticket103 | Adjust Tonnage from Rig Board | 700 | 6 | 1 | Bright.liu | 6
Ticket104 | Propagate Consultant Information while updating | 700 | 10 | 1 | Linsee.lin | 6
Ticket105 | Move Rig Job from Confirmed to Scheduled status on Rig Board | 650 | 8 | 1 | Bright.liu | 8
Ticket108 | Add rig name validation to create rig | 650 | 3 | 1 | Bright.liu | 3
Ticket109 | Add rig name validation to update rig | 650 | 3 | 1 | Bright.liu | 3
Ticket112 | Update Top Drive flag to all related job | 650 | 5.5 | 1 | Linsee.lin | 5.5
Ticket116 | Add attachment from Rig Board to call sheet | 650 | 8 | 0 | 0 | 0
Ticket119 | Confirmation for deactivating a rig | 650 | 6 | 1 | Bright.liu | 4.5
Ticket123 | Update Reference data is not loaded for use | 650 | 8 | 0 | Bright.liu | 5
Ticket128 | Refactor Product Haul_Background | 630 | 15 | 1 | Bright.liu | 23
Ticket131 | Refactor Product Load_Background | 630 | 9 | 1 | Bright.liu | 14
Ticket107 | Modify Schedule product haul page | 630 | 6 | 1 | Bright.liu | 6
Ticket93 | Add a "Create Job Alert" page | 630 | 8 | 0 | Linsee.lin | 12
Ticket120 | Align Create Rig Job logic with Create Job Alert page | 630 | 4 | 1 | Linsee.lin | 4
Ticket111 | Schedule a new product haul- create product haul&product load &Unit/ThirdParty | 600 | 4 | 1 | Bright.liu | 3.5
Ticket113 | Schedule a load to an existing haul-update product haul&create product load | 600 | 6 | 1 | Bright.liu | 9.5
Ticket114 | Modify Reschedule a Product Haul page and right click menu | 600 | 10 | 1 | Linsee.lin | 11.5
Ticket125 | View rig board-get job alert data_RigJobProcess | 600 | 6 | 1 | Linsee.lin | 4.5
Ticket129 | Display rigjob list | 600 | 10 | 1 | Linsee.lin | 13.5
Ticket118 | Reschedule a Product Haul | 550 | 8 | 0 | Bright.liu | 1.5
Ticket124 | Reschedule a Product load-modify to use existing haul or not-update product haul&product load | 550 | 6 | 0 | Bright.liu | 0
Ticket126 | Modify Cancel a Product Haul right click menu | 550 | 6 | 1 | Linsee.lin | 3
Ticket130 | Cancel product haul | 500 | 6 | 1 | Linsee.lin | 6
Ticket132 | Cancel a product load-update product load&product haul | 500 | 4 | 1 | Linsee.lin | 5.5
Ticket133 | Product haul on location | 500 | 4 | 1 | Bright.liu | 5
Ticket127 | Rigjob Dao modify about JobAlert status | 500 | 8 | 1 | Linsee.lin | 2
Ticket121 | Update job alert | 500 | 6 | 1 | Linsee.lin | 1.5
Ticket122 | Delete a job alert | 500 | 4 | 1 | Linsee.lin | 6
Ticket135 | Print LoadSheet | 450 | 4 | 0 | 0 | 3
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 |  | 0 | 0
Note on A1: Ying Li: 与ProductBacklogID保持一致
Note on B1: Ying Li: 与ProductBacklog名称保持一致
Note on C1: Ying Li: 与ProductBacklog优先级保持一致
Note on D1: Ying Li: 与ProductBacklog保持一致
Note on E1: Ying Li: 1已完成 0未完成
Note on F1: Ying Li: 任务负责人
Note on G1: Ying Li: 任务投入总时间