## Analysis of results(UserCase)
| UseCase Name | Est(Hour) | Actual(Hour) | StartDate | EndDate |  | Est(Hour) | Actual(Hour)
Elaboration | Review code | 0 | 122.5 | 2015-11-02 | 2015-12-10 | Elaboration | 40 | 173.5
Elaboration | Architecture Prepare | 40 | 51 | 2015-11-09 | 2015-11-20 | Construction | 408 | 908.3
Construction | Create Program | 64 | 183.2 | 2015-11-19 | 2016-01-08 | Transition | 80 | 146.9
Construction | Attach Files to Program | 64 | 13 | 2015-12-07 | 2015-12-23 | Total | 528 | 1228.7
Construction | Clone Program | 64 | 47 | 2015-12-01 | 2015-12-22
Construction | Import Program from JDT | 64 | 133.6 | 2015-12-04 | 2015-12-26
Construction | Search Program | 64 | 30 | 2015-12-01 | 2015-12-29
Construction | Update Program | 64 | 54 | 2015-12-01 | 2015-12-23
Construction | Implement MainForm and Navigator | 8 | 6 | 2015-11-16 | 2015-11-20
Construction | Implement Navigator and high level View and Presenter Interfaces and Mocks | 16 | 17 | 2015-11-17 | 2015-11-20
Construction | Environment to build | 0 | 42 | 2016-11-02 | 2015-12-24
Construction | Print Program | 0 | 2.5 | 2015-12-03 | 2015-12-03
Construction | Refactor | 0 | 350 | 2015-12-01 | 2016-01-12
Construction | Svn Branches Merge | 0 | 23 | 2015-11-02 | 2015-12-03
Transition | CruiseControl.net | 0 | 46.5 | 2015-12-30 | 2016-01-12
Transition | Integration usecase | 80 | 159.4 | 2015-12-28 | 2016-01-19
| Total | 528 | 1280.7

## 2015-11-9
ID | Name | Prioritize | Est(Hour) | Completion Status | StartDate | EndDate | Assign To | Actual(Hour) | Remark
Elaboration - Architecture Prepare | Import JDT to Program Architecture Spike | 10000 | 40 | 1 | 2015-11-09 | 2015-11-20 | Bela Zhao | 51
Implement Program Client | Implement MainForm and Navigator | 9100 | 8 | 1 | 2015-11-16 | 2015-11-20 | Randy Ling | 6
Implement Program Client | Implement Navigator and high level View and Presenter Interfaces and Mocks | 9000 | 16 | 1 | 2015-11-17 | 2015-11-20 | Randy Ling | 17
Implement Program Client | Create Program | 8900 | 64 | 0 | 2015-11-19 |  | Randy Ling | 56.5
0 | Refactor-Sanjel.Common.WinUI | 8501 | 0 | 1 | 2015-11-23 | 2015-11-23 | Bela Zhao | 4
0 | Refactor-Sanjel.Common.UIProcess | 8502 | 0 | 1 | 2015-11-23 | 2015-11-23 | Bela Zhao | 8
0 | Refactor-Sanjel.Common.MockView | 8503 | 0 | 1 | 2015-11-23 | 2015-11-24 | Serena Li | 9
0 | Environment to build | 8504 | 0 | 1 | 2015-11-02 | 2015-11-09 | Bela Zhao | 34
0 | Review code | 8505 | 0 | 1 | 2015-11-02 | 2015-11-20 | Bela Zhao | 74
0 | Svn Branches Merge | 8506 | 0 | 1 | 2015-11-12 | 2015-11-25 | Serena Li | 13

## 2015-11-30
ID | Name | Prioritize | Est(Hour) | Completion Status | StartDate | EndDate | Assign To | Actual(Hour) | Remark
Implement Program Client | Create Program | 9700 | 64 | 0 | 2015-11-19 |  | Randy Ling | 115.7
Implement Program Client | Update Program | 9600 | 64 | 1 | 2015-12-01 | 2015-12-23 | Bela Zhao | 54
Implement Program Client | Attach Files to Program | 9500 | 64 | 1 | 2015-12-07 | 2015-12-23 | Serena Li | 13
Implement Program Client | Import Program from JDT | 9400 | 64 | 0 | 2016-12-04 |  | Serena Li | 58.5
Implement Program Client | Search Program | 9300 | 64 | 0 | 2015-12-01 |  | Serena Li | 26
Implement Program Client | Clone Program | 9200 | 64 | 1 | 2015-12-01 | 2015-12-22 | Serena Li | 47
0 | Svn Branches Merge | 0 | 64 | 1 | 2016-12-02 | 2016-12-03 | Serena Li | 10
0 | Review code | 0 | 64 | 1 | 2015-11-02 | 2015-12-10 | Olivia.Ge | 48.5
0 | Refactor-Sanjel.Common.WinUI | 0 | 64 | 1 | 2015-12-01 | 2016-12-24 | Jimmy.Liu | 15
0 | Refactor-Sanjel.Common.UIProcess | 0 | 64 | 1 | 2015-12-02 | 2016-12-24 | Serena Li | 39
0 | Refactor-Sanjel.Common.MockView | 0 | 64 | 1 | 2015-12-03 | 2016-12-24 | Bella.Bi | 2
0 | Environment to build | 0 | 64 | 1 | 2015-12-02 | 2015-12-24 | Jimmy.Liu | 8
0 | Print Program | 0 | 64 | 1 | 2015-12-03 | 2015-12-03 | Bela Zhao | 2.5
0 | Refactor-EServiceTestData | 0 | 64 | 0 | 2015-12-04 |  | Bella.Bi | 201.5

## 2015-12-28
ID | Name | Prioritize | Est(Hour) | Completion Status | StartDate | EndDate | Assign To | Actual(Hour)
Implement Program Client | Create Program | 9700 | 0 | 1 | 2015-11-19 | 2016-01-08 | Randy Ling | 8
Implement Program Client | Search Program | 9300 | 0 | 1 | 2015-12-01 | 2015-12-29 | Randy Ling | 4
Implement Program Client | Clone Program | 9200 | 0 | 1 | 2015-12-01 | 2016-12-22 | Serena Li | 0
0 | Refactor-EServiceTestData | 0 | 0 | 0 | 2015-12-05 |  | Bella.Bi | 68.5
US001 | Import JDT file to JDT Program | 1000 | 7 | 0 | 2015-12-28 |  | Bela Zhao | 46
Test001 | Test.Prototype | 950 | 2 | 1 | 2015-12-28 | 2016-12-28 | Randy Ling | 4.9
US002 | JDT Program to program | 900 | 12 | 1 | 2015-12-28 | 2015-12-31 | Bela Zhao | 8
US003 | Program to View | 800 | 1 | 1 | 2015-12-28 | 2015-12-29 | Randy Ling | 1.5
US004 | GetReferenceDataFromProgarm UI | 750 | 5 | 1 | 2015-12-28 | 2015-12-29 | Randy Ling | 1.6
US005 | ReadGroupSetionFromExcelToJdtGroupSetion | 700 | 0 | 1 | 2015-12-29 | 2015-12-29 | Bela Zhao | 1
US006 | ReadJdtPriceLineItemSectionFromExcelToJdtGroupSetion | 650 | 0 | 1 | 2015-12-29 | 2015-12-29 | Bela Zhao | 1
US007 | RefactorReaderHeader(Enter Number of Well(s)) | 0 | 0 | 1 | 2015-12-29 | 2015-12-29 | Bela Zhao | 5
US008 | RefactorReaderValue(Method) | 0 | 3 | 1 | 2015-12-31 | 2016-12-31 | Bela Zhao | 4
Test002 | Test.ExcelWorkBook | 0 | 0 | 1 | 2015-12-31 | 2016-12-31 | Bela Zhao | 0
Test003 | Test.ProgramExcelWorkBook | 0 | 0 | 0 |  |  |  | 0
Test004 | Test.ClassDescriptor | 0 | 0 | 0 |  |  |  | 0
Test005 | Test.PropertyDescriptor | 0 | 0 | 0 |  |  |  | 0
Test006 | Integration usecase | 0 | 0 | 0 | 2015-12-28 |  | Serena Li | 95.5
0 | CruiseControl.net | 0 | 0 | 0 | 2015-12-30 |  | Jimmy.Liu | 39.5
0 | Add JobData | 0 | 0 | 0 | 2016-01-07 | 2016-01-08 | Randy Ling | 3

## 2016-01-12
ID | Name | Prioritize | Est(Hour) | Completion Status | StartDate | EndDate | Assign To | Actual(Hour)
0 | Refactor-EServiceTestData | 0 | 0 | 1 | 2015-12-05 | 2016-01-12 | Bella.Bi | 3
US001 | Import JDT file to JDT Program | 1000 | 0 | 1 | 2015-12-28 | 2016-01-12 | Bela Zhao | 7
Test003 | Test.ProgramExcelWorkBook | 0 | 0 | 1 | 2016-01-13 | 2016-01-15 | Bela Zhao | 14
Test004 | Test.ClassDescriptor | 0 | 5 | 1 | 2016-01-18 | 2016-01-18 | Bela Zhao | 2
Test005 | Test.PropertyDescriptor | 0 | 5 | 0 | 2016-01-18 |  | Bela Zhao | 10
Test006 | Integration usecase | 0 | 0 | 1 | 2015-12-28 | 2016-01-15 | Serena Li | 30.5
0 | CruiseControl.net | 0 | 0 | 1 | 2015-12-30 | 2016-01-12 | Jimmy.Liu | 7
73.5

## Summary
ID | Name | Prioritize | Est(Hour) | Completion Status | StartDate | EndDate | Assign To | Actual(Hour) | Remark
Architecture Prepare | Import JDT to Program Architecture Spike | 10000 | 40 | 1 | 2015-11-09 | 2015-11-20 | Bela Zhao | 51
Attach Files to Program | Attach Files to Program | 9500 | 64 | 1 | 2015-12-07 | 2015-12-23 | Serena Li | 13
Clone Program | Clone Program | 9200 | 64 | 1 | 2015-12-01 | 2015-12-22 | Serena Li | 47 | 47
Clone Program | Clone Program | 9200 | 0 | 1 | 2015-12-01 | 2016-12-22 | Serena Li | 0
Create Program | Add JobData | 0 | 0 | 0 | 2016-01-07 | 2016-01-08 | Randy Ling | 3 | 183.2
Create Program | Create Program | 8900 | 64 | 0 | 2015-11-19 |  | Randy Ling | 56.5
Create Program | Create Program | 9700 | 64 | 0 | 2015-11-19 |  | Randy Ling | 115.7
Create Program | Create Program | 9700 | 0 | 1 | 2015-11-19 | 2016-01-08 | Randy Ling | 8
CruiseControl.net | CruiseControl.net | 0 | 0 | 0 | 2015-12-30 |  | Jimmy.Liu | 39.5 | 46.5
CruiseControl.net | CruiseControl.net | 0 | 0 | 1 | 2015-12-30 | 2016-01-12 | Jimmy.Liu | 7
Environment to build | Environment to build | 8504 | 0 | 1 | 2015-11-02 | 2015-11-09 | Bela Zhao | 34 | 42
Environment to build | Environment to build | 0 | 64 | 1 | 2015-12-02 | 2015-12-24 | Jimmy.Liu | 8
Implement MainForm and Navigator | Implement MainForm and Navigator | 9100 | 8 | 1 | 2015-11-16 | 2015-11-20 | Randy Ling | 6 | 6
Implement Navigator and high level View and Presenter Interfaces and Mocks | Implement Navigator and high level View and Presenter Interfaces and Mocks | 9000 | 16 | 1 | 2015-11-17 | 2015-11-20 | Randy Ling | 17 | 17
Import Program from JDT | GetReferenceDataFromProgarm UI | 750 | 5 | 1 | 2015-12-28 | 2015-12-29 | Randy Ling | 1.6 | 133.6
Import Program from JDT | Import JDT file to JDT Program | 1000 | 7 | 0 | 2015-12-28 |  | Bela Zhao | 46
Import Program from JDT | Import JDT file to JDT Program | 1000 | 0 | 1 | 2015-12-28 | 2016-01-12 | Bela Zhao | 7
Import Program from JDT | Import Program from JDT | 9400 | 64 | 0 | 2016-12-04 |  | Serena Li | 58.5
Import Program from JDT | JDT Program to program | 900 | 12 | 1 | 2015-12-28 | 2015-12-31 | Bela Zhao | 8
Import Program from JDT | Program to View | 800 | 1 | 1 | 2015-12-28 | 2015-12-29 | Randy Ling | 1.5
Import Program from JDT | ReadGroupSetionFromExcelToJdtGroupSetion | 700 | 0 | 1 | 2015-12-29 | 2015-12-29 | Bela Zhao | 1
Import Program from JDT | ReadJdtPriceLineItemSectionFromExcelToJdtGroupSetion | 650 | 0 | 1 | 2015-12-29 | 2015-12-29 | Bela Zhao | 1
Import Program from JDT | RefactorReaderHeader(Enter Number of Well(s)) | 0 | 0 | 1 | 2015-12-29 | 2015-12-29 | Bela Zhao | 5
Import Program from JDT | RefactorReaderValue(Method) | 0 | 3 | 1 | 2015-12-31 | 2016-12-31 | Bela Zhao | 4
Integration usecase | Integration usecase | 0 | 0 | 0 | 2015-12-28 |  | Serena Li | 95.5 | 159.4
Integration usecase | Integration usecase | 0 | 0 | 1 | 2015-12-28 | 2016-01-15 | Serena Li | 30.5
Integration usecase | Test.ClassDescriptor | 0 | 0 | 0 |  |  |  | 0
Integration usecase | Test.ClassDescriptor | 0 | 5 | 1 | 2016-01-18 | 2016-01-18 | Bela Zhao | 2
Integration usecase | Test.ExcelWorkBook | 0 | 0 | 1 | 2015-12-31 | 2016-12-31 | Bela Zhao | 0
Integration usecase | Test.ProgramExcelWorkBook | 0 | 0 | 0 |  |  |  | 0
Integration usecase | Test.ProgramExcelWorkBook | 0 | 0 | 1 | 2016-01-13 | 2016-01-15 | Bela Zhao | 14
Integration usecase | Test.PropertyDescriptor | 0 | 0 | 0 |  |  |  | 0
Integration usecase | Test.PropertyDescriptor | 0 | 5 | 0 | 2016-01-18 |  | Bela Zhao | 10
Integration usecase | Test.Prototype | 950 | 2 | 1 | 2015-12-28 | 2016-12-28 | Randy Ling | 4.9
Print Program | Print Program | 0 | 64 | 1 | 2015-12-03 | 2015-12-03 | Bela Zhao | 2.5 | 350
Refactor | Refactor-EServiceTestData | 0 | 64 | 0 | 2015-12-04 |  | Bella.Bi | 201.5
Refactor | Refactor-EServiceTestData | 0 | 0 | 0 | 2015-12-05 |  | Bella.Bi | 68.5
Refactor | Refactor-EServiceTestData | 0 | 0 | 1 | 2015-12-05 | 2016-01-12 | Bella.Bi | 3
Refactor | Refactor-Sanjel.Common.MockView | 8503 | 0 | 1 | 2015-11-23 | 2015-11-24 | Serena Li | 9
Refactor | Refactor-Sanjel.Common.MockView | 0 | 64 | 1 | 2015-12-03 | 2016-12-24 | Bella.Bi | 2
Refactor | Refactor-Sanjel.Common.UIProcess | 8502 | 0 | 1 | 2015-11-23 | 2015-11-23 | Bela Zhao | 8
Refactor | Refactor-Sanjel.Common.UIProcess | 0 | 64 | 1 | 2015-12-02 | 2016-12-24 | Serena Li | 39
Refactor | Refactor-Sanjel.Common.WinUI | 8501 | 0 | 1 | 2015-11-23 | 2015-11-23 | Bela Zhao | 4
Refactor | Refactor-Sanjel.Common.WinUI | 0 | 64 | 1 | 2015-12-01 | 2016-12-24 | Jimmy.Liu | 15
Review code | Review code | 8505 | 0 | 1 | 2015-11-02 | 2015-11-20 | Bela Zhao | 74 | 122.5
Review code | Review code | 0 | 64 | 1 | 2015-11-02 | 2015-12-10 | Olivia.Ge | 48.5
Search Program | Search Program | 9300 | 64 | 0 | 2015-12-01 |  | Serena Li | 26 | 30
Search Program | Search Program | 9300 | 0 | 1 | 2015-12-01 | 2015-12-29 | Randy Ling | 4
Svn Branches Merge | Svn Branches Merge | 8506 | 0 | 1 | 2015-11-12 | 2015-11-25 | Serena Li | 13 | 23
Svn Branches Merge | Svn Branches Merge | 0 | 64 | 1 | 2016-12-02 | 2016-12-03 | Serena Li | 10
Update Program | Update Program | 9600 | 64 | 1 | 2015-12-01 | 2015-12-23 | Bela Zhao | 54