## 项目日程安排
在此工作表中创建项目日程安排。 在单元格 B1 中输入此项目的标题。 有关如何使用此工作表（包括屏幕阅读器的说明）以及此工作簿作者的信息包含在“关于”工作表中。 继续向下浏览 A 列，获取进一步指示。 | MetaShare Project Statement - March 2024
在单元格 B3 中输入项目主管的姓名。在单元格 E3 中输入项目开始日期。项目开始：标签位于单元格 C3 中。 | Start Date | 2024-03-05 | Total EST(hour) | 578 | Project Start |  | 2024-03-12
单元格 E4 中的显示周数表示单元格 I4 中项目日程安排内显示的起始周数。项目开始日期视为第 1 周。要更改显示周数，只需单元格 E4 中输入新的周数。 从单元格 E4 的显示周数开始，每周的开始日期从单元格 I4 开始并且说自动计算得出的。在该视图中，从单元格 I4 到单元格 BF4 共有 8 周的时间。 请勿修改这些单元格。 显示周数：标签位于单元格 C4 中。 | End Date | 2024-03-25 | Available Resource(hour) | 640 | 显示周数： |  | 1 |  |  |  | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [5 empty] | 2024-06-09 | [5 empty] | 2024-06-15 | [5 empty] | 2024-06-21 | [5 empty] | 2024-06-27 | [5 empty] | 2024-07-03 | [5 empty] | 2024-07-09 | [5 empty] | 2024-07-15 | [5 empty] | 2024-07-21 | [5 empty] | 2024-07-27 | [5 empty] | 2024-08-02 | [5 empty] | 2024-08-08 | [5 empty] | 2024-08-14 | [5 empty] | 2024-08-20 | [5 empty] | 2024-08-26 | [5 empty] | 2024-09-01 | [5 empty] | 2024-09-07 | [5 empty] | 2024-09-13 | [5 empty] | 2024-09-19 | [5 empty] | 2024-09-25 | [5 empty] | 2024-10-01 | [5 empty] | 2024-10-07 | [5 empty] | 2024-10-13 | [5 empty] | 2024-10-19 | [5 empty] | 2024-10-25 | [5 empty] | 2024-10-31 | [5 empty] | 2024-11-06 | [5 empty] | 2024-11-12 | [5 empty] | 2024-11-18 | [5 empty] | 2024-11-24 | [5 empty] | 2024-11-30 | [5 empty] | 2024-12-06 | [5 empty] | 2024-12-12 | [5 empty] | 2024-12-18 | [5 empty] | 2024-12-24 | [5 empty] | 2024-12-30 | [5 empty] | 2025-01-05 | [5 empty] | 2025-01-11 | [5 empty] | 2025-01-17 | [5 empty] | 2025-01-23 | [5 empty] | 2025-01-29 | [5 empty] | 2025-02-04 | [5 empty] | 2025-02-10
单元格 I5 到 BL5 包含每个日期单元格上方单元格块中表示的星期的日期数字并且是自动计算得出的。 请勿修改这些单元格。 今天的日期带有红色（十六进制 #AD3815）轮廓（从第 5 行中显示今天日期的列及至项目日程安排结尾的该列）。 | time axis 2024-03-11 to 2025-02-15
此行包含其后面的项目日程安排的标题。 从 B6 浏览到 BL6 以获取内容。该标题上方日期一周中每一天的首字母，从单元格 I6 开始，直到单元格 BL6。 所有项目日程表图表都是根据输入的开始和结束日期使用条件格式自动生成的。 从单元格 I7 开始的列 I 之后，请勿修改列内单元格中的内容。 | Number | Task |  | Assign to | Est | 进度 | Start Date | End Date | Pre-Task | Days | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六
请勿删除此行。隐藏了此行，以保留用于突出显示项目日程安排中当天的公式。
单元格 B8 包含第 1 阶段示例标题。 在单元格 B8 中输入新标题。 如果适用于你的项目，请在单元格 C8 中输入名称以指定阶段。 如果适用于你的项目，请在单元格 D8 中输入整个阶段的进度。 如果适用于你的项目，请在单元格 E8 和 F8 中输入整个阶段的开始和结束日期。 甘特图将根据输入的进度自动填充适当的日期和着色。 要仅从任务中删除阶段和工作，只需删除此行即可。 | MetaShare Project Statement - March 2024 |  |  |  | 578
|  | Project management |  | LiYing | 48 | 30% | 2024-03-05 | 2024-03-25
|  | Requirements analysis and clarification |  | SunTing | 40 | 30% | 2024-03-05 | 2024-03-25
| 1 | eService & eProgram
| 1.1 | Excess import - eProgram#164 |  | TongTao | 24 | 100% | 2024-03-05 | 2024-03-07 |  | 3
| 1.2 | MPC |  | TongTao | 0 | 100%
| 1.3 | Supervisor - Prevent removal of units in eService |  |  | 0 | 100%
| 1.3.1 | Prevent removal of units in eService |  |  | 0 | 100%
| 1.3.2 | With the integration of product hauls, this cannot be removed from eService job package. |  |  | 0 | 100%
| 1.3.3 | Units can be modified, but not removed when a product haul. This is the desired behavior. |  |  | 0 | 100%
| 1.4 | Bug Fix |  |  | 0 | 100%
| 1.4.1 | Replace expired client secret value in the eService MailUtility#34 |  |  | 0 | 100%
| 1.4.2 | POR pricing distribution bug fix |  |  | 0 | 100%
| 1.5 | Test Case & Test |  | SunTing | 32 | 10% | 2024-03-07 | 2024-03-11 |  | 5
| 1.6 | eProgram 6.12 release |  |  | 0 |  | 2024-03-15 | 2024-03-15 |  | 1
| 1.7 | eService 6.12 release |  |  | 0 |  | 2024-03-15 | 2024-03-15 |  | 1
| 2 | eService Express
| 2.2 | Add 4 Inch Coriolis Rate to WITS setting#161 |  |  | 32 | 100% | 2024-03-08 | 2024-03-12 |  | 5
| 2.3 | Bug Fix
| 2.3.1 | WITS setting issue working for two trucks |  | TongTao | 8 | 100% | 2024-03-08 | 2024-03-08 |  | 1
| 2.3.2 | Post Job page header is broken.#167 |  | TongTao | 8 | 100% | 2024-03-08 | 2024-03-08 |  | 1
| 2.3.3 | Chart print paging issue#170 |  | TongTao | 16 | 0% | 2024-03-12 | 2024-03-13
| 2.4 | Messaging Library Upgrade - Post Job Data#165
| 2.4.1 | Update eService Express for release |  | ZhangYuan | 0 | 0%
| 2.4.2 | MQTT Server deployment |  | Miguel | 56 | 70% | 2024-03-01
| 2.4.3 | Post Job Data server end deployment |  | ZhangYuan | 0 | 0%
| 2.1 | MQTT installation packing and support Sanjel deployment and testing |  | ZhangYuan | 16 | 0%
| 2.5 | Test Case & Test |  | SunTing | 32 | 50% | 2024-03-08 | 2024-03-12 |  | 5
| 2.6 | eService Express 1.2.2.31 Field Trial |  |  |  |  | 2024-03-18 | 2024-03-18 |  | 1
| 3 | eService Online |  |  |  | 100% | 2024-03-06 | 2024-03-11 |  | 6
| 3.1 | Bulk Plant Board: Bulker not shown after it is loaded#308 |  | ZhangYuan | 24 | 100% | 2024-03-06 | 2024-03-08 |  | 3
| 3.2 | Test |  | SunTing | 16 | 100% | 2024-03-08 | 2024-03-11 |  | 4
第 10 行到第 13 行重复第 9 行的模式。 请对此工作表中的所有任务行重复单元格 A9 中的指令。覆盖任何示例数据。 另一个阶段的示例从单元格 A14 开始。 继续在单元格 A10 到 A13 中输入任务或转到单元格 A14 了解详细信息。 | 3.3 | eServiceOnline 6.12 release |  |  |  |  | 2024-03-12 | 2024-03-12 |  | 1
| 4 | Digital Resource Board (DRB) – Job board
| 4.1 | Requirements analysis and clarification |  | SunTing | 16 | 0%
| 4.2 | Producthaul not show up on the job board
| 4.2.1 | Creating a back haul |  | ZhangYuan | 16 | 0%
| 4.2.2 | Creating a haul from a program |  | ZhangYuan | 16 | 0%
| 4.3 | Job Board Bulker Assignment Update
| 4.3.1 | Use Client Short Name |  | ZhangYuan | 8 | 0%
| 4.3.2 | Add Icons for haul type |  | ZhangYuan | 16 | 0%
| 4.3.3 | Look of the information on the Job Board |  | ZhangYuan | 16 | 0%
| 4.4 | Test |  | SunTing | 16 | 0%
| 4.5 | Release
|  | eService Framework Upgrade |  | Miguel | 0 | 0%
|  | Blend Library |  | Miguel | 0 | 0%
|  | Blend Signature |  | Miguel | 0 | 0%
|  | Dry blend signature: generate a hash string from 1T breakdown of preblend ingredients. |  | Miguel | 0 | 0%
|  | Full blend signature: generate a hash string from 1 breakdown of all ingredients. |  | Miguel | 0 | 0%
|  | The purpose for this signature is to compare the blends by ingredients not by other artifacts it is attached. |  | Miguel | 0 | 0%
|  | Well Library |  | Miguel | 0 | 0%
|  | Excess Calculation |  | Miguel | 0 | 0%
|  | There are 2 excesses that are desired |  | Miguel | 0 | 0%
|  | Pumped Excess |  | Miguel | 0 | 0%
|  | Required Excess |  | Miguel | 0 | 0%
|  | The above calculations will use eService as the data source. This will provide details of the excess per job and add this data to the data warehouse so that this information is available to the BI tool. |  | Miguel | 0 | 0%
|  | The calculation would also like to be used from the job design template through API, or other connection, from the excel template. |  | Miguel | 0 | 0%
|  | Application Integration |  | Miguel | 0 | 0%
|  | Messaging Library |  | Miguel | 0 | 0%
|  | PLC data real-time transmission |  | Miguel | 0 | 0%
Migration Upgrade Project
PrintService
|  | PrintingService refactor 2.006 Print configuration file problem modification（add ImageResourcesPath argument） |  | ZhaoBaoHong | 16 | 100% | 2024-03-04 | 2024-03-06
|  | PrintingService refactor 2.007 bug-ReportLayout构建Model（TextBoxControl，TextFieldControl构建Model错误） |  | ZhaoBaoHong | 8 | 60% | 2024-03-05 | 2024-03-05
|  | PrintingService refactor 2.003.008 TextBoxControl (Incorrect height calculation) |  | ZhaoBaoHong | 32 | 10% | 2024-03-08 | 2024-03-15
|  | Write explanatory document |  | ZhaoBaoHong | 16 | 0% | 2024-03-19 | 2024-03-20
|  | PrintingService refactor 2.008 bug- page number error（TocSection） |  | ZhaoBaoHong | 6 | 0% | 2024-03-18 | 2024-03-18
Application upgrade
|  | Old component replacement-Express |  | TongTao | 8 | 0% | 2024-03-14 | 2024-03-14
|  | Old component replacement-Eservice |  | TongTao | 12 | 0% | 2024-03-15 | 2024-03-15
|  | Old component replacement-EProgram |  | TongTao | 8 | 0% | 2024-03-18 | 2024-03-18
|  | Print function verification in the application |  | SunTing | 16 | 0%
此行标记项目日程安排的结尾。请勿在此行中输入任何内容。 在此行上方插入新行，以继续构建项目日程安排。 | 在此行上方插入新行

## Sheet1
160
4
640

## 关于
关于此模板
此模板提供了一种创建甘特图的简单方法，可帮助直观呈现和跟踪项目。只需输入任务以及开始和结束日期 - 无需公式。甘特图中的条形表示任务的持续时间，并且使用条件格式显示。通过插入新行插入新任务。