## SubSystems
SubSystems
ID | Name | Description
SY01 | Win Form Frontend | Win Form前台
SY02 | Express Frontend | Express前台
SY03 | Win Form Backend | Win Form后台
SY04 | Express Backend | Express后台
SY05 | eService Online Frontend | Online前台
SY06 | eService Online Backend | Online后台

## SY01-Win Form Frontend
System | ID | Name | Importance | Status | Description | Note | Part
SY01 | UC001 | Code refactoring to separate framework | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC002 | Refactor Program Import function import new template | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC003 | Change Import template | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC004 | Import Product information from spreadsheet to Program | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC005 | Well information import from spreadsheet | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC006 | Create Call Sheet from Program | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC007 | Create multiple call sheet from a multiple job type program | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC008 | Update Print Service Ticket from local | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC009 | Validation for Importing excel | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC010 | Update ProgramID | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC011 | Refining billing info section calculation | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC012 | Update GroupedLineItemControl | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC013 | Micellenous fixes | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC014 | Refactor for Excel importing | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC015 | Change for Create Program | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC016 | Re-organize the program treeview | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC017 | Add Targeted Formation | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC018 | Change for Call Information in CallSheet | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC019 | Create Call Sheet from Program | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC020 | Create Job Package from Call Sheet | 1902-09-26 | Completed |  | 历史数据，前三期已完成 | Part 1
SY01 | UC021 | Add Service Ticket | 1902-09-26 | Completed | When a new job package is created on local, in the data grid, both Service Ticket and Service Report status are “empty”. Eservice requires user to add Service Ticket and Service Report by clicking corresponding button explicitly. This feature was designed for multiple service line job before. | 历史数据，已实现的功能 | Part 1
SY01 | UC022 | Add Service Report | 1902-09-26 | Completed | When a new job package is created on local, in the data grid, both Service Ticket and Service Report status are “empty”. Eservice requires user to add Service Ticket and Service Report by clicking corresponding button explicitly. This feature was designed for multiple service line job before. | 历史数据，已实现的功能 | Part 1
SY01 | UC023 | New job package from local | 1902-06-18 | Completed | 1)Remove “Add Service Ticket” (SY01.UC015)and “Add Service Report” buttons(SY01.UC016) 2) Field Supervisor clicks “New” button to create Job Package, enters required data and click “Finish” button. 3) New job will show up in data grid. Job Status , Service Ticket Status and Service Report Status are all “In Progress”. 4) Double-click the newly created job in data grid, Job, Service Ticket and Service Report all show up in the tree view. | UC001 | Part 4
SY01 | UC024 | Update job package | 1902-06-18 | Completed | 当update job的时候，如果job的ClientVersionStamp小于当前版本，自动将ticket和report的状态改为Inprogress，并加载。 | UC002 | Part 4
SY01 | UC025 | Add “Eservice Express” button | 1902-06-18 | Completed | Add a new “Eservice Express” button on left side of “Job Packages From Local” page. When a job package is highlighted, the button is enabled when the website service is available and the job package is not in the sending status; otherwise the button is disabled. | UC003 | Part 4
SY01 | UC026 | Click“Eservice Express” button | 1902-06-18 | Completed | click “Eservice Express” button, a web page will pop up to show this job editing page in Eservice Express website. While the editing page is open, “Eservice Express” button is disabled. | UC004 | Part 4
SY01 | UC027 | Modify Company Information | 800 | N/A | 修改公司信息：Add COD clear flag |  | Part 6
SY01 | UC028 | Update Rig information | 800 | N/A | 1. Change Rig Number to Dropdown list 2. Add “Top Drive” textbox and “Rig Name” textbox after Rig Size 3. Change Rig Contractor, Rig Number as cascading dropdown list, when select a Rig Contractor, Rig Number will populate with the rig number of active rigs in Rig Database, Top Drive and Rig Name will be populated. 4. If there is a new rig, user needs to create a new rig from Rig Board before use it. 5. Update rig information, user needs to update an existing rig from Rig Board. |  | Part 6
SY01 | UC029 | Add Bin requirements | 800 | N/A | 1. Add a check box “Need Bins?” and a textbox Number of Bin to Unit Personnel page Sanjel Storage Equipment section. 2. Add call sheet validation for ready status, to check the number of bins added in Sanjel Storage Equipment meet the needed number |  | Part 6
SY01 | UC030 | Flag a haul needed | 800 | N/A | 1. Add a check box “Need Haul?” to product page for each blend editing page. |  | Part 6
SY01 | UC031 | Update client consultant | 800 | N/A | 将client consultant 存到数据库中，建立Consultant数据访问层，服务层CRUD，在eService的First Call部分，将名字域改为下拉框，名字由Consulatant参考数据，经Customer过滤。 d. 名字域选定一个名字，Phone Number和Email自动填写。填写后可以修改。但不要求存回数据库。 e. 名字域如果名字不存在，允许输入名字，但只保存在目前的Call Sheet数据库中，不写回Consultant参考数据库，这与eservice中现在的实现是一样的。Call Sheet Header数据库中需要加上ID字段。 f. 历史数据可以正常加载 |  | Part 6
SY01 | UC032 |  |  | N/A |  |  | Part 6
SY01 | UC033 |  |  | N/A |  |  | Part 6
SY01 | UC034
SY01 | UC035
SY01 | UC036
SY01 | UC037
SY01 | UC038
SY01 | UC039
SY01 | UC040
SY01 | UC041
SY01 | UC042
SY01 | UC043
SY01 | UC044
SY01 | UC045
SY01 | UC046
SY01 | UC047
SY01 | UC048
SY01 | UC049
SY01 | UC050
SY01 | UC051
SY01 | UC052
SY01 | UC053
SY01 | UC054
SY01 | UC055
SY01 | UC056
SY01 | UC057

## SY02-Express Frontend
System | ID | Name | Importance | Status | Description | Note
SY02 | UC001
SY02 | UC002 | Edit “Adjusted Quantity” in Pricing Items | 1902-09-26 | N/A | Within Eservice Express local website, implement one web page with contains an inline editable datagrid for editing eligible pricing items in Service Ticket. The page needs to take in Job Package Job Number and Unique Id as parameter. In the Pricing Item editing page, only modification of “Adjusted Quantity” column is allowed. After the adjusted quantities are modified, click “Save” button in web page, the changes will be saved in Service Ticket. Click “Cancel” button in web page, all changes will be dropped
SY02 | UC003 |  |  | N/A
SY02 | UC004 |  |  | N/A
SY02 | UC005 |  |  | N/A
SY02 | UC006 |  |  | N/A
SY02 | UC007 |  |  | N/A
SY02 | UC008 |  |  | N/A
SY02 | UC009 |  |  | N/A
SY02 | UC010 |  |  | N/A
SY02 | UC011 |  |  | N/A
SY02 | UC012 |  |  | N/A
SY02 | UC013 |  |  | N/A
SY02 | UC014 |  |  | N/A
SY02 | UC015 |  |  | N/A
SY02 | UC016 |  |  | N/A
SY02 | UC017
SY02 | UC018
SY02 | UC019
SY02 | UC020
SY02 | UC020
SY02 | UC021
SY02 | UC022
SY02 | UC023
SY02 | UC024
SY02 | UC025
SY02 | UC026
SY02 | UC027
SY02 | UC028
SY02 | UC029
SY02 | UC030
SY02 | UC031
SY02 | UC032
SY02 | UC033
SY02 | UC034
SY02 | UC035
SY02 | UC036
SY02 | UC037
SY02 | UC038
SY02 | UC039
SY02 | UC040
SY02 | UC041
SY02 | UC042
SY02 | UC043
SY02 | UC044
SY02 | UC045
SY02 | UC046
SY02 | UC047
SY02 | UC048
SY02 | UC049
SY02 | UC050

## SY03-Win Form Backend
System | ID | Name | Importance | Status | Description | Note
SY03 | UC001 | Update job package |  | N/A
SY03 | UC002 |  |  | N/A
SY03 | UC003 |  |  | N/A
SY03 | UC004 |  |  | N/A
SY03 | UC005 |  |  | N/A
SY03 | UC006 |  |  | N/A
SY03 | UC007 |  |  | N/A
SY03 | UC008 |  |  | N/A
SY03 | UC009 |  |  | N/A
SY03 | UC010 |  |  | N/A
SY03 | UC011 |  |  | N/A
SY03 | UC012 |  |  | N/A
SY03 | UC013 |  |  | N/A
SY03 | UC014 |  |  | N/A
SY03 | UC015 |  |  | N/A
SY03 | UC016 |  |  | N/A
SY03 | UC017
SY03 | UC018
SY03 | UC019
SY03 | UC020
SY03 | UC020
SY03 | UC021
SY03 | UC022
SY03 | UC023
SY03 | UC024
SY03 | UC025
SY03 | UC026
SY03 | UC027
SY03 | UC028
SY03 | UC029
SY03 | UC030
SY03 | UC031
SY03 | UC032
SY03 | UC033
SY03 | UC034
SY03 | UC035
SY03 | UC036
SY03 | UC037
SY03 | UC038
SY03 | UC039
SY03 | UC040
SY03 | UC041
SY03 | UC042
SY03 | UC043
SY03 | UC044
SY03 | UC045
SY03 | UC046
SY03 | UC047
SY03 | UC048
SY03 | UC049
SY03 | UC050

## SY04-Express Backend
System | ID | Name | Importance | Status | Description | Note | Phase
SY04 | UC001 | View job editing page | 1902-09-26 | N/A | click “Eservice Express” button, a web page will pop up to show this job editing page in Eservice Express website. While the editing page is open, “Eservice Express” button is disabled.与SY01.UC020关联 When job editing page is closed. “Eservice Express” button is enabled in eService Win Form application. Technical Hint: Enabling/Disabling button is cross-thread operation. The feasibility is to be determined. |  | Part 4
SY04 | UC002 | Edit “Adjusted Quantity” in Pricing Items | 1902-09-26 | N/A | In Adjusted Quantity field, on numbers and decimal point are allowed, and two decimal places are allowed. After the updated data are submitted, pricing items recalculation is enforced at backend. |  | Part 4
SY04 | UC003 | Implement lock mechanism | 1902-09-26 | N/A | Local job version needs to be added to implement proper lock mechanism to assure local data integrity. |  | Part 4
SY04 | UC004 |  |  | N/A
SY04 | UC005 |  |  | N/A
SY04 | UC006 |  |  | N/A
SY04 | UC007 |  |  | N/A
SY04 | UC008 |  |  | N/A
SY04 | UC009 |  |  | N/A
SY04 | UC010 |  |  | N/A
SY04 | UC011 |  |  | N/A
SY04 | UC012 |  |  | N/A
SY04 | UC013 |  |  | N/A
SY04 | UC014 |  |  | N/A
SY04 | UC015 |  |  | N/A
SY04 | UC016 |  |  | N/A
SY04 | UC017
SY04 | UC018
SY04 | UC019
SY04 | UC020
SY04 | UC020
SY04 | UC021
SY04 | UC022
SY04 | UC023
SY04 | UC024
SY04 | UC025
SY04 | UC026
SY04 | UC027
SY04 | UC028
SY04 | UC029
SY04 | UC030
SY04 | UC031
SY04 | UC032
SY04 | UC033
SY04 | UC034
SY04 | UC035
SY04 | UC036
SY04 | UC037
SY04 | UC038
SY04 | UC039
SY04 | UC040
SY04 | UC041
SY04 | UC042
SY04 | UC043
SY04 | UC044
SY04 | UC045
SY04 | UC046
SY04 | UC047
SY04 | UC048
SY04 | UC049
SY04 | UC050

## SY05-Online Frontend
System | ID | Name | Importance | Status | Description | Comments | Note | Phase
SY05 | UC001 | Display CallSheet on calendar | 1902-06-18 | Invalid | 暂时不实现 |  | SY05UC001 | Part 5
SY05 | UC002 | Display Upcoming job list | 1902-06-18 | Completed | 做一个Datagride显示列表 | Display Rig Board修改为Display Upcoming job list | SY05UC002 | Part 5
SY05 | UC003 | Sign in to Online through Domain Name | 1902-06-18 | Completed | eService Online 使用用户的Domain Name的用户部分，作为eService的用户名来接入权限检查。如SNJ\awang，用户名是awang。用户不需输入密码 |  | SY05UC003 | Part 5
SY05 | UC004 | Display job page | 1902-04-29 | Completed | 显示Job Page |  | SY05UC004 | Part 5
SY05 | UC005 | Add a Product Haul | 1902-04-29 | Completed | 新增一次产品运输 |  | SY05UC005 | Part 5
SY05 | UC006 | View Load Sheet | 1902-04-09 | Completed | 查看装载表 |  | SY05UC006 | Part 5
SY05 | UC007 | Print Load Sheet | 1902-04-09 | Completed | 打印装载表 |  | SY05UC007 | Part 5
SY05 | UC008 | View Product Haul Page | 1902-04-09 | Completed | 查看产品拖运页面 |  | SY05UC008 | Part 5
SY05 | UC009 | Filter by Service Point in Job Page | 1902-03-30 | Completed | 按照Service Point进行筛选 |  | SY05UC009 | Part 5
SY05 | UC010 | Display Rig Board data from callsheet | 810 | N/A | 显示Rig Board，包括Company、LSD、RIG、JOB、DATE、BL1、BL2、BL2、BL3、Notes、BANS、BIN、CONSULTANT CONTACTS |  |  | Part 6
SY05 | UC011 | Filter in Rig Board | 810 | N/A | 在Rig Board上按照条件对数据进行筛选 |  |  | Part 6
SY05 | UC012 | Display context menu by Right click cell | 800 | N/A | 在Rig Board上右键单击某个单元格，根据所载列的属性和单元格的值、状态显示菜单。 |  |  | Part 6
SY05 | UC013 | Add new rig | 800 | N/A | 新增Rig |  |  | Part 6
SY05 | UC014 | Update rig information | 800 | N/A | 修改Rig |  |  | Part 6
SY05 | UC015 | View rig details | 800 | N/A | 查看Rig |  |  | Part 6
SY05 | UC016 | Delete rig | 800 | Invalid | 10-30Adam：确认无此功能/删除Rig |  |  | Part 6
SY05 | UC017 | Create Rig Job | 800 | N/A | 10-30Adam：Rig Job没有创建功能，它是一个虚拟的job, 贯穿整个流程。它的创建有很多场景，可能从job alert，call sheet, job 生成，在开发过程中不存在就创建一个。删除此用例，功能包括在其他具体场景中。/创建Rig Job |  |  | Part 6
SY05 | UC018
SY05 | UC019
SY05 | UC020
SY05 | UC020
SY05 | UC021
SY05 | UC022
SY05 | UC023
SY05 | UC024
SY05 | UC025
SY05 | UC026
SY05 | UC027
SY05 | UC028
SY05 | UC029
SY05 | UC030
SY05 | UC031
SY05 | UC032
SY05 | UC033
SY05 | UC034
SY05 | UC035
SY05 | UC036
SY05 | UC037
SY05 | UC038
SY05 | UC039
SY05 | UC040
SY05 | UC041
SY05 | UC042
SY05 | UC043
SY05 | UC044
SY05 | UC045
SY05 | UC046
SY05 | UC047
SY05 | UC048
SY05 | UC049
SY05 | UC050
SY05 | UC018 | Create Call Sheet from Rig Board | 800 | N/A |  |  |  | Part 6
SY05 | UC019 | Create client consultant | 800 | N/A | 创建Client Consultant，并将eservice中相应地方修改为选择项，而不是输入项 |  |  | Part 6
SY05 | UC020 | Update Well Location/Direction | 800 | N/A | 更新Well Location/Direction |  |  | Part 6
SY05 | UC021 | Update Job Date Time for call back/confirmation | 800 | N/A | 更新Job Date Time |  |  | Part 6
SY05 | UC022 | Implement special instruction | 1902-03-10 | N/A | 10-30Adam确认此功能不包括在第六期/ 实现道路禁令，许可证和其他重要的特殊指令，用来监控工作的进度 |  |  | Part 7
SY05 | UC023 | Update Notes | 800 | N/A | 实现Bin的需求 |  |  | Part 6
SY05 | UC024 | Update client consultant | 800 | N/A | 更新Client Consultant |  |  | Part 6
SY05 | UC025 | View client consultant details | 800 | N/A | 查看Client Consultant详细信息 |  |  | Part 6
SY05 | UC026 | Delete client consultant | 800 | N/A | 删除Client Consultant |  |  | Part 6
SY05 | UC027 | Display hover over content for cell of rig board |  | N/A | 鼠标悬停在RIG BOARD的单元格上时显示相应内容 |  |  | Part 6
SY05 | UC028 | Add flag a haul needed |  | N/A | 右击BL，显示菜单Need a haul，点击后修改need a haul的标志为选中状态 |  |  | Part 6
SY05 | UC029 | Schedule Product Haul |  | N/A | Schedule Product Haul.点击后弹出安排Product Haul的窗口，创建Loading Sheet并分配bulker和Driver。 |  |  | Part 6
SY05 | UC030 | Change status of Product Haul |  | N/A | 点击后更新product haul的状态为On location |  |  | Part 6
SY05 | UC031 | Display Row Styles |  | N/A | 根据Rig的状态显示 |  |  | Part 6
SY05 | UC032 | Modify the rig's status |  | N/A | • Update the Rig. Click to Pops up a “Update Rig” Window, Company and Rig Number is not changeable. • Down for maintenance. Click to change Rig status to “status 2 – Down for maintenance.” • Down but holding equipment. Click to change Rig status to “status 2 – Down but holding equipment.” • Down for weather. Click to change Rig status to “status 2 – Down for weather.” • Down for new lease/licenses. Click to change Rig status to “status 2 – Down for new lease/licenses.” • Deactivate. Click to change status to “status 3 – Deactivated” • Activate. Click to change status to “Status 1 – Active” |  |  | Part 6
SY05 | UC033 | Modify COD Cleared status |  | N/A | 当显示为绿色图标时，右击显示Remove COD cleared，点击后将COD cleared的状态改为未选中；当显示为红色图标时，右击显示COD cleared，点击后将COD cleared的状态改为选中状态。 |  |  | Part 6
SY05 | UC034 | Change status of "Need bins" |  | N/A | 在bin一列右键时弹出菜单Need bins，修改Sanjel Storage Equipment部分的Need Bin选项。 |  |  | Part 6
SY05 | UC035 | Add a bin |  | N/A | 在bin一列右键时弹出菜单add a bin，新增一个bin。 |  |  | Part 6
SY05 | UC036 | Remove a bin |  | N/A | 在bin一列右键时弹出菜单Remove a bin，移除一个bin。 |  |  | Part 6
SY05 | UC037 | Display rig job data in rig board |  | N/A | Rig Board上根据要求显示各列的数据 |  |  | Part 6
SY05 | UC038 | Extend call sheet workflow |  | N/A | 10-30Adam确认此功能不包括在第六期/ 扩展Call Sheet的工作流，实现监控和警告功能。 |  |  | Part 7
SY05 | UC039 | Add product haul unit personnel to call sheet through Rig Board |  | N/A | 10-30Adam确认此功能不包括在第六期/ 通过Rig Board为Call Sheet新增产品拖运的单位人员 |  |  | Part 7
SY05 | UC040 | Display cell style in Rig Board |  | N/A | 单元格的样式处理 |  |  | Part 6
SY05 | UC041 | Implement Job Alert |  | N/A | 实现Job Alert功能，填充Call Sheet之前的流程 |  |  | Part 6
|  |  |  | N/A |  |  |  | Part 6
Part 6
Part 6

## SY06-Online Backend
System | ID | Name | Importance | Status | Description | Note | Phase
SY06 | UC001 | Display Upcoming job list | 1902-06-18 | Completed | 做一个Datagride显示列表，Display Rig Board修改为Display Upcoming job list | SY06UC001 | Part 5
SY06 | UC002 | Sign in to Online through Domain Name | 1902-06-18 | Completed | eService Online 使用用户的Domain Name的用户部分，作为eService的用户名来接入权限检查。如SNJ\awang，用户名是awang。用户不需输入密码 | SY06UC002 | Part 5
SY06 | UC003 | Display job page | 1902-04-29 | Completed | 显示输入页面 | SY06UC003 | Part 5
SY06 | UC004 | Add a Product Haul | 1902-04-29 | Completed | 新增一次产品运输 | SY06UC004 | Part 5
SY06 | UC005 | View Load Sheet | 1902-04-09 | Completed | 查看装载表 | SY06UC005 | Part 5
SY06 | UC006 | Print Load Sheet | 1902-04-09 | Completed | 打印装载表 | SY06UC006 | Part 5
SY06 | UC007 | View Product Haul Page | 1902-04-09 | Completed | 查看产品拖运页面 | SY06UC007 | Part 5
SY06 | UC008 | Edit a Product Haul | 1902-03-30 | Completed | 编辑Product Haul | SY06UC008 | Part 5
SY06 | UC009 | Delete a Product Haul | 1902-03-20 | Completed | 删除Product Haul | SY06UC009 | Part 5
SY06 | UC010 | Filter by Service Point in Upcoming jobs | 1902-03-20 | Completed | 按照Service Point筛选 |  | Part 6
SY06 | UC011 | Display Rig Board | 1902-03-20 | N/A | 显示Rig Board，包括Company、LSD、RIG、JOB、DATE、BL1、BL2、BL2、BL3、Notes、BANS、BIN、CONSULTANT CONTACTS |  | Part 6
SY06 | UC012 | Filter in Rig Board | 1902-03-20 | N/A | 在Rig Board上按照条件对数据进行筛选 |  | Part 6
SY06 | UC013 | Add new rig | 1902-03-10 | N/A | 新增Rig |  | Part 6
SY06 | UC014 | Update rig | 1902-03-10 | N/A | 修改Rig，右击弹出菜单，点击后弹出更新rig 的窗口，Company和Rig Number不变。 |  | Part 6
SY06 | UC015 | View rig details | 1902-03-10 | N/A | 查看Rig |  | Part 6
SY06 | UC016 | Delete rig | 1902-03-10 | N/A | 删除Rig |  | Part 6
SY06 | UC017 | Create Rig Job | 1902-03-10 | N/A | 从Call Sheet创建Rig Job |  | Part 6
SY06 | UC018 | Create client consultant | 1902-03-10 | N/A | 创建Client Consultant，并将eservice中相应地方修改为选择项，而不是输入项 |  | Part 6
SY06 | UC019 | Update client consultant | 1901-11-30 | N/A | 更新Client Consultant |  | Part 6
SY06 | UC020 | View client consultant details | 1901-11-30 | N/A | 查看Client Consultant详细信息 |  | Part 6
SY06 | UC021 | Delete client consultant | 1901-11-30 | N/A | 删除Client Consultant |  | Part 6
SY06 | UC022 | Display context menu | 1901-11-30 | N/A | 右击显示菜单 |  | Part 6
SY06 | UC023 | [5 empty] | Part 6
SY06 | UC024 | [5 empty] | Part 6
SY06 | UC025 | [5 empty] | Part 6
SY06 | UC026 | [5 empty] | Part 6
SY06 | UC027 | [5 empty] | Part 6
SY06 | UC028 | [5 empty] | Part 6
SY06 | UC029 | [5 empty] | Part 6
SY06 | UC030 | [5 empty] | Part 6
SY06 | UC031 | [5 empty] | Part 6
SY06 | UC032 | [5 empty] | Part 6
SY06 | UC033 | [5 empty] | Part 6
SY06 | UC034
SY06 | UC035
SY06 | UC036
SY06 | UC037
SY06 | UC038
SY06 | UC039
SY06 | UC040
SY06 | UC041
SY06 | UC042
SY06 | UC043
SY06 | UC044
SY06 | UC045
SY06 | UC046
SY06 | UC047
SY06 | UC048
SY06 | UC049
SY06 | UC050

## Reference Data
SubSystems | ID | Name | Description | Phase | Part 1
| SY01 | Win Form Frontend | Win Form前台 |  | Part 2
| SY02 | Express Frontend | Express前台 |  | Part 3
| SY03 | Win Form Backend | Win Form后台 |  | Part 4
| SY04 | Express Backend | Express后台 |  | Part 5
| SY05 | Online Frontend | Online前台 |  | Part 6
| SY06 | Online Backend | Online后台 |  | Part 7
Part 8