## Sheet1
Issue# | Appliucation | Type | Reported By | Description | Solution/Fix | DevelopmentTips | Size | Status | Developer | Estimate | Priority | Comments | EST by MetaShare
6 | eSe | Required Improvement | C Eykelbosh | Cannot add comments / pump schedule to the chart printed off for the client. 无法将评论/泵计划添加到为客户打印的图表中。 | "Provide a method for them to enter their comments in eSe. I think this may already be there on the Job Setup Tab under ""Pumping Procedure"". If this is what this area is for, I (CE) propose we change the name to Job Comments or something similar. AW: We need to confirm with CS, if this is needed, since this was ignored in requirement discussion. Has been brought to the CS Team, no answer yet. Info can be gathered from the treatment report. Chris suggests that this is a future release 04/08/19 AW: Any decision on requirement? Should we compile the comments from the treatment report or production section? Or we ask supervior to type them again? NATHAN TO COMMENT 4/11/2019 CRE - CS has confimred that they want to include comments on the FDAS chart. Include type of fluid and amount pumped. Ideally this would be automated from the treatment report/products section, but eSe does not support stages right now. Immeadiate plan is quote out two times, one to have them manually enter the coments, the other to have them be able to pull from a template/dropdown to assemble their mini-treatment report. Left with Adam/Nathan " “提供一种方法让他们在eSe中输入他们的评论。我认为这可能已经存在于”“Pumping Procedure”下的“job setup”选项卡上。“如果这是这个领域的用途，我（CE）建议我们改变如果需要，我们需要与CS确认，因为在需求讨论中忽略了这一点。已经提交给CS团队，还没有回答。可以从treatment report中收集信息Chris建议这是未来发布的04/08/19 AW：关于要求的任何决定？我们是否应该编写treatment report或生产部分的评论？或者我们要求超级行为再次输入？NATHAN TO COMMENT 4/11 / 2019年CRE-CS已经确认他们希望在FDAS图表中包含评论。包括type of fluid and amount pumped。理想情况下，这将从 treatment report/产品部分自动化，但eSe目前不支持阶段。立即计划是引用两次，一次手动输入，在另一方面，让他们能够从模板/下拉菜单中提取他们的treatment report。“ |  | ? | New | MetaShare | 40 | 2 | 在Job Setup页面新加Pumping Procedure Tab，包括一个Comments文本框，用户可以输入评论。打印PDF时将内容打印到页面的末尾。是这样吗？ | 40
22 | eService | Required Improvement | C Eykelbosh | Adjust widths for the columns in the treatment report to make it easier for supervisors to fill in their reports | "04/08/19 AW: Do you mean to make the report Comments column wider? Since ti is hard to see full text. We may have to review the column headers to use abbreviations to shrink the width of some columns 4/08/2019 CRE - We need to look at what they are currently doing and make it easier. I can arrage a demo with a supervisor. " |  |  |  |  | 4 | 1
24 | eSe | Required Improvement | C Eykelbosh | Add digital display for current trends - maybe underneath the billing 为当前趋势添加数字显示 - 可能在billing按钮下方 | "04/08/19 AW: Display digital meters corresponding to the chart selection, is it right? If so, there will be many digital meters, there is not enough space underneath billing button. NATHAN TO COMMENT 4/11/2019 - Confirmed that we need something. Only need to see values for the 4 key items displayed. See if the charting application has the ability to show the current value, Adam to investigate further now that the objective is clear."显示与图表选择对应的数字仪表，是不是？如果是这样，会有很多数字仪表，计费按钮下面没有足够的空间.NATHAN TO COMMENT 4/11/2019 - 确认 我们需要一些东西。只需要查看显示的4个关键项的值。看看图表应用程序是否能够显示当前值，Adam现在进一步调查目标是明确的。 | I haven't found this feature through quick research. Suggested solution can be add digital indicator by Chart Selection after each series checkbox. TODO: 1. Ask developer to do further research on native feature. 2. Prototype suggested solution for Nathan and EOS team | M | New | MetaShare | 40 | 1 | 花一天时间研究原生控件，根据研究结果选择相应方案实现。 | 24
25 | SCM DC | Required Improvement | N Dholoo | Ability to regenerate eSe charts from a csv file read in via USB stick in case of complete T/B or TCP communication failure. 能够在通过USB记忆棒读取的csv文件中重新生成eSe图表，以防T / B或TCP通信完全失败。 | " DataCollector can read from USB & write to Database, eSe can generate plots. eSe might need to handle multiple datasets with same timestamps in the database. 4/11/2019 - This should be considered one of the top priority items for development. Supervisors must be able to generate a chart for a client prior to leaving location. Data is imported as a separate set, the sup can choose to use CSV data from inside eSe" “DataCollector可以从USB读取并写入数据库，eSe可以生成图表.eSe可能需要处理数据库中具有相同时间戳的多个数据集.4 / 11 / 201-这应该被认为是开发的首要任务之一。 必须能够在离开位置之前为客户生成图表。数据作为单独的集导入，sup可以选择使用来自eSe内部的CSV数据 | Here may cause duplicate data in database, we need to implement a flag all the way through to differentiate the two sets of data. 1. Add a IsCvsdata flag in configuration, use this flag to drive all the logic for data loading, both of mornitor and printing. Mornitor UI, add "CSV" check box before "Update" button. 2. Real-time, which means no end time in configuration. Ignore CSV data. If no end time, disable the CSV checbox. 这里可能会导致数据库中的重复数据，我们需要一直实现一个标志来区分这两组数据。 1.在配置中添加一个IsCvsdata标志，使用此标志来驱动数据加载的所有逻辑，包括mornitor和print。 Mornitor UI，在“更新”按钮之前添加“CSV”复选框。 2.实时，这意味着配置没有结束时间。 忽略CSV数据。 如果没有结束时间，请禁用CSV checbox。 | M | New | MetaShare | 24 | 1 | CSV文件的存放路径是一个固定的路径，对吗？ 回答：我们不处理CSV文件，它会被写到数据库，我们只需要对数据根据这个标志进行过滤。 | 32
30 | eSe | Required Improvement | C Eykelbosh | Printing time intervals should be adjustable. 打印时间间隔应该可以调节 | "As initial thinking of design, the print configuration is a sub-set of job configuration. Given up due to the fear of introducing complication to field guys. But it seems we need to consider build some customized configuration for print as requested. Will put in enhancement backlog. 12/19/18 - CRE - Agreed, I think this will likely not be an issue once the guys get used to the new system 03/20/19 - CRE - Adjust to set time scale to 5/10/15/30/1 hr increments from the closest increment. 04/08/19 AW: Currently interval is set to increase by 5 minutes, which goes 5/10/15/20/25/30/35 and so on, which presents 6-12 interval based on the calculation. It seems the requirement is asking for fixed number of intervals for a consistent looking. Can we get how many intervals should we use? 4/11/2019 - The purpose is mostly to help them complete the treatment report. If they had a way of easily identifying the timestamp for a certain event this would not be an issue. Adam to look at it further On the PDF charts we would round the time up/down to the neaest even interval, then not display data that was outside of the time set on the job monitor screen, hide the duration and interval controls" “作为设计的初步思考，打印配置是作业配置的一个子集。由于担心会给现场人员引入复杂功能而放弃。但似乎我们需要考虑根据要求构建一些自定义配置进行打印。03/20/19 - CRE - 调整将时间刻度设置为5/10 /从最近的增量开始增加15/30/1小时.04 / 08/19 AW：当前间隔设置为增加5分钟，即5/10/15/20/25/30/35，依此类推6-12间隔基于计算。似乎要求固定数量的间隔以保持一致。我们可以得到我们应该使用多少间隔？4/11/2019 - 目的主要是帮助他们完成 treatment report。如果他们有办法轻松识别某个事件的时间戳，这不会成为问题。Adam要看它她在PDF图表上我们将时间向上/向下舍入到最近的偶数间隔，然后不显示超出作业监视器屏幕上设置的时间的数据，隐藏持续时间和间隔控制“ | Here are two tasks: 1.In PrintOut, Round start time to last even minutes before, e.g. 14:00 instead of 14:02. Round end time to earliest even minutes after. Total duration must be even with interval. No data print out for the make-up perioed at beginning and end. 2. Enable crosshair on chart, it will show the value indicator. Will demo Nathan and EOS. 这有两个任务： 1.在PrintOut中，将开始时间持续到前几分钟，例如 14:00而不是14:02。 结束时间最早到最后几分钟。 总持续时间必须是偶数间隔。 在开始和结束时没有打印出make-up的数据。 2.在图表上启用十字准线，它将显示值指示器。 将演示Nathan和EOS。 | M | Pending | MetaShare | 16 | 1 | 不太理解。开始和结束时间具体的调整规则需要明确一下。 2. Enable crosshair on chart, it will show the value indicator. Will demo Nathan and EOS.这句不明白是什么意思 | 24
33 | eSe | Required Improvement | C Eykelbosh | Add WITS Connectivity Indicator to Job Setup Screen 将WITS连接指示符添加到Job Setup界面 | "Will require an update to DC to write the WITS connectivity status to the config DB 4/11/2019 - Also add indicator to the monitor window. Neville/Adam/Viktor will sort it out ASAP." “将要求更新DC以将WITS连接状态写入配置DB 4/11/2019 - 还要在监视器窗口中添加指示器.Neville / Adam / Viktor将尽快对其进行排序。” | Here are two tasks: 1. Read WITS connectivity from config DB. 2. Implement WITS indicator in mornitor page. After we hide duration and interval. There will be space after Time configuration Box. This area will used as indicator area. 3. Add WITS indicator in Job Setup Page 这有两个任务： 1.从配置数据库读取WITS连接。 2.在mornitor页面中实现WITS指标。 我们隐藏持续时间和间隔。 时间配置框后会有空格。 该区域将用作指标区域。 3.在作业设置页面中添加WITS指示器 | M | Pending | MetaShare | 40 | 1 | WITS的连接状态从哪里获取到？是要把这个连接状态显示在页面上吗 | 40
40 | eSe | Required Improvement | C Eykelbosh | The job list in eSe is ever growing, jobs that have been transmitted should be cleaned out. eSe中的工作列表不断增长，应该清理已传输的工作。 | Add this to Data Clean-up feature. 将其添加到数据清理功能。 04/08/19 AW: Database clean up code was done, need to be tested. Folder clean up will be included. 4/11/2019 - Preference is to be time based 30 days | After Adam sort out the whole design, Metashare will assist some implementation. 在Adam完成整个设计之后，Metashare将协助一些实施。 | M | Pending | MetaShare | 24 | 2 | 将本地XML数据和SQLite数据库中的数据清理 | 32
42 | eService | Required Improvement | C Eykelbosh | The user needs to be able to click the eService Express button in eService at anytime to open up the browser. Helps out with pressure testing mode. Also, is there any way to programatically add a link to eSe in the Chrome bookmark bar when eSe is installed? 用户需要能够随时单击eService中的eService Express按钮以打开浏览器。 帮助进行压力测试模式。 此外，安装eSe时，有没有办法以编程方式在Chrome书签栏中添加指向eSe的链接？ | "I think we can create a eService Express shortcut icon on desktop. User can click the icon instead of opening Chrom. Will talk to Debain to get a easy solution. 04/08/19 AW: eservice button issue is duplicated with #44. Shortcut creation script is doable, we may create it and embedd it in installation script 4/11/2019 - Button is handled as a bug fix, add script to place new icon on desktop " “我认为我们可以在桌面上创建一个eService Express快捷方式图标。用户可以点击图标而不是打开Chrom。将与Debain交谈以获得一个简单的解决方案.04/08/19 AW：eservice按钮问题与＃44重复。 快捷方式创建脚本是可行的，我们可以创建它并将其嵌入安装脚本4/11/2019 - 按钮作为错误修复处理，添加脚本以在桌面上放置新图标“ | Add windows comman script in installation script. Check if a shortcut of opening Chrome with link of eService Express exists, If not, create one. 在安装脚本中添加Windows命令脚本。 检查是否存在使用eService Express链接打开Chrome的快捷方式，如果不存在，请创建一个。 | S | Pending | MetaShare | 4 | 2 | 目前没写过windows脚本，需要探讨 | 8
28 | eService | Required Improvement | C Eykelbosh | "Billing Info - Editing a cement line item in eService. When the edit button is clicked, the cursor position goes somewhere else, pressing tab shoots you to the top of the screen, must press tab a bunch of times to get to the data entry part. As per D Triska. 12/11/2018 - The tab order for the p-tanks also needs to be fixed" | "Fix the tab order? 04/08/19 AW: Should be an easy fix." |  | S | Pending | Adam |  | 2
43 | eSe | Required Improvement | C Eykelbosh | The kg/m3 on the PDF chart needs to be super scripted | "The superscript printing has a technical difficulty for a while. We have been living with this for a decade. The fix cost is high which pushed it to lower priority always. 4/11/2019 - Adam is going to talk to developers, could also have an image and import that" |  |  |  |  | 16 | 1
44 | eService | Bug | C Eykelbosh | The eService Express button was greyed out in eService even though the supervisor had selected the current job and it was "in progress" status. See also item #40 尽管主管已经选择当前job并且处于“in progress”状态，Express按钮依然是灰色的。 | "04/08/19 AW: Since we rolled out new version eService Express to all district, we can change the eService Express button definition to bring up Chrome browser and load up current job page. Should we land on Job list page or Job Set Up page? I would like to listen to front line's opinion. CRE - My vote is the job list NATHAN to comment 4/11/2019 - Land on the list page " “08/08/19 AW：由于我们向所有地区推出了新版eService Express，我们可以更改eService Express按钮定义以启动Chrome浏览器并加载当前作业页面。我们是否应该加载Job List页面或Job Set Up页？我想听听前线的意见.CRE - 我的投票是Job List NATHAN评论4/11/2019 - Job List“ |  | S | Pending | MetaShare | 4 | 1 | eService点击Epress按钮跳转到Local jobs页面，是否需要同时设置为Curren Job？ 回答： 只跳转，不设置 | 4
45 | eSe | Bug | C Eykelbosh | On several occasions since the release of 1.2.0.27 there have been instances where the trends do not show up correctly in Chrome. It is possible to get them to show back up by manipulating the start time. Clearing the browser data and restarting chrome have also been effective fixes. | "Click ""Update"" button, it is working properly. Click ""Fresh"" button on Chrome, the chart not shown from start time, to current time. The charting works from current time and on. It is cache issue, will be fixed. 4/11/2019 CRE - There was an instance of this today with version 1.2.0.33P More testing is required, no potential fix as of yet" |  |  |  |  | 40
34 | eService | Required Improvement | C Eykelbosh | Get rid of FDAS ZIP file upload option, be able to attach multiple charts at once in eService, Remove the JobChartData selection. Review and clean up all data fields | "Will update eSerice client validation rule and attachment optionlist to fit in the transition from FDAS to eService Express 04/08/19 AW: Agreed " |  | M | Pending | Adam |  | 3
39 | eSe | Required Improvement | C Eykelbosh | JobChartPrintOut Folder, any plans to clean this out automatically? | "Add this to Data Clean-up feature. 04/08/19 AW: Database clean up code was done, need to be tested. Folder clean up will be included. 4/11/2019 - Preference is to be time based 30 days" |  | M | Pending | Adam |  | 3
50 | eSe | Bug | C Eykelbosh | After confirming the supervisor selection in eSe you have to also confirm the WITS setup 在eSe中确认主管选择后，你还必须确认WITS设置 | "Looks like the button to Unlock the units was copied for the unlock supervisor button, WITS logic is still attached. 04/08/19 AW: Double confirm should only apply to unit related settings. We can fix this. 4/11/2019 - This is a bug and will be fixed" “看起来解锁Unit的按钮被复制用于解锁管理员按钮，WITS逻辑仍然附加.04/08/19 AW：双重确认应该只适用于Unit相关设置。我们可以解决这个问题.4 / 11/201 - 这是一个错误，将被修复“ |  | S | Pending | MetaShare | 4 | 1 |  | 4
43 | eSe | Required Improvement | C Eykelbosh | The kg/m3 on the PDF chart needs to be super scripted | "The superscript printing has a technical difficulty for a while. We have been living with this for a decade. The fix cost is high which pushed it to lower priority always. 4/11/2019 - Adam is going to talk to developers, could also have an image and import that" |  |  | New |  |  | 3
51 | eSe | Required Improvement | C Eykelbosh | Is there any way that we can make it so the strip chart area is equal on all three charts in the job monitor window? Right now all three are different sizes and it makes it difficult to correlate one graph to another. 我们有什么方法可以使作业监视器窗口中的所有三个图表上的条形图区域相等？ 现在这三个都是不同的大小，这使得很难将一个图形与另一个图形相关联。 | 04/08/19 AW: Currently the Y-Axis description is included in the total chart size. This can be solved anyway. 目前，Y轴描述包含在总图表大小中。 无论如何这都可以解决。 | Figure out the right size for each chart to make all charts vertically aligned by Y-Axis and secondary Y Axis ( ending border if no secondary one. The final check is that all interval grid lines are aligned. 找出每个图表的正确尺寸，使所有图表垂直对齐Y轴和辅助Y轴（如果没有次要轴，则结束边界。最后检查是所有间隔网格线对齐。 | S | Pending | MetaShare | 16 | 3 | 上次这个问题就没有解决，补精度的方案不行，还得再想别的办法 | 24
52 | eService | Required Improvement | B Mattock | " Morning Ben, Im just in the shop doing my weekly pressure test on the unit. And in the set up process for E servive express. Which was easy enough. I thought that if we had a weekly auto populated call sheet for pressure tests in E Service. Then guys would see this and then it would be record in E service that the test is being done From Kevin Wilkinson - Kindersley" | 4/11/2019 - This is the direction we need to go, needs a lot more discussion |  |  | New |  |  | 3
56 | eSe | Required Improvement | B Mattock | Make it so that chart cannot be printed unless the header information is completed. |  |  |  | New |  |  | 3
57 | eSe | Required Improvement | B Mattock | Temp/density moved to the same trend on PDF. Must make sure that all axis' align correclty! |  |  |  | New |  |  | 2
58 | IT | Required Improvement | B Mattock | Regenerating charts from online/BI data. Once the data has been uploaded from the toughbook to the server and has been cleaned off of the toughbook, we still need a way to easily regenerate charts from the data now located on the server. |  |  |  | New |  |  | 3
59 | SCM DC | Required Improvement | B Mattock | Treatment Report Timestamp Capture. Allows the SCM operator to mark an event from the PLC that will transfer to the treating report. This will include some pre-defined actions (pressure test, lead, tail, etc.) but could also be manually completed by the supervisor post-job |  |  |  | New |  |  | 2
60 | SCM DC | Required Improvement | B Mattock | Recipe Auto Transfer to PLC |  |  |  | New |  |  | 2
45 | eSe | Bug | C Eykelbosh | On several occasions since the release of 1.2.0.27 there have been instances where the trends do not show up correctly in Chrome. It is possible to get them to show back up by manipulating the start time. Clearing the browser data and restarting chrome have also been effective fixes. | "Click ""Update"" button, it is working properly. Click ""Fresh"" button on Chrome, the chart not shown from start time, to current time. The charting works from current time and on. It is cache issue, will be fixed. 4/11/2019 CRE - There was an instance of this today with version 1.2.0.33P More testing is required, no potential fix as of yet" |  |  | Testing |  |  | 1
52 | eService | Required Improvement | B Mattock | " Morning Ben, Im just in the shop doing my weekly pressure test on the unit. And in the set up process for E servive express. Which was easy enough. I thought that if we had a weekly auto populated call sheet for pressure tests in E Service. Then guys would see this and then it would be record in E service that the test is being done From Kevin Wilkinson - Kindersley" | 4/11/2019 - This is the direction we need to go, needs a lot more discussion |  |  |  |  | 16 | 2
22 | eService | Required Improvement | C Eykelbosh | Adjust widths for the columns in the treatment report to make it easier for supervisors to fill in their reports | "04/08/19 AW: Do you mean to make the report Comments column wider? Since ti is hard to see full text. We may have to review the column headers to use abbreviations to shrink the width of some columns 4/08/2019 CRE - We need to look at what they are currently doing and make it easier. I can arrage a demo with a supervisor. " |  | S | New |  |  | 2
53a | eSe | Required Improvement | C Eykelbosh | The scaling in the PDF is set for all charts of a similar type, in one case, the rate had a spike to 10m3/min, all 3 rate charts re-scaled to the point where they were no longer usefull (unit 1 / unit 2 / Total Rate). Suggest imposing maximum values for y axis scaling on the PDF charts to address issues like this. PDF中的缩放设置为所有相似类型的图表，在一种情况下，速率达到10m3 / min，所有3个速率图表重新缩放到不再有用的点（单位1 /单位） 2 /总费率）。 建议在PDF图表上为y轴缩放施加最大值以解决此类问题。 | "04/08/19 AW: I need an example to discuss this. 4/08/2019 CRE - Sent example to Adam, will need to specify that max rate a single unit can pump at (I.E. 1.5 m3/min) 4/11/2019 - PDF charts, max for single unit rate 2.0m3/min, max rate for total rate on 2 truck job 4m3/min, max rate for 3 truck job 6m3/min. Everything above the max value would be clipped. Humor us and take a look at the temperature max value." “04/08/19 AW：我需要一个例子来讨论这个问题.4 / 08/201 CRE - 发送给Adam的例子，将需要指定单个单位可以泵送的最大速率（IE 1.5 m3 / min）4 / 11/2019 - PDF图表，单个单位速率2.0m3 / min的最大值，2个卡车作业总速率的最大速率4m3 / min，3个卡车作业的最大速率6m3 / min。超出最大值的所有内容都将被剪裁。。“ | Currently we use monitor configuration for print. We need to apply specfic rules in rate charts to make the charts looks better. 目前我们使用显示器配置进行打印。 我们需要在费率图表中应用特定规则，以使图表看起来更好。 | s | New | MetaShare | 16 | 1 | 根据数据最大最小值自适应Y轴的最大值 | 16
53b | eSe | Required Improvement | C Eykelbosh | All rate/pressure/density trends will maintain the standard blue/red/green colors on the PDF charts, no need to have different colors for rate2/3/etc. 所有速率/压力/密度趋势将在PDF图表上保持标准的蓝色/红色/绿色，不需要为rate2 / 3 / etc提供不同的颜色。 | 04/08/19 AW: Agreed | Currenlty, chart printing is using configuration from monitor, we need to use the color code in series template. 目前，图表打印是使用Monitor Configuration，我们需要使用series template中的颜色代码。 | S | Pending | MetaShare | 8 | 1 |  | 12
54 | eSe | Required Improvement | N Dholoo | When the chart hits its duration, it doubles the x-scale, can this be made less to keep the chart more readable? 当图表达到其持续时间时，它会使x尺度加倍，是否可以减少图表的可读性？ | "04/08/19 AW: What is preference of a step? Add one interval each time? 4/11/2019 - Confimred recalculate and add one interval" 什么是步骤的偏好？ 每次添加一个间隔？ 4/11/2019 - 确认计算并添加一个间隔“ | Change the interval calculation algorithm to add one interval when interval is not change. E.g. Initially 12 of 5 min interval for one hour. When it is full, recalculate, interval will be increased to 10 min, it will add one interval to display 70 min, then 80, 90 until two hours, interval will be 15, it will be add one interval to 135 minutes, and so on. 更改间隔计算算法以在间隔未更改时添加一个间隔。 例如。 最初12个，间隔5分钟，持续1小时。 当它满了，重新计算时，间隔时间会增加到10分钟，它会加一个间隔显示70分钟，然后是80,90到两个小时，间隔时间是15，它会加一个间隔到135分钟，所以 上。 | S | Pending | MetaShare | 8 | 1 | 步长每次加5min，每次增加一个新的步长 | 12
55 | eSe | Bug | C Eykelbosh | "If the supervisor has not specified an end time when they try to transmit the ticket eService throws and error. For this job, the supervisor had everything setup and eSe open, but they did not end up pumping a job that day, so he did not put in an end time. I have asked that he does press End in eSe even if they haven't pumped to avoid this error down the road. reported by Donal Triska" “如果主管没有指定结束时间，他们试图传送Ticket，eService抛出错误。对于这项工作，主管已经完成了所有设置并且eSe打开了，但他们当天没有结束工作，所以他做了 没有结束时间。我已经要求他确实在eSe中按End，即使他们还没有避免这种错误.Donal Triska说 | "4/10/2019 CRE - If there is no end time entered when the sup is trying to transmit the ticket, use the current time as the end time. 4/11/2019 AW: Current time maynot be the best candudate, in case any delay of sending job to server. I would like to take Job-Complete time in treatment report. 4/11/2019 CRE - Confirmed. Must also consider the data packing and automatically close open jobs after a certain amount of time, or if a defualt time (8 hours) has elapsed" 如果在sup尝试传输Ticket时没有输入结束时间，请使用当前时间作为结束时间。 4/11/2019 AW：当前时间可能不是最好的候选者，以防任何延迟向服务器发送作业。 我想在Treatment report中获取Job完成时间。 4/11/2019 CRE - 确认。 还必须考虑数据打包并在一定时间后自动关闭打开的作业，或者如果已经过了一个违规时间（8小时） | This can be handled with Data Packing process。 | M | Completed | MetaShare | 16 | 1 | 在Packing service中增加异常处理 | 16
56 | eSe | Required Improvement | B Mattock | Make it so that chart cannot be printed unless the header information is completed. | [5 empty] | 8 | 1
57 | eSe | Required Improvement | B Mattock | Temp/density moved to the same trend on PDF. Must make sure that all axis' align correclty! | [5 empty] | 24 | 1
58 | IT | Required Improvement | B Mattock | Regenerating charts from online/BI data. Once the data has been uploaded from the toughbook to the server and has been cleaned off of the toughbook, we still need a way to easily regenerate charts from the data now located on the server. | [5 empty] | 40
59 | SCM DC | Required Improvement | B Mattock | Treatment Report Timestamp Capture. Allows the SCM operator to mark an event from the PLC that will transfer to the treating report. This will include some pre-defined actions (pressure test, lead, tail, etc.) but could also be manually completed by the supervisor post-job | [5 empty] | 80
60 | SCM DC | Required Improvement | B Mattock | Recipe Auto Transfer to PLC | [5 empty] | 80
39 | eSe | Required Improvement | C Eykelbosh | JobChartPrintOut Folder, any plans to clean this out automatically? | "Add this to Data Clean-up feature. 04/08/19 AW: Database clean up code was done, need to be tested. Folder clean up will be included. 4/11/2019 - Preference is to be time based 30 days" |  | M | Pending |  | 40 | 2
73 |  | Required Improvement | A Wang | Create Data Upload Utility to load PLC data from eService data folder to server directly. This is for support use only. Once we grap the local data folder for investigation, toughbook local folder should be wiped off to let supervisor to have a clean start. |  |  | New |  |  |  | 1
78 | eSe | Required Improvement | Murray Bickley | Move the density trends to the top on both the live charting data and the print-outs |  |  | New |  |  |  | 1
79 | eSe | Bug | C Eykelbosh | Where there is no end time set and the print button is pressed, the system mis-calculates the interval time by a factor of 10 (is 30min, is displayed as 3min). Charts need to print right regardless of whether or not an end time is set. Current workaround is to end the job, print the chart, then resume live data logging by deleting the end date/time. |  |  | New |  |  |  | 1
34 | eService | Required Improvement | C Eykelbosh | "Get rid of FDAS ZIP file upload option, be able to attach multiple charts at once in eService, Remove the JobChartData selection. Review and clean up all data fields 6-18-2019 - CRE - eService needs to be scrubbed of references to FDAS, The treatment report screen has a selection for ""Did FDAS Function Correctly"", this should be renamed to ""Did eService Express Function Correctly"", this whole section should also be moved to the job performance tab vs. being on the treatment report tab." | "Will update eSerice client validation rule and attachment optionlist to fit in the transition from FDAS to eService Express 04/08/19 AW: Agreed " | 24 | Pending |  |  |  | 1
77 | eService | Required Improvement | C Eykelbosh | "Make ""Chart"" the defualt attachement type in eService (it is currently bid proposal) and have it open to the c:\jobchartprintout folder every time vs. the last folder that a file was uploaded from 7-4-2019 CRE - eService should pop up a message if no chart is attached to the ticket as a reminder. They can still choose not to attach a chart in cases like product sales, day rates, etc." |  |  | New |  |  |  | 1
78 | eSe | Required Improvement | Adam Wang | Make each chart title with title chart only, e.g. RATE (m3/min)
79 | eSe | Required Improvement | Adam Wang | Clean up temp folder & print out folder | 和#39合并
时