## Sheet1
Function | Breakdown | Dependency | Priority 1 | Priority 2 | Priority 3 | Priority 4
1. Enhance eServiceOnline Product Haul function to add pod allocation. | 1.1 Add unit pod information master data. |  |  |  | 16
| 1.2 Enhance load sheet structure to support pods |  | 16
| 1.3 Business rule implementation to validate load amount against pod capacity, legal limit and road ban factors. | 1.1 |  |  | 40
| 1.4 User interface improvement to split tonnage to pods | 1.2 |  | 24
| 1.5 Enhance load sheet printing to support pods | 1.2 |  | 16
| 1.6 Enhance load sheet API expose data to Blend Verification App | 1.2 | 8
2. Add Inventory Checking API to query AX by location and product name. | 2.1 Fix GetLoadSheet API to assure product names is using AX product name. |  |  | 8
| 2.2 Create inventory view in SanjelData database to connect to AX database |  |  | 8
| 2.3 Build Inventory Checking API | 2.1, 2.2 |  | 8
3.Add Load Sheet status update APIs. | 3.1 Add BLENDING, COMPLETE status to load sheet |  |  | 16
| 3.2 Add BLENDING status update API | 3.1 |  | 8
| 3.3 Add Loaded Load sheet data structure |  | 8
| 3.4 Add COMPLETE status and load sheet details post back API | 3.1, 1.2, 3.3 |  | 24
| 3.5 Improve Rig Board to show BLENDING, COMPLETE status | 3.1 |  |  |  | 16
| 3.6 Filter out COMPLETE load sheet in get load sheet API | 3.4 |  | 8
4.Integration for posting movement journal to AX | 4.1 Add integration to compile movement journal export file | 3.4 |  |  | 16
| 4.2 Add import movement journal function in AX. | 4.1 |  |  | NTT Data
| 4.3 Add new function to handle post failures and repost. | 4.2 |  |  | 40
5.MTS | 5.1 Port load sheet printing code to print MTS from server | 3.3, 3.4 |  | 40
| 5.2 Loaded load sheet database implement as MTS central repository | 3.3 |  |  | 40
| 5.3 MTS print from server standalone API | 3.3 | 60 |  |  | This is alternative solution without implement server functions.