## Sheet1
Product Introduction Process
Actions | BU BLE | BU Client Technical Support | BU Technology | Corporate Engineering | Corporate Technology | BU Client Solutions | Corporate Client Solutions | IS Applications | Operations | Project Leader | Marketing | Supply Chain | VP/Excecutive
Idea Generating Project Request
A1. Project Request filled out | Anyone
A2. Project Request vetted by BLE or CSM Manager | R | C |  | A | C | R
A3. Project Requests forwarded to Corp. Eng. Advisor | A | R |  | I | R | C
A4. Stakeholders consulted, Impact Assessed | R | C | C | A | C | C |  |  | C |  |  | C
A5. Project approved* and assigned or rejected | C | C | C | R | C | C | [5 empty] | I | A
*If approved for Rapid Response, goto C2
Concept Phase
B1. Complete Concept Summary | A |  | I | C | I | I |  |  |  | R |  |  | I
B1a. Review for proper Sanjel IP or existing IP | I |  | I | A | R | I |  |  |  | I |  |  | I
B2. Project approved and assigned or rejected | C | C | C | R | C | C | [6 empty] | A
Feasibility Phase
C1. Complete Business Plan if required | A | I |  | C | C | C | C |  |  | R |  | I
C2. Complete Rapid Response Project Scope if needed | A | I |  | C | C | C |  |  |  | R |  | I
C3. Project approved, put on hold or terminated | C | C | C | R | C | C | [6 empty] | A
Development Phase
D1. Lab testing plan developed | I | I | A | C | A | I |  |  |  | R
D2. Lab testing carried out | I | I | A | C | A | I |  |  |  | R
D3. Lab Report issued to stakeholders | I | I | A | C | A | I |  |  |  | R |  | I | I
D4. Stakeholders consider creating LDP number | C | I | C | R | C | C |  |  |  | I |  |  | A
D5. LDP # Issued | I | I | I | I | R | I |  | I |  | C | I | I | A
D6. Field Trial Plan completed if needed | A |  | S | C |  | S |  |  | S | R
D7. Project approved, put on hold or terminated | R | I | I | A | C | C |  |  | C | I |  | I | I
Field Testing Phase
E1. Create Candidate Selection sheets if needed |  |  |  | I | A | I | [5 empty] | R
E2. LDP entered into SBS |  |  |  | I | A | I | [5 empty] | R
E3. Price the Product | I |  |  | I |  | R | A |  |  |  |  | C | I
E4. LDP entered into Pricebook, eService, Invoice App | I |  |  | I |  | C | A | R | I | I | I | I
E5. LDP Entered into Job Design Template | I |  |  | A |  | R |  |  | I
E6. Create product regulatory set (SDS, labels, QC) | I |  | I | A | R | I |  |  | I | I |  | I
E7. Product is ordered for trial | A | I | I | I | I | C |  |  | I | C |  | R
E8. If replacing a product, begin deletion process | C | I | I | I | I | A |  | I | C |  | I | R | I
E9. Product is QC'd prior to field trial | I | A | R | I | I | I |  |  | I | C |  | I
E10. Operational fact sheet or WI is created if needed | A | I | C | C | I | I |  |  | I | R |  | C
E11. Conduct field trial | A | I | S | I | I | C |  |  | S | R |  | I | I
E12. Produce Field Trial Summary Report | A | I | C | I | I | C |  |  | C | R | I | I | I
E13. Project approved on to Commercialization | C | C | I | R | C | C |  |  | C | C | I | I | A
Commercialization
F1. Determine marketing tier (1,2 or 3) |  | C |  | C | C | C | A |  |  |  | R |  | I
F2.Name product | I | C | I | R | C | C | A |  | I | I | C | I | I
F3. Determine inventory locations and levels | C |  | I |  |  | A |  |  | C |  |  | R | I
F4. Update regulatory set (SDS, labels,QC) | I |  | I | A | R |  |  |  | I |  |  | S
F5. Create PDS and post | I | C | I | A | R | C |  |  |  | C | S
F6. Update name in SBS |  |  |  | I | A | I | [5 empty] | R
F7. Update name in eService, Pricebook, Invoice App |  |  |  | I |  | C | A | R | I | I | I | I
F8. Update name in JDT, Test Request | I |  |  | A |  | R |  | C | I
F9. Update lab calculators and/or worksheets |  | A | R |  | I
F10. Review for possible case history | R | S |  | C |  | A | C |  | C |  | C
F11. Communicate name change Internally | I | R | I | I | A | I |  | I | I | I | I | I | I
F12. Create Operations Training materials | R |  | C | C |  | I | C |  | A | C
F13. Create Sales Training materials | C | A | C | C | C | I | C |  |  | R | S
F14. Approved Product Launch Complete | C | C | I | R | C | C |  |  | C | C | I | I | A
R = Responsible - The person/group that is ultimately responsible for delivering
A = Accountable - The person/group who has ultimate accountability and authority, they are the person to whom "R" is accountable
S = Supportive - The person or individuals who are needed to do the work
C = Consulted - Someone whose input adds value and/or buy in is essential for ultimate result
I = Informed - Individuals who need to be informed of results or actions taken but don't need to be involved in the decision making process