## Sheet1
Product Introduction Process
Actions | Lab | Well Integrity Expert | Director Technical Sales & Engineering | Technical Sales | Technical Engineering | IT | Operations | Accounting | Marketing | Supply Chain | Excecutive
Project Request
A1. Project Request submitted | Anyone
A2. Project Request vetted by Well Integrity Expert
A4. Stakeholders consulted, Impact Assessed
A5. Project approved and assigned or rejected
Feasibility Phase
B2. Complete Project Scope if needed
B1. Review for proper Sanjel IP or existing IP
B1. Review for HSE and ESG affects positive and negative
B3. Project approved, put on hold or terminated
Development Phase
D1. Lab testing plan developed
D2. Experimental blend and/or additives name added to Blend Master Database | [5 empty] | R
D3. Lab testing carried out
D4. Lab Report issued to stakeholders
D5. Stakeholders consider creating LDP number
D6. LDP # Issued
D7. Change from experimental to LDP in Blend Master Database | [5 empty] | R
D8. Field Trial Plan completed if needed
D9. Project approved, put on hold or terminated
D10. If Project is terminated, delete blend/additives from Blend Master Database | [5 empty] | R
Field Testing Phase
E1. Create Candidate Selection sheets if needed
E2.0. If LDP is a new product or existing product replacement from a vendor, add to AX and assign an IIN | [5 empty] | S |  |  |  | R
E2.1. If LDP is a Sanjel Blend, enter LDP recipe into Blend Master Database | [5 empty] | R
E3. Price the Product
E4. LDP pricing entered Pricebook, price code entered in Blend Master Database | [5 empty] | R
E5. LDP blend name, recipe and pricing are available to Job Design Template, eService Applications, and BPAVS | [5 empty] | R
E6. Create product regulatory set (SDS, labels, QC)
E7. Product is ordered for trial
E8. If replacing a product, begin deletion process
E9. Product is QC'd prior to field trial
E10. Operational fact sheet or WI is created if needed
E11. Conduct field trial
E12. Produce Field Trial Summary Report
E13. Project approved on to Commercialization
Commercialization
F1. Determine marketing tier
F2.Name product
F3.Change LDP to Published, update name in Blend Master Database | [5 empty] | R
F4. Update Price Book with final product name. | [5 empty] | R
F5. Determine inventory locations and levels
F6. Update regulatory set (SDS, labels,QC)
F7. Create PDS and post
F8. If the product has an IIN, update name in AX | [5 empty] | S |  |  |  | R
F7. Update name in eService, Pricebook, Invoice App | [11 empty] | Blend Master Database provides single souce of truth for all appliation now.
F8. Update name in JDT, Test Request
F9. Update lab calculators and/or worksheets
F10. Review for possible case history
F11. Communicate name change Internally
F12. Create Operations Training materials
F13. Create Sales Training materials
F14. Approved Product Launch Complete
R = Responsible - The person/group that is ultimately responsible for delivering
A = Accountable - The person/group who has ultimate accountability and authority, they are the person to whom "R" is accountable
S = Supportive - The person or individuals who are needed to do the work
C = Consulted - Someone whose input adds value and/or buy in is essential for ultimate result
I = Informed - Individuals who need to be informed of results or actions taken but don't need to be involved in the decision making process