## Stick
DALY UNIT NO. 3 HZNTL 5-1-10-28
[9 empty] | CASING & CEMENTING |  |  | DRILLING PROCEDURES
Bottom Hole: 103/05-01-010-28 WPM | [8 empty] | Surface Casing: 244.5mm, 48.1kg/m, H-40, ST&C @ 200m |  |  | BHA #1
Horizontal f/ Surface 6A-2-10-28 WPM | [8 empty] | Burst: | 16,000 kPa |  | 349mm Bit, 205mm motor, 1 x 205mm DC, X/O, 6 x 159mm DC's, X/O, 101.6mm DP
AFE#: | D17DAL004 |  | RIG: | Ensign 651 |  |  | Objective Formation | Middle Daly | Collapse: | 10,000 kPa |  | BHA #02 - Drill from casing shoe to Int. casing Point. Flowrate 1.3 - 1.9 m3/min and differential between 3500 - 4500 Kpa
AFE $: | 720718 |  | Licence No. | 10692 |  |  | Reservoir Pressure | 8000 - 15000 kPa | Tensile: | 113,000 daN |  | TBD PDC, 7/8 5.0 stage Fixed Mud Motor w/ 2.38° bend, UBHO sub, Non Mag Pony Sub, NMDC, Gap Sub, NM Pony Sub
ELEVATIONS & COORDINATES | [8 empty] | Minimum Torque: | 2590 N-m |  | Lockdown Sub, 2xNMFC, Hydraulic/Mechanical Jars, X/O, 4" HWDP (Install HWDP as required to maintain WOB), 4" Drill Pipe
Ground Elevation: |  | 498.62 | m | [5 empty] | Optimum Torque; | 3440 N-m |  | BHA #03 - Drill Int. casing point to Total Depth - Flowrate 1.0 - 1.3 m3/min and differential between 3500 - 4500 Kpa
KB to Ground (est): |  | 4.35 | est. | [5 empty] | Maximum Torque: | 4310 N-m |  | TBD PDC, 6/7 8.0 Stage Motor w/ 1.5/1.83° bend, UBHO Sub, NMDC, Gap Sub, NM Pony Sub, Lockdown Sub, NMFC, X/O,
KB ELEVATION (est): |  | 502.97 | m |  |  |  | BOP Stack |  | Install 1 centralizer on shoe joint, 1 on next 2 jts and then every 3rd jt to surface |  |  | 4" DP (enough to keep HWDP in vertical section), 4" HWDP, 4" DP
CO-ORDINATES: | Surface: | 550 | m | North of South | Bdy of Sec 2 |  | 278 mm x 21 Mpa |  | Cement: See Sanjel Cementing Program |  |  | BITS & MOTORS
|  | 613 | m | East of West | Bdy of Sec 2 |  |  |  | Surface Cement: SURFACEmix LW PRO (SK) + 0.5% SCA-6 + 0.5% SCA-7 + 0.15% CDF-6P |  |  | HOLE SECTION | BIT PROVIDER | MODEL | NOZZLES | MOTORS
| Landing Pt | 750 | m | North of South | Bdy of Sec 2 |  | Casing Bowl |  | If losses are anticipated, add 1kg/m3 LCF-7 to cement slurry |  |  | Surface: 349mm | Tanner Bits Supply | GLL | 15.9's | None
|  | 685.48 | m | West of East | Bdy of Sec 2 |  | 279 mm x 244.5 mm - 21 mPa
| Bottomhole: | 770 | m | North of South | Bdy of Sec 1 |  |  |  | Intermediate Casing |  |  | 222mm: | TBD | PDC | 11.1's | 7/8 5.0 Stage w/ 2° Fixed Bend
|  | 282.11 | m | East of West | Bdy of Sec 1 |  |  |  | 177.8mm, 34.23kg/m, J-55, LT&C: 0 - 689mTVD (~745mMD)
SURFACE CASING | [8 empty] | Burst: | 30,100kPa |  | 159 mm: | TBD | PDC | 10.3's | 6/7 8.0 Stage w/ 1.5°/1.83° Bend
[9 empty] | Collapse: | 22,500 kPa |  | GEOLOGY
[9 empty] | Tensile: | 162,800 daN |  | Objective: | Middle Daly - Oil
Surface Casing Setting Depth: |  |  | 150 | m KB |  |  |  |  | Minimum Torque: | 3180 N-m |  | Samples: | Corex: 5m intervals from 650 mTVD to landing point, 10m intervals through lateral to Total Depth
|  | This is a High Risk Well (Offsetting Injectors) | [6 empty] | Optimum Torque; | 4240 N-m |  |  | MIEM: As per Well Licence
|  | Perform Leak Off Test | [6 empty] | Maximum Torque: | 5300 N-m |  | Coring: | None
[9 empty] | Intermediate Casing Cement - See Sanjel Cementing Program |  |  | Logging: | GR-MWD from surface casing drill out to Total depth. No openhole logs required.
Install a PVT system that is sensitive to +/- 0.5 m3 and alarm at +/- 1.0m3. | [8 empty] | 3m3 Fresh Water |  |  | Gas Detection: | From Surface Casing Shoe to Total Depth
FORMATION TOPS & PRESSURES | [8 empty] | 3m3 Visweep mixed at 1200kg/m3
FORMATION | Subsea | TVD | MD | Isopach | Expected |  |  |  | Lead (0 - 520m): LITEmix 1400 (SK) + 0.75% SCA-6 + 0.75% SCA-7 + 0.3% MCR-7 + 0.25% CDF-6P |  |  | H2S CONTENT
| (m) | (m) | (m) | (m) | Lithology |  |  |  | Tail (520 - ICP) : PRODUCTIONmix 1600 (SK) + 1% SCA-6 + 1% GSS-1 + 0.2% CDF-6P
Favel (Second White Specks) | 131 | 371.97 | 371.97 | 70 | Clastic |  |  |  | If losses are anticipated, add 1kg/m3 LCF-7 |  |  | Possible in the Lodgepole
Base Fish Scales | 61 | 441.97 | 441.97 | 61 | Clastic |  |  |  | Production Casing:
KOP | 49 | 453.97 | 453.97 | [5 empty] | 114.3mm, 17.26kg/m, L-80, LT&C: TD - 790mMD. Run liner hanger with 30m overlap; ~ 50-55°
Jurassic | 0 | 502.97 | 503 | 176.5 | Clastic |  |  |  | Tie back string to be run with drilling rig
Upper Amaranth Anhydrite | -176.5 | 679.47 | 736 | 26 | Anhydrite |  |  |  | Frac sleeves to be placed every 40m in lateral. Casing tally to be approved by Calgary office
Lower Amaranth (Spearfish) | -202.5 | 705.47 | 811 | 2.5 | Shale, Anhydrite |  |  |  | Burst: | 54,000 kPa |  | CONTACT LIST
Flossie Lake | -205 | 707.97 | 819 | 18 | Dolomite, Anhydrite |  |  |  | Collapse: | 44,000 kPa |  | Corex | Contact | Office | Cell | Email
Middle Daly | -223 | 725.97 | 902 | 6 | Limestone |  |  |  | Tensile: | 119,000 daN |  | Drilling Superintendent | Wade Schell | 403-718-6346 | 403-510-2606 | wades@corexresources.ca
Landing Point | -229 | 731.97 | 982 | [5 empty] | Minimum Torque: | 2260 N-m |  | Chief Operating Officer | Harley Rea | 403-718-6372 | 403-660-3362 | harleyr@corexresources.ca
Total Depth | -228 | 730.97 | 1980 | [5 empty] | Optimum Torque; | 3020 N-m |  | Completion Superintendent | Bruce Standing | 403-718-6363 | 403-862-2506 | bruces@corexresources.ca
[9 empty] | Maximum Torque: | 3780 N-m |  | Geologist | Andrea Henry |  | 403-999-5545 | andreah@corexresources.ca
Lower Daly | -231 | 733.97 |  | 9 | Limestone |  |  |  | Production Casing Cement - See Sanjel Cementing Program |  |  | Manager EH&S | Rob Crawford | 403-718-6354 | 403-831-7911 | robc@corexresources.ca
Comments | [11 empty] | Field Superintendent | Harv Jacobsen |  | 204-851-3949 | harvj@corexresources.ca
Landing target is 6m below top of Middle Daly | [8 empty] | DIRECTIONAL PROFILE & SURVEY PROGRAM |  |  | Construction Supervisor | Kirk Gilliard |  | 204-522-0803 | crudeoperating@outlook.com
Well trajectory follows Middle Daly structure and rises 5m over the first 450m of lateral, then drops 4m to toe | [8 empty] | Approved Directional Plan No. 3
[9 empty] | 349 mm Surface |  |  | Wellsite Supervisor | Cal Dumaine |  | 306-482-7020 | cobrettcal@sasktel.net
Objective Formation | Reservoir Pressure | [7 empty] | Drill with 349mm surface bit to 150m. Maintain inclination below 3°. |  |  | Wellsite Supervisor | Scott Bertholet |  | 204-851-3338 | scottbertholet@gmail.com
Middle Daly | 7000 - 15,000 kPa | [7 empty] | 222mm Vertical hole & Build Section
Offset Injectors & Surface Pressures | [8 empty] | KOP @ 453m. Build @ 6.8°/30m to 689mTVD. Set 177.8mm Casing 10mTVD into U. Amaranth |  |  | Corex Resources | 24hr Emergency | 1-403-265-1805
100/12-1-10-28: 0 kPa(718m) | [8 empty] | 159mm Build and Lateral Section |  |  | Corex Resources | Virden Field Office | 204-748-1334
100/16-2-10-28: 2000 kPa: | [8 empty] | Continue 159mm Build @ 6.8°/30m to 759mMD. Hold @ 70° from 759 - 779 m for 20m Tangent
102/14-35-9-28: Suspended | [8 empty] | Continue to build to 982mMD, 731mTVD landing point. Drill 159mm lateral section to 1980mMD, 730mTVD.
102/16-35-9-28: Suspended | [11 empty] | POTENTIAL PROBLEMS
Recent pressures have shown variable pressure in the range of 5000 - 12000kPa. Be prepared for 15,000kPa | [11 empty] | Lost Circulation: Possible on surface hole. Possible in Jurassic & Lodgepole during lateral. Generally not severe.
that was seen in the Amaranth in this Unit. | [8 empty] | Heel | 982 | m | Abnormal Pressure: High pressures could be expected throughout. Daly zone 8,000-15,000 kPa
The 100/7-2-10-28 vertical has high pressure consistently | [8 empty] | Total Depth | 1980 | m | Tight Hole / Reaming: Circulate hole clean prior to penetrating the Jurassic. Ensure hole is cleaning properly.
102/10-1-10-28: Encountered flow at 1028mMD. | [8 empty] | Azimuth | 90.06 | ° | Mix sawdust through upper part of Lodgepole if required when drilling. Wiper trip if hole conditions dictate.
102/5-1-10-28: Drilled lateral with 1250kg/m3 Density, no sign of flow while drilling lateral. | [8 empty] | Hz Length | 998 | m | Water Flow: Possible in the Mannville.
[9 empty] | Drilling Fluids |  |  | Amaranth Anhydrite: Pretreat with Soda Ash to prevent issues.
Drilling Rig | Ensign 651 | Derek Katzberg - Rig Manager: 306-485-8540 | [6 empty] | Surface Hole: GEL SLURRY 0 - 150m |  |  | Mud Rings: Possible on surface hole. Visc builds rapidly due to Native Clays.
Directional | Phoenix | [7 empty] | Density: < 1080kg/m3 |  |  | Torque & Drag: Mix walnut shells as required to reduce T&D
Wellsite Shacks | Campbell | [7 empty] | Visc.: 45 - 55 sec/L drilling; 60+ for casing; 42 - 45sec/L Cementing |  |  | Differential Sticking: Maintain low fluid loss and low Density. Good drillingpractices should be followed.
Centrifuge | Campbell | [7 empty] | pH: Neutral
Water Truck | Heritage Water Hauling | [7 empty] | Fluid Loss: No Control
Vac Truck | Pump Action | [7 empty] | Main Hole: Floc Water 150 - 450m |  |  | WELL PLAN OVERVIEW
Waste Treatment System | Double Barrel Oilfield | [7 empty] | Density: 1000 - 1010kg/m3 |  |  | 1. Drill 349mm surface hole to 150m. Run & Cement 244.5mm, 48.07kg/m, H-40, ST&C casing.
Drilling Fluids | Secure Energy Services | Brad Coffey |  | 1-204-761-0249 |  |  |  |  | pH: Neutral |  |  | 2. Drill out and perform leak off test required.
Potable Water | Field | [7 empty] | Visc.: 28 - 30 sec/L |  |  | 3. Drill 222mm vertical section to 453m, kick off and drill build section, building at 6.8°/30m to ~ 745mMD (~10mTVD into U. Amaranth), intermediate Casing Point,
Cementing | Sanjel | Estevan, Sk - 1-888-778-4075 | [6 empty] | Calcium: 800 - 1000 mg/L |  |  | 4. Run 177.8mm, 34.23kg/m, J-55, LT&C Intermediate Casing and Cement.
Garbage/Dumpster | Field | [7 empty] | Clay Free High Calcium Polymer: 450 m - Total Depth |  |  | 5. Drill 159mm build section, building at 6.8°/30m, hold @ 70° from 759 - 779mMD for 20m tangent, continue build section to 982mMD, 731mTVD, landing point.
Environmental | Wellsite Environmental | Murray Green - 403-740-5054 | [6 empty] | Density: 1020 - 1100kg/m3 |  |  | Drill 159mm lateral section to 1980mMD, 730mTVD, total depth.
Wellhead / Csg Bowl | Weatherford | [7 empty] | Visc: 34 - 36sec/L; 50 - 55 sec/L 50m prior to TD |  |  | 6. Circulate hole clean. Monitor hole conditions while POOH, should nothing appear, proceed with POOH and running casing without wiper trip. In case of
Volant Tool | Top Torque Services | [7 empty] | Fluid Loss: 8 - 10 mL/30 min |  |  | difficulty, wiper trip to intermediate casing point. Run 114.3mm casing with frac sleeves spaced 40m apart. Run liner hanger with 30m overlap to ~ 50 - 55°.
Pressure Testing | Field | [7 empty] | pH: Neutral |  |  | and cement 114.3mm liner. Sting out and back wash cement as required, set compression set Import Liner Hanger packer as instructed by import Tool Rep.
Welding | Field | [7 empty] | Ca++: 800 - 900mg/L |  |  | 7. Circulate, POOH and L/D DP. RIH with 114.3mm tie back string.
Fuel | Mar-Dee | [7 empty] | Refer to Secure Drilling Fluids Program |  |  | 8. POOH, tear out.
Surface Bits | Tanner Bits
Main Hole Bits | Halliburton
Main Hole Bits | Baker
Frac Sleeves | Gryphon Oilfield Solutions |  |  | Emergency Contacts:
Casing | Tenaris |  |  | MIEM District Office: | Virden | 204-748-4260
Float Equipment | Top-Co |  |  | RCMP: | Virden | 204-748-2135
Casing Dispatch | Fontana Trucking |  |  | Hospital: | Virden | 204-748-1230
Rig Moves | Fast Trucking |  |  | Ambulance/Fire |  | 911
|  |  |  | County | R.M. of Wallace-Woodworth
Note: Prior to ordering any services ensure they are listed on the Comply Works
159 mm Lateral Section
Surface Hole
349mm hole
244.5mm, 48.1 kg/m
H-40, ST&C Set @ 150m
CEMENT TOP: Ground Level
222mm Vertical & Build Section
KOP @ 453m; Build @ 6.8°/30m
Set 177.8mm Int. Csg ~10mTVD into U. Amaranth
Tangent @ 70°, hold from 759 - 779m
Landing Point @ 982mMD; 731mTVD @ 90°
Total Depth: 1980mMD; 730mTVD