## 项目日程安排
在此工作表中创建项目日程安排。 在单元格 B1 中输入此项目的标题。 有关如何使用此工作表（包括屏幕阅读器的说明）以及此工作簿作者的信息包含在“关于”工作表中。 继续向下浏览 A 列，获取进一步指示。 | Sanjel Migration Upgrade Project Plan
在单元格 B3 中输入项目主管的姓名。在单元格 E3 中输入项目开始日期。项目开始：标签位于单元格 C3 中。 | 开始时间 | 2023-07-03 | 工作量合计(人时) | #REF! |  | 项目开始： |  | 2023-07-04
单元格 E4 中的显示周数表示单元格 I4 中项目日程安排内显示的起始周数。项目开始日期视为第 1 周。要更改显示周数，只需单元格 E4 中输入新的周数。 从单元格 E4 的显示周数开始，每周的开始日期从单元格 I4 开始并且说自动计算得出的。在该视图中，从单元格 I4 到单元格 BF4 共有 8 周的时间。 请勿修改这些单元格。 显示周数：标签位于单元格 C4 中。 | 结束时间 | 2024-05-17 | 工作量合计(人天) | #VALUE! |  | 显示周数： |  | 1 |  |  |  | 2023-07-03 | [6 empty] | 2023-07-10 | [6 empty] | 2023-07-17 | [6 empty] | 2023-07-24 | [6 empty] | 2023-07-31 | [6 empty] | 2023-08-07 | [6 empty] | 2023-08-14 | [6 empty] | 2023-08-21 | [6 empty] | 2023-08-28 | [6 empty] | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25 | [5 empty] | 2023-10-01 | [5 empty] | 2023-10-07 | [5 empty] | 2023-10-13 | [5 empty] | 2023-10-19 | [5 empty] | 2023-10-25 | [5 empty] | 2023-10-31 | [5 empty] | 2023-11-06 | [5 empty] | 2023-11-12 | [5 empty] | 2023-11-18 | [5 empty] | 2023-11-24 | [5 empty] | 2023-11-30 | [5 empty] | 2023-12-06 | [5 empty] | 2023-12-12 | [5 empty] | 2023-12-18 | [5 empty] | 2023-12-24 | [5 empty] | 2023-12-30 | [5 empty] | 2024-01-05 | [5 empty] | 2024-01-11 | [5 empty] | 2024-01-17 | [5 empty] | 2024-01-23 | [5 empty] | 2024-01-29 | [5 empty] | 2024-02-04 | [5 empty] | 2024-02-10 | [5 empty] | 2024-02-16 | [5 empty] | 2024-02-22 | [5 empty] | 2024-02-28 | [5 empty] | 2024-03-05 | [5 empty] | 2024-03-11 | [5 empty] | 2024-03-17 | [5 empty] | 2024-03-23 | [5 empty] | 2024-03-29 | [5 empty] | 2024-04-04 | [5 empty] | 2024-04-10 | [5 empty] | 2024-04-16 | [5 empty] | 2024-04-22 | [5 empty] | 2024-04-28 | [5 empty] | 2024-05-04 | [5 empty] | 2024-05-10 | [5 empty] | 2024-05-16 | [5 empty] | 2024-05-22 | [5 empty] | 2024-05-28 | [5 empty] | 2024-06-03
单元格 I5 到 BL5 包含每个日期单元格上方单元格块中表示的星期的日期数字并且是自动计算得出的。 请勿修改这些单元格。 今天的日期带有红色（十六进制 #AD3815）轮廓（从第 5 行中显示今天日期的列及至项目日程安排结尾的该列）。 | time axis 2023-07-03 to 2024-06-08
此行包含其后面的项目日程安排的标题。 从 B6 浏览到 BL6 以获取内容。该标题上方日期一周中每一天的首字母，从单元格 I6 开始，直到单元格 BL6。 所有项目日程表图表都是根据输入的开始和结束日期使用条件格式自动生成的。 从单元格 I7 开始的列 I 之后，请勿修改列内单元格中的内容。 | 任务编号 | 任务 |  |  | 分配到 | 预估时间 | 进度 | 开始日期 | 结束日期 | 前置任务 | 天数 | time axis 2023-07-03 to 2024-06-08
请勿删除此行。隐藏了此行，以保留用于突出显示项目日程安排中当天的公式。
单元格 B8 包含第 1 阶段示例标题。 在单元格 B8 中输入新标题。 如果适用于你的项目，请在单元格 C8 中输入名称以指定阶段。 如果适用于你的项目，请在单元格 D8 中输入整个阶段的进度。 如果适用于你的项目，请在单元格 E8 和 F8 中输入整个阶段的开始和结束日期。 甘特图将根据输入的进度自动填充适当的日期和着色。 要仅从任务中删除阶段和工作，只需删除此行即可。 | 阶段 1 Build Blend Library、Split Printing Library、Split Well Library、Replace Logging library |  |  |  |  | 24 |  | 2023-07-03
| 1.1 | Build Blend Library | One blend master database and blend calculator serves all applications. |  |  |  | 100%
| 1.2 | （optional） | Unit test
| 1.3 |  | Replace old components in application
| 1.4 |  | The affected apps need to be upgraded
| 1.5 | （optional） | System function verification after component replacement
| 1.6 |  | The affected apps is Released
| 2.1 | Split Printing Library | One printing library serves all applications, replace legacy printouts to make PDF copy available automatically. |  | 童韬 |  | 100%
| 2.2 | （optional） | Unit test |  |  |  | 0%
| 2.3 |  | Replace old components in application
| 2.4 |  | The affected apps need to be upgraded
| 2.5 | （optional） | System function verification after component replacement
| 2.6 | （optional） | Synchronize related requirements to wiki
| 2.7 |  | The affected apps is Released |  |  | 0
单元格 B9 包含示例任务“任务 1”。 在单元格 B9 中输入新的任务名称。 在单元格 C9 中输入任务负责人。 在单元格 D9 中输入任务进度。进度条出现在单元格中，并根据单元格中的数字进行着色。例如，50% 的进度将着色一半的单元格。 在单元格 E9 中输入任务开始日期。 在单元格 F9 中输入任务结束日期。 从单元格 I9 到 BL9 的块中显示输入日期的已着色状态栏。 | 3.1 | Split Well Library | One well library serves all application, include well location parsing, wellbore definition. |  | Miguel | ??? | 0%
| 3.2 |  | Unit test
| 3.3 |  | Replace old components in application
| 3.4 |  | The affected apps need to be upgraded
| 3.5 | （optional） | System function verification after component replacement
| 3.6 | （optional） | Synchronize related requirements to wiki
| 3.7 |  | The affected apps is Released |  |  | 0
第 10 行到第 13 行重复第 9 行的模式。 请对此工作表中的所有任务行重复单元格 A9 中的指令。覆盖任何示例数据。 另一个阶段的示例从单元格 A14 开始。 继续在单元格 A10 到 A13 中输入任务或转到单元格 A14 了解详细信息。 | 4.1 | Replace Logging library | Log files format, location, retention cycle will be determined. |  | 童韬 | 24 | 0%
| 4.2 |  | Unit test
| 4.3 |  | Replace old components in application
| 4.4 |  | The affected apps need to be upgraded
| 4.5 | （optional） | System function verification after component replacement
| 4.6 | （optional） | Synchronize related requirements to wiki
| 4.7 |  | The affected apps is Released |  |  | 0
| 阶段 2 Replace Messaging Library |  |  |  |  | 524 |  | 2023-07-03
| 5.1 | Azure IOT Hub | Documentation, Add PLC data transmission to message queue. Currently PLC data is packed in job package, we are experiencing the local plc data clean up issue very often. With this implementation, we will achieve a real-time PLC data transmission, this will allow remote monitoring possible. |  | Miguel | 24 | 0
| 5.1.1 | Architecture prototype verification | Create an Proof of concept of the arquitecture using either onpremises MQTT or Azure IOT Hub |  | Miguel | 40 | 0 |  |  |  | 5
| 5.2.1 | Sanjel.Common.Messaging | Replace it with a Message Queue. Introduce Metashare.Messaging library, it is a MQTT based library. There will be a shared effort to enhance messaging library to meet Sanjel's requirement. |  | Miguel 、童韬、宫洁 | 300 | 0% |  |  | 5.1
| 5.2.2 | Sanjel.Common.UIFramework | Change messaging logic |  | 童韬、宫洁 | 80 | 0 |  |  | 5.2.1
| 5.2.3 |  | Unit test
| 5.2.4 |  | Replace old components in application
| 5.2.5 |  | The affected apps need to be upgraded
| 5.2.6 | （optional） | System function verification after component replacement
| 5.2.7 | （optional） | Synchronize related requirements to wiki
| 5.2.8 |  | The affected apps is Released |  |  | 0
| 5.3.1 | Add Eservice data transmission to message queue | Currently job package data is transferred by eService Messaging Library. eService Messaging Library was developed almost two decades ago by Sanjel development team. It is still working and stable, but it lack of the modern message queue features, such like monitoring, guarantee of delivery, subscription mechanism, multiple topic supports, etc. |  | Miguel | 40 | 0 |  |  | 5.2
| 5.3.2 | Add PLC data transmission to message queue. | Currently PLC data is packed in job package, we are experiencing the local plc data clean up issue very often. With this implementation, we will achieve a real-time PLC data transmission, this will allow remote monitoring possible. - Alternative solution, will Azure IOT Hub be a solution to accommodate this need as well? |  | 童韬 | 40 | 0 |  |  | 5.2
| 5.3.3 |  | Unit test
| 5.3.4 | （optional） | System function verification after component replacement
| 5.3.5 | （optional） | Synchronize related requirements to wiki
| 5.3.6 |  | The affected apps is Released |  |  | 0
右侧的单元格包含第 2 阶段示例标题。 可随时在 B 列中创建新阶段。此项目日程安排不需要阶段。要删除阶段，只需删除该行即可。 要在此行中创建新的阶段块，请在右侧的单元格中输入新的标题。 要继续向上述阶段添加任务，请在此行上方输入一个新行，并按照单元格 A9 的指令填写任务数据。 根据单元格 A8 的指令更新右侧单元格中的阶段详细信息。 继续向下浏览 A 列单元格，了解更多信息。 如果尚未在此工作表中添加任何新行，将在单元格 B20 和 B26 中找到已创建的 2 个其他示例阶段块。否则，请浏览 A 列单元格以查找其他块。 在需要时重复单元格 A8 和 A9 的说明进行操作。 | 阶段 3 Upgrade Sanjel Business Entity Library |  |  |  |  | 2618 |  | 2023-08-07 | 2024-01-08 |  | 155
| 6.1.1 | Common.core changes | Implement cache |  | Miguel | 80 | 0% | 2023-08-07 | 2023-09-01 |  | 26
| 6.1.2 | MetaShare.Common.Core | Deprecate or Move some namespaces (offline, Proxies, serialization, NetPipeService) |  | Miguel、宫洁 | 80 | 0%
| 6.1.3 | Sanjel.Common.Utilities | Deprecate Proxies, WCFExtensions,NetPipeService; ContextedGateway should call the right instance of the interface API only); |  |  | 40 | 0%
| 6.1.4 | Sanjel.BusinessEntities.Standard | Generate MMC Classes. ~90 classes, |  | 童韬、宫洁 、Miguel | 400 | 0% | 2023-08-07 | 2023-09-01 |  | 26
| 6.1.5 | MetaShare.Common.ServiceModel | Deprecate DAO, move controller namespace to another lib, deprecate services, migrate missing methods to MMC or Common.core |  | Miguel | 80 | 0% | 2023-08-27 | 2023-09-08 |  | 13
| 6.1.6 | Sanjel.Common.RDLReporting | Deprecated. Generate ~17 Main reports and 164 sections with printing services. Redevelop all printouts to make a modern look and feel |  | 童韬、宫洁 、Miguel | 600 | 0% | 2023-09-03 | 2023-10-16 |  | 44
| 6.1.7 | Support e-signature. | PDF |  | Miguel、童韬 | 80 | 0% | 2023-10-16 | 2023-10-20 |  | 5
| 6.2.1 | Mapper | Lib PoC performance or generate MMC mappers, (mapperly,automaper, custom, ) |  | 宫洁 | 32 | 0% | 2023-10-23 | 2023-10-26 | 6.1 | 4
| 6.2.2 | Sanjel.Common.BusinessEntities.Standard | Refactor Reference Data update using SanjelData as source, remove dependency on WCF service. |  | Miguel、童韬、宫洁 | 150 | 0% | 2023-10-23 | 2023-11-03 | 6.1 | 12
| 6.2.3 | Sanjel.Common.Gateways.Standard | Create new Gateway using factory, replace it with MMC Sqlite (offline).Introduce SQLite database to replace File System/xml. |  | Miguel、童韬、宫洁 | 300 | 0% | 2023-11-06 | 2023-11-22 | 6.1 | 17
| 6.2.4 | Sanjel.Common.UIFramework | Replace Reports, |  | 童韬、宫洁 | 32 | 0% | 2023-11-22 | 2023-11-24 | 6.1 | 3
| 6.3 | Sanjel.BusinessEntities.Standard Mappers | Create mappers |  | Miguel、童韬、宫洁 | 400 | 0% | 2023-11-24 | 2023-12-18 | 6.2 | 25
| 6.4 | MetaShare.Common.Core | Clean up local attachment/MS Excel Utility to remove dependency to legacy caching mechanism. |  | Miguel、童韬、宫洁 | 80 | 0% | 2023-12-19 | 2023-12-22 | 6.3 | 4
| 6.5 | Sanjel.Common.UIProcess | Replace gateways, Replace services |  | Miguel、童韬、宫洁 | 120 | 0% |  |  | 7.4
| 6.5 | Sanjel.Common.Gateways | Replace eService Online Gateway, Web Api + Asynchronous programing to improve performance |  | Miguel、银幸元、宫洁 | 120 | 0% | 2023-12-25 | 2024-01-08 | 6.4 | 15
| 6.6 | Data Hand Book Management tool |  |  |  | ?？ | 0% |  |  | 6.5
| 6.7 | Price Book Management tool |  |  |  | ?？ | 0% |  |  | 6.6
| 6.8 | Sanjel.Security.UI | Deprecate lib and Move LogIn form |  | 童韬 | 24 | 0 | 2024-01-09 | 2024-01-11 |  | 3
| 6.9 | Security Management tool | Use SanjelData + web api |  |  | ?？ | 0% |  |  | 6.7
示例阶段标题块 | 阶段 4 Upgrade Win UI to .Net 6 |  |  |  |  | 1162 |  | 2024-01-08 | 2024-04-05 |  | 89
| 7.1.1 | Sanjel.BusinessEntities, Sanjel.Common.BusinessEntities, etc. | Target NET 6/Standard2.0 |  | Miguel | 40 | 0% | 2024-01-08 | 2024-01-12 |  | 5
| 7.2 | MetaShare.Common.Foundation | Migrate Microsoft.Exchange.WebServices; |  | 宫洁 | 32 | 0% | 2024-01-09 | 2024-01-12 | 7.1 | 4
| 7.3.2 | Sanjel.Common.UI | Microsoft office interop compatibility/runtime test |  | 童韬 | 80 | 0% | 2024-01-15 | 2024-01-26 | 7.2 | 12
| 7.4.1 | Sanjel.Common.Utilities | Target NET6/NetStandard2.0, Create a PoC and Migrate Impersonation. |  | Miguel、宫洁 | 40 | 0% | 2024-01-22 | 2024-01-26 | 7.3 | 5
| 7.4.2 | Sanjel.Common.WinUI | Target to Net 6, Refactor namespaces |  | Miguel、童韬、宫洁 | 180 | 0% | 2024-01-29 | 2024-02-08 | 7.3 | 11
| 7.5.1 | Sanjel.Common.Core | Target NET 6, migrate impersonation |  | Miguel、宫洁 | 80 | 0% | 2024-02-19 | 2024-02-23 | 7.4 | 5
| 7.5.2 | Sanjel.Common.UIProcess | Target to Net 6 upgrade namespaces or dll's |  | Miguel、童韬、宫洁 | 150 | 0% | 2024-02-19 | 2024-03-01 | 7.4 | 12
| 7.6 | SanjelEService\EService.WinUI | Target to NET6, Migrate MainMenu/MenuItem to ContextMenuStrip |  | Miguel | 40 | 0% | 2024-03-04 | 2024-03-08 | 7.5 | 5
| 7.7 | SanjelEService\EService.UIProcess | Target to Net 6, upgrade namespaces or dll's |  | 童韬、宫洁 | 80 | 0% | 2024-03-04 | 2024-03-08 | 7.6 | 5
| 7.8 | Upgrade eProgram to .Net 6 | Target to Net 6, upgrade namespaces or dll's |  | Miguel、童韬、宫洁 | 120 | 0% | 2024-03-11 | 2024-03-15 | 7.7 | 5
| 7.8.1 |  | Functional testing
| 7.8.2 |  | The affected apps is Released
| 7.9 | Upgrade eService to .Net 6 | Target to Net 6, upgrade namespaces or dll's |  | Miguel、童韬、宫洁 | 120 | 0% | 2024-03-18 | 2024-03-22 | 7.8 | 5
| 7.9.1 |  | Functional testing
| 7.9.2 |  | The affected apps is Released
| 7.10 | Upgrade eServiceExpress to .Net 6 | Target to Net 6, upgrade namespaces or dll's |  | Miguel、童韬、宫洁 | 120 | 0% | 2024-03-25 | 2024-03-29 | 7.9 | 5
| 7.10.1 |  | Functional testing
| 7.10.2 |  | The affected apps is Released
| 7.11 | Change Clickonce to dotnetmage 7 deployment tools | Unsupported CheckForDetailedUpdate / time estimated using alternative or create a launcher using net framework https://github.com/clowd/Clowd.Squirrel |  | 童韬、宫洁 | 80 | 0% | 2024-04-01 | 2024-04-05 | 7.10 | 5
示例阶段标题块 | 阶段 5 Proof of Concept New Architecture |  |  |  | Miguel、童韬、宫洁 | 60 | 0% | 2024-05-06 | 2024-05-10 |  | 5
|  | Sanjel.BusinessEntities.Facades | ???
|  | Sanjel.Common.UIDemo | ??? | ???
|  | Sanjel.Security.ManagerWinClient | ??? | ???
这是一个空行
此行标记项目日程安排的结尾。请勿在此行中输入任何内容。 在此行上方插入新行，以继续构建项目日程安排。 | 在此行上方插入新行

## 关于
关于此模板
此模板提供了一种创建甘特图的简单方法，可帮助直观呈现和跟踪项目。只需输入任务以及开始和结束日期 - 无需公式。甘特图中的条形表示任务的持续时间，并且使用条件格式显示。通过插入新行插入新任务。