## Sheet1
Total Time | 2247
| Tasks | Project | difficulty 4=hard, 1=easy | Estimate Time(H) | Suggestions and Questions | alternative
1 | Migrate Microsoft.Exchange.WebServices | SanjelCommonLibrary | 2 | 24 | change to use smtp or Microsoft Graph
2 | Change default font | \SanjelCommonLibrary | 1 | 2
| HighDpiMode needs to set in Application Starter | \SanjelCommonLibrary | 1 | 8
| Microsoft.Reporting.WinForms.ReportViewer (print pdf out) |  | 2 |  | in case of pdf preview and printing
| Microsoft.Reporting.WinForms.ReportViewer (generate pdf) |  | 4 |  | ~17 Main reports and 164 sections
| Migrate Libraries/Applications to NetStandard and/or NET 6 | \SanjelCommonLibrary | 2 | 80
obsolete | Create CoreWCF ASP.NET Core web host. | \SanjelEservice | 3 | 40
obsolete | Migrate WCF Services files to asp.net Startup and migrate web.config to wcf config | \SanjelEservice | 3 | 40
obsolete | Migrate url "test" endpoints | \SanjelEservice | 2 | 24
obsolete | Migrate WCFProxyBuilder | \SanjelCommonLibrary | 2 | 40 | Unsupported NetPipeBinding, NetNamedPipeBinding | https://learn.microsoft.com/en-us/dotnet/architecture/grpc-for-wcf-developers/migrate-wcf-to-grpc
obsolete | Change Clickonce to dotnetmage 7 deployment tools | \SanjelEservice | 2 | 100 | Unsupported CheckForDetailedUpdate / time estimated using alternative | https://github.com/clowd/Clowd.Squirrel
obsolete | Change/Crate namespace System.Deployment.Application using env variables | \SanjelCommonLibrary | 1 | 8
| Migrate Impersonation | \SanjelCommonLibrary | 2 | 40
| Microsoft office interop compatibility/runtime test | \SanjelCommonLibrary | 2 | 16 | change reference
| Migrate MainMenu/MenuItem to ContextMenuStrip | \SanjelEservice | 2 | 32
| Migrate WCF Tests projects |  | 2 | 32
| Upgrade Test Projects |  | 2 | 80
| DaoBase implements Cache Data -> implement in commoncore | commoncore\SanjelCommonLibrary | 2 | 32
| Change WCF ServiceBase to use commonCore service | commoncore\SanjelCommonLibrary | 2 | 24 | Create a interface to inject and implement an instance of trace utility in common.core
| (Optional) Deprecate the localCache related classes and instead create a common.core DAO instance with SQLite encryption version. | commoncore\SanjelCommonLibrary | 3 | 120
| Create CommonObject Extension Class/Library | commoncore\SanjelCommonLibrary | 2 | 16
| Add EServiceSection class and JobNumber property |  | 1 | 20 | depends on degin
| Add AggregatedObject class and properties |  | 2 | 20 | depends on degin
| Create ObjectBase Extension Library for common.core base object |  | 2 | 20 | depends on degin
| Include EServiceEntity and AggregatedObject properties |  | 2 | 20 | depends on degin
| Replace VersionedCollection entities with commoncore entities | \SanjelCommonLibrary | 2 | 16
| Sanjel.Common.PrintingService upgrade O2S.Components.PDF4NET lib. Replace some Classes/Methods | \SanjelCommonLibrary | 1 | 8
| Replace New Entity Classes or use old classes as a DTO's or ViewModels | All | 3 | 80 | I would recommend using DTOs and keeping MMC entities isolated from the presentation and wcf service layers.
| Modify MMC Code template | SanjelData | 2 | 80
| Design | All | 2 | 40
| Fix wrong namespaces after migrate to NET 6 | All | 2 | 150 | we are not sure of how many errors we are going to have
| Fix wrong packages after migrate to NET 6 | All | 2 | 150 | we are not sure of how many errors we are going to have
| Tests | All | 2 | 300
| Fix other net framework not build-time error but run-time error |  | 3 | 80
Total Time |  |  |  | 1742
Partial Migrate to EF Core
| Tasks | Project | difficulty 4=hard, 1=easy | Estimate Time(H)
1 | Create ContextBuilder ( to register connectionString) | MetaMetaCube RoadMap Template | 2 | 14
2 | Modify Program.cs web and api to register context builder | MetaMetaCube RoadMap Template | 1 | 8
3 | Create SanjelDataContext and implement interface | MetaMetaCube RoadMap Template | 4 | 68
4 | Modify Projects csproj to include new references | MetaMetaCube RoadMap Template | 1 | 8
5 | Modify XServicecs to inherit from new object version | MetaMetaCube RoadMap Template | 1 | 8
6 | Modify XServicecs to overwrite methods containing isAggregatedChildren parameter | MetaMetaCube RoadMap Template | 3 | 54
7 | Modify XService.cs to change custom methods containing isAggregatedChildren parameter | MetaMetaCube RoadMap Template | 3 | 54
8 | Modify XService.cs to change custom methods containing aggregationInfo parameter | MetaMetaCube RoadMap Template | 3 | 54
9 | Create Base context class and Interface | CommonCore extensions | 2 | 32
10 | Create Dao Extension utility to create and activate Context | CommonCore extensions | 2 | 41
11 | Crate new implementation for ObjectVersionService using EF context | CommonCore extensions | 3 | 54
12 | overwrite objectversion methods that can implement because of agregation | MetaMetaCube RoadMap Template | 3 | 54
13 | Test |  |  | 32
14 | Deployment |  |  | 24
Total Time |  |  |  | 505

## Sheet2
[5 empty] | Total | 7477
| Project Order Dependency | Stage | Dependencies | Details | difficulty 4=hard, 1=easy | Estimate Time(H)
| MetaShare.Common.Utilities | 1 |  | Move it to Common.Core | 1 | 16
| MetaShare.Common.Foundation |  | MetaShare.Common.Utilities | Move some namespaces to another library. Add Target NET 6, Migrate Microsoft.Exchange.WebServices; deprecate Iservice | 1 | 300
| MetaShare.Common.Core |  | MetaShare.Common.Foundation, MetaShare.Common.Utilities | Move some namespaces to another library or create new one, Target NET 6, Deprecate or Move some namespaces (offline, Proxies, serialization, NetPipeService) | 2 | 300
| Sanjel.Common.Utilities |  | windows specific libs | Target NET6/NetStandard2.0, Create a PoC and Migrate Impersonation. No usages found in eService APP | 2 | 60
| Sanjel.Common.Core |  | MetaShare.Common.Foundation, MetaShare.Common.Utilities, new lib | Target NET 6, Deprecate Proxies, WCFExtensions,NetPipeService; ContextedGateway should call the right instance of the interface API only); migrate impersonation | 2 | 80
| Sanjel.Common.BusinessEntities.Standard |  | Sanjel.Common.Utilities,MetaShare.Common.Foundation | Move Namespaces, generate MMC code. ~120 classes | 1 | 600
| Sanjel.Common.BusinessEntities.Mdd |  | SanjelData.Entities,Common.Core | - |  | 0
| Sanjel.Common.BusinessEntities |  | MetaShare.Common.Foundation, Sanjel.BusinessEntities.Standard, Sanjel.Common.BusinessEntities.Mdd | Target NET 6/Standard2.0, | 1 | 16
| Sanjel.BusinessEntities.Standard |  | MetaShare.Common.Utilities, MetaShare.Common.Foundation, MetaShare.Common.Core, Sanjel.Common.BusinessEntities.Standard | generate MMC Classes. ~90 classes, | 2 | 400
| Sanjel.BusinessEntities.Standard Mappers | 2 |  | create mappers | 1 | 240
| Sanjel.BusinessEntities |  | Sanjel.BusinessEntities.Standard, MetaShare.Common.Foundation, Sanjel.Common.Core. Sanjel.Common.BusinessEntities.Standard, Common.Core, SanjelData.Entities | Target NET 6/Standard2.0 | 1 | 16
| Mapper | 1 |  | Lib PoC performance or generate MMC mappers | 2 | 32
| Sanjel.Common.Messaging | 1 |  | Replace it with a Message Queue. Create a new library to manage the queues; | 3 | 300
| Sanjel.Services.Interfaces.Standard |  |  | Replace Iservice Interface with Common.Core | 1 | 32
| Sanjel.Common.Services.Interfaces.Standard |  |  | Replace Iservice Interface with Common.Core | 1 | 80
| Sanjel.Services.Interfaces |  |  | Replace Factories with Common.Core | 1 | 32
| Sanjel.Common.RDLReporting | 1 |  | Deprecated. Generate ~17 Main reports and 164 sections with printing services | 3 | 600
| Sanjel.Common.Security.Services.Interfaces |  |  | Replace Iservice Interface with Common.Core, replace factory, target netstandard | 1 | 24
| MetaShare.Common.ServiceModel |  |  | Deprecate DAO, move controller namespace to another lib, deprecate services, migrate missing methods to MMC or Common.core | 3 | 180
| Sanjel.Common.Security.Daos.Interfaces |  |  | Deprecated
| Sanjel.Common.Security.Services | 1 |  | Move SecurityService to Services, replace factory and Iservice Interface | 2 | 40
| Sanjel.Security |  |  | Deprecated
| Sanjel.Common.Security.Gateways.Interfaces | 1 |  | Move interface. | 1 | 16
| Sanjel.Common.Security.Gateways |  |  | move to another lib, Create new Gateway using factory | 2 | 120
| Sanjel.Common.UI |  |  | Replace metashare namespaces, Microsoft office interop compatibility/runtime test | 1 | 80
| Sanjel.Security.UI | 1 |  | Deprecate and Move LogIn form | 2 | 24
| Sanjel.Common.Daos.Interfaces |  |  | Deprecated
| Sanjel.Common.Daos | 2 |  | Deprecated, also EService.Daos Generate it with MMC and customize methods | 3 | 1000
| Sanjel.Common.Security.Daos |  |  | Deprecated
| Sanjel.Common.UIFramework |  |  | Replace Reports, Change messaging logic | 2 | 80
| Sanjel.Common.Gateways.Interfaces |  |  | Create new Gateway using factory | 1 | 32
| Sanjel.Common.ApiServices.Interfaces |  |  | Change entities to DTO's | 1 | 300
| Sanjel.Common.Gateways.Standard |  |  | Create new Gateway using factory, replace it with MMC Sqlite (offline) | 1 | 120
| Sanjel.BusinessEntities.Facades |  |  | ?? This might deprecate using mappers???
| Sanjel.Common.Services |  |  | Task related to Sanjel.Common.Daos, migrate custom Methods | 2 | 40
| Sanjel.Common.UIProcess |  |  | Target to Net 6/Netstandard, replace namespaces(Metashare.Common.Core, metashare.common.foundation, metashare.common.utilities). Replace gateways, Replace services | 2 | 300
| Sanjel.Common.Services.Interfaces |  |  | Deprecate (did not find usages )
| Sanjel.Common.WinUI |  |  | Target to Net 6. replace metashare namespaces | 2 | 180
| Sanjel.Common.MockViews |  |  | ------
| Sanjel.Common.Gateways |  |  | refactor with mmc generated code, new factory | 2 | 120
| Sanjel.Common.MockGateways |  |  | ------
| Sanjel.Common.Mocks |  |  | ------
| Sanjel.Common.MockServices |  |  | ------
| Sanjel.Common.Security.MockServices |  |  | ------
| Sanjel.Common.MockDaos |  |  | ------
| Sanjel.Common.Security.MockGateways |  |  | ------
| Sanjel.Security.ManagerWinClient |  |  | ??
| Sanjel.Common.PrintingService |  |  | ------
| Sanjel.Common.UIDemo |  |  | ??
| Sanjel.Common.ApiServices |  |  | ------
| Sanjel.Common.MdmUtilities |  |  | deprecated
| SanjelEService\EServiceR6WCFServices | 1 |  | Create CoreWCF ASP.NET Core web host. Migrate WCF Services files to asp.net Startup and migrate web.config to wcf config, in the first stage we can create only the host and register services using net 4.6.2. Since coreWCF is netstandard compatible all sanjel lib can still work without changes. in the second stage we can migrate services and the host to NET 6 | 3 | 104
| Change Clickonce to dotnetmage 7 deployment tools | 1 |  | Unsupported CheckForDetailedUpdate / time estimated using alternative or create a launcher using net framework https://github.com/clowd/Clowd.Squirrel | 2 | 80
| SanjelEService\EService.WinUI |  |  | Target to NET6, Migrate MainMenu/MenuItem to ContextMenuStrip | 1 | 40
| SanjelEService\EService.UIProcess |  |  | Target to Net 6, upgrade namespaces or dll's | 2 | 80
| SanjelEService\EService.Services, EService.Daos |  |  | related to Sanjel.Common.Services
| SanjelEservice\Eservice.Gateways |  |  | related to Sanjel.Common.Gateways
| SanjelEService\SanjeleServiceSustainment Client, Demo, Production |  |  | Target to Net 6, upgrade namespaces or dll's | 1 | 120
| Common.core changes | 1 |  | Implement cache, CommonObject Extension or utility Class/Library, ObjectBase Extension or utility class/Library | 2 | 68
| Proof of Concept New Architecture | 2 |  |  |  | 120
| Test |  |  |  |  | 600
Total Time | [5 empty] | 6972
Partial Migrate to EF Core
| Tasks |  | Stage | Project | difficulty 4=hard, 1=easy | Estimate Time(H)
1 | Create ContextBuilder ( to register connectionString) |  | 1 | MetaMetaCube RoadMap Template | 2 | 14
2 | Modify Program.cs web and api to register context builder |  | 1 | MetaMetaCube RoadMap Template | 1 | 8
3 | Create SanjelDataContext and implement interface |  | 1 | MetaMetaCube RoadMap Template | 4 | 68
4 | Modify Projects csproj to include new references |  | 1 | MetaMetaCube RoadMap Template | 1 | 8
5 | Modify XServicecs to inherit from new object version |  | 2 | MetaMetaCube RoadMap Template | 1 | 8
6 | Modify XServicecs to overwrite methods containing isAggregatedChildren parameter |  | 2 | MetaMetaCube RoadMap Template | 3 | 54
7 | Modify XService.cs to change custom methods containing isAggregatedChildren parameter |  | 2 | MetaMetaCube RoadMap Template | 3 | 54
8 | Modify XService.cs to change custom methods containing aggregationInfo parameter |  | 2 | MetaMetaCube RoadMap Template | 3 | 54
9 | Create Base context class and Interface |  | 1 | CommonCore extensions | 2 | 32
10 | Create Dao Extension utility to create and activate Context |  | 1 | CommonCore extensions | 2 | 41
11 | Crate new implementation for ObjectVersionService using EF context |  | 2 | CommonCore extensions | 3 | 54
12 | overwrite objectversion methods that can implement because of agregation |  | 2 | MetaMetaCube RoadMap Template | 3 | 54
13 | Test |  | 1&2 |  |  | 32
14 | Deployment |  | 1&2 |  |  | 24
Total Time | [5 empty] | 505
Note on C2: miguel anguiano: stage 1 can start do develop without dependencies
Note on C54: miguel anguiano: (only the coreWFC net 4.6.1 part)