## Sheet1
Use Case
No. | Name | Comments | Execution Date | Execution Result
UC001 | Assign Bin on Bin column |  | 2023-10-30 | Pass
UC002 | Release Bin on Bin column |  | 2023-10-31 | Pass
UC003 | Adjust Blend Amount on Bin column |  | 2023-10-31 | Pass
UC004 | Schedule Blend Request on Bin column |  | 2023-10-31 | Pass
UC005 | Reschedule Blend Request on Bin column |  | 2023-10-31 | Pass
UC006 | Empty Bin |  | 2023-10-31 | Pass
UC007 | Cancel Blend Request on Bin column | 新增加 | 2023-10-31 | Pass
UC008 | Haul Blend of Bin column | 新增加 | 2023-11-01
UC009 | Reschedule Product Haul on Bin column | 新增加 | 2023-11-01
UC010 | Cancel Prodcut Haul of Bin column | 新增加 | 2023-11-01
UC011 | On Location of Bin column | 新增加 | 2023-11-01
UC012 | Transfer Blend of Bin column | 新增加，优先级低 | 2023-11-01
UC013 | Don't need bin of Bin column | 新增加，优先级低 | 2023-11-01
UC014 | Bulk Plant Board Panel | 新增加 | 2023-11-02
UC001 | Schedule Product Haul of Blend column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-02
UC002 | Assign Bin of Bin column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-02
UC003 | Release Bin of Bin column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-02
UC004 | Adjust Blend Amount of Bin column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-02
UC005 | Reschedule Product Haul of Blend column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-02
UC006 | Reschedule Product Haul Request of Blend column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-03
UC007 | Schedule Blend Request of Blend column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-03
UC008 | Reschedule Blend Request of Blend column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-03
UC009 | Cancel Product Haul of Blend column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-03
UC010 | Cancel Product Haul Load of Blend column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-03
UC011 | OnLocation Blend Request of Blend column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-03
UC012 | OnLocation Product Haul Load of Blend column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-04
UC013 | Product Haul page display for all above schedule features | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-04
UC014 | Haul Blend of Blend column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-04
UC015 | Schedule Product Haul of Bin column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-04
UC016 | Reschedule Product Haul of Bin column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-04
UC017 | Cancel Product Haul of Bin column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-04
UC018 | OnLocation Product Haul of Bin column | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-05
UC050 | Rig Board Panel | 需要根据系统当前实现补充，更新用例，优先级高 | 2023-11-05