## 项目日程安排
在此工作表中创建项目日程安排。 在单元格 B1 中输入此项目的标题。 有关如何使用此工作表（包括屏幕阅读器的说明）以及此工作簿作者的信息包含在“关于”工作表中。 继续向下浏览 A 列，获取进一步指示。 | MetaShare Project Statement - May 2024
在单元格 B3 中输入项目主管的姓名。在单元格 E3 中输入项目开始日期。项目开始：标签位于单元格 C3 中。 | Start Date | 2024-05-01 |  | Estimated total(hour) | 872 | 192 |  | 2024-05-31
单元格 E4 中的显示周数表示单元格 I4 中项目日程安排内显示的起始周数。项目开始日期视为第 1 周。要更改显示周数，只需单元格 E4 中输入新的周数。 从单元格 E4 的显示周数开始，每周的开始日期从单元格 I4 开始并且说自动计算得出的。在该视图中，从单元格 I4 到单元格 BF4 共有 8 周的时间。 请勿修改这些单元格。 显示周数：标签位于单元格 C4 中。 | End Date | 2024-05-31 |  | Available Resource(hour) | 640 | 显示周数： |  | 1 |  |  |  | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01 | [6 empty] | 2024-07-08 | [6 empty] | 2024-07-15 | [6 empty] | 2024-07-22 | [6 empty] | 2024-07-29 | [6 empty] | 2024-08-05 | [6 empty] | 2024-08-12 | [6 empty] | 2024-08-19 | [5 empty] | 2024-08-25 | [5 empty] | 2024-08-31 | [5 empty] | 2024-09-06 | [5 empty] | 2024-09-12 | [5 empty] | 2024-09-18 | [5 empty] | 2024-09-24 | [5 empty] | 2024-09-30 | [5 empty] | 2024-10-06 | [5 empty] | 2024-10-12 | [5 empty] | 2024-10-18 | [5 empty] | 2024-10-24 | [5 empty] | 2024-10-30 | [5 empty] | 2024-11-05 | [5 empty] | 2024-11-11 | [5 empty] | 2024-11-17 | [5 empty] | 2024-11-23 | [5 empty] | 2024-11-29 | [5 empty] | 2024-12-05 | [5 empty] | 2024-12-11 | [5 empty] | 2024-12-17 | [5 empty] | 2024-12-23 | [5 empty] | 2024-12-29 | [5 empty] | 2025-01-04 | [5 empty] | 2025-01-10 | [5 empty] | 2025-01-16 | [5 empty] | 2025-01-22 | [5 empty] | 2025-01-28 | [5 empty] | 2025-02-03 | [5 empty] | 2025-02-09 | [5 empty] | 2025-02-15 | [5 empty] | 2025-02-21 | [5 empty] | 2025-02-27 | [5 empty] | 2025-03-05 | [5 empty] | 2025-03-11 | [5 empty] | 2025-03-17 | [5 empty] | 2025-03-23 | [5 empty] | 2025-03-29 | [5 empty] | 2025-04-04 | [5 empty] | 2025-04-10 | [5 empty] | 2025-04-16 | [5 empty] | 2025-04-22 | [5 empty] | 2025-04-28
单元格 I5 到 BL5 包含每个日期单元格上方单元格块中表示的星期的日期数字并且是自动计算得出的。 请勿修改这些单元格。 今天的日期带有红色（十六进制 #AD3815）轮廓（从第 5 行中显示今天日期的列及至项目日程安排结尾的该列）。 | time axis 2024-05-27 to 2025-05-03
此行包含其后面的项目日程安排的标题。 从 B6 浏览到 BL6 以获取内容。该标题上方日期一周中每一天的首字母，从单元格 I6 开始，直到单元格 BL6。 所有项目日程表图表都是根据输入的开始和结束日期使用条件格式自动生成的。 从单元格 I7 开始的列 I 之后，请勿修改列内单元格中的内容。 | Number | Task | Priority |  | Assign to | Est | Progress | Start Date | End Date | Pre-Task | Days | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 四 | 五 | 六
请勿删除此行。隐藏了此行，以保留用于突出显示项目日程安排中当天的公式。
单元格 B8 包含第 1 阶段示例标题。 在单元格 B8 中输入新标题。 如果适用于你的项目，请在单元格 C8 中输入名称以指定阶段。 如果适用于你的项目，请在单元格 D8 中输入整个阶段的进度。 如果适用于你的项目，请在单元格 E8 和 F8 中输入整个阶段的开始和结束日期。 甘特图将根据输入的进度自动填充适当的日期和着色。 要仅从任务中删除阶段和工作，只需删除此行即可。 | MetaShare Project Statement - May 2024 |  |  | Release |  | 872
Project management
|  | ProjectPlan | 1000 | 2024-05-01 | LiYing | 32 | 100%
|  | Organize meetings&Track project progress | 1000 | 2024-05-01 | LiYing | 32 | 100%
|  | Daily stand-up meeting | 1000 | 2024-05-01 | All | 55 | 100%
|  | Analysis | 1000 | 2024-05-01 | Miguel | 48 | 100%
|  | Estimated tasks workload | 1000 | 2024-05-01 | Developer | 32 | 100%
| 1 | SanjelCommonLibrary Upgrade | 1000 |  |  |  | 100% | 2024-05-06 | 2024-05-08
| 1.1 | SanjeleServiceUAT做为启动项目，SanjelCommonLibary中的Common UI的引用并没有更新 | 1000 | 2024-05-01 | TongTao | 10 | 100% | 2024-05-06 | 2024-05-07
| 1.2 | Add configuration parameters | 1000 | 2024-05-01 | TongTao | 2 | 100% | 2024-05-07 | 2024-05-07
| 1.3 | Move the incorrectly migrated classes back to the eService project | 1000 | 2024-05-01 | TongTao | 4 | 100% | 2024-05-08 | 2024-05-08
| 2 | Message Library Upgrade - Phase II- PLC Data Upgrade
| 2.1 | LocalData Update |  | 2024-04-01 |  |  | 100%
| 2.1.1 | Merge MMC LocalData into SanjelData | 0 | 2024-04-01 | Bela |  | 100% | 2024-04-01 | 2024-04-30
| 2.1.2 | Move/Refactor eServiceExpress.Daos, eServiceExpress.Daos.Interfaces, eServiceExpress.LocalDataManager, CachedPlcData entities, to customized code to SanjelData libraries LocalData path | 0 | 2024-04-01 | Zhangyuan |  | 100% | 2024-04-01 | 2024-04-30
| 2.1.3 | Configure and Synchronize customized code to MMC to include it when code is generated | 0 | 2024-04-01 | Miguel |  | 100% | 2024-04-01 | 2024-04-30 | 2.1.1,2.1.2
| 2.1.4 | Replace code in eServiceExpress | 0 | 2024-04-01 | Zhangyuan |  | 100% | 2024-04-01 | 2024-04-30 | 2.1.2
| 2.1.5 | Unit Test | 0 | 2024-04-01 | Zhangyuan |  | 100% | 2024-04-01 | 2024-04-30 | 2.1.4
| 2.1.6 | Create a simple database migration tool for old Database schema to the new (MMC NET 6) | 0 | 2024-04-01 | TongTao |  | 100% | 2024-04-01 | 2024-04-30
| 2.1.7 | Deploy libraries and upgrade projects references | 0 | 2024-04-01 | Zhangyuan |  | 100% | 2024-04-01 | 2024-04-30
| 2.1.8 | Smoke Tests | 0 | 2024-04-01 | Zhangyuan |  | 100% | 2024-04-01 | 2024-04-30
| 2.1.9 | eServiceExpress release without functionalities change. | 0 | 2024-04-01 | Zhangyuan |  | 100% | 2024-04-01 | 2024-04-30
| 2.1.10 | Use Plc simulator to test the original real-time monitoring function. | 1000 | 2024-05-01 | Zhangyuan | 24 | 100%
Release 1: Replacing legacy entities with MMC entities.
| 2.2 | PLC data sender
| 2.2.1 | Add customized queries and methods in SanjelData/LocalData for extracting all data records in full records based on data index "D":"214" and timestamp with a flag in ese_flags table (ESE_flags keeps the latest record read) | 900 | 2024-05-01 | Zhangyuan | 32 | 100% |  |  | 2.1
| 2.2.2 | Explore the possibility to run LocalDataManager features in eServiceExpress | 0 | 2024-04-01 | TongTao | 0 | 100%
| 2.2.3 | Add HangFire library to execute only one instance at a time and execute Functions | 900 | 2024-05-01 | Miguel | 8 | 1% |  |  | 2.2.1
| 2.2.4 | MMC udpdate: adding new classes in sanjelData->LocalData for archive database mechanism and table for data confirmation | 900 | 2024-05-01 | Bela | 24 | 100% |  |  | 2.1
| 2.2.5 | Configure Messaging SanjelLibrary | 900 | 2024-05-01 | TongTao | 8 | 100%
| 2.2.6 | Setup task to send PLC data periodically | [7 empty] | 2.2.1
| 2.2.6.1 | Create Class and Configure scheduler library to abstract the execution of quartz/hangfire to execute the task accordingly | 900 | 2024-05-01 | TongTao | 35 | 100% |  |  | 2.2.1
| 2.2.6.2 | Create and execute a facade method to send correct messages with PLC data | 900 | 2024-05-01 | ZhangYuan | 22 | 100% |  |  | 2.2.1
| 2.2.6.2 | Mark messages (plcData) that were sent to local mqtt but not received in server, so they can be marked as received in later task below | 900 | 2024-06-01 | ZhangYuan | 16 | 60% |  |  | 2.2.1
| 2.2.6.3 | Run simulator and sender to confirm correct data is sent | 900 | 2024-06-01 | ZhangYuan | 6 | 1% |  |  | 2.2.1
| 2.2.7 | Confirm data received on the server (notifier) add another table if needed to save what records are sent but not received, add flag to records that are actually received on server (ready to archive). think about how to mantain table. A table lock may be required depending of the mechanism used to mark messages sent and/or received | 900 | 2024-06-01 | ZhangYuan | 24 | 1% |  |  | 2.2.5
| 2.2.8 | Data archiving: move expired data out of runtime local database. Any data received on server and older than 15 days will be archived. Data archiving will only happen when PLC is idle, which means no PLC records are found while trying to send. SCM_PLC_DB_LOCK needs to be set while doing WRITE operation to SCM_PLC database to lock Data table. Unlock is needed after the operation is done. | 900 | 2024-05-01 |  |  | 0% |  |  | 2.2.4
| 2.2.8.1 | Execute the database lock, applying rules when the operation is ready to start data archiving. | 900 | 2024-05-01 | Miguel | 8 | 1% |  |  | 2.2.4
| 2.2.8.2 | Delete data from pclData and insert it in Archive DB according to rules: time and confirmed data, unlock DB after processing | 900 | 2024-05-01 | Miguel | 24 | 1% |  |  | 2.2.4
| 2.2.9 | Data archiving execution task (scheduler), it should be configurable with app.settings setting | 900 | 2024-05-01 | Miguel | 8 | 1% |  |  | 2.2.8
| 2.2.10 | Unit Test | 900 | 2024-06-01 | Miguel | 56 | 0%
| 2.2.11 | Integration testing-SanjelData | 900 | 2024-05-01 | Bela | 24 | 100%
| 2.2.12 | Deploy | 900 | 2024-05-01 |  | 16 | 100%
| 2.2.13 | use the simulator to create your DB for your tests | 1000 | 2024-06-01 | Miguel | 18 | 0%
| 2.3 | PLC data receiver (Messaging.Server app)
| 2.3.1 | Create a server based off Messaging.Server project (see Architecture_ProtoType repository) rename namespaces project, etc, and commit to a new repository | 900 | 2024-05-01 | ZhangYuan | 10 | 100%
| 2.3.2 | Create a generic method for list insert in metashare common.Core.ng | 900 | 2024-05-01 | Bela | 20 | 100%
| 2.3.2.1 | Create a generic method for list update in metashare common.Core.ng | 900 | 2024-05-01 | Bela | 20 | 0%
| 2.3.3 | Execute inserts for PlcData coming from message into sql server DB | 900 | 2024-05-01 | ZhangYuan | 20 | 60% |  |  | 2.1
| 2.3.4 | Configure messaging and configure Daos/Services Registrations to Insert data in Staging DB | 900 | 2024-05-01 | ZhangYuan | 18 | 100% |  |  | 2.1
| 2.3.5 | Unit Test | 900 | 2024-05-01 | ZhangYuan | 18 | 1%
| 2.3.6 | Integration testing | 900 | 2024-05-01 | ZhangYuan | 24 | 1%
| 2.3.7 | Deploy | 900 | 2024-05-01 | ZhangYuan | 16 | 1%
| 2.4 | Online monitor
| 2.4.1 | Syncfusion real-time charting component evaluation | 600 | 2024-06-01 | Miguel | 8 | 0%
| 2.5 | eServiceOnline
| 2.5.1 | JobTag improvement to be ready for online. | 600 | 2024-06-01 |  | ? | 0%
| 2.5.2 | Add JobTag to Post Data message queue | 600 | 2024-06-01 |  | ? | 0%
| 2.5.3 | Eliminate the dependency on eServiceMDM.WebAPI | 1000 | 2024-05-01 | TongTao
| 2.6 | PLC Data Online Monitor
| 2.6.1 | new project like DRB (pending definition) | 500 | 2024-06-01 |  | ? | 0%
| 2.6.2 | Unit Test | 500 | 2024-06-01 |  | ? | 0%
| 2.6.3 | Integration testing | 500 | 2024-06-01 |  | ? | 0%
| 2.6.4 | Deploy | 500 | 2024-06-01 |  | ? | 0%
| 2.7 | eService
| 2.7.1 | Stop eService PLC data packing in same release. Remove it from job sending feature | 900 | 2024-06-01 | Miguel | 8 | 0%
| 2.7.2 | Eliminate the dependency on eServiceMDM.WebAPI | 1000 | 2024-05-01 | Miguel
Release 4: PLC data transmission with MQTT.
| 2.8 | eServiceExpress
| 2.8.1 | Explore options to upgrade to NET 6/8 and new syncFusion library compatibility | 0 | 2024-04-01 | Miguel | 0 | 100% | 2024-04-01 | 2024-04-30
| 2.8.2 | Upgrading eServiceExpress. | 600 | 2024-06-01 |  | ? | 0%
Release 3: Upgrade eServiceExpress .net framework to Net 6/8 (optional)
| 3 | NuGet publish-Release 1
| 3.1 | Sanjel Library NuGet publish | 0 | 2024-04-01 | Miguel | 0 | 100% | 2024-04-01 | 2024-04-30
| 3.1.1 | Modify workflow actions file | 0 | 2024-04-01 | Miguel | 0 | 100% | 2024-03-14 | 2024-03-14 | 0
| 3.1.2 | Publish first stable release for each library individually with GitHub Actions | 0 | 2024-04-01 | Miguel | 0 | 100% | 2024-03-14 | 2024-03-14 | 0
| 3.1.3 | Update application library corresponding to Sanjel Library NuGet source | 0 | 2024-04-01 | TongTao | 0 | 100% | 2024-03-15 | 2024-03-15 | 0
| 3.1.4 | Document Sanjel Library Guidelines. | 0 | 2024-04-01 | Miguel | 0 | 100%
| 3.1.5 | Modify projects to use a shared configuration file to embed the pdb files as resources under the Debug configuration, which helps in debugging with NuGet packages, also configure source_link | 0 | 2024-04-01 | Miguel | 0 | 100% |  |  | 0
| 3.1.6 | Ask Adam (optional) cofnigure dependanbot or automatic updater | 0 | 2024-05-01 | Miguel | 0 | 0%
| 3.2 | Sanjel Common Library NuGet publish | 1000
| 3.2.1 | Move eService projects which are referenced by eProgram and eServiceOnline to SanjelCommonLibrary to decouple the dependencies. |  | 2024-05-01 | TongTao | 0 | 100%
| 3.2.2 | Create workflow file to push nugets | 1000 | 2024-05-01 | Miguel | 45 | 100%
| 3.2.3 | Publish SanjelCommonLibrary to NuGet | 1000 | 2024-05-01 | Miguel | 16 | 100%
| 3.2.4 | Update eService, eProgram, eServiceOnline and eSerivceExpress reference to use NuGet | 1000 | 2024-05-01 | Miguel | 20 | 100%
| 3.2.5 | Build github workflow to build above applications upon PR merge. | 1000 | 2024-05-01 | Miguel | 45 | 1%
| 3.2.6 | Fix Missing ResourceException for SDK-Style Project Resource Loading | 1000 | 2024-05-01 | Miguel | 16 | 100%
| 3.3 | Release 2: Replacing references by NuGet packages.
此行标记项目日程安排的结尾。请勿在此行中输入任何内容。 在此行上方插入新行，以继续构建项目日程安排。 | 在此行上方插入新行